## SCHEDULE VI-M-3.1
| (a) Project Name (with CCN Docket No., if Any) | (b) Estimated Costs at the Time of ERCOT Review (If Any) | (c) Estimated Costs in First MCPR Entry | (d) First MCPR Where Project Appeared | (e) Final Total Project Costs | (f) Last MCPR Where Project Appeared | (g) Percent difference between (c) and (e) | Variance Explanation
1 | CCN Docket No. 54733
| 0PT51087 -- ROANOKE SWITCH - DEEN SWITCH 138KV LINE: RETERMINATION AT KELLER WALL PRICE (WEST) | 285900000 | 12018000 | 2023-04-15 | 14185829.44 |  | 18.04% | Variance is due to a change in the scope of the project and increased material and labor costs. The scope of work expanded to include upgrading the existing switches at Keller Wall Price to 3200 A and to meet city permitting requirements, including additional grading, adding a masonry wall, and landscaping/vegetation management. Material and labor costs increased due additional materials and labor required for the scope changes and due to price increases for various materials that occurred between 2020, when the estimate was created, to 2023-2024, when the costs were incurred.
| 0PT51093 -- KELLER WALL PRICE SUB: RECONFIGURE STATION FOR CONNECTION TO KINGSRIDGE SWITCH |  |  | 2023-04-15
| 0PT51094 -- ROANOKE SWITCH: MODIFY RELAYING FOR KINGSRIDGE SWITCH |  |  | 2023-04-15
| 0PT51096 -- EULESS SUB: MODIFY RELAYING FOR KINGSRIDGE SWITCH |  |  | 2023-04-15
| 0PT51249 -- KELLER MAGNOLIA - KELLER WALL PRICE 138KV LINE: GREENFIELD |  |  | 2023-04-15
| 0PT53025 -- KELLER MAGNOLIA - KELLER WALL PRICE 138KV LINE: GREENFIELD: ROW ACQUISITION |  |  | 2023-04-15
| 0PT51092 -- KINGSRIDGE SWITCH (FORMERLY KELLER WALL PRICE SWITCH): ESTABLISH 138 KV STATION |  |  | 2023-04-15 |  | 2024-02-15
2 | CCN Docket No. 55574
| 0PT44941 -- EXCHANGE SWITCH (FKA ALLIANCE EXPANSION) - PURCHASE OF LAND | 285900000 | 66002000 | 2023-10-15 | 51907574.5 |  | -21.35% | Not Applicable
| 0PT51097 -- EXCHANGE SWITCH: ESTABLISH 345/138 KV STATION |  |  | 2023-10-15 |  | 2023-10-15 |  | 0
| 0PT53097 -- ALLIANCE SUB - EXCHANGE SWITCH 138KV LINE: TIE LINES |  |  | 2023-10-15 |  | 2024-07-15 |  | 0
| 0PT49510 -- EXCHANGE SWITCH: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER #1 |  |  | 2023-10-15 |  |  |  | 0
| 0PT47814 -- EXCHANGE SWITCH: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER #2 |  |  | 2023-10-15 |  |  |  | 0
3 | CCN Docket No. 55067
| 0PT44942 -- RAMHORN HILL SWITCH (FKA NORTH HICKS SWITCH) - PURCHASE OF LAND | 285900000 | 251797000 | 2023-06-15 | 8809244.54 |  | -96.5% | Not Applicable
4 | 0PT51088 -- ROANOKE SWITCH - DEEN SWITCH 138KV LINE: RETERMINATION AT KELLER WALL PRICE (EAST) | 285900000 | 10238228 | 2024-02-15 | 8238292.27 | 2025-02-14 | -19.53% | Not Applicable
| 0PT50513 -- KELLER MAGNOLIA - KELLER WALL PRICE 138 KV LINE: REBUILD |  |  | 2024-02-15 |  | 2025-02-14
| 0PT53094 -- ROANOKE SWITCH - DEEN SWITCH 138KV LINE : ROW ACQUISITION |  |  | Not Applicable
5 | 0PT47524 -- BOWMAN SWITCH : REPLACE AUTO TRANSFORMER #2 | 285900000 | 7893819.97 | 2023-07-15 | 7846314.28 | 2025-02-14 | -0.6018% | Not Applicable
| 0PT49508 -- BOWMAN SWITCH: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER #2 |  |  | 2023-07-15 |  | 2025-02-14 |  | 0
6 | 0PT53160 -- ROANOKE SWITCH - HICKS SWITCH 345KV LINE (SOUTH): CUT-IN TO ESTABLISH EXCHANGE SWITCH | 285900000 | 4619826.85 | 2024-03-15 | 3385963.21 | 2025-02-14 | -26.71% | Not Applicable
| 0PT49487 -- HICKS SW - ROANOKE SW 345KV EXCHANGE SWITCH STATION - PURCHASE OF EASEMENT |  |  | Not Applicable |  | 2025-02-14
7 | 0PT51098 -- ALLIANCE SUB: REBUILD STATION WITH THREE TRANSFORMERS | 285900000 | 12863642.68 | 2023-12-15 | 10277227.02 | 2025-02-14 | -20.11% | Not Applicable
8 | 0PT46399 -- ROANOKE SWITCH - HICKS SWITCH 345 KV LINE (NORTH): CUT-IN TO ESTABLISH EXCHANGE SWITCH | 285900000 | 4409075.38 | 2024-04-15 | 4465522.64 | 2025-02-14 | 1.28% | Not Applicable
9 | CCN Docket No. 54524
| 0PT40468 -- NACOGDOCHES SOUTHEAST SWITCH - REDLAND SWITCH 345 KV LINE: ADD 345 KV CIRCUIT TO EXISTING DOUBLE CIRCUIT LATTICE TOWERS | 71260000 | 38625000 | 2023-01-15 | 52092754.06 |  | 34.87% | The variance is primarily due to the CCN estimate not including the CCN-exempt upgrades (0PT52385) or the CCN-exempt acquisition of a capital spare autotransformer (0PT49515). Without the cost of these items the variance from the CCN estimate is approximately 10%. Other variance drivers are a change in the scope of the project and increased material and labor costs. The scope of work expanded to include relocating and recommissioning an autotransformer at Nacogdoches Southeast. Additional ground grid, foundation pier and slab removals, equipment, and buswork; additional helicopter work due to ROW access limitations; retrofitting structure foundations; relocating two static masts due their close proximity to incoming 345 kV circuits; and higher-than-expected matting costs. Material costs increased due to higher-than-estimated prices for circuit breakers, disconnect switches, deadend structures, instrument transformers, control center, control cable, and relay panels. Labor costs increased due to economic change adjustments after the estimate was created; additional resources and hours for a compressed construction schedule due to pad delays; pass-through costs for grounding material, which the contractor purchased to expedite the construction timeline; additional costs associated with concrete delivery due to the distance between job site and the plant; installation of aggregate and base material, grounding, conduit, and buswork; hand-digging a ditch for conduit in close proximity to energized equipment; two additional months of security; and mobilization charges to relocate the static masts. When Final Estimated costs from the January 2023 MCPR are compared against the Final Actual costs, the cost variance is -9%.
| 0PT41070 -- REDLAND SWITCH (HERTY NORTH): INSTALL 345 KV SWITCHYARD AND AUTOTRANSFORMER |  |  | 2023-01-15
| 0PT41164 -- NACOGDOCHES SOUTHEAST SWITCH : ESTABLISH 345 KV THREE BREAKER RING BUS YARD |  |  | 2023-01-15
| 0PT49515 -- ROYAL SMIT 2024 SLOT#1: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER |  |  | 2023-01-15
| 0PT52385 -- NACOGDOCHES SOUTHEAST - REDLAND SWITCH 138 KV LINE: UPGRADES FOR THE ADDITION OF 345 KV CIRCUIT |  |  | 2024-03-15 |  | 2024-03-15
10 | CCN Docket No. 53491
| 0PT46696 -- FLAT IRON – BARR RANCH – QUICKRIVER TAP 138 KV LINE | 50700000 | 43708985 | 2022-05-15 | 40018299.76 | 2023-07-15 | -8.444% | Not Applicable
| 0PT46728 -- FLAT IRON - BARR RANCH - QUICKRIVER 138 KV LINE : EASEMENT ACQUISITION |  |  | 2022-05-15 |  |  |  | 0
| 0PT46818 -- QUICKRIVER TAP (FKA: SWEETIE PECK TAP) : ACQUISITION OF STATION EASEMENT |  |  | 2022-05-15 |  |  |  | 0
| 0PT46983 -- QUICKRIVER TAP : ESTABLISH 138 KV TAP |  |  | 2022-05-15 |  |  |  | 0
| 0PT46984 -- BARR RANCH SWITCH: ESTABLISH 138KV 3 BREAKER RING BUS AND 55.2 MVAR CAPACITOR BANK |  |  | 2022-05-15 |  |  |  | 0
| 0PT47825 -- BARR RANCH SUB EXPANSION (SUPPLEMENTAL EASEMENT) |  |  | 2022-05-15 |  |  |  | 0
11 | 0PT46901 -- PEGASUS SOUTH TAP - QUICKRIVER TAP 138 KV LINE : REBUILD | 50700000 | 8987319 | 2022-06-15 | 6792308.52 | 2024-12-15 | -24.42% | Not Applicable
12 | 0PT46966 -- PLEASANT FARMS (LCRA) TAP - PEGASUS SOUTH TAP 138 KV LINE : REBUILD | 50700000 | 8454264 | 2022-06-15 | 7151339.06 | 2024-12-15 | -15.41% | Not Applicable
13 | CCN Docket No. 51737
| 0PT04088 -- KYLE RANCH - QUARRY FIELD SW 138 KV LINE: CONSTRUCT GREENFIELD LINE | 29000000 | 17161000 | 2021-12-15 | 17862497.05 | 2023-07-15 | 4.088% | Not Applicable
| 0PT42631 -- KYLE RANCH - QUARRY FIELD SWITCH 138 KV - TRANSMISSION LINE - ROW : NEW |  |  | 2021-12-15 |  | 2023-07-15 |  | 0
14 | CCN Docket No. 50410
| 0PT42867 -- BEARKAT - LONGSHORE 345KV TRANSMISSION LINE : ROW ACQUISITION | 53260000 | 31039500 | 2021-09-15 | 39897821 | 2024-10-01 | 28.54% | Variance is due to increased material and labor costs. Initial estimate was created in 2019. Material costs for structures increased due to the price of structural steel and the need for shorter span lengths to address terrain on the approved route, which increased the number of structures required. Right-of-way acquisition costs were higher than estimated. Labor costs increased due to the need for additional structures due to prices for lattice tower erection increasing between initial estimate and construction. An economic change adjustment for contract labor further increased labor costs. Additionally, unexpected material delays disrupted construction timelines and required multiple re-mobilizations, which further increased labor costs. When Final Estimated costs from the September 2021 MCPR are compared against the Final Actual costs, the cost variance is -9%.
| 0PT44980 -- BEARKAT (WETT) SWITCH - LONGSHORE SWITCH 345 KV LINE : BUILD NEW LINE |  |  | 2021-09-15 |  | 2024-10-01
| 0PT45164 -- LONGSHORE 345 KV SWITCH : INSTALL ONE 3200 A, 345 KV CIRCUIT BREAKER |  |  | 2021-09-15
15 | CCN Docket No. 53053
| 0PT42146 -- IVY LEAGUE SUB (PRINCETON EAST) : ESTABLISH WITH ONE 47 MVA 138-24.9 KV TRANSFORMER AND TWO 25 KV UG FEEDER BREAKERS | Not Applicable | 13521000 | 2022-01-15 | 25396712.07 | 2025-02-01 | 87.83% | Variance is due to a change in project scope and increased material and labor costs. The scope of work expanded to include additional grading, drainage management, stabilization, erosion control, and a retaining wall, as well as additional ROW acquisition, a masonry perimeter wall, concrete driveway, and engineering work to satisfy municipal permitting requirements. Material costs increased due to price increases for structural steel, transformers, relay control equipment, and control centers; the need for additional base and lime stabilization materials; and additional materials for drainage and erosion control. Transformer manufacturer rigging, crane, and transportation service costs also increased. Labor costs increased due various factors that required additional engineering consultant services, on-site inspection services, on-site security services, and Oncor and contractor labor costs. The increased scope of work resulted in additional labor costs for grading, stabilization, erosion control, drainage, and a retaining wall. Labor costs also increased due to the need for transformer leaker and oil retention installation. Poor soil conditions increased costs to install foundations, conduit, and grounding. The project schedule was delayed by weather conditions, material delivery delays, ERCOT clearance coordination, and municipal permitting requirements that necessitated additional engineering for surveys and platting, a masonry wall, and a driveway. Project delays resulted in multiple work crew remobilizations, extended the need for security services, and led to additional protection and control resources being required to meet the project’s in-service date and ERCOT's clearance restriction deadline. When Final Estimated costs from the January 2022 MCPR are compared against the Final Actual costs to date, cost variance is 3%.
| 0PT42342 -- IVY LEAGUE - LONGNECK (TNMP) 138 KV LINE: CONSTRUCT NEW LINE |  |  | 2022-01-15 |  | 2025-02-01
| 0PT50566 -- IVY LEAGUE - LONGNECK (TNMP) 138 KV LINE : ROW ACQUISITION |  |  | 2022-01-15
16 | CCN Docket No. 52455
| 0PT50737 -- OLD COUNTRY SWITCH 345 KV TAP LINE: ROW ACQUISITION | Not Applicable | 18217000 | 2023-07-15 | 3232065.22 |  | -82.26% | Not Applicable
17 | CCN Docket No. 56220
| 0PT54477 -- DRIVER SUB - PECK SUB 138 KV LINE - CUSTOMER ROW ACQUISITION | 36200000 | 15481000 | 2024-03-15 | 14780180.79 |  | -4.527% | Not Applicable
| 0PT49407 -- DRIVER SUB - PECK SUB 138 KV LINE : GREENFIELD |  |  | 2024-03-15 |  |  |  | 0
| 0PT49352 -- PECK SUB: CONVERT STATION HIGH-SIDE FROM 69 KV RADIAL TO 138 KV LOOP-IN-LOOP-OUT OPERATION |  |  | 2024-03-15 |  | 2024-07-15 |  | 0
| 0PT49528 -- SL DRIVER SUB: 138 KV LINE TERMINAL ADDITION |  |  | 2024-03-15 |  | 2024-07-15 |  | 0
18 | 0PT48860 -- RANGER CAMP SWITCH (FKA MORGAN CREEK NORTH REBUILD) PURCHASE APPROXIMATELY 70 ACRES IN FEE TITLE | 1116340000 | 73905086.77 | 2023-10-15 | 10624901.91 |  | -85.62% | Not Applicable
| 0PT49509 -- RANGER CAMP SWITCH: AUTOTRANSFORMER #1 345/138 KV, 600 MVA |  |  | 2023-10-15 |  |  |  | 0
| 0PT49520 -- RANGER CAMP SWITCH: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER #2 |  |  | 2023-10-15 |  |  |  | 0
19 | 0PT47062 -- CATTLEMAN SWITCH: PURCHASE LAND IN FEE TITLE (SOUTH OF MORGAN CREEK) | 1116340000 | 70654900 | 2023-11-15 | 2505059.76 |  | -96.45% | Not Applicable
| 0PT49514 -- CATTLEMAN SWITCH: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER #1 |  |  | Not Applicable
20 | 0PT48503 -- REITER SWITCH : PURCHASE IN FEE | 1116340000 | 47467679.22 | 2024-08-15 | 1615119.2 |  | -96.6% | Not Applicable
21 | 0PT55560 -- WILMER SWITCH EXPANSION RADER : PURCHASE IN FEE | 158200000 | Not Applicable | Not Applicable | 2755314.39 |  | Not Applicable | Not Applicable
22 | 0PT49507 -- TEMPLE PECAN CREEK: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER | 120700000 | 15041966.87 | 2023-07-15 | 17722067.5 | 2025-02-14 | 17.82% | Variance is due to a change in project scope to address increased short circuit fault currents, which increased material and labor costs. Additional scope of work included installing lightning arresters and upgrading telecommunications equipment to facilitate the addition of fiber. Performing all work at the same time reduced outage time for customers, efficiently utilized work crews, and reduced overall project costs.
| 0PT50194 -- TEMPLE PECAN CREEK SWITCH: INSTALL 345 -138 KV AUTO 2 AND TWO 345 KV LINE TERMINALS |  |  | 2023-07-15 |  | 2025-02-14
23 | 0PT47300 -- THREE CREEK SWITCH (FKA FORNEY SWITCH RELOCATION) - PURCHASE LAND IN FEE | 103500000 | Not Applicable | Not Applicable | 4921533.97 |  | Not Applicable | Not Applicable
24 | 0PT51090 -- GREY WELL DRAW SWITCH - YOSEMITE SUB 138KV LINE: CUT IN AZALEA SUB FOR TARGA | 97000000 | 9548929 | 2023-12-15 | 8078271.96 | 2025-02-14 | -15.4% | Not Applicable
25 | 0PT51437 -- SL GREY WELL DRAW SWITCH - BLUE ACRES SUB 138 KV LINE: RETERMINATE LINE AT GREY WELL DRAW | 97000000 | 1067852.29 | 2023-11-15 | 731577.67 | 2025-02-14 | -31.49% | Not Applicable
26 | 0PT51581 -- GREY WELL DRAW SWITCH - AZALEA SUB - YOSEMITE SUB 138KV LINE: ADD SECOND CIRCUIT | 97000000 | 9706367 | 2024-03-15 | 8341884.97 | 2025-02-14 | -14.06% | Not Applicable
27 | 0PT51582 -- YOSEMITE SUB - BUFFALO SWITCH 138KV LINE: ADD SECOND CIRCUIT | 97000000 | 17266919 | 2024-07-15 | 13478979.57 | 2025-02-14 | -21.94% | Not Applicable
| 0PT54529 -- YOSEMITE SUB - BUFFALO SWITCH 138KV LINE: ADD SECOND CIRCUIT - PURCHASE LAND IN FEE |  |  | 2024-07-15 |  | 2025-02-14
| 0PT54977 -- YOSEMITE SUB-BUFFALO SWITCH 138KV SECOND CIRCUIT : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
28 | 0PT51583 -- SL BUFFALO SWITCH - TRIANGLE SUB 138KV LINE: RETERMINATE LINE AT BUFFALO SWITCH | 97000000 | 1726425 | 2023-12-15 | 625176.96 | 2025-02-14 | -63.79% | Not Applicable
| 0PT53438 -- SL BUFFALO SWITCH - TRIANGLE SUB 138KV LINE: RETERMINATE LINE AT BUFFALO SWITCH : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
29 | 0PT49512 -- ROCKHOUND #1 SWITCH: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER #1 | 97000000 | 59513275.35 | 2023-11-15 | 12175551.06 |  | -79.54% | Not Applicable
| 0PT51619 -- ROCKHOUND SWITCH (FKA ROUGH SWITCH) : PURCHASE OF EASEMENT |  |  | 2023-11-15 |  |  |  | 0
| 0PT49513 -- ROCKHOUND SWITCH: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER #2 |  |  | 2023-11-15 |  |  |  | 0
30 | 0PT51777 -- GREY WELL DRAW SWITCH : 138KV TERMINAL ADDITION | 97000000 | 1458858.35 | 2023-11-15 | 1302933.94 | 2025-02-14 | -10.69% | Not Applicable
31 | 0PT51778 -- SL BUFFALO SWITCH : 138KV TERMINAL ADDITION | 97000000 | 1252764.49 | 2023-12-15 | 1143145.96 | 2025-02-14 | -8.75% | Not Applicable
32 | 0PT51868 -- MIDLAND EAST - FALCON SEABOARD 345 KV LINE: CUT IN ROCKHOUND SWITCH | 97000000 | 5033925.58 | 2024-03-15 | 3452720.14 | 2025-02-14 | -31.41% | Not Applicable
33 | 0PT51869 -- BUFFALO - YOSEMITE 138 KV LINE: CUT IN ROCKHOUND SWITCH | 97000000 | 1102099.77 | 2024-03-15 | 571254.35 | 2025-02-14 | -48.17% | Not Applicable
34 | 0PT51870 -- SL BUFFALO - AZALEA 138 KV LINE: CUT IN ROCKHOUND SWITCH | 97000000 | 1084625.98 | 2024-03-15 | 907942.09 | 2025-02-14 | -16.29% | Not Applicable
35 | 0PT48331 -- CATCLAW SWITCH (FKA MIDKIFF SWITCH REBUILD & EXPANSION - STANTON LOOP) - PURCHASE OF LAND IN FEE | 96900000 | 22401326.63 | 2023-10-15 | 20905980.23 | 2025-02-14 | -6.675% | Not Applicable
| 0PT51182 -- CATCLAW 138 KV SWITCH (FKA MIDKIFF WEST SWITCH): ESTABLISH 138 KV STATION |  |  | 2023-10-15 |  | 2025-02-14
| 0PT53673 -- CATCLAW SWITCH - ACCESS ROAD EASEMENT |  |  | Not Applicable
36 | 0PT50599 -- MIDKIFF SWITCH - DESERT WIND/MCDONALD ROAD 138KV LINE: RETERMINATE INTO CATCLAW SWITCH | 96900000 | 4426137 | 2024-03-15 | 2748243.8 | 2025-02-14 | -37.91% | Not Applicable
37 | 0PT50714 -- SL PEMKIFF - CANAL ROAD 138KV LINE: RETERMINATE INTO CATCLAW SWITCH | 96900000 | 3282613 | 2024-03-15 | 2101319.24 | 2025-02-14 | -35.99% | Not Applicable
| 0PT52243 -- NTUSU CANAL ROAD - RINGO 138KV LINE: RETIREMENTS ASSOCIATED WITH CATCLAW RETERMS |  |  | Not Applicable |  | 2025-02-14
38 | 0PT50718 -- SL PEMKIFF - RINGO 138KV LINE: RETERMINATE INTO CATCLAW SWITCH | 96900000 | 2629188 | 2024-03-15 | 1548022.7 | 2025-02-14 | -41.12% | Not Applicable
39 | 0PT39494 -- GREENBRIER SWITCH (FORMERLY PRINCETON) : ESTABLISH SWITCHING STATION | 91200000 | 7283918 | 2021-03-15 | 8719128.85 | 2025-02-14 | 19.7% | Variance is due to a change in project scope and increased material and labor costs, including engineering consultant costs, on-site inspection services, on-site security services, and Oncor and contractor labor. Additional scope of work includes engineering, design, and construction labor and materials needed to meet municipal permitting requirements, mitigate erosion and drainage issues, and work around poor soil conditions. Materials that experienced cost increases include structural steel, high-voltage breakers, air switches, equipment, relay control equipment, and control centers. Contractor construction labor costs were higher than estimated due to poor soil conditions that increased the time and labor needed for foundation, conduit, and grounding installations, and remobilization charges caused by delays for ERCOT clearance coordination, weather, and material deliveries. Engineering consultant costs were higher than estimated due to municipal surveying, platting, and permitting requirements. Additional protection and control resources were required to meet the project in-service date ahead of ERCOT's clearance restriction deadline. The estimated contractor grading and regrade costs were higher than originally estimated due to extensive site work required to address erosion control and site drainage issues, requiring additional site fill base material installation costs. The multiple delays resulted in an accelerated construction schedule, which required more contract resources to be mobilized for the project, further increasing labor costs.
40 | 0PT42416 -- PAYNE SWITCH - ROYSE CITY 138 KV LINE : REBUILD AUDIE MURPHY POI TO ROYSE SWITCH | 91200000 | 28941915 | 2021-09-15 | 28062740.96 | 2025-02-14 | -3.038% | Not Applicable
| 0PT44921 -- PAYNE SWITCH - ROYSE CITY 138 KV LINE : REBUILD GREENBRIER SWITCH TO ROYSE CITY : ACKNOWLEDGMENT OF PAYMENTS AND EASEMENT MODIFICATION AGREEMENTS |  |  | Not Applicable |  | 2025-02-14
41 | 0PT43646 -- ROYSE SWITCH: 138 KV CB 1970 LINE TERMINAL UPGRADE | 91200000 | 700683 | 2022-03-15 | 788802.91 | 2024-03-15 | 12.58% | Variance is due to a change in project scope and increased material and labor costs. Scope additions include upgrading the existing relaying controls and installing a transfer trip panel to improve operational efficiency and maintain system security. Material costs increased for due to the scope change and price increases for structural steel, high-voltage breakers, air switches, and relaying control equipment. Labor costs increased due to scope changes; a two-month delay in material delivery and associated remobilization costs; additional demolition work; hand-digging for conduit, grounding, and foundations due to the proximity to energized equipment; additional buswork upgrades; additional hauling of equipment and materials; additional job site security; and additional protection and control resources to meet the in-service date.
42 | 0PT45225 -- PAYNE SWITCH - ROYSE CITY 138 KV LINE : REBUILD GREENBRIER SWITCH TO AUDIE MURPHY POI | 91200000 | 11537572 | 2022-07-15 | 12760474.39 | 2024-12-15 | 10.6% | Variance is due to increased material and labor costs for matting and foundation reveals. Substantial additional matting was needed due to rain that caused water levels to rise to as much as 4 feet, covering the ROW. Additional foundation volume was required for higher structure reveals at Lake Lavon crossing, resulting in higher labor cost.
| 0PT49226 -- PAYNE SWITCH - ROYSE CITY 138 KV LINE : ROW ACQUISITION |  |  | Not Applicable |  | 2024-12-15
43 | 0PT45226 -- NEVADA SUBSTATION TO ROYSE SWITCH 138 KV LINE REBUILD | 91200000 | 3029964 | 2021-09-15 | 2155576.18 | 2023-09-15 | -28.86% | Not Applicable
44 | 0PT45401 -- PAYNE SWITCH - ROYSE CITY 138 KV LINE: GREENBRIER SWITCH RETERMINATION | 91200000 | 2278377 | 2021-12-15 | 2617432.83 | 2023-09-15 | 14.88% | Variance is due to increased labor costs. Project required crews to coordinate work over another utility’s substation, work in confined spaces near energized equipment, and provide extensive security for the substation and traffic control in the surrounding area. Additional foundation and wire-pulling crews were required due to an accelerated project schedule. Poor soil conditions resulted in additional labor costs for permanent casings, slurry, and deeper foundations.
45 | 0PT47229 -- ROYSE SWITCH : 138 KV CB 1710 LINE TERMINAL UPGRADE | 91200000 | Not Applicable | Not Applicable | 340104.3 |  | Not Applicable | Not Applicable
46 | 0PT47830 -- CONSAVVY #2: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER | 90200000 | 42462890 | 2022-04-15 | 43252585.49 | 2025-02-14 | 1.86% | Not Applicable
| 0PT47832 -- CONSAVVY #1: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER |  |  | 2022-04-15 |  |  |  | 0
| 0PT46771 -- CONSAVVY SWITCH: ESTABLISH 345/138 KV STATION |  |  | 2022-04-15 |  | 2025-02-14 |  | 0
47 | 0PT46934 -- MIDLAND EAST SUB - SPRABERRY SWITCH 138 KV LINE : CUT IN TO CONSAVVY SWITCH | 90200000 | 1278057 | 2022-06-15 | 1009237.15 | 2024-12-15 | -21.03% | Not Applicable
48 | 0PT46936 -- SPRABERRY SWITCH - STANTON EAST SWITCH 69 KV LINE : REROUTE AROUND CONSAVVY SWITCH | 90200000 | 2104393 | 2022-06-15 | 1699830.26 | 2024-06-15 | -19.22% | Not Applicable
49 | 0PT46941 -- MORGAN CREEK SWITCH - QUAIL SWITCH 345 KV LINE : CUT-IN TO ESTABLISH CONSAVVY SWITCH | 90200000 | 2351854 | 2022-06-15 | 2520321.66 | 2024-06-15 | 7.163% | Not Applicable
50 | 0PT47314 -- LONGSHORE SWITCH - ODESSA EHV SUB 345 KV LINE: CUT-IN TO ESTABLISH CONSAVVY SWITCH | 90200000 | 1748991 | 2022-06-15 | 2508916.98 | 2024-06-15 | 43.45% | Variance is due to a change in project scope and increased material and labor costs. ERCOT cancelled outages, requiring Oncor to build a temporary bypass to maintain the project timeline. The lattice tower crew responsible for the project built the temporary bypass using monopoles, which increased installation costs.
51 | 0PT38107 -- MIDLAND EAST SWITCH - SPRABERRY SWITCH 138 KV LINE : REBUILD | 88500000 | 21717063 | 2021-07-15 | 19302694.7 | 2024-12-15 | -11.12% | Not Applicable
| 0PT45301 -- MIDLAND EAST SWITCH - SPRABERRY SWITCH 138 KV LINE : REBUILD : EASEMENT MODIFICATION AGREEMENTS AND ACKNOWLEDGEMENT OF PAYMENTS |  |  | Not Applicable |  | 2024-12-15
52 | 0PT43250 -- MIDLAND EAST SWITCH - MIDLAND COUNTY NORTHWEST SWITCH 345 KV LINE : RETERMINATE | 88500000 | 2147515 | 2021-09-15 | 3220401.65 | 2024-09-15 | 49.96% | Variance is due to increased material and labor costs resulting from ERCOT clearance issues. ERCOT denied Oncor’s request for an outage to re-terminate the transmission line into the new Midland East Switch, requiring Oncor to build a temporary bypass and redesign structure locations to minimize customer impacts.
53 | 0PT43251 -- MIDLAND EAST SWITCH - FALCON SEABOARD SWITCH 345 KV LINE : RETERMINATE AT MIDLAND EAST SWITCH | 88500000 | 1558975 | 2021-09-15 | 2709758.52 | 2023-12-15 | 73.82% | Variance is due to increased material and labor costs. ERCOT denied Oncor’s outage request, requiring construction of a temporary bypass and redesigned structure locations to minimize customer impacts. Material costs for lattice towers increased from the estimate.
54 | 0PT43312 -- MIDLAND COUNTY NORTHWEST SWITCH - TEXACO MABEE TAP 138 KV LINE : REBUILD | 88500000 | 13082826 | 2022-04-15 | 13504413.71 | 2025-02-14 | 3.222% | Not Applicable
| 0PT46324 -- MIDLAND COUNTY NORTHWEST SWITCH - TEXACO MABEE TAP 138 KV LINE : REBUILD : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
55 | 0PT43651 -- MOCKINGBIRD SUB: 138 KV LINE TERMINAL UPGRADE TO MEET OR EXCEED 3200 A. | 88500000 | 248277 | 2021-07-15 | 356326.49 | 2024-06-15 | 43.52% | Variance is due to a change in project scope, leading to increased labor and remobilization costs. Scope additions include replacing a failed motor operator and the removal, repair, and replacement of existing fencing that was in poor condition.
56 | 0PT43957 -- MIDLAND EAST SWITCH: 345 KV STATION REBUILD | 88500000 | 20264435 | 2021-06-15 | 32367602.06 | 2024-09-15 | 59.73% | Variance is due to a change in project scope that increased material and labor costs, including engineering consultant costs, on-site inspection services, on-site security services, and Oncor and contractor labor costs. Material costs increased due to prices for structural steel, auto-transformers, high-voltage breakers, relay control equipment, and control centers. The autotransformer rigging, crane, and transportation service costs were higher than estimated due to the presence of energized overhead 345 kV and 138 kV circuits. Labor costs increased due to the close proximity of energized equipment, which required hand-digging and hydro-excavation for the conduit, grounding and foundation installations; additional hauling of equipment and materials; additional job site security; and multiple remobilization charges due to clearance and material delays. Contractor grading and regrade costs increased due to additional site work required for erosion control and site drainage, additional base materials for the site expansion, increased transformer leaker and oil retention installation costs, and upgrades to the existing perimeter fence. Additional protection and control contractor resources were required to beat ERCOT's clearance restriction deadline and maintain the in-service date. The expedited construction schedule increased labor costs for installation and demolition services.
| 0PT44928 -- MIDLAND EAST #2: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER |  |  | 2021-06-15 |  | 2024-09-15
| 0PT44608 -- MIDLAND EAST #1: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER |  |  | 2021-06-15 |  | 2024-09-01
57 | 0PT44750 -- MIDLAND EAST SWITCH - MIDESSA SOUTH SWITCH 138 KV LINE : RETERMINATE | 88500000 | 462521 | 2021-04-15 | 576754.11 | 2024-03-15 | 24.7% | Variance is due to increased labor costs resulting from ERCOT clearance issues. ERCOT denied Oncor’s outage request, so a portion of the work was delayed while other projects at Midland East were completed. In order to safely complete the retermination, the remaining work was delayed until an outage was available, which required remobilizations and additional construction labor and coordination.
58 | 0PT50447 -- HACKBERRY SWITCH - DFW B-EAST 138 KV LINE : REBUILD | 80000000 | 7267793 | 2023-11-15 | 7644289.15 | 2025-02-14 | 5.18% | Not Applicable
59 | 0PT50837 -- HACKBERRY SWITCH: INSTALL FIBER COMMUNICATIONS | 80000000 | Not Applicable | Not Applicable | 291989.65 | 2024-02-15 | Not Applicable | Not Applicable
60 | 0PT42525 -- BURNETT SWITCH - OLD LAKE SWITCH 69 KV LINE : REBUILD LANHAM TAP - OLD LAKE SECTION TO 138 KV | 79700000 | 19604624 | 2023-04-15 | 16012262.51 | 2025-02-14 | -18.32% | Not Applicable
61 | 0PT42879 -- BELLEVUE SUB - BOWIE SUB 69 KV LINE: REBUILD SMITH CREEK SUB - TOWER ONE SUB 138 KV LINE | 79700000 | 11036755 | 2022-04-15 | 11507293.05 | 2025-02-14 | 4.263% | Not Applicable
| 0PT47805 -- BELLEVUE SUB - BOWIE SUB 69 KV LINE: REBUILD SMITH CREEK SUB - TOWER ONE SUB 138 KV LINE: ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
62 | 0PT43089 -- HOPEWELL SWITCH: ESTABLISH 4-BREAKER 69 KV RING BUS STATION | 79700000 | 5142682 | 2022-03-15 | 5171712.99 | 2024-12-15 | 0.5645% | Not Applicable
| 0PT44822 -- HOPEWELL SWITCH (AKA MONTAGUE SWITCH) - PURCHASE OF EASEMENT |  |  | Not Applicable |  | 2024-12-15
63 | 0PT43100 -- FISHER ROAD SWITCH: ADD NEW 138 KV TERMINAL | 79700000 | 1190508 | 2022-09-15 | 1279294.04 | 2024-12-15 | 7.458% | Not Applicable
64 | 0PT43108 -- OLD LAKE SWITCH: ESTABLISH STATION WITH A 100 MVA 138/69 KV AUTOTRANSFORMER AND A 3-BREAKER 69 KV RING BUS | 79700000 | 8224356 | 2023-01-15 | 7623175.65 | 2025-02-14 | -7.31% | Not Applicable
65 | 0PT43163 -- SMITH CREEK (FORMERLY BELLEVUE SUB): REBUILD 69 KV STATION WITH A RURAL DESIGN | 79700000 | 2200977 | 2022-04-15 | 2867032.25 | 2025-02-14 | 30.26% | Variance is due to a change in project scope that increased labor costs. The scope changes include a reconfiguration to meet additional clearance requirements and design changes to implement a new standard design for rural substations.
66 | 0PT43226 -- TOWER ONE SUB: ESTABLISH NEW 138X69-12.5 KV SUBSTATION | 79700000 | 4880808 | 2022-03-15 | 6516585.1 | 2024-12-15 | 33.51% | Variance is due to increased material and labor costs resulting from scope changes and unforeseen construction obstacles. The scope change included adding high-voltage equipment for system reliability, low-voltage equipment for utility safety, and a 69 kV voltage transformer, which increased the materials required for the project. Labor costs increased due to unexpected foundation removals; costs to install additional conduit, cable, and foundations; a two-month material delay that resulted in additional costs for security, labor, and remobilizations; and increased contractor costs due to rock encountered in the soil, the amount of cut to build the access road, added riprap, erosion control measures on slopes, and underground culverts.
67 | 0PT46786 -- OLD LAKE SWITCH - BELLEVUE SUB 69 KV LINE: REBUILD TO OLD LAKE SWITCH - SMITH CREEK SUB | 79700000 | 13824822 | 2024-06-15 | 12881962.54 | 2025-02-14 | -6.82% | Not Applicable
| 0PT54267 -- OLD LAKE SWITCH - BELLEVUE SUB 69 KV LINE: REBUILD TO OLD LAKE SWITCH - SMITH CREEK SUB : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
68 | 0PT47460 -- HOPEWELL - JOHNSON SS (BEPC) 138 KV LINE: RETERMINATE TO ESTABLISH HOPEWELL SWITCH | 79700000 | 297610 | 2022-07-15 | 313995.01 | 2025-02-14 | 5.506% | Not Applicable
69 | 0PT47462 -- HOPEWELL - JOY (BEPC) 138 KV LINE: RETERMINATE TO ESTABLISH HOPEWELL SWITCH | 79700000 | 407914 | 2022-07-15 | 345120.85 | 2025-02-14 | -15.39% | Not Applicable
70 | 0PT48506 -- BELLEVUE SUB - BOWIE SUB 69 KV LINE: RECONFIGURATION REMOVE BOWIE SUB CONNECTION | 79700000 | 262528.8 | 2022-10-15 | 268481.54 | 2024-12-15 | 2.267% | Not Applicable
71 | 0PT48508 -- FISHER ROAD SWITCH - RILEY 345 KV LINE: REPLACE STRUCTURE 1/1 | 79700000 | 871584 | 2022-10-15 | 1262369.15 | 2024-12-15 | 44.84% | Variance is due to increased labor costs resulting from ERCOT outage constraints that increased standby time for crews and equipment; the need for grouting around drilled pier structure foundations; and labor for pass-through traffic control.
72 | 0PT48509 -- BURNETT SWITCH - OLD LAKE SWITCH 69 KV LINE: REBUILD FISHER ROAD - LANHAM TAP SECTION TO 138 KV | 79700000 | 15051629 | 2022-08-15 | 13942129.2 | 2025-02-14 | -7.371% | Not Applicable
| 0PT49817 -- BURNETT SWITCH - OLD LAKE SWITCH 69 KV LINE: REBUILD FISHER ROAD - LANHAM TAP SECTION TO 138 KV : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
| 0PT50835 -- FISHER ROAD - LANHAM TAP REBUILD TO 138 KV PURCHASE LAND IN FEE |  |  | Not Applicable |  | 2025-02-14
73 | 0PT50632 -- WATERMILL SWITCH : REBUILD 138 KV YARD | 74900000 | 25111624.53 | 2023-11-15 | 27193893.1 | 2025-02-14 | 8.292% | Not Applicable
74 | 0PT50180 -- WATERMILL SWITCH EXPANSION - PURCHASE OF LAND IN FEE | 74900000 | 48039312.95 | 2024-03-15 | 6193853.45 |  | -87.11% | Not Applicable
| 0PT49516 -- WATERMILL SWITCH: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER #2 |  |  | 2024-03-15 |  |  |  | 0
75 | 0PT52269 -- WATERMILL SWITCH - CEDAR CREST SWITCH 138 KV LINE : RETERMINATION TO NEW WATERMILL SWITCH | 74900000 | 877179.11 | 2024-02-15 | 387813.35 | 2025-02-14 | -55.79% | Not Applicable
76 | 0PT52270 -- WATERMILL SWITCH - CEDAR HILL 138 KV LINE : RETERMINATION TO NEW WATERMILL SWITCH | 74900000 | 2292510.18 | 2024-02-15 | 1001332.02 | 2025-02-14 | -56.32% | Not Applicable
77 | 0PT52325 -- WATERMILL SWITCH - SARGENT ROAD SUB 345 KV LINE : RETERMINATION TO NEW WATERMILL SWITCH | 74900000 | 2701894 | 2024-03-15 | 1317548.75 | 2025-02-14 | -51.24% | Not Applicable
78 | 0PT50184 -- WATERMILL SWITCH - PARKDALE SWITCH 138KV LINE : RETERMINATION TO NEW WATERMILL SWITCH | 74900000 | 1977466.66 | 2024-03-15 | 1457425.9 | 2025-02-14 | -26.3% | Not Applicable
79 | 0PT50185 -- WATERMILL SWITCH - SEAGOVILLE SWITCH 138KV LINE : RETERMINATION TO NEW WATERMILL SWITCH | 74900000 | 1400851.71 | 2024-03-15 | 942105.61 | 2025-02-14 | -32.75% | Not Applicable
80 | 0PT50181 -- WATERMILL SWITCH - CEDAR HILL SWITCH 138KV LINE: RETERMINATION TO NEW WATERMILL SWITCH | 74900000 | 785899 | 2024-04-15 | 524815.51 | 2025-02-14 | -33.22% | Not Applicable
81 | 0PT57059 -- SANDOW - AUSTROP 345 KV LINE : EASEMENT FOR CUT IN TO THE PROPOSED WALLEYE CREEK SWITCH | 74000000 | Not Applicable | 2025-02-15 | 2110989.84 |  | Not Applicable | Not Applicable
82 | 0PT53444 -- WALLEYE CREEK SWITCH : ACQUISITION OF LAND FOR SWITCHING STATION IN FEE TITLE | 74000000 | Not Applicable | 2024-06-15 | 1312227.23 |  | Not Applicable | Not Applicable
83 | 0PT42592 -- ROYSE SWITCH: REMOVE 69 KV YARD AND ESTABLISH 138 KV TERMINAL TO COMMERCE SWITCH | 72100000 | 799329.21 | 2023-02-15 | 1107436.19 | 2025-02-14 | 38.55% | Variance is due to increased material and labor costs resulting from a scope change. The scope change included modifying the existing station layout to install a 138 kV circuit breaker, associated switches, and relaying equipment. Material costs increased due to the additional equipment and price increases for structural steel, high-voltage breakers, air switches, and relaying equipment. Labor costs increased due to the additional demolition work, hauling additional equipment and materials, extended job-site security, buswork upgrades, and the proximity of work to energized equipment, which required hand-digging for the conduit, grounding, and foundations. Material delays resulted in additional remobilization charges.
84 | 0PT42594 -- INGLE SUB - ESTABLISH A NEW 138-25 KV SUBSTATION WITH TWO 28 MVA TRANSFORMERS TO REPLACE CADDO MILLS SUB | 72100000 | 6922256 | 2021-10-15 | 6962153.13 | 2024-09-15 | 0.5764% | Not Applicable
85 | 0PT42598 -- COMMERCE SWITCH : ADD 138 KV TERMINAL ADDITION FOR 138 KV ROYSE LINE CONVERSION | 72100000 | 1488433.79 | 2023-03-15 | 1995309.1 | 2025-02-14 | 34.05% | Variance is due to increased material and labor costs associated with a project scope change. Upgrades to the existing relaying controls and installation of a transfer trip panel were added to the project scope. Material costs increased due to the additional equipment and price increases for structural steel, high-voltage breakers, air switches, and relaying control equipment. Labor costs increased due to the additional demolition work, hauling additional equipment and materials, extended job-site security, buswork upgrades, and proximity of energized equipment, which required hand-digging for the conduit, grounding, and foundation. Material delays resulted in additional remobilization charges.
86 | 0PT42599 -- COMMERCE SUB: REMOVE 69 KV YARD | 72100000 | 1086869.4 | 2023-09-15 | 970422.37 | 2025-02-14 | -10.71% | Not Applicable
87 | 0PT43958 -- BURROW POI - CADDO MILLS EXPLORER TAP 69 KV LINE REBUILD | 72100000 | 10835669 | 2022-02-15 | 9743064.21 | 2024-06-15 | -10.08% | Not Applicable
88 | 0PT43959 -- CADDO MILLS EXPLORER TAP - CADDO MILLS EXPLORER SUB 69 KV LINE REBUILD | 72100000 | 6069434 | 2022-02-15 | 4525399.91 | 2024-12-15 | -25.44% | Not Applicable
| 0PT46325 -- CADDO MILLS EXPLORER TAP - CADDO MILLS EXPLORER SUB 138 KV LINE: REBUILD AND CONVERT 69 KV LINE TO 138 KV OPERATION : ROW ACQUISITION |  |  | Not Applicable | 12639649.27 | 2024-12-15
89 | 0PT43960 -- COMMERCE SWITCH - SCATTER BRANCH SUB 69 KV LINE REBUILD | 72100000 | 12433688 | 2021-06-15 | 12631521.75 | 2025-02-14 | 1.591% | Not Applicable
| 0PT46326 -- COMMERCE SWITCH - SCATTER BRANCH SUB 138 KV LINE: REBUILD AND CONVERT 69 KV LINE TO 138 KV OPERATION : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
90 | 0PT43962 -- SCATTER BRANCH SUB - CADDO MILLS EXPLORER TAP 69 KV LINE REBUILD | 72100000 | 30785002 | 2022-05-15 | 31308650.91 | 2025-02-14 | 1.701% | Not Applicable
91 | 0PT43963 -- BURROW POI - ROYSE SWITCH 138 KV LINE: REBUILD AND CONVERT 69 KV LINE TO 138 KV OPERATION | 72100000 | 11913848.83 | 2023-03-15 | 8723639.31 | 2025-02-14 | -26.78% | Not Applicable
92 | 0PT45299 -- COMMERCE SWITCH - SULPHUR SPRINGS SWITCH 138 KV LINE: RE-TERM AT COMMERCE SWITCH | 72100000 | 639877 | 2021-08-15 | 593740.52 | 2023-09-15 | -7.21% | Not Applicable
93 | 0PT46500 -- BURROW POI : CONVERT FROM 69 KV TO 138 KV | 72100000 | 1160565.62 | 2023-02-15 | 819259.84 | 2025-02-14 | -29.41% | Not Applicable
| 0PT48949 -- BURROW POI/POD ACCESS : PURCHASE IN FEE |  |  | Not Applicable |  | 2025-02-14
94 | 0PT46628 -- CADDO MILLS EXPLORER TAP : REBUILD TAP AS MO STATION | 72100000 | 878313 | 2022-04-15 | 895944.87 | 2024-12-15 | 2.007% | Not Applicable
| 0PT47096 -- CADDO MILLS EXPLORER TAP SWITCH EXPANSION - PURCHASE OF EASEMENT |  |  | Not Applicable |  | 2024-12-15
95 | 0PT50909 -- COMMERCE SUB - COMMERCE SWITCH 138 KV LINE : RE-TERMINATION AT COMMERCE SWITCH | 72100000 | 928794 | 2023-09-15 | 1103866.45 | 2025-02-14 | 18.85% | Variance is due to a change in project scope to install an additional structure for worker safety. After the estimate was submitted, an on-site evaluation determined that construction teams would require an additional structure in order to safely pull wire into the station.
96 | 0PT40562 -- YUCCA DRIVE SWITCH - ROYALTY SUB 69 KV: REBUILD YUCCA DRIVE SWITCH - STRUCTURE 3/6 TO 138 KV | 65000000 | 4439451.35 | 2023-03-15 | 3480451.65 | 2025-02-14 | -21.6% | Not Applicable
| 0PT49411 -- YUCCA DRIVE SWITCH - ROYALTY SUB 69 KV : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
97 | 0PT41044 -- ROYALTY SUB: CONVERT STATION TO 138 KV OPERATION | 65000000 | 4063623.16 | 2023-12-15 | 5048144.01 | 2025-02-14 | 24.23% | Variance is due to a change in project scope and increased material and labor costs. The scope of work expanded to include upgrading backhaul communications for the remote terminal unit. Additional materials and labor were needed to transfer the transformer, including new bushings, gaskets, and contacts, due to the transformer’s age. Lightning arrestors that were installed failed during testing and needed to be replaced. Additional protection and control resources were needed to complete commissioning.
98 | 0PT42092 -- ROYALTY SUBSTATION – BLAIR LAKE SUBSTATION 69 KV LINE : CONVERSION TO 138 KV | 65000000 | 13756725.8 | 2022-12-15 | 15000133.04 | 2025-02-14 | 9.039% | Not Applicable
99 | 0PT42093 -- BLAIR LAKE SUBSTATION - COURTNEY CREEK SWITCH 69 KV LINE: CONVERSION TO 138 | 65000000 | 16108141 | 2022-10-15 | 16009061.64 | 2025-02-14 | -0.6151% | Not Applicable
| 0PT42844 -- BLAIR LAKE SUBSTATION - COURTNEY CREEK SWITCH 69 KV LINE: ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
100 | 0PT42619 -- WOLFCAMP TAP - COURTNEY CREEK SWITCH 69 KV LINE: ADD 2ND CIRCUIT | 65000000 | 4205659 | 2022-10-15 | 3142423.67 | 2025-02-14 | -25.28% | Not Applicable
101 | 0PT45958 -- YUCCA DRIVE SWITCH – CRANE SUB 69 KV LINE: REBUILD STR 3/4 TO WARD SWITCH TO 138 KV | 65000000 | 13490729 | 2023-03-15 | 11924285.49 | 2025-02-14 | -11.61% | Not Applicable
| 0PT49410 -- YUCCA DRIVE SWITCH – CRANE SUB 69 KV LINE : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
102 | 0PT45959 -- WARD SWITCH - ROYALTY SUBSTATION 69 KV LINE : CONVERSION TO 138 KV | 65000000 | 7114968 | 2023-05-15 | 7660117.14 | 2025-02-14 | 7.662% | Not Applicable
| 0PT49227 -- WARD SWITCH - ROYALTY SUBSTATION 69 KV LINE : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
103 | 0PT46113 -- YUCCA DRIVE SWITCH: 138 KV LINE TERMINAL ADDITION | 65000000 | 1025973.82 | 2023-08-15 | 1088688.25 | 2025-02-14 | 6.113% | Not Applicable
104 | 0PT46114 -- THORNTONVILLE SUB: CONVERT STATION TO 138 KV OPERATION | 65000000 | 495864.08 | 2023-09-15 | 877931.54 | 2025-02-14 | 77.05% | Variance is due to a change in project scope and increased material and labor costs. A mobile transformer was added to the project scope due to outage limitations. Labor costs increased due to the mobile transformer, remobilization charges, additional job site security, and additional protection and control resources being needed to maintain the in-service timeline.
105 | 0PT51728 -- COURTNEY CREEK SWITCH - ATHEY SWITCH (AEP) 138 KV LINE: INSTALL LINE FOR ATHEY SWITCH (AEP) POI | 65000000 | 1064616.1 | 2023-11-15 | 278930.83 | 2025-02-14 | -73.8% | Not Applicable
| 0PT51888 -- YUCCA DRIVE SWITCH - NORTHERN NATURAL GAS SUB 69 KV LINE: RETIRE COURTNEY CREEK SWITCH - FORT STOCKTON SWITCH (AEP) 138 KV LINE |  |  | Not Applicable |  | 2025-02-14
106 | 0PT51797 -- COURTNEY CREEK SWITCH: MODIFY RELAYING FOR AEP'S ATHEY SWITCH & INSTALL 69 KV MOAS CONTROLS | 65000000 | Not Applicable | Not Applicable | 302575.31 |  | Not Applicable | Not Applicable
107 | 0PT47577 -- WATERMILL SWITCH - DESOTO SWITCH 345 KV LINE : CUT-IN LOOP NINE SWITCH | 63000000 | 12324127.93 | 2023-01-15 | 10120134.44 | 2025-02-14 | -17.88% | Not Applicable
108 | 0PT47041 -- PEBBLE CREEK SWITCH - LOOP NINE SWITCH 138 KV LINE: CONSTRUCT LINE | 63000000 | 9458796.14 | 2023-01-15 | 8005471.94 | 2025-02-14 | -15.36% | Not Applicable
109 | 0PT47812 -- ESTABLISH LOOP NINE 345/138 KV SWITCH #2 : PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER | 63000000 | 38570962 | 2022-08-15 | 41413973.92 | 2025-02-14 | 7.371% | Not Applicable
| 0PT47816 -- ESTABLISH LOOP NINE 345/138 KV SWITCH #1: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER |  |  | 2022-08-15 |  |  |  | 0
| 0PT47579 -- LOOP NINE SWITCH : ESTABLISH 345/138 KV SWITCHYARD WITH TWO (2) 600 MVA AUTOTRANSFORMERS |  |  | 2022-08-15 |  | 2025-02-14 |  | 0
110 | 0PT47662 -- DESOTO SWITCH: MODIFY RELAYING FOR NEW LOOP NINE SWITCH 345 KV LINE TERMINAL | 63000000 | 301610.47 | 2023-09-15 | 309559.64 | 2025-02-14 | 2.636% | Not Applicable
111 | 0PT47761 -- PEBBLE CREEK SWITCH: INSTALL TWO 138 KV LINE TERMINALS TO LOOP NINE SWITCH AND TWO 138 KV PODS TO COMPASS | 63000000 | 4461165 | 2022-09-15 | 4868351.94 | 2025-02-14 | 9.127% | Not Applicable
112 | 0PT46111 -- BROWNSBORO SUB : REBUILD SUBSTATION | 62700000 | 7076270.08 | 2023-10-15 | 7658560.17 | 2025-02-14 | 8.229% | Not Applicable
| 0PT48726 -- BROWNSBORO SUBSTATION EXPANSION : ACQUISITION OF EASEMENT |  |  | Not Applicable |  | 2025-02-14
113 | 0PT46112 -- ECHOLS SUB : REBUILD STATION TO 138 KV OPERATION (RURAL DESIGN) FORMERLY MURCHISON SUB | 62700000 | 5256713.59 | 2024-02-15 | 3257779.15 | 2025-02-14 | -38.03% | Not Applicable
| 0PT48324 -- ECHOLS SUB (FKA MURCHISON SUBSTATION REBUILD) - PURCHASE OF LAND IN FEE |  |  | Not Applicable |  | 2025-02-14
114 | 0PT46136 -- CHANDLER WEST SWITCH TO MURCHISON SWITCH 69KV: REBUILD TO 138KV | 62700000 | 18559930.84 | 2022-12-15 | 19314500.92 | 2025-02-14 | 4.066% | Not Applicable
| 0PT48269 -- CHANDLER WEST SWITCH TO MURCHISON SWITCH 69KV : EASEMENT ACQUISITION |  |  | Not Applicable |  | 2025-02-14
115 | 0PT48049 -- ATHENS - TYLER SWITCH 69 KV: REBUILD STR 29/2 TO MURCHISON TO 138 KV | 62700000 | 11693852 | 2023-10-15 | 10643579.13 | 2025-02-14 | -8.981% | Not Applicable
| 0PT48236 -- MURCHISON SWITCH TO ATHENS SWITCH 69KV: REBUILD TO 138KV : EASEMENT ACQUISITION |  |  | Not Applicable |  | 2025-02-14
116 | 0PT48339 -- ATHENS - TYLER SWITCH 69KV: REBUILD MURCHISON TO STR 33/1 TO 138KV | 62700000 | 12690433 | 2022-09-15 | 13388184.9 | 2024-12-15 | 5.498% | Not Applicable
| 0PT48464 -- ATHENS - TYLER SWITCH 69KV : EASEMENT ACQUISITION |  |  | Not Applicable |  | 2024-12-15
117 | 0PT52721 -- ATHENS SUB - TYLER SWITCH 69 KV LINE : BROWNSBORO SUB RETERMINATION | 62700000 | 904831 | 2024-02-15 | 901107.71 | 2025-02-14 | -0.4115% | Not Applicable
118 | 0PT52722 -- ATHENS SUB - TYLER SWITCH 69 KV LINE : ECHOLS SUB RETERMINATION | 62700000 | 1288174 | 2024-04-15 | 650242.46 | 2025-02-14 | -49.52% | Not Applicable
119 | 0PT45889 -- HOLLAND SUB - BARTLETT TAP 69KV LINE: REBUILD FROM HOLLAND SUB TO STR. 62/5 | 60800000 | 8791887.09 | 2022-12-15 | 8694936.51 | 2025-02-14 | -1.103% | Not Applicable
120 | 0PT49025 -- CATHEY CREEK SUB: INSTALL STATION #1 | 60800000 | 5312637 | 2023-08-15 | 5206611.45 | 2025-02-14 | -1.996% | Not Applicable
121 | 0PT49813 -- HOLLAND SUB - TAYLOR SUB 69 KV LINE : REBUILD FROM STR. 62/6 - STR. 67/14 | 60800000 | 16319801 | 2023-12-15 | 13894535.83 | 2025-02-14 | -14.86% | Not Applicable
| 0PT53093 -- HOLLAND SUB - TAYLOR SUB 69 KV LINE : REBUILD FROM STR. 62/6 - STR. 67/14 : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
122 | 0PT50122 -- TEMPLE SWITCH - TAYLOR SWITCH 69 KV LINE : REBUILD FROM STR. 67/14 TO STR. 74/13 | 60800000 | 18843818.77 | 2024-04-15 | 12401045.17 | 2025-02-14 | -34.19% | Not Applicable
123 | 0PT50639 -- TEMPLE SWITCH - TAYLOR SWITCH 69 KV LINE : CUT IN FOR CATHEY CREEK SUB & DECOMMISSION HOLLAND SUB | 60800000 | 517785 | 2024-03-15 | 340117.24 | 2025-02-14 | -34.31% | Not Applicable
124 | 0PT47127 -- DONAHOE SUBSTATION : PURCHASE IN FEE | 60800000 | Not Applicable | Not Applicable | 321308.17 |  | Not Applicable | Not Applicable
125 | 0PT47352 -- DONAHOE SUB: ESTABLISH STATION | 60800000 | Not Applicable | Not Applicable | 4983666.13 |  | Not Applicable
126 | 0PT48505 -- ODESSA EHV SWITCH - EDWARDS TAP 138 KV LINE: REBUILD | 60770000 | 38327027 | 2024-03-15 | 32322529.22 | 2025-02-14 | -15.67% | Not Applicable
| 0PT52751 -- ODESSA EHV SWITCH - REXALL SWITCH 138 KV LINE : RETIREMENT ONLY |  |  | Not Applicable |  | 2025-02-14
| 0PT52755 -- REXALL SWITCH - GENERAL TIRE SWITCH 138 KV LINE : RETIREMENT ONLY |  |  | Not Applicable |  | 2025-02-14
127 | 0PT48690 -- WOLF SWITCH: 138 KV CB 14245/14240 LINE TERMINAL MODIFICATIONS | 60770000 | 313936.86 | 2023-12-15 | 284473.57 | 2025-02-14 | -9.385% | Not Applicable
128 | 0PT48694 -- OLEFIN SWITCH: 138 KV LINE TERMINAL MODIFICATIONS | 60770000 | Not Applicable | Not Applicable | 265097.8 |  | Not Applicable | Not Applicable
129 | 0PT40890 -- YUCCA DRIVE SWITCH - MOSS SWITCH 138 KV LINE : REBUILD SECTION FROM MOSS SWITCH TO RACEWAY SWITCH (OXY) POD | 60700000 | 24119836 | 2023-01-15 | 20726565.2 | 2025-02-14 | -14.07% | Not Applicable
| 0PT51209 -- YUCCA DRIVE SWITCH - MOSS SWITCH 138 KV LINE : REBUILD SECTION FROM MOSS SWITCH TO FUTURE OXY POD : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
| 0PT50173 -- MOSS SWITCH - HOLT SWITCH 138 KV LINE : RETIREMENTS ONLY |  |  | 2022-09-15 |  | 2025-02-14
130 | 0PT50174 -- YUCCA DRIVE SWITCH - MOSS SWITCH 138 KV LINE : REBUILD 13.7 MILE SECTION FROM RACEWAY SWITCH (OXY) POD TO SHIN OAK POD | 60700000 | 25073599 | 2023-11-15 | 22910220.71 | 2025-02-14 | -8.628% | Not Applicable
131 | 0PT49654 -- MOSS SWITCH: 138 KV CB 3960 LINE TERMINAL MODIFICATIONS | 60700000 | Not Applicable | Not Applicable | 268920.74 |  | Not Applicable | Not Applicable
132 | 0PT44619 -- BASE CAMP SWITCH: PURCHASE LAND IN FEE TITLE (FOR REBUILD OF EAGLE MOUNTAIN SWITCHYARDS) | 57000000 | 25331071.08 | 2023-02-15 | 610203.12 |  | -97.59% | Not Applicable
133 | 0PT48572 -- SPRABERRY SWITCH – POLECAT CREEK SWITCH 138 KV LINE: REBUILD SPRABERRY SWITCH TO QUARTZ SAND SWITCH | 56900000 | 22619614 | 2023-08-15 | 21328045.71 | 2025-02-14 | -5.71% | Not Applicable
134 | 0PT48573 -- SPRABERRY SWITCH – POLECAT CREEK SWITCH 138 KV LINE: REBUILD QUARTZ SAND SWITCH TO POLECAT CREEK SWITCH | 56900000 | 21169215 | 2024-01-15 | 15113489.97 | 2025-02-14 | -28.61% | Not Applicable
135 | 0PT43159 -- RED LAKES SWITCH - PENWELL POD 138 KV LINE: REBUILD | 56200000 | 18306531 | 2022-12-15 | 20008772.15 | 2025-02-14 | 9.299% | Not Applicable
| 0PT49345 -- RED LAKES SWITCH - PENWELL POD 138 KV LINE : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
136 | 0PT46515 -- MOSS SWITCH: 138 KV CB 3920 LINE TERMINAL UPGRADE | 56200000 | 413295 | 2023-07-15 | 343041.4 | 2025-02-14 | -17% | Not Applicable
137 | 0PT46516 -- ECTOR HARPER SUB: 138 KV LINE TERMINAL UPGRADE | 56200000 | 408478 | 2023-08-15 | 593568.04 | 2025-02-14 | 45.31% | Variance is due to a change in project scope. A temporary bypass was needed to keep the station energized during related construction on the transmission line. The cost of the bypass was charged to the station project.
138 | 0PT48355 -- MOSS SWITCH - RED LAKES SWITCH 138 KV LINE : REBUILD | 56200000 | 21838771 | 2022-07-15 | 20120257.43 | 2025-02-14 | -7.869% | Not Applicable
139 | 0PT48359 -- PENWELL POD - WOLF SWITCH 138 KV LINE : REBUILD | 56200000 | 17500394 | 2022-12-15 | 12094708.11 | 2025-02-14 | -30.89% | Not Applicable
140 | 0PT48561 -- BIG SPRING WEST SWITCH – STANTON EAST SWITCH 138 KV LINE: REBUILD | 52000000 | 32043703 | 2023-08-15 | 24894806.5 | 2025-02-14 | -22.31% | Not Applicable
141 | 0PT49742 -- ONEMILE SWITCH: ESTABLISH 138 KV STATION | 52000000 | 6898882.99 | 2023-11-15 | 5639744.07 | 2025-02-14 | -18.25% | Not Applicable
142 | 0PT49745 -- STANTON EAST SWITCH: 138 KV CB 10325/10330 LINE TERMINAL MODIFICATIONS | 52000000 | 751654.5 | 2023-09-15 | 670485.51 | 2025-02-14 | -10.8% | Not Applicable
143 | 0PT50436 -- BIG SPRING SWITCH - STANTON EAST 138 KV LINE: RECONFIGURE & REBUILD | 52000000 | 7400613 | 2024-04-15 | 4511285.8 | 2025-02-14 | -39.04% | Not Applicable
| 0PT52903 -- BIG SPRING SWITCH - NATURAL DAM SUB 138 KV LINE: RECONFIGURE & REBUILD : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
| 0PT48560 -- BIG SPRING SWITCH – BIG SPRING WEST 138 KV LINE: RETIREMENT ONLY |  |  | Not Applicable |  | 2025-02-14
144 | 0PT51419 -- BEALS CREEK SUB: INSTALL 138 KV CAPACITOR BANK | 52000000 | 3114927.22 | 2024-02-15 | 3076406.22 | 2025-02-14 | -1.237% | Not Applicable
145 | 0PT51027 -- BIG SPRING WEST SWITCH - AIR PARK SWITCH 138 KV LINE: RETERM AT ONEMILE SWITCH | 52000000 | 763091.67 | 2024-03-15 | 766642.76 | 2025-02-14 | 0.4654% | Not Applicable
146 | 0PT48223 -- PALESTINE SOUTH - LONG LAKE 138KV LINE: RETERMINATE AT PALESTINE SOUTH | 50890000 | 1159099 | 2022-10-15 | 1191066.67 | 2025-02-14 | 2.758% | Not Applicable
147 | 0PT48229 -- PALESTINE - PALESTINE SOUTH 138KV LINE: RETERMINATE AT PALESTINE SOUTH | 50890000 | 628258 | 2022-10-15 | 806841.36 | 2025-02-14 | 28.43% | Variance is due to increased material and labor costs. Wet weather and poor soil conditions required the use of matting and additional work for access. Additional costs were incurred due to this project being delayed for a construction season after material had already been received by the contractor.
148 | 0PT48590 -- TESORO SWITCHING STATION (FKA: QUAIL EAST SWITCHING STATION) : ACQUISITION OF EASEMENT | 50200000 | 51315612 | 2022-11-15 | 60258239.11 |  | 17.43% | Variance is due to a change in project scope, increased land acquisition costs, and increased material and labor costs. The scope change added grounding capable of withstanding a higher fault current than the original design. Oncor learned of the need for this change after construction had begun. Land acquisition costs increased due to a combination of extremely limited options for station siting, numerous existing pipelines with exclusive easements in the project area, and urgency to meet the in-service date. To avoid indefinite delays for a CCN and condemnation, Oncor agreed to terms that included relocating existing water pipelines. Material costs increased due to price increases for structural steel, high-voltage circuit breakers, switches, and control centers. Labor costs increased due to additional foundation work required to address sandy soil conditions; additional grading and excavation to install cattle guards and culverts and relocate the pipelines; material delays that resulted in a compressed construction schedule; and additional security due to the extended construction timeline. The costs for additional base for pipeline cover, cattle guards, and culverts, as well as the actual work associated with those items, were not included in the contractor estimates provided to Oncor and were not identified as necessary until after grading/construction began.
| 0PT48541 -- TESORO SWITCH: ESTABLISH 345/138 KV STATION |  |  | 2022-11-15 |  | 2025-02-14
| 0PT46372 -- ESTABLISH TESORO 345/138 KV SWITCH #1: PURCHASE AND STORE (ONE) 345/138 KV, 600 MVA AUTOTRANSFORMER |  |  | 2022-11-15 |  | 2025-02-14
| 0PT43296 -- ESTABLISH TESORO 345/138 KV SWITCH #1: PURCHASE AND STORE (ONE) 345/138 KV, 600 MVA AUTOTRANSFORMER |  |  | Not Applicable
149 | 0PT48645 -- ODESSA EHV SWITCH - SPRABERRY SWITCH 138 KV LINE : ESTABLISH TESORO SWITCH | 50200000 | 2298381.93 | 2023-04-15 | 2197256.96 | 2025-02-14 | -4.4% | Not Applicable
150 | 0PT48648 -- MIDESSA SOUTH SWITCH - ODESSA EHV SWITCH 345 KV LINE : ESTABLISH TESORO SWITCH | 50200000 | 3167643.39 | 2023-04-15 | 3617782.09 | 2025-02-14 | 14.21% | Variance is due to a change in project scope, including an additional 345 kV steel deadend that was needed to match station phasing and a temporary bypass that was needed to keep one circuit of an existing 345 kV double-circuit transmission line energized as required by ERCOT.
151 | 0PT49765 -- CONSAVVY SWITCH - QUAIL SWITCH 345 KV LINE : ESTABLISH TESORO SWITCH | 50200000 | 2605656.42 | 2023-04-15 | 2800606.94 | 2025-02-14 | 7.482% | Not Applicable
152 | 0PT49766 -- ODESSA SUB - MIDESSA SOUTH SWITCH 138 KV LINE : ESTABLISH TESORO SWITCH | 50200000 | 2510464.08 | 2023-03-15 | 2379287.7 | 2025-02-14 | -5.225% | Not Applicable
153 | 0PT47833 -- ESTABLISH EXPANSE #1: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER | 45200000 | 31195698 | 2022-06-15 | 27067622.49 | 2025-02-14 | -13.23% | Not Applicable
| 0PT47813 -- ESTABLISH EXPANSE #2: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER |  |  | 2022-06-15 |  |  |  | 0
| 0PT46566 -- EXPANSE SWITCH (FKA: LENORAH SWITCH): PURCHASE IN FEE |  |  | 2022-06-15 |  |  |  | 0
| 0PT46894 -- EXPANSE SWITCH: ESTABLISH 345/138 KV STATION |  |  | 2022-06-15 |  | 2025-02-14 |  | 0
154 | 0PT46932 -- SL BROWN SUB - GRADY SUB 138 KV LINE: EXPANSE SWITCH CUT IN | 45200000 | 1774555 | 2022-10-15 | 2197658.65 | 2025-02-14 | 23.84% | Variance is due to a change in project scope and increased labor costs to provide line grounding, testing, and inspection services and for daily outages to facilitate construction of another utility’s transmission line cut-in to the Oncor transmission line and crossing needed to establish a new switching station.
| 0PT48703 -- NTUSU BROWN SUB - GRADY SUB 138 KV LINE: RETIREMENTS ONLY |  |  | Not Applicable |  | 2025-02-14
155 | 0PT48805 -- EXPANSE SWITCH - VOLTA SWITCH (WETT) 345KV LINE: TIE LINES | 45200000 | 513300.15 | 2023-03-15 | 303806.48 | 2025-02-14 | -40.81% | Not Applicable
156 | 0PT43548 -- BAYLOR - SEYMOUR 69 KV LINE : REBUILD | 44300000 | 25016336 | 2022-02-15 | 20671519.9 | 2024-12-15 | -17.37% | Not Applicable
| 0PT49066 -- BAYLOR - SEYMOUR 69 KV LINE : REBUILD : EASEMENT ACQUISITION |  |  | Not Applicable |  | 2024-12-15
157 | 0PT47567 -- BAYLOR SWITCH : ADD MOTOR OPERATOR AND TRANSCLOSURE FOR LINE SWITCH | 44300000 | 521974 | 2022-05-15 | 700157.05 | 2024-12-15 | 34.14% | Variance is due to increased material and labor costs and unexpected construction obstacles. Grading and fencing costs increased due to unexpectedly steep slopes at the construction site. Based on the results of a grounding study, the top rock outside the station fence was expanded from 10 feet to 14 feet.
158 | 0PT47396 -- SEYMOUR TAP - OLNEY BEPC SWITCH 69 KV LINE : REPLACE 3 STRUCTURES | 44300000 | 597852 | 2022-04-15 | 500025.76 |  | -16.36% | Not Applicable
159 | 0PT51713 -- HOLLIDAY SUB : INSTALL FIBER COMMUNICATIONS AND RETIRE TERMINAL 69KV CB1700 | 44300000 | Not Applicable | Not Applicable | 276085.52 |  | Not Applicable | Not Applicable
160 | 0PT48570 -- MCDONALD ROAD SWITCH - MORGAN CREEK SWITCH 138 KV LINE: REBUILD NAVIGATION SUB TO MORGAN CREEK SWITCH | 40200000 | 27897986 | 2023-08-15 | 23985771.78 | 2025-02-14 | -14.02% | Not Applicable
| 0PT51255 -- MCDONALD ROAD SUB-MORGAN CREEK SWITCH : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
161 | 0PT48571 -- MCDONALD ROAD SWITCH - MORGAN CREEK SWITCH 138 KV LINE: REBUILD MCDONALD ROAD TO NAVIGATION SUB | 40200000 | 11292287 | 2023-08-15 | 9850213.04 | 2025-02-14 | -12.77% | Not Applicable
| 0PT51254 -- MCDONALD ROAD SWITCH-MORGAN CREEK : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
162 | 0PT49833 -- MORGAN CREEK SWITCH: 138 KV CB 1280 AND CB 1290/1420 LINE TERMINAL UPGRADE | 40200000 | 660366.6 | 2023-09-15 | 516220.11 | 2025-02-14 | -21.83% | Not Applicable
163 | 0PT45724 -- ANDREWS NORTH SUB - MUSTANG SUB 138 KV LINE : REBUILD | 37000000 | 22845646 | 2022-03-15 | 16069672.01 | 2025-02-14 | -29.66% | Not Applicable
164 | 0PT45726 -- MUSTANG SUB - PAUL DAVIS TAP 138 KV LINE : REBUILD | 37000000 | 14717483 | 2022-08-15 | 13054248.42 | 2024-09-15 | -11.3% | Not Applicable
| 0PT48485 -- MUSTANG SUB - PAUL DAVIS TAP 138 KV LINE : EASEMENT ACQUISITION |  |  | Not Applicable |  | 2024-09-15
165 | 0PT46381 -- ANDREWS NORTH SUB : UPGRADE CB 13180/13185 TERMINAL TO 3200A | 37000000 | 493862.36 | 2024-01-15 | 913086.3 | 2025-02-14 | 84.89% | Variance is due to multiple scope changes that increased material and labor costs. The scope changes consisted of replacing three additional 138 kV switches and upgrading the carrier communication to fiber. The scope changes required a temporary mobile transformer for personnel safety and to maintain reliable service, as well as increased labor costs.
166 | 0PT49596 -- LAMESA SWITCH - MCKENZIE DRAW SWITCH 138 KV LINE : REBUILD FROM JIM PAYNE POI - LAMESA SWITCH | 36800000 | 14022070 | 2023-08-15 | 13317266.72 | 2025-02-14 | -5.026% | Not Applicable
167 | 0PT49605 -- MCKENZIE DRAW SWITCH - LAMESA SWITCH 138 KV LINE : REBUILD FROM PAUL DAVIS TAP - JIM PAYNE POI | 36800000 | 22312950 | 2023-12-15 | 17239895.7 | 2025-02-14 | -22.74% | Not Applicable
168 | 0PT48332 -- MUDSTONE SWITCH (FKA PECK TAP SWITCH - STANTON LOOP) - PURCHASE OF EASEMENT | 36200000 | 10623184.54 | 2023-11-15 | 12134832.28 | 2025-02-14 | 14.23% | Variance is due to increased material and labor costs. Material costs increased due to price increases for structural steel, relay panels, circuit breakers, and control schedule. Project experienced several delays that impacted labor costs, including for a delay of the customer project on which this project was dependent; delays to the Station PAD due to land acquisition and grading; and construction of an access road, due to the number of pipeline crossings that had to be negotiated.
| 0PT49261 -- MUDSTONE (PECK TAP) SWITCH: ESTABLISH 138 KV SWITCHING STATION |  |  | 2023-11-15 |  | 2025-02-14
169 | 0PT49527 -- SPRABERRY SWITCH: 138 KV LINE TERMINAL ADDITION | 36200000 | 1465419.46 | 2023-11-15 | 1519983.35 | 2025-02-14 | 3.723% | Not Applicable
170 | 0PT49534 -- SPRABERRY SWITCH - MCDONALD ROAD SUB 138KV LINE AND SPRABERRY SWITCH - GARDEN CITY 69 KV LINE : CUT-IN TO MUDSTONE SWITCH AND CONVERT 69KV TO 138KV | 36200000 | 2529330 | 2024-02-15 | 2300372.52 | 2025-02-14 | -9.052% | Not Applicable
171 | 0PT51820 -- SL DRIVER - SKYWEST 138 KV LINE : RETERM TO NEW TERMINAL AT DRIVER | 36200000 | 998546.76 | 2023-12-15 | 625781.68 | 2025-02-14 | -37.33% | Not Applicable
| 0PT51642 -- NTUSU DRIVER - SKYWEST 138 KV LINE: RETIREMENT ONLY |  |  | Not Applicable |  | 2025-02-14
172 | 0PT49404 -- MUDSTONE SWITCH - PECK SUB 69 KV LINE : REBUILD AND CONVERT TO 138KV | 36200000 | 7579628.62 | 2024-03-15 | 6983481.11 | 2025-02-14 | -7.865% | Not Applicable
| 0PT52433 -- MUDSTONE SWITCH - PECK SUB 69 KV LINE : REBUILD AND CONVERT TO 138KV : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
173 | 0PT49455 -- SPRABERRY SWITCH - MCDONALD ROAD SUB 138KV LINE AND SPRABERRY SWITCH - GARDEN CITY 69 KV LINE : RE-TERMINATE AT SPRABERRY SWITCH AND CONVERT 69KV TO 138KV | 36200000 | 387837 | 2024-04-15 | 323448.2 | 2025-02-14 | -16.6% | Not Applicable
174 | 0PT38110 -- EVERMAN SWITCH - VENUS SWITCH 345 KV LINE : RETERMINATE AT TIMBERVIEW SWITCH | 36000000 | 6350000 | 2020-04-15 | 5400129.29 | 2023-12-15 | -14.96% | Not Applicable
175 | 0PT38113 -- EVERMAN SWITCH - CEDAR HILL SWITCH 345 KV LINE : RETERMINATION AT TIMBERVIEW SWITCH | 36000000 | 3550000 | 2020-04-15 | 3534165.47 | 2023-12-15 | -0.446% | Not Applicable
176 | 0PT38114 -- EVERMAN SWITCH - DECORDOVA SWITCH 345 KV LINE : RETERMINATION AT TIMBERVIEW SWITCH | 36000000 | 3150000 | 2020-04-15 | 2767671.67 | 2023-12-15 | -12.14% | Not Applicable
177 | 0PT41032 -- EVERMAN SWITCH: RECONFIGURE 345 KV STATION BY CONSTRUCTING A 4-BREAKER 345 KV IN A RING BUS ARRANGEMENT | 36000000 | 4728468 | 2021-04-15 | 5786100.93 | 2023-12-15 | 22.37% | Variance is due to a change in project scope and increased material and labor costs. The project scope changed due to the need for an interim design to transition from a breaker-and-a-half to a ring bus configuration while keeping the 345/138 kV autotransformer and 138 kV switching station energized. A temporary bypass was also added to the scope of the project. Material costs increased due to prices rising for structural steel, instrument transformers, relay control equipment, and control centers. Labor costs increased due to the need for demolition of existing equipment and foundations; proximity to energized equipment, which required hand-digging and hydro-excavation for conduit, grounding, and foundations; hauling additional equipment and materials; regrade work to mitigate drainage issues; and additional protection and control resources to upgrade existing relay communications and meet ERCOT’s clearance restriction deadline. The project experienced delays caused by ERCOT clearance coordination and material deliveries, which caused remobilization charges and additional security for the duration of the construction schedule. The compressed construction schedule also increased labor costs.
178 | 0PT46164 -- TIMBERVIEW SWITCH - EVERMAN SWITCH 345 KV LINE : STATION INTERCONNECT | 36000000 | 1722481 | 2021-10-15 | 695979.5 | 2023-08-15 | -59.59% | Not Applicable
179 | 0PT47024 -- WACO WEST SWITCH - TEMPLE 69 KV LINE: REBUILD EDDY SUB – TROY SUB SECTION TO 138 KV | 36000000 | 17551335 | 2024-01-15 | 13751644.69 | 2025-02-14 | -21.65% | Not Applicable
| 0PT53137 -- WACO WEST SWITCH - TEMPLE 69 KV LINE: RECONFIGURE TO PEPPERVINE - TEMPLE ELM CREEK 138 KV LINE : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
180 | 0PT47140 -- PEPPERVINE SWITCH: INSTALL ONE 138 KV LINE TERMINAL | 36000000 | 1653350.44 | 2023-09-15 | 1511917.94 | 2025-02-14 | -8.554% | Not Applicable
181 | 0PT47141 -- TEMPLE ELM CREEK SWITCH: INSTALL ONE 138 KV LINE TERMINAL | 36000000 | 1292171.74 | 2023-10-15 | 1588086.45 | 2025-02-14 | 22.9% | Variance is due to increased material and labor costs and a change in project scope. Project scope expanded to replace yard lights that were no longer in working condition. Material costs increased for circuit breaker, instruments transformers, steel, cable and relay panels. Additional protection and control resources were needed for commissioning.
182 | 0PT47142 -- ROSENTHAL SUB: ESTABLISH 28 MVA 138X69-26.4X13.2 KV TRANSFORMER WITH TWO FEEDER BREAKERS AND ONE TIE BREAKER. | 36000000 | 5451267.38 | 2022-09-15 | 6692692.91 | 2025-02-14 | 22.77% | Variance is due to increased material and labor costs. Material cost increases were driven by higher prices for structural steel, power transformers, and control centers. Labor costs increased due to remobilization charges resulting from the need to coordinate this work with an outage on an upstream transmission line and costs for additional personnel to complete the project on-schedule.
183 | 0PT47143 -- EDDY SUB: REBUILD TO 138/69 KV SUBSTATION WITH (2) 138/69-25 KV TRANSFORMERS | 36000000 | 7674888.26 | 2022-12-15 | 8168526.27 | 2025-02-14 | 6.432% | Not Applicable
184 | 0PT49790 -- BRONZE AGE SUB : ESTABLISH SUBSTATION WITH (1) 138/69-12.5 KV TRANSFORMER AND (2) 12.5 KV FEEDER BREAKERS | 36000000 | 6280985 | 2023-03-15 | 5962631.31 | 2025-02-14 | -5.069% | Not Applicable
| 0PT47302 -- BRONZE AGE SUB (FKA TROY SUBSTATION EXPANSION) - PURCHASE OF LAND |  |  | Not Applicable |  | 2025-02-14
185 | 0PT50108 -- EDDY SUB : STATION MODIFICATIONS FOR CONVERSION TO 138 KV | 36000000 | Not Applicable | Not Applicable | 252682.46 | 2024-05-15 | Not Applicable | Not Applicable
186 | 0PT50157 -- WACO WEST SWITCH - TEMPLE 69 KV LINE: CUT-IN TO ESTABLISH ROSENTHAL 138 KV SWITCH | 36000000 | 1119200.8 | 2023-03-15 | 980538.4 | 2025-02-14 | -12.39% | Not Applicable
187 | 0PT50158 -- WACO WEST SWITCH - TEMPLE 69 KV LINE: CUT-IN TO ESTABLISH EDDY 138 KV SWITCH | 36000000 | 625763.33 | 2023-03-15 | 504834.58 | 2025-02-14 | -19.32% | Not Applicable
188 | 0PT50159 -- WACO WEST SWITCH - TEMPLE 69 KV LINE: CUT-IN TO ESTABLISH BRONZE AGE 138 KV SUB | 36000000 | 959294.86 | 2023-03-15 | 1043246.54 | 2025-02-14 | 8.751% | Not Applicable
189 | 0PT53372 -- WACO WEST SWITCH - TEMPLE 69 KV LINE: RETERMINATE AT TEMPLE ELM CREEK SWITCH | 36000000 | 2639656 | 2024-02-15 | 1825951.93 | 2025-02-14 | -30.83% | Not Applicable
190 | 0PT53373 -- TEMPLE ELM CREEK SWITCH - TEMPLE PECAN CREEK SWITCH 138 KV LINE: REBUILD STR 6/4 TO 6/5 RR XING SPAN | 36000000 | 835538 | 2024-02-15 | 609630.36 | 2025-02-14 | -27.04% | Not Applicable
191 | 0PT52873 -- MONTFORT SWITCH - SHANKLE SWITCH 138 KV LINE: REBUILD TELICO TAP - ENNIS PUMP TAP | 33800000 | 8171027.97 | 2024-02-15 | 7218582.07 | 2025-02-14 | -11.66% | Not Applicable
| 0PT53525 -- MONTFORT SW. - SHANKLE SW. 138KV LINE: REBUILD MONTFORT - ENNIS PUMP TAP : ROW ACQUISITION |  |  | Not Applicable |  | 2025-02-14
192 | 0PT04063 -- EAGLE MOUNTAIN SWITCH: MODIFY RELAYING FOR 138 KV DEEN SWITCH DOUBLE CIRCUIT | 32000000 | 766999 | 2021-04-15 | 519502.63 | 2022-09-15 | -32.27% | Not Applicable
193 | 0PT38432 -- BIG SPRING CRMWD SUB: CONVERT STATION TO 138KV | 32000000 | 2178049 | 2021-06-15 | 2173507.32 | 2023-06-15 | -0.2085% | Not Applicable
194 | 0PT46851 -- BRUSHY CREEK SWITCH - MALLARD SWITCH 138 KV LINE : 69 KV LINE REBUILD FROM BRUSHY CREEK TO STR. 1/5 | 29700000 | 19985182.47 | 2022-12-15 | 13236637.95 | 2025-02-14 | -33.77% | Not Applicable
| 0PT47714 -- TAYLOR SWITCH - ELGIN SWITCH 69 KV LINE : REMOVE 69 KV LINE FROM TAYLOR TO ELGIN SW |  |  | 2022-12-15 |  | 2025-02-14
| 0PT48213 -- BRUSHY CREEK SWITCH - MALLARD SWITCH 138 KV LINE : 69 KV LINE REBUILD FROM TAYLOR - ELGIN : EASEMENT ACQUISITION |  |  | Not Applicable |  | 2025-02-14
195 | 0PT47136 -- TEAL SWITCH: ESTABLISH 345/138 KV STATION | 29700000 | 37104354.76 | 2023-01-15 | 48356254.25 |  | 30.33% | Variance is due to increased material and land acquisition costs. Material costs increased due to price increases for the two autotransformers needed to establish the switching station. Land acquisition costs increased due to a higher property valuation than was included in the estimate.
| 0PT51132 -- TEAL 345/138 KV SWITCH #2: PURCHASE (ONE) 345/138 KV, 600 MVA AUTOTRANSFORMER |  |  | 2023-01-15
| 0PT45862 -- TEAL 345/138 KV SWITCH #1: PURCHASE AND STORE (ONE) 345/138 KV, 600 MVA AUTOTRANSFORMER |  |  | 2023-01-15
| 0PT52905 -- TEAL SWITCH: INSTALL ONE 345 KV LINE TERMINAL FOR HARD TAP CONNECTION |  |  | 2023-01-15
| 0PT47111 -- TEAL SWITCH (FKA: HUTTO EAST SWITCH) : PURCHASE IN FEE |  |  | 2023-01-15
196 | 0PT47717 -- BRUSHY CREEK SWITCH : INSTALL 138 KV LINE TERMINAL FOR MALLARD SWITCH | 29700000 | 1487748 | 2023-01-15 | 1444071.76 | 2025-02-14 | -2.936% | Not Applicable
197 | 0PT50224 -- HUTTO - TAYLOR 138 KV LINE: CUT IN TEAL SWITCH | 29700000 | 6286166.72 | 2023-05-15 | 6415422.22 | 2025-02-14 | 2.056% | Not Applicable
| 0PT49040 -- TAYLOR - HUTTO SWITCH 138KV TAP TO TEAL SWITCH : TRANSMISSION LINE EASEMENT ACQUISITION |  |  | 2023-05-15 |  | 2025-02-14 |  | 0
198 | 0PT46956 -- MUSCOVY SWITCH : PURCHASE IN FEE | 29700000 | Not Applicable | Not Applicable | 12736507.27 |  | Not Applicable | Not Applicable
199 | 0PT50059 -- VINCENT SUB - WILDHORSE POD 138 KV LINE : REBUILD | 29300000 | 7732021 | 2023-09-15 | 6466918.07 | 2025-02-14 | -16.36% | Not Applicable
200 | 0PT50062 -- WILDHORSE POD - TRIBUTARY SWITCH 138 KV LINE : REBUILD | 29300000 | 12675279 | 2023-12-15 | 8742515.91 | 2025-02-14 | -31.03% | Not Applicable
201 | 0PT50196 -- TRIBUTARY SWITCH: ESTABLISH 138 KV STATION | 29300000 | 11504530.45 | 2024-07-15 | 10819267.55 | 2025-02-14 | -5.956% | Not Applicable
| 0PT49359 -- TRIBUTARY SWITCH: PURCHASE APPROXIMATELY 22 ACRES IN FEE TITLE |  |  | 2024-07-15 |  | 2025-02-14 |  | 0
202 | 0PT51769 -- BIG SPRING SWITCH - CHINA GROVE SWITCH 138KV LINE: TRIBUTARY SWITCH (FKA GETTY VEALMOOR TAP) CUT IN | 29300000 | 1707428 | 2024-03-15 | 1031769.06 | 2025-02-14 | -39.57% | Not Applicable
203 | 0PT41233 -- ROANOKE SWITCH - EULESS 138KV LINE: OPGW REPLACEMENT | 25000000 | 495463 | 2020-02-15 | 585428.11 | 2023-06-15 | 18.16% | Variance is due to a change in project scope. Due to the proximity of a portion of the project to a railroad track, a helicopter was used to install OPGW instead of standard ground setup wire stringing methods.
204 | 0PT46074 -- SL EAST STILES SUB - ST. LAWRENCE SUB 138 KV LINE: REBUILD | 23000000 | 15574364 | 2022-08-15 | 13897091.11 | 2025-02-14 | -10.77% | Not Applicable
| 0PT46072 -- NTUSU EAST STILES SUB - ST. LAWRENCE SUB 138 KV LINE : RETIREMENTS ONLY |  |  | Not Applicable |  | 2025-02-14
205 | 0PT47752 -- REPLACE BOWMAN SWITCH #1: PURCHASE AND STORE ONE 345/138 KV, 600 MVA AUTOTRANSFORMER | 13000000 | 8095355.11 | 2022-09-15 | 7932201.65 | 2025-02-14 | -2.015% | Not Applicable
| 0PT46092 -- BOWMAN SWITCH : REPLACE AUTO TRANSFORMER #1 |  |  | 2022-09-15 |  | 2025-02-14 |  | 0
206 | 0PT43019 -- VENUS SWITCH - CEDAR HILL SWITCH 345 KV LINE: RECONDUCTOR VENUS SWITCH - BRITTON ROAD | 10300000 | 5674693 | 2021-11-15 | 5233183.19 | 2025-02-14 | -7.78% | Not Applicable
207 | 0PT43591 -- VENUS SWITCH: REPLACE AS 4486 AND UPGRADE LINE TERMINAL AND ASSOCIATED EQUIPMENT TO MEET OR EXCEED 3200 A FOR CB 4485 AND 4490 | 10300000 | 458141 | 2021-08-15 | 477479.79 | 2024-03-15 | 4.221% | Not Applicable
208 | 0PT45598 -- VENUS SWITCH - CEDAR HILL SWITCH 345 KV LINE: RECONDUCTOR BRITTON ROAD - STR 14/4 | 10300000 | 4461425 | 2021-11-15 | 4235497.73 | 2024-06-15 | -5.064% | Not Applicable
209 | 0PT48097 -- MCGREGOR PHILLIPS TAP SWITCH - WACO WEST SWITCH 69 KV LINE : REBUILD STRUCTURE 15/2 TO HARRIS CREEK SUB | Not Applicable | 12561670 | 2023-03-15 | 11165167.63 | 2025-02-14 | -11.12% | Not Applicable
| 0PT49201 -- MCGREGOR PHILLIPS TAP SWITCH - WACO WEST SWITCH 69 KV LINE : EASEMENT ACQUISITION |  |  | 2023-03-15 |  |  |  | 0
210 | 0PT48098 -- MCGREGOR PHILLIPS TAP SWITCH - WACO WEST SWITCH 69 KV LINE : REBUILD STRUCTURE 24/4B TO MCGREGOR PHILLIPS SWITCH | Not Applicable | 3443330.22 | 2022-10-15 | 4238275.48 | 2025-02-14 | 23.09% | Variance is due to a change in project scope to add one mile of temporary bypass, which resulted in additional material and labor costs. The temporary bypass required additional access work and matting due to ROW conditions.
| 0PT49115 -- MCGREGOR PHILLIPS TAP SWITCH - WACO WEST SWITCH 69 KV LINE : EASEMENT ACQUISITION |  |  | 2022-10-15
211 | 0PT51679 -- AZALEA SUB - PURCHASE OF STATION EASEMENT | Not Applicable | 15381947.99 | 2023-12-15 | 12770815.31 |  | -16.98% | Not Applicable
| 0PT51845 -- AZALEA SUB : ESTABLISH SUBSTATION WITH THREE 47 MVA, 138-25 KV TRANSFORMERS AND FOUR FEEDER BREAKERS |  |  | 2023-12-15 |  |  |  | 0
212 | 0PT51566 -- NTUSU PEMKIFF SWITCH - RINGO SWITCH - STILES SUB 138 KV LINE : RE-TERMINATE RINGO SWITCH RETIREMENT ONLY | Not Applicable | 804564 | Not Applicable | 479563.83 |  | -40.39% | Not Applicable
| 0PT51538 -- SL PEMKIFF SWITCH - RINGO SWITCH - STILES SUB 138 KV LINE : RE-TERMINATE RINGO SWITCH |  |  | 2023-11-15 |  |  |  | 0
213 | 0PT53874 -- BORDER SWITCH - (FKA KYLE RANCH SWITCH) - PURCHASE OF ACCESS ROAD EASEMENT | Not Applicable | Not Applicable | Not Applicable | 1451223.38 |  | Not Applicable | Not Applicable
| 0PT49004 -- BORDER SWITCH - (FKA KYLE RANCH SWITCH) PURCHASE OF LAND IN FEE TITLE |  |  | Not Applicable |  |  | Not Applicable | 0
214 | 0PT49951 -- BEWLEY SUB : REBUILD 138 KV SUBSTATION | Not Applicable | 5112873 | 2022-12-15 | 5202728.82 | 2025-02-14 | 1.757% | Not Applicable
215 | 0PT44103 -- FLAT IRON (FORMERLY TARGA PARKS PLT) SUB : ESTABLISH THREE 138-25 KV 46.7 MVA TRANSFORMERS WITH SIX FEEDER BREAKERS FOR POD, TARGA PIPELINE MID-CONTINENT WESTTEX LLC | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable
216 | 0PT44118 -- JOHNSON DRAW POD - FLAT IRON SUB (TARGA PARKS) 138 KV LINE | Not Applicable | 5257000 | 2021-08-15 | 6133738.95 | 2024-09-15 | 16.68% | Variance is due to increased material and labor costs for the installation of a temporary bypass into Flat Iron Substation. Final costs include costs to prepare a CCN application, which was ultimately withdrawn after the legislature made the project CCN-exempt.
| 0PT44874 -- JOHNSON DRAW SW - FLAT IRON SUB - TL EASEMENTS (TARGA) |  |  | 2021-08-15
217 | 0PT50035 -- ROADRUNNER POI TAP EXPANSION OF LAND RIGHTS FOR CAPACITOR BANK - PURCHASE IN EASEMENT | Not Applicable | 3536983.25 | 2023-08-15 | 3893046.22 |  | 10.07% | Variance is due to increased material and labor costs resulting from the need for additional fill material to meet water runoff requirements and installation of an additional culvert. Additionally, material delays resulted in idle time and remobilization costs. Additional protection and control resources were required to maintain the in-service date.
| 0PT51523 -- ROADRUNNER POD: INSTALL 138 KV CAPACITOR BANK |  |  | 2023-08-15
218 | 0PT51217 -- RIDGEVIEW SUB: ESTABLISH STATION WITH THREE 47MVA 138/26.4KV TRANSFORMERS AND 6 FEEDERS | Not Applicable | 16396730.23 | 2023-08-15 | 13250442.29 |  | -19.19% | Not Applicable
| 0PT48501 -- RIDGEVIEW SUBSTATION : PURCHASE IN FEE |  |  | 2023-08-15 |  |  |  | 0
219 | 0PT49792 -- NTUSU DEWEY LAKE TAP SWITCH - DEWEY LAKE SUB 138 KV LINE : RETIREMENT | Not Applicable | 555031 | 2023-10-15 | 545098.33 |  | -1.79% | Not Applicable
| 0PT51154 -- QUARTZ SAND SWITCH - DEWEY LAKE SUB 138 KV LINE : CONSTRUCT NEW LINE |  |  | 2023-10-15 |  |  |  | 0
220 | 0PT49550 -- TEN MILE SUB (FKA BELTLINE ROAD #1 SUB) - PURCHASE IN FEE | Not Applicable | 10464275.35 | 2023-09-15 | 11258704.36 |  | 7.592% | Not Applicable
| 0PT50975 -- TEN MILE SUB (FORMERLY GREENE SUB): ESTABLISH STATION WITH TWO TRANSFORMERS |  |  | 2023-09-15 |  |  |  | 0
221 | 0PT50045 -- HOWE SUB (FKA SHERMAN SOUTH SUBSTATION) : PURCHASE IN FEE | Not Applicable | 10973846.62 | 2023-11-15 | 10245091.3 |  | -6.641% | Not Applicable
| 0PT50967 -- HOWE SUB (FORMERLY SHERMAN SOUTH SUB): ESTABLISH STATION WITH TWO TRANSFORMERS |  |  | 2023-11-15 |  |  |  | 0
222 | 0PT52842 -- NTUSU BUFFALO SUB - SALE RANCH SUB 138 KV LINE : REMOVE EXISTING STRUCTURE 4/1 | Not Applicable | 1978800 | 2023-11-15 | 1179229.71 |  | -40.41% | Not Applicable
| 0PT50901 -- SL BUFFALO SUB - SALE RANCH SUB 138 KV LINE : ESTABLISH WISHBONE POD FOR BRAZOS MIDSTREAM |  |  | 2023-11-15 |  |  |  | 0
223 | 0PT51504 -- LAZY RANCH FKA MUSTANG SPRINGS SUB - PURCHASE LAND IN FEE TITLE | Not Applicable | 8793582.66 | 2023-07-15 | 8251329.94 |  | -6.166% | Not Applicable
| 0PT50817 -- LAZY RANCH SUB (FKA MUSTANG SPRINGS SUB) : ESTABLISH STATION WITH TWO 138-25 KV TRANSFORMERS |  |  | 2023-07-15 |  |  |  | 0
224 | 0PT50253 -- SL ROUGHNECK TAP: 138 KV LINE TERMINAL UPGRADE | Not Applicable | 459939.13 | 2023-09-15 | 144885.98 |  | -68.5% | Not Applicable
| 0PT50769 -- NTUSU ROUGHNECK TAP : RETIRE SWITCH ASSETS | Not Applicable |  | 2023-09-15 |  |  |  | 0
225 | 0PT51085 -- SL FALCON SEABOARD-MIDLAND EAST 345KV LINE : ROW ACQUISITION | Not Applicable | 4633089 | 2023-03-15 | 4183877.14 |  | -9.696% | Not Applicable
| 0PT49807 -- FALCON SEABOARD - MIDLAND EAST 345KV LINE: REPLACE STRS 61/2-61/5 | Not Applicable |  | 2023-03-15 |  |  |  | 0
226 | 0PT48318 -- STEER SUBSTATION (FKA BIG SPRINGS) : PURCHASE IN FEE | Not Applicable | 8326843.3 | 2023-07-15 | 8063547.42 |  | -3.162% | Not Applicable
| 0PT49746 -- STEER SUB: ESTABLISH 138-12.5 KV STATION WITH TWO TRANSFORMERS |  |  | 2023-07-15
| 0PT54643 -- STEER SUBSTATION EXPANSION : PURCHASE IN FEE |  |  | 2023-07-15
227 | 0PT49664 -- ENDEAVOR SWITCH : ESTABLISH 345 KV STATION FOR A POINT-OF-INTERCONNECTION (POI) FOR DESERT WILLOW BESS | Not Applicable | 11325067.55 | 2023-06-15 | 10406203.01 |  | -8.114% | Not Applicable
| 0PT51698 -- ENDEAVOR SWITCH (DESERT WILLOW BESS) PURCHASE LAND IN FEE TITLE | Not Applicable |  | 2023-06-15 |  |  |  | 0
228 | 0PT48928 -- QUARTZ SAND SWITCH (FKA DEWEY LAKE) : PURCHASE IN FEE | Not Applicable | 9228939.54 | 2023-05-15 | 9860377.99 |  | 6.842% | Not Applicable
| 0PT49660 -- QUARTZ SAND (DEWEY LAKE) SWITCH: ESTABLISH 138 KV STATION | Not Applicable |  | 2023-05-15 |  |  |  | 0
229 | 0PT50541 -- NTUSU EXPANSE SWITCH - BROWN SWITCH 138 KV LINE : RETIREMENTS ONLY FOR MERRICK TAP | Not Applicable | 2573674 | 2023-10-15 | 2463846.34 |  | -4.267% | Not Applicable
| 0PT49445 -- SL EXPANSE SWITCH - BROWN SWITCH 138 KV LINE : INSTALL MERRICK TAP | Not Applicable |  | 2023-10-15 |  |  |  | 0
230 | 0PT49546 -- PIN OAK SWITCH - FAIRFIELD WEST SWITCH 138KV LINE : ROW ACQUISITION | Not Applicable | 4953213 | 2023-03-15 | 5082855.85 |  | 2.617% | Not Applicable
| 0PT48909 -- PIN OAK SWITCH - FAIRFIELD WEST SWITCH 138KV LINE: REBUILD FAIRFIELD SWITCH (BEPC) - BIG BROWN TAP | Not Applicable |  | 2023-03-15 |  |  |  | 0
231 | 0PT47487 -- NTUSU OGALLALA SWITCH - TULE CANYON SWITCH 345 KV LINE: REMOVAL FOR OZARK TRAIL SWITCH CUT-IN | Not Applicable | 1665988 | 2022-10-15 | 1248548.19 |  | -25.06% | Not Applicable
| 0PT48780 -- SL OGALLALA SWITCH - TULE CANYON SWITCH 345 KV LINE : CUT-IN FOR OZARK TRAIL SWITCH | Not Applicable |  | 2022-10-15 |  |  |  | 0
232 | 0PT48727 -- W. PLANO-ANNA SW - STONE CREEK : ROW - TRANSMISSION LINE 138KV EASEMENTS | Not Applicable | 9770654.45 | 2023-02-15 | 8316833.11 |  | -14.88% | Not Applicable
| 0PT48698 -- STONE CREEK SW - ANNA SW 138 KV LINE: CUT IN HAGGERTY SWITCH | Not Applicable |  | 2023-02-15 |  |  |  | 0
233 | 0PT51660 -- NTUSU MIDKIFF SWITCH - PEMKIFF SUB 138 KV LINE : RETIREMENT ONLY | Not Applicable | 1754563 | 2023-10-15 | 1593122.2 |  | -9.201% | Not Applicable
| 0PT48568 -- SL MIDKIFF SWITCH – PEMKIFF 138 KV LINE: REBUILD | Not Applicable |  | 2023-10-15 |  |  |  | 0
234 | 0PT43110 -- NTUSU LUTHER SUB - VEALMOOR SUB 138 KV LINE : RETIREMENT ONLY | Not Applicable | 18076053 | 2023-08-15 | 15140141.9 |  | -16.24% | Not Applicable
| 0PT52074 -- SL LUTHER-VEALMOOR 138KV LINE: REBUILD : ROW ACQUISITION |  |  | 2023-08-15 |  |  |  | 0
| 0PT48567 -- SL LUTHER – VEALMOOR 138 KV LINE: REBUILD |  |  | 2023-08-15 |  |  |  | 0
235 | 0PT49583 -- NTUSU TALL CITY - PECAN GROVE 138KV LINE: RETIREMENT ONLY | Not Applicable | 15694795 | 2023-08-15 | 12456649.34 |  | -20.63% | Not Applicable
| 0PT48562 -- SL TALL CITY – PECAN GROVE 138 KV LINE: REBUILD |  |  | 2023-08-15 |  |  |  | 0
236 | 0PT50404 -- NTUSU DRIVER – HADACOL CORNER 138 KV LINE: REMOVALS ONLY | Not Applicable | 8367555 | 2023-08-15 | 7461641.34 |  | -10.83% | Not Applicable
| 0PT51390 -- NTUSU HADACOL CORNER - CANAL ROAD 138 KV LINE: REMOVALS ONLY | Not Applicable |  | 2023-08-15 |  |  |  | 0
| 0PT48559 -- SL DRIVER – HADACOL CORNER 138 KV LINE: REBUILD | Not Applicable |  | 2023-08-15 |  |  |  | 0
237 | 0PT49571 -- NTUSU EINSTEIN – ST. LAWRENCE 138 KV LINE: RETIREMENT ONLY | Not Applicable | 11264371 | 2023-03-15 | 9753092.01 |  | -13.42% | Not Applicable
| 0PT50862 -- SL EINSTEIN – ST. LAWRENCE 138 KV LINE: REBUILD : ROW ACQUISITION | Not Applicable |  | 2023-03-15 |  |  |  | 0
| 0PT48554 -- SL EINSTEIN – ST. LAWRENCE 138 KV LINE: REBUILD | Not Applicable |  | 2023-03-15 |  |  |  | 0
238 | 0PT49641 -- NTUSU SOUTH MIDLAND – PECAN GROVE 138KV LINE: RETIREMENT ONLY | Not Applicable | 20949939 | 2023-01-15 | 17080151.56 |  | -18.47% | Not Applicable
| 0PT48553 -- SL SOUTH MIDLAND – PECAN GROVE 138 KV LINE: REBUILD | Not Applicable |  | 2023-01-15 |  |  |  | 0
| 0PT51256 -- SL SOUTH MIDLAND-PECAN GROVE 138KV REBUILD : ROW ACQUISITION | Not Applicable |  | 2023-01-15 |  |  |  | 0
239 | 0PT48742 -- NTUSU BLUE ACRES- YOSEMITE 138 KV LINE: REBUILD RETIREMENTS ONLY | Not Applicable | 13566439 | 2023-03-15 | 11179354.46 |  | -17.6% | Not Applicable
| 0PT48544 -- SL BLUE ACRES- YOSEMITE 138 KV LINE: REBUILD | Not Applicable |  | 2023-03-15 |  |  |  | 0
| 0PT50861 -- SL BLUE ACRES- YOSEMITE 138 KV LINE: REBUILD : ROW ACQUISITION | Not Applicable |  | 2023-03-15 |  |  |  | 0
240 | 0PT46856 -- FLOYD BRANCH SUB FKA CEDARDALE SUBSTATION : ACQUISITION OF LAND | Not Applicable | 10049090.88 | 2023-07-15 | 10911100.46 |  | 8.578% | Not Applicable
| 0PT48489 -- FLOYD BRANCH SUB (FKA CEDARDALE SUB): ESTABLISH 138-12.5 KV STATION WITH ONE 47 MVA TRANSFORMER & THREE FEEDER BREAKERS |  |  | 2023-07-15 |  |  |  | 0
241 | 0PT49382 -- SL CONSAVVY SWITCH - PRONGHORN SWITCH 138 KV LINE : ROW ACQUISITION | Not Applicable | 10445048 | 2022-07-15 | 7112782.39 |  | -31.9% | Not Applicable
| 0PT48360 -- SL CONSAVVY SWITCH - PRONGHORN SWITCH 138 KV LINE: REBUILD | Not Applicable |  | 2022-07-15 |  |  |  | 0
242 | 0PT52793 -- MORGAN CREEK SWITCH - BARBER LAKE SWITCH 138 KV LINE : REBUILD WEST CIRCUIT : ROW ACQUISITION | Not Applicable | 8654396 | 2024-01-15 | 6472110.13 |  | -25.22% | Not Applicable
| 0PT48020 -- MORGAN CREEK SWITCH - BARBER LAKE SWITCH 138 KV LINE : REBUILD WEST CIRCUIT | Not Applicable |  | 2024-01-15 |  |  |  | 0
243 | 0PT49372 -- WACO WEST SWITCH - TEMPLE ELM CREEK SWITCH 138 KV LINE : ROW ACQUISITION | Not Applicable | 180666.19 | 2023-03-15 | 848248.64 |  | 369.5% | The variance between the reported cost estimate and actual costs is due to a reporting error on Oncor's September 2023 MCPR, where the cost estimate was first reported. Variance from correct cost estimate is -27%.
| 0PT47962 -- WACO WEST SWITCH - TEMPLE ELM CREEK SWITCH 138 KV LINE : WACO SANGER AVENUE CUT IN | Not Applicable |  | 2023-03-15
244 | 0PT49224 -- WACO NORTH TAP - WACO WEST SUB 138 KV LINE : ROW ACQUISITION | Not Applicable | 839736.37 | 2023-03-15 | 673995.73 |  | -19.74% | Not Applicable
| 0PT47961 -- WACO NORTH TAP - WACO WEST SUB 138 KV LINE : WACO SANGER AVENUE TERMINATION | Not Applicable |  | 2023-03-15 |  |  |  | 0
245 | 0PT49225 -- WACO WEST SWITCH - WACO EAST SWITCH - ELM MOTT SWITCH 138 KV LINE : ROW ACQUISITION | Not Applicable | 988490.45 | 2023-03-15 | 725290.64 |  | -26.63% | Not Applicable
| 0PT47958 -- WACO WEST SWITCH - WACO EAST SWITCH - ELM MOTT SWITCH 138 KV LINE : WACO SANGER AVENUE RETERMINATION | Not Applicable |  | 2023-03-15 |  |  |  | 0
246 | 0PT47900 -- NTUSU TRIANGLE - YOSEMITE 138KV LINE: RETIREMENT ONLY | Not Applicable | 23686900 | 2023-03-15 | 25169774.11 |  | 6.26% | Not Applicable
| 0PT50219 -- SL TRIANGLE - YOSEMITE 138KV LINE: REBUILD : ROW ACQUISITION |  |  | 2023-03-15 |  |  |  | 0
| 0PT47911 -- SL TRIANGLE - YOSEMITE 138KV LINE: REBUILD |  |  | 2023-03-15 |  |  |  | 0
247 | 0PT49243 -- NTUSU BUFFALO SUB : REMOVE AND RETIRE 138 KV BUS PROTECTION PANELS | Not Applicable | 560304 | 2022-09-15 | 1228270.49 |  | 119.2% | Variance is due to increased material and labor costs resulting from ERCOT clearance restrictions and the need to add a temporary bypass and mobile transformer to the scope of work. ERCOT cancelled Oncor’s requested outage, which led to an increase in labor costs for energized work and remobilizing construction resources. ERCOT clearance restrictions also resulted in Oncor needing to install a temporary bypass and a mobile transformer to maintain reliable service in the area, which added material and labor costs that were not included in the estimate. Commissioning this legacy Sharyland station to Oncor’s standards required additional protection and control resources that further increased labor costs.
| 0PT47745 -- SL BUFFALO SUB: 138 KV CB 5103/5105 LINE TERMINAL UPGRADE AND MODIFY 138 KV BUS PROTECTION |  |  | 2022-09-15
248 | 0PT51210 -- PEBBLE CREEK SWITCH - DESOTO SWITCH 138 KV LINE : REBUILD : ROW ACQUISITION | Not Applicable | 7074033 | 2023-08-15 | 8717386.53 |  | 23.23% | Variance is due to increased material and labor costs. This project was in an area of heavy residential and commercial development. Based on unique circumstances such as limited work space due to congested ROW, proximity of residential and commercial structures, and traffic control plans, MSA labor unit pricing was not applicable for this project, resulting in higher cost. To prevent damage to residential property, matting was also needed for the entire length of the project. The initial estimate was based on previous projects in the area, limited matting and access costs, MSA unit labor pricing, and assumed minimal negotiated items. However, when project plans were finalized with the contractor, it was determined that construction would need to take additional precautions to safely rebuild the line. Due to the close proximity of residential buildings, quantity of distribution line crossings, quantity of road and driveway crossings within the ROW, the contractor would need additional traffic control, equipment, and time to transfer old conductor to new structures and pull new wire in. Additionally, due to wet conditions along the ROW and the residential area, matting would be needed to access new structure locations and prevent damage to landowner property.
| 0PT47658 -- PEBBLE CREEK SWITCH - DESOTO SWITCH 138 KV LINE : REBUILD |  |  | 2023-08-15
249 | 0PT48959 -- WOLF SWITCH - GENERAL TIRE SWITCH: REBUILD SANDHILLS TAP 138 KV LINE TO STR 4/5: ROW ACQUISITION | Not Applicable | 7446053 | 2022-04-15 | 6611390.94 |  | -11.21% | Not Applicable
| 0PT47613 -- WOLF SWITCH - GENERAL TIRE SWITCH: REBUILD SANDHILLS TAP 138 KV LINE UP TO STR. 4/5 USING DOUBLE-CIRCUIT STRUCTURES | Not Applicable |  | 2022-04-15 |  |  |  | 0
250 | 0PT48287 -- DRY WIND 138 KV TAP: ACQUIRE LAND RIGHTS FOR A NEW TAP LINE BETWEEN YARBOROUGH SUB AND SANDHILLS TAP LINE | Not Applicable | 867633 | 2022-05-15 | 849274.84 |  | -2.116% | Not Applicable
| 0PT47533 -- DRY WIND TAP : ESTABLISH NEW H-FRAME TAP ON THE ODESSA EHV - WOLF SWITCH 138 KV LINE | Not Applicable |  | 2022-05-15 |  |  |  | 0
251 | 0PT48955 -- SANDHILLS 138 KV TAP EXPANSION LAND RIGHT ACQUISITIONS | Not Applicable | 857678 | 2022-10-15 | 836873.18 |  | -2.426% | Not Applicable
| 0PT47532 -- SANDHILLS TAP: INSTALL SCADA-CONTROLLED MOTOR OPERATORS ON EXISTING TAP. | Not Applicable |  | 2022-10-15 |  |  |  | 0
252 | 0PT51397 -- MCGREGOR PHILLIPS - MCGREGOR HERCULES 69 KV LINE: RETIREMENTS ONLY | Not Applicable | 6163600 | 2023-01-15 | 6384718.15 |  | 3.587% | Not Applicable
| 0PT47500 -- BEWLEY SUBSTATION - MCGUFFEY POD 138 KV LINE: ESTABLISH MCGUFFEY POD FOR MESSER LLC | Not Applicable |  | 2023-01-15 |  |  |  | 0
253 | 0PT49132 -- ASHBY POD; ROW-ACQUIRE STATION IN DEED | Not Applicable | 2075348 | 2022-05-15 | 2164604.16 |  | 4.301% | Not Applicable
| 0PT47494 -- ASHBY POD : ESTABLISH 138KV POINT OF DELIVERY (ENERGY TRANSFER GC NGL PIPELINES LP) | Not Applicable |  | 2022-05-15 |  |  |  | 0
254 | 0PT46905 -- CASTLEMAN SUBSTATION : PURCHASE IN FEE | Not Applicable | 6220625 | 2023-03-15 | 6506556.33 |  | 4.597% | Not Applicable
| 0PT47405 -- CASTLEMAN SUB (FKA SOUTH HEWITT SUB): ESTABLISH STATION | Not Applicable |  | 2023-03-15 |  |  |  | 0
255 | 0PT47108 -- VANGUARD SUBSTATION : PURCHASE IN FEE | Not Applicable | 10372355.48 | 2023-07-15 | 9167211.43 |  | -11.62% | Not Applicable
| 0PT47403 -- VANGUARD SUB (FORMERLY MESQUITE LUCAS SUB): ESTABLISH 138/12.5 KV STATION | Not Applicable |  | 2023-07-15 |  |  |  | 0
256 | 0PT47363 -- PLANO SUB: REBUILD STATION | Not Applicable | 10581061 | 2022-08-15 | 10866401.15 |  | 2.697% | Not Applicable
| 0PT46957 -- PLANO SUB : PURCHASE IN FEE |  |  | 2022-08-15
257 | 0PT47880 -- PLANO TENNYSON ROAD SUB : REPLACE STATION #2 RELAYING |  | Not Applicable | Not Applicable | 1490379.16 |  | Not Applicable | Not Applicable
258 | 0PT47361 -- TEMPLETON SUB: ESTABLISH SUBSTATION WITH ONE 28 MVA TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable | 6068762 | 2023-07-15 | 5730449.45 |  | -5.575% | Not Applicable
| 0PT47104 -- TEMPLETON SUBSTATION (FKA REAGOR SPRINGS SUB) - PURCHASE OF LAND |  |  | 2023-07-15 |  |  |  | 0
259 | 0PT46922 -- RUNAWAY BAY SUBSTATION (FORMERLY BALSORA SUBSTATION) - PURCHASE OF LAND | Not Applicable | 5865337 | 2023-03-15 | 5163458.75 |  | -11.97% | Not Applicable
| 0PT47356 -- RUNAWAY BAY SUB: ESTABLISH WITH ONE 138-12.5 KV TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable |  | 2023-03-15 |  |  |  | 0
260 | 0PT46906 -- CIRCLE POINT SUBSTATION : PURCHASE IN FEE | Not Applicable | 9314574.12 | 2023-07-15 | 8586934.75 |  | -7.812% | Not Applicable
| 0PT47355 -- CIRCLE POINT SUB: ESTABLISH STATION | Not Applicable |  | 2023-07-15 |  |  |  | 0
261 | 0PT52384 -- THORNDALE NORTH SUB EXPANSION : PURCHASE IN FEE | Not Applicable | 2901985.88 | 2023-09-15 | 2694753.47 |  | -7.141% | Not Applicable
| 0PT47354 -- THORNDALE NORTH SUB: INSTALL 138 KV CAPACITOR BANK | Not Applicable |  | 2023-09-15 |  |  |  | 0
262 | 0PT47102 -- VINCENT SWITCH (FKA GETTY VEALMOOR SWITCH) - PURCHASE OF LAND | Not Applicable | 5650762 | 2023-01-15 | 5883929.82 |  | 4.126% | Not Applicable
| 0PT47350 -- VINCENT SUB (FKA GETTY VEALMOOR SUB): ESTABLISH STATION WITH A 138-25 KV 46.4 MVA TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable |  | 2023-01-15 |  |  |  | 0
263 | 0PT47343 -- PINTAIL SWITCH : ESTABLISH BREAKER-AND-A-HALF STATION FOR SAS | Not Applicable | 13890108 | 2022-04-15 | 14895297.24 |  | 7.237% | Not Applicable
| 0PT47759 -- PINTAIL SWITCH POD - ROW STATION - PURCHASE IN FEE | Not Applicable |  | 2022-04-15 |  |  |  | 0
264 | 0PT47105 -- STARR RANCH SUBSTATION (FKA NORMAN CROSSING) - PURCHASE OF LAND | Not Applicable | 12035583.3 | 2022-12-15 | 11501381.59 |  | -4.439% | Not Applicable
| 0PT47255 -- STARR RANCH SUB (NORMAN CROSSING): ESTABLISH 138/24.9 KV STATION | Not Applicable |  | 2022-12-15 |  |  |  | 0
265 | 0PT47929 -- NTUSU BLUE ACRES SUB - SOUTH MIDLAND SUB 138KV LINE: RETIREMENT ONLY | Not Applicable | 12400488 | 2022-10-15 | 9929435.31 |  | -19.93% | Not Applicable
| 0PT47106 -- SL BLUE ACRES SUB - GREY WELL DRAW SUB 138 KV LINE : REBUILD | Not Applicable |  | 2022-10-15 |  |  |  | 0
266 | 0PT47345 -- NTUSU BUFFALO SUB - TRIANGLE SUB 138 KV LINE : RETIREMENT ONLY | Not Applicable | 7913408 | 2022-12-15 | 6526672.97 |  | -17.52% | Not Applicable
| 0PT47103 -- SL BUFFALO SWITCH - TRIANGLE SWITCH 138 KV LINE : REBUILD | Not Applicable |  | 2022-12-15 |  |  |  | 0
267 | 0PT47071 -- NAVIGATION SUB (WEST MITCHELL COUNTY) PURCHASE LAND IN FEE TITLE | Not Applicable | 5480525 | 2022-08-15 | 6493396.37 |  | 18.48% | Variance is due to increased material and labor costs. Price increases for the power transformer, control center, and other items led to higher material costs. Additionally, labor costs for field construction, protection and control services, and geotechnical services were higher than originally estimated due to additional needs for ditch-digging and associated underground utility locates, rock cushion sand, and drilling; grounding; conduit and control cable installation; bus supports; bus couplers; and static wire installation being greater than initially estimated.
| 0PT46981 -- NAVIGATION SUB : ESTABLISH SUBSTATION WITH ONE 47 MVA TRANSFORMER AND TWO 25 KV FEEDER BREAKERS TARGA'S PS4 | Not Applicable |  | 2022-08-15
268 | 0PT48954 -- WOLF SWITCH - GENERAL TIRE SWITCH: REBUILD SANDHILLS TAP FROM STR 4/5 TO SANDHILLS SUB: ROW ACQUISITION | Not Applicable | 11133776 | 2022-04-15 | 14132920.99 |  | 26.94% | Variance is due to a change in project scope and increased material and labor costs. Right-of-way acquisition issues made it necessary to relocate and redesign a portion of the project. This effort included developing alternative designs to relocate Dry Wind Tap, adding structures to accommodate the revised line and tap design, and additional construction for access due to soil conditions at the alternate tap location. Sandy soil conditions required casing on every structure foundation and more extensive erosion control than previously estimated.
| 0PT46954 -- WOLF SWITCH - GENERAL TIRE SWITCH: REBUILD SANDHILLS TAP FROM STR. 4/5 TO SANDHILLS SUBSTATION 138 KV LINE SECTION USING DOUBLE-CIRCUIT STRUCTURES | Not Applicable |  | 2022-04-15
269 | 0PT48085 -- ODESSA EHV SWITCH - MONAHANS - WOLF SWITCH: LINE WORK FOR DRY WIND TAP TO SANDHILLS SUB RETIREMENTS ONLY | Not Applicable | 3706579 | 2022-04-15 | 2509001.98 |  | -32.31% | Not Applicable
| 0PT46950 -- ODESSA EHV SWITCH - MONAHANS - WOLF SWITCH: LINE WORK FOR DRY WIND TAP TO SANDHILLS SUB | Not Applicable |  | 2022-04-15 |  |  |  | 0
270 | 0PT47001 -- SANDHILLS SUB: SECURE ADDITIONAL ELECTRIC POWER STATION EASEMENT AREA | Not Applicable | 5919552 | 2022-05-15 | 6256091.06 |  | 5.685% | Not Applicable
| 0PT46892 -- SANDHILLS SUB: REPLACE BANK #1 WITH A 138-21.6 KV, 46.7 MVA TRANSFORMER AND TWO 21.6 KV FEEDER BREAKERS ; AND INSTALL 3 - 138 KV 18.4 MVAR CAPACITOR BANK STAGES | Not Applicable |  | 2022-05-15 |  |  |  | 0
271 | 0PT47739 -- YANTIS RANCH POD - ROW - EASEMENT FOR STATION | Not Applicable | 1911568 | 2022-10-15 | 1847757.4 |  | -3.338% | Not Applicable
| 0PT46875 -- YANTIS RANCH POD : ESTABLISH 138 KV POINT OF DELIVERY | Not Applicable |  | 2022-10-15 |  |  |  | 0
272 | 0PT48981 -- TEXACO MABEE TAP - MIDLAND EAST SWITCH 138 KV LINE : EASEMENT ACQUISITION | Not Applicable | 13902212 | 2022-08-15 | 13633128.89 |  | -1.936% | Not Applicable
| 0PT46842 -- TEXACO MABEE TAP - MIDLAND EAST SWITCH 138 KV LINE : DOUBLE CIRCUIT LINE REBUILD | Not Applicable |  | 2022-08-15 |  |  |  | 0
273 | 0PT49067 -- ITALY SUB - HILLSBORO SWITCH 69 KV LINE : EASEMENT ACQUISITION | Not Applicable | 23726345 | 2022-12-15 | 21028612.74 |  | -11.37% | Not Applicable
| 0PT46785 -- ITALY SUB - HILLSBORO SWITCH 69 KV LINE: REBUILD MILFORD EXXON TAP - HILLSBORO SWITCH | Not Applicable |  | 2022-12-15 |  |  |  | 0
274 | 0PT50786 -- DESOTO HAMPTON ROAD SUB - CEDAR HILL SUB 138 KV LINE RECONDUCTOR | Not Applicable | 7987985 | 2022-08-15 | 7896839.22 |  | -1.141% | Not Applicable
| 0PT46764 -- DESOTO PLEASANT RUN SUB - DESOTO HAMPTON ROAD SUB 138 KV LINE RECONDUCTOR | Not Applicable |  | 2022-08-15 |  |  |  | 0
275 | 0PT46760 -- NTUSU SOUTH MIDLAND SWITCH - PRONGHORN SWITCH 138 KV LINE : RETIREMENT ONLY | Not Applicable | 4682906 | 2022-07-15 | 5455603.27 |  | 16.5% | Variance is due to a change in project scope that increased material and labor costs. Project was conceived as a rebuild of existing facilities from South Midland-Cottonfield-Consavvy using the existing right-of-way for the South Midland-Pronghorn 138 kV transmission line. As construction neared, it became apparent that the rebuild was too long to complete without a continuous outage that could not be obtained due to ERCOT clearance restrictions. The scope change resulted in a shorter rebuild utilizing the vacant circuit of another transmission line but also added a loop through the Cottonfield station, which required additional structures and conductor. Because the change occurred late in the design process, materials for the original scope of work had already been ordered. The materials not used for this project are being reallocated to other projects, but materials that have not yet been reallocated are still reflected as a charge to this project, which is inflating the material cost.
| 0PT46759 -- SL SOUTH MIDLAND SWITCH - COTTONFIELD 138 KV LINE: REBUILD | Not Applicable |  | 2022-07-15
276 | 0PT48788 -- BEPC FLAT ROCK TAP SWITCH – BEPC FLAT ROCK BEPC SUBSTATION : EASEMENT ACQUISITION | Not Applicable | 7584140 | 2022-12-15 | 3258850.11 |  | -57.03% | Not Applicable
| 0PT46733 -- BEPC FLAT ROCK TAP SWITCH – BEPC FLAT ROCK BEPC SUBSTATION: REBUILD 138 KV LINE SECTION USING A CONDUCTOR RATED 2569 A OR GREATER. | Not Applicable |  | 2022-04-15 |  |  |  | 0
277 | 0PT47758 -- MALLARD SWITCH POD - ROW STATION - PURCHASE IN FEE | Not Applicable | 16173528 | 2022-03-15 | 17365310.03 |  | 7.369% | Not Applicable
| 0PT46695 -- MALLARD SWITCH (PROJECT WINSTON-FEBRUARY): ESTABLISH BREAKER-AND-A-HALF STATION FOR SAS |  |  | 2022-03-15 |  |  |  | 0
| 0PT47760 -- MALLARD SWITCH POD - ROW ROAD ACCESS - PURCHASE ROAD ACCESS EASEMENT |  |  | 2022-03-15 |  |  |  | 0
278 | 0PT48591 -- CALMONT SWITCH - LOCKEED SUB 69 KV LINE : EASEMENT ACQUISITION | Not Applicable | 6410336 | 2024-02-15 | 5499081.89 |  | -14.22% | Not Applicable
| 0PT46671 -- CALMONT SWITCH - LOCKHEED SUB 69 KV LINE : REBUILD | Not Applicable |  | 2024-02-15 |  |  |  | 0
279 | 0PT48345 -- NTUSU BROWN SWITCH - KILLEEN SWITCH 345 KV LINE : RETIREMENTS ONLY | Not Applicable | 1999500 | 2022-07-15 | 2258679.96 |  | 12.96% | Cost variance is due to increased labor costs after an outage was cancelled, resulting in a compressed construction schedule to meet the in-service date.
| 0PT46610 -- BROWN SWITCH - KILLEEN SWITCH 345 KV LINE : CUT-IN TO ESTABLISH RUSSELL GAP SWITCH | Not Applicable |  | 2022-07-15
280 | 0PT50443 -- ROSEDALE SUB: ACQUIRE EASEMENTS ON POWER PLANT PROPERTY | Not Applicable | 6478207 | 2022-01-15 | 7748532.4 |  | 19.61% | Variance is due to a change in project scope, increased labor costs, and increased property acquisition costs. Initial station and line designs were not feasible due to the presence of underground utilities that prevented pole placement. Alternate designs were created to bring the line into the station on a different route, which required additional property to accommodate the entire station footprint. The redesigned route crossed a yard where customer stored equipment, so Oncor incurred additional costs to relocate the equipment as part of the deal to acquire the needed land rights. Labor costs increased as a result of the design changes and equipment relocation.
| 0PT46414 -- ROSEDALE SUB : (FORMERLY KNOWN AS RANSOM TERRACE SUB) ESTABLISH SUBSTATION WITH TWO 138-12.5 KV 47 MVA TRANSFORMERS | Not Applicable |  | 2022-01-15
281 | 0PT46409 -- PARKER SWITCH : REPLACE OVERDUTIED BREAKER #9875 | Not Applicable | 1171492 | 2021-12-15 | 1600618.82 |  | 36.63% | Variance is due to a change in project scope and increased material and labor costs. Scope was revised to include the installation of work platforms on circuit breakers to provide safe access to breaker cubicles during maintenance. Increased material and labor costs were due to the additional steel, foundations, and labor needed for installation.
| 0PT50103 -- PARKER SWITCH : REPLACE OVERDUTIED BREAKERS #6860 | Not Applicable |  | 2021-12-15
282 | 0PT47740 -- QUARRY FIELD SW - WINK SW TRANSMISSION LINE - ROW EASEMENT FOR YANTIS RANCH POD | Not Applicable | 2175798 | 2022-04-15 | 2002132.37 |  | -7.982% | Not Applicable
| 0PT46339 -- QUARRY FIELD SWITCH - WINK SWITCH 138 KV LINE : INSTALL YANTIS RANCH POD FOR WPX ENERGY PERMIAN'S MONUMENT DRAW NORTH SUBSTATION | Not Applicable |  | 2022-04-15 |  |  |  | 0
283 | 0PT47028 -- TERRELL SOUTH SW. – ROSE HILL SW. 138 KV - ROW TRANSMISSION LINE EASEMENT | Not Applicable | 879157 | 2022-02-15 | 909497.6 |  | 3.451% | Not Applicable
| 0PT46332 -- TERRELL SOUTH SWITCH - ROSE HILL SWITCH 138 KV LINE : RETERMINATE ROSE HILL STATION | Not Applicable |  | 2022-02-15 |  |  |  | 0
284 | 0PT49964 -- PEPPER CREEK SWITCH - ROW LAND IN DEED | Not Applicable | 15402937.36 | 2022-05-15 | 15001613.03 |  | -2.606% | Not Applicable
| 0PT46327 -- PEPPER CREEK SWITCH: ESTABLISH STATION TO PROVIDE FOUR 138 KV PODS FOR POLMER LLC | Not Applicable |  | 2022-05-15 |  |  |  | 0
285 | 0PT48273 -- NTUSU SKYWEST SWITCH : RETIREMENT ONLY | Not Applicable | 616609 | 2023-10-15 | 600892.2 |  | -2.549% | Not Applicable
| 0PT46296 -- SL SKYWEST : UPGRADE 138 KV DRIVER LINE TERMINAL |  |  | 2023-10-15 |  |  |  | 0
| 0PT47588 -- SL SKYWEST SWITCH: CB 5101/5102 LINE TERMINAL UPGRADE |  |  | 2023-10-15 |  |  |  | 0
286 | 0PT48759 -- NTUSU DRIVER SUB : RETIREMENT ONLY | Not Applicable | 906192.32 | 2022-10-15 | 2232955.79 |  | 146.4% | Variance is due to a change in project scope and associated increases in material and labor costs. Items added to project scope include installing an additional 138 kV gang operated switch, replacing two 25 kV switches on stations with totalizing switches, replacing three 25 kV reclosers with circuit breakers, and installing a mobile substation. Increased material costs, extended project construction timeline, and addition of mobile for outages. The 138 kV switch was originally scheduled to be upgraded with a different project but was added to this project’s scope to ensure all 138 kV switches at the station were rated at a minimum of 3200 A. The replacement of two 25 kV switches was added to the project scope due to safety concerns of manually operating the switches under load. The replacement of 25 kV reclosers was added due to mis-operations of the existing reclosers. These added items increased material and labor costs due to the increased scope of work and the extended construction timelines.
| 0PT46295 -- SL DRIVER SUB : UPGRADE 138 KV SKYWEST LINE TERMINAL | Not Applicable |  | 2022-10-15
287 | 0PT46062 -- WINK SWITCH - KEYSTONE NO 1 EAST 69 KV LINE: SHIFTING SANDS SUB - WINK GULF TAP 69 KV SECTION REBUILD STRUCTURE 8/7 TO SHIFTING SANDS SUB | Not Applicable | Not Applicable | 2022-01-15 | 5251594.18 |  | Not Applicable | Not Applicable
| 0PT46292 -- WINK SWITCH - KEYSTONE NO 1 EAST 69 KV LINE: SHIFTING SANDS SUB - WINK GULF TAP 69 KV SECTION REBUILD STRUCTURE 8/7 TO SHIFTING SANDS SUB: ROW ACQUISITION |  |  | 2022-01-15 |  |  |  | 0
288 | 0PT44327 -- WINK SWITCH - KEYSTONE NO 1 EAST 69 KV LINE: SHIFTING SANDS SUB - WINK GULF TAP 69 KV SECTION REBUILD STRUCTURE 4/8 TO 8/7 | Not Applicable | 10000000 | 2021-04-15 | 6722751.86 |  | -32.77% | Not Applicable
289 | 0PT46236 -- WINK BASIN TAP NO 1 EAST 69 KV LINE: STRUCTURE 3/2 - STRUCTURE 4/1 69 KV SECTION REBUILD TO 138 KV | Not Applicable | 1555655 | 2022-01-15 | 1087840.1 |  | -30.07% | Not Applicable
290 | 0PT51317 -- WRAGE RANCH POD (REBEL POD ETC TEXAS PIPELINES) | Not Applicable | Not Applicable | 2023-09-15 | 1107302.16 |  | Not Applicable | Not Applicable
| 0PT52027 -- SPRABERRY SWITCH - POLECAT CREEK SWITCH 138 KV LINE: INSTALL H-FRAME SWITCH STRUCTURE FOR WRAGE RANCH POD |  |  | 2023-09-15 |  |  |  | 0
291 | 0PT46090 -- FOUNDRY SWITCH : ESTABLISH FOUR BREAKER 138 KV RING BUS FOR AEP HERON SWITCH | Not Applicable | 6592900.37 | 2023-11-15 | 7208898.86 |  | 9.343% | Not Applicable
| 0PT44803 -- FOUNDRY SWITCH: ACQUIRE STATION EASEMENT |  |  | 2023-11-15 |  |  |  | 0
292 | 0PT50402 -- ARCO CRANE TAP - CRANE ARCO POD 138 KV LINE : CUT-IN TO ESTABLISH FOUNDRY SWITCH | Not Applicable | 3274709.12 | 2024-03-15 | 3131019.95 |  | -4.388% | Not Applicable
293 | 0PT48258 -- PIN OAK SWITCH - FAIRFIELD WEST SWITCH 138KV LINE: : EASEMENT ACQUISITION | Not Applicable | 9413391 | 2022-10-15 | 10895509.81 |  | 15.74% | Variance is due to increased material and labor costs. Cost estimate provided for 3 months of matting, but wet weather slowed construction progress and matting was needed for 2 additional months and at multiple points throughout the duration of the project to cover areas affected by heavy rains. Labor costs increased due to inefficiencies caused by weather delays, material delays, and rework at the station to address a phasing issue discovered at the time of energization.
| 0PT46085 -- PIN OAK SWITCH - FAIRFIELD WEST SWITCH 138KV LINE: REBUILD FROM FAIRFIELD WEST TO FAIRFIELD SWITCH (BEPC) 138KV | Not Applicable |  | 2022-10-15
294 | 0PT51211 -- BENNETT ROAD SWITCH - BOWIE SWITCH 69 KV LINE : CMPC LINE HARDENING (STR. 86/3 - 86/4) : ROW ACQUISITION | Not Applicable | 698288 | 2023-03-15 | 570046.21 |  | -18.37% | Not Applicable
| 0PT45938 -- BENNETT ROAD SWITCH - BOWIE SWITCH 69 KV LINE : CMPC LINE HARDENING (STR. 86/3 - 86/4) | Not Applicable |  | 2023-03-15 |  |  |  | 0
295 | 0PT46000 -- NTUSU SALT FLAT ROAD - SKYWEST 138KV LINE: REBUILD RETIREMENTS ONLY | Not Applicable | 2630091 | 2021-10-15 | 3362605.5 |  | 27.85% | Variance is due to a change in project scope to construct a temporary bypass due to unexpected ERCOT outage restrictions. Construction of the temporary bypass resulted in additional material and labor costs that were not included in the estimate, as well as inefficient construction sequencing.
| 0PT45834 -- SL SALT FLAT ROAD - SKYWEST 138KV LINE: REBUILD | Not Applicable |  | 2021-10-15
296 | 0PT46724 -- CRATER ROCK SWITCH - ROAD ACCESS EASEMENT - ROW | Not Applicable | 6077188 | 2021-12-15 | 5465774.45 |  | -10.06% | Not Applicable
| 0PT45737 -- CRATER ROCK SWITCH : ESTABLISH 3 BREAKER RING POI STATION | Not Applicable |  | 2021-12-15 |  |  |  | 0
297 | 0PT47747 -- WINK SWITCH - WINK BASIN SUB 138 KV LINE : EASEMENT ACQUISITION | Not Applicable | 3853819 | 2022-01-15 | 4407825.49 |  | 14.38% | Variance is due to a change in project scope and increased labor costs. A temporary bypass was added to the project scope because Oncor could not obtain an outage on an associated transmission line during construction. A bypass was not originally in this project scope as the construction was to align with the outages needed to bring a separate substation online. The extension of the project schedule interfered with the planned outage scheduling. Labor costs increased due to a contract adjustment and the need for a Level A subsurface utility survey, due to the large number of pipelines and underground utilities in the area.
| 0PT45707 -- WINK SWITCH - WINK BASIN SUB 138 KV LINE : 69 KV CONVERSION TO 138 KV | Not Applicable |  | 2022-01-15
298 | 0PT48288 -- BELFALLS SWITCH - STATION - BY DEED | Not Applicable | 7911903 | 2022-07-15 | 7914318.35 |  | 0.03053% | Not Applicable
| 0PT45535 -- BELFALLS SWITCH - ESTABLISH A 345 KV POI FOR BIG ELM SOLAR (APEX CLEAN ENERGY, INC) | Not Applicable |  | 2022-07-15 |  |  |  | 0
299 | 0PT43815 -- HANDLEY SWITCH - LIGGETT SWITCH 138 KV LINE : RECONDUCTOR THE HURST SUB - INTERNATIONAL AIRPORT SUB 138 KV LINE | Not Applicable | 6709213 | 2022-04-15 | 6824121.86 |  | 1.713% | Not Applicable
| 0PT45495 -- HANDLEY SWITCH - EXECUTIVE PARKWAY SWITCH 138 KV LINE : RECONDUCTOR THE HURST SUB - INTERNATIONAL AIRPORT SUB 138 KV LINE | Not Applicable |  | 2022-04-15 |  |  |  | 0
300 | 0PT45955 -- OLD MICHIGAN POD - ACQUIRE TRANSMISSION LINE EASEMENT | Not Applicable | 1444467 | 2021-09-15 | 1591107.62 |  | 10.15% | Variance is due to increased labor costs due to unavailability of construction contractors with established pricing units. This resulted in a new construction contractor being awarded the project at a higher cost after the initial estimates were created.
| 0PT45399 -- HORSESHOE SPRINGS SWITCH - RIVERTON SWITCH 138 KV LINE : INSTALL OLD MICHIGAN POD FOR CIMAREX ENERGY'S STATION | Not Applicable |  | 2021-09-15
301 | 0PT45956 -- OLD MICHIGAN POD - ACQUIRE EASEMENTS FOR STATION SITE AND ROAD ACCESS | Not Applicable | 1602497 | 2021-10-15 | 2018317.6 |  | 25.95% | Cost variance is due to a change in project scope. A temporary bypass was added to the project scope, which increased the station footprint and resulted in increased material and labor costs.
| 0PT45378 -- OLD MICHIGAN POD : ESTABLISH 138KV POINT OF DELIVERY (CIMAREX) | Not Applicable |  | 2021-10-15
302 | 0PT45229 -- TERRELL SWITCH - KAUFMAN NORTHWEST - SEAGOVILLE SWITCH 138 KV LINE: RETERMINATION AT TERRELL SWITCH | Not Applicable | 1864912.7 | 2023-03-15 | 1297237.19 |  | -30.44% | Not Applicable
303 | 0PT48785 -- TERRELL SUBSTATION EXP : PURCHASE IN FEE | Not Applicable | 6274501 | 2023-10-15 | 8101804.68 |  | 29.12% | Variance is due to a change in project scope and associated increase in material and labor costs. Scope was revised to replace equipment that was beyond its serviceable life, including two steel structures that did not pass a structural analysis, two 138 kV switches, two 138 kV CCTVs, three low-voltage breakers, a bus tie switch, and a distribution bus. These material and labor costs were not included in the reported estimate. Labor costs were higher than estimated for autotransformer transport, a manlift for transformer dressing, secondary oil containment, and demolition work.
| 0PT44273 -- TERRELL SWITCH: ESTABLISH A NEW 138 KV TERMINAL AND RETIRE 69 KV STATION AND RELAY UPGRADE ON FEEDERS 1201, 1202, 1203 & 1204 FOR DA AND FEEDER 2401 |  |  | 2023-10-15
304 | 0PT45952 -- KINGS CREEK SWITCH POI - TRANSMISSION LINE EASEMENTS | Not Applicable | 2345172 | 2021-09-15 | 1816932.53 |  | -22.52% | Not Applicable
| 0PT45090 -- KAUFMAN NW SWITCH - MANKIN SWITCH 138 KV LINE : INSTALL KINGS CREEK SWITCH FOR AND RE-TERMINATE RAYBURN'S OAK GROVE TAP | Not Applicable |  | 2021-09-15 |  |  |  | 0
305 | 0PT46036 -- KINGS CREEK SWITCH - ROAD ACCESS | Not Applicable | 4525866 | 2022-04-15 | 4782324.84 |  | 5.667% | Not Applicable
| 0PT45089 -- KINGS CREEK SWITCH : 138 KV ESTABLISH NEW STATION | Not Applicable |  | 2022-04-15 |  |  |  | 0
306 | 0PT49586 -- HOG CREEK SWITCH - ROW LAND IN FEE | Not Applicable | 8486799 | 2022-07-15 | 8846349.85 |  | 4.237% | Not Applicable
| 0PT45041 -- HOG CREEK SWITCH: ESTABLISH 345 KV POI FOR EASTBELL MILAM SOLAR (CATTLEMAN SOLAR PARK) | Not Applicable |  | 2022-07-15 |  |  |  | 0
307 | 0PT46670 -- FLAT ROCK BEPC SWITCH - AZLE SWITCH 138 KV LINE : ROW ACQUISITION | Not Applicable | 5370613 | 2021-09-15 | 4504146.19 |  | -16.13% | Not Applicable
| 0PT45033 -- BEPC FLAT ROCK SUBSTATION - AZLE SWITCH 138 KV LINE: REBUILD 138 KV LINE SECTION USING A CONDUCTOR RATED 2569 A OR GREATER | Not Applicable |  | 2021-09-15 |  |  |  | 0
308 | 0PT50208 -- WACO M&M MARS SUB: UPGRADE STATIONS #1 & #2 TO SUB IV | Not Applicable | 6227656 | 2021-08-15 | 9375309.01 |  | 50.54% | Cost variance is due to two separate projects being combined into a single project. Oncor consolidated two projects planned at the same substation after reporting the cost estimate for the first project. This increased the scope of the project to include the installation of a new transformer bank, two new feeder breakers, feeder ties, relays, and low-voltage bus equipment that were not included in the initial estimate.
| 0PT44887 -- WACO M&M MARS SUB : INSTALL BANK #3 WITH ONE 138-12.5 KV 46.7 MVA WYE-WYE TRANSFORMER WITH 2 FEEDER BREAKERS | Not Applicable |  | 2021-08-15
309 | 0PT46251 -- BRUSHY CREEK SWITCH - TAYLOR SWITCH 138KV LINE: REBUILD : EASEMENT MODIFICATION AGREEMENT | Not Applicable | 18400000 | 2022-03-15 | 14896214.1 |  | -19.04% | Not Applicable
| 0PT44782 -- BRUSHY CREEK SWITCH - TAYLOR SWITCH 138KV LINE: REBUILD | Not Applicable |  | 2022-03-15 |  |  |  | 0
310 | 0PT50495 -- BARR RANCH SW - QUICKRIVER TAP 138 KV TRANSMISSION LINE - EASEMENT FOR BULL HEAD POD | Not Applicable | 6252425 | 2023-01-15 | 4387594.72 |  | -29.83% | Not Applicable
| 0PT52026 -- BARR RANCH SWITCH - QUICKRIVER TAP 138 KV LINE: INSTALL H-FRAME SWITCH STRUCTURE FOR BULL HEAD POD |  |  | 2023-01-15 |  |  |  | 0
| 0PT44611 -- BARR RANCH SWITCH - QUICKRIVER TAP 138 KV LINE: INSTALL BULL HEAD POD FOR ENERGY TRANSFER |  |  | 2023-01-15 |  |  |  | 0
311 | 0PT44430 -- NTUSU DRIVER SUB - SKYWEST SUB 138 KV LINE : RETIREMENT ONLY | Not Applicable | 18259397 | 2022-12-15 | 16767557.6 |  | -8.17% | Not Applicable
| 0PT44429 -- SL DRIVER SWITCH - SKYWEST SWITCH 138 KV LINE : REBUILD |  |  | 2022-12-15 |  |  |  | 0
312 | 0PT44337 -- FROW SUB: ESTABLISH SUBSTATION WITH 1 – 28 MVA TRANSFORMER AND 2 – 12.5 KV FEEDER BREAKERS | Not Applicable | 2992104 | 2021-10-15 | 7476368.65 |  | 149.9% | Variance is due to a change in project scope. The initial cost estimate was for the rebuild of the Waco Katy substation. Instead, the existing station was retired and the project was revised to establish the new Frow Substation, a 138-12.5 kV substation with one 47 MVA transformer, two 15 kV feeder circuit breakers, one 15 kV bus tie breaker, and one control center with relaying and controls.
| 0PT46862 -- FROW SUBSTATION - PURCHASE OF LAND | Not Applicable |  | 2021-10-15
313 | 0PT45336 -- WEATHERFORD SW. – FLAT ROCK BEPC SW. 138 KV LINE – EASEMENT MODIFICATION AGREEMENTS AND ACKNOWLEDGEMENT OF PAYMENTS | Not Applicable | 4046458 | 2021-08-15 | 3938513.5 |  | -2.668% | Not Applicable
| 0PT43481 -- WEATHERFORD SWITCH – BEPC FLAT ROCK TAP SWITCH 138 KV LINE: REBUILD 138 KV LINE SECTION USING A CONDUCTOR RATED 2569 A OR GREATER. |  |  | 2021-08-15 |  |  |  | 0
314 | 0PT44296 -- AZLE SUB : UPGRADE 138 KV LINE TERMINALS | Not Applicable | 694686 | 2021-08-15 | 1007797.24 |  | 45.07% | Variance is due to a change in project scope and associated material and labor cost increases for a mobile transformer and expedited restoration, as well as the need for hot work to modify two 138 kV switches to facilitate the installation of two new interrupters.
315 | 0PT44210 -- PADERA SUBSTATION (FKA: GIFFORD HILL LAKE SUBSTATION): PURCHASE IN FEE | Not Applicable | 7665758 | 2022-10-15 | 7491756.84 |  | -2.27% | Not Applicable
| 0PT44259 -- PADERA SUB : ESTABLISH WITH TWO 47 MVA TRANSFORMERS AND FOUR 12.5 KV BREAKERS | Not Applicable |  | 2022-10-15 |  |  |  | 0
316 | 0PT44755 -- NOLAN CREEK SUB - PURCHASE LAND | Not Applicable | 6441930.3 | 2023-02-15 | 6990612.3 |  | 8.517% | Not Applicable
| 0PT44256 -- CHARCA SUB (FORMERLY NOLAN CREEK SUB) : ESTABLISH WITH ONE 47 MVA 138-25 KV TRANSFORMER, TWO FEEDER BREAKER AND RELAY UPGRADE ON FEEDER 5511 FOR DA | Not Applicable |  | 2023-02-15 |  |  |  | 0
317 | 0PT44255 -- WILSHIRE SUB (FORMERLY BURLESON SOUTHWEST SUB) : ESTABLISH WITH ONE 47 MVA 138/25 KV TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable | 7816660 | 2022-10-15 | 8030016.26 |  | 2.73% | Not Applicable
| 0PT44779 -- WILSHIRE SUBSTATION (FKA: BURLESON SOUTHWEST SUBSTATION) : PURCHASE OF LAND IN FEE | Not Applicable |  | 2022-10-15 |  |  |  | 0
318 | 0PT44245 -- HORSEMAN SUB (FORMERLY SAGINAW SE SUB) : ESTABLISH TWO 47 MVA TRANSFORMERS AND FOUR BREAKERS | Not Applicable | 9046995 | 2022-07-15 | 10387694.46 |  | 14.82% | Variance is due to a change in project scope and increased material and labor costs. Scope change included additional labor and equipment required to address rocky soil conditions and additional work for erosion control and drainage issues, which required additional base materials. Material costs were higher than estimated due to price increases for structural steel, transformers, relay control equipment, and the control center. Labor costs for engineering consultants, on-site inspection services, Oncor and contractor labor, and on-site security services exceeded estimates. Engineering consultant costs increased due to additional municipal surveying, platting and permitting requirements. Additional protection and control resources were required to meet the in-service date ahead of ERCOT's clearance restriction deadline. Transformer manufacturer rigging, crane and transportation services, and transformer leaker and oil retention installation costs exceeded estimates. Contractor construction costs increased due to an expedited construction schedule resulting from weather delays, delays in acquiring the station property, and municipal permitting delays, in addition to rocky soil conditions that increased costs for the foundation, conduit, and grounding. Project delays resulted in multiple remobilizations and an extended construction timeline, which required additional costs for security services. Grading and regrade costs increased to account for erosion control and drainage work. Municipal requirements for a pre-cast perimeter wall design, landscaping, and concrete driveway further increased construction costs.
| 0PT44780 -- HORSEMAN SUBSTATION (FORMERLY SAGINAW SOUTHEAST SUBSTATION) : PROPERTY ACQUISITION IN FEE | Not Applicable |  | 2022-07-15
319 | 0PT46722 -- MALLARD SWITCH / PINTAIL SWITCH - TAYLOR - ROW EASEMENTS - TRANSMISSION LINE | Not Applicable | 9053879 | 2022-07-15 | 9478722.35 |  | 4.692% | Not Applicable
| 0PT44238 -- TAYLOR SWITCH - HUTTO SWITCH 138 KV LINE: MALLARD SWITCH CUT-IN | Not Applicable |  | 2022-07-15 |  |  |  | 0
320 | 0PT44749 -- APPLE SUB - PURCHASE LAND | Not Applicable | 5171022 | 2022-03-15 | 5303872.45 |  | 2.569% | Not Applicable
| 0PT47519 -- APPLE TRANSMISSION TAP LINE - PURCHASE OF EASEMENT |  |  | 2022-03-15 |  |  |  | 0
| 0PT44232 -- APPLE SUB (FORMERLY PLEASANT FARMS SUB) : ESTABLISH STATION WITH ONE 47 MVA, 138/69 KV AND TWO FEEDER BREAKERS |  |  | 2022-03-15 |  |  |  | 0
321 | 0PT47655 -- DOUBLE CREEK SUBSTATION - PURCHASE OF LAND | Not Applicable | 12237395 | 2022-10-15 | 11340875.07 |  | -7.326% | Not Applicable
| 0PT44231 -- DOUBLE CREEK SUB (FORMERLY LOUIS HENNA SUB): ESTABLISH TWO 47 MVA 138-25 KV TRANSFORMERS AND FOUR 25 KV UG FEEDER BREAKERS | Not Applicable |  | 2022-10-15 |  |  |  | 0
| 0PT48829 -- DOUBLE CREEK SUB. 138KV TAP LINE - PURCHASE OF EASEMENT | Not Applicable |  | 2022-10-15 |  |  |  | 0
322 | 0PT46714 -- KIMBALL RD. SUBSTATION: EASEMENT ACQUISITION FOR DRIVEWAY | Not Applicable | 4018618 | 2021-08-15 | 4742367.19 |  | 18.01% | Variance is due to material and labor cost increases to install a second driveway to resolve access issues. Installing the second driveway required demolishing and rebuilding a masonry wall. Additionally, landscaping and pavers had to be installed due to proximity to a business park.
| 0PT44230 -- KIMBALL ROAD SUB : INSTALL BANK #3 WITH A 138-24.9 KV 47 MVA TRANSFORMER WITH ONE FEEDER BREAKER | Not Applicable |  | 2021-08-15
323 | 0PT48161 -- DFW MID CITIES SUB : PURCHASE OF EASEMENT | Not Applicable | 14501213.58 | 2022-09-15 | 2438362.99 |  | -83.19% | Not Applicable
324 | 0PT44139 -- PACIFIC SWITCH: ESTABLISH A 345 KV POI FOR MOCKINGBIRD SOLAR CENTER | Not Applicable | 6924290.09 | 2022-05-15 | 8354708.81 |  | 20.66% | Variance is due to a change in project scope and increased material and labor costs. Scope change included installing worker platforms for 345 kV circuit breakers and a concrete antenna pole and a radio for the communication system. These changes required additional engineering, materials, and labor. Material prices and contractor labor were higher than estimated due to ground grid materials and labor that were not captured in the estimate and an associated increase in grading costs.
| 0PT51654 -- PACIFIC SWITCH (BAKER BRANCH SOLAR) - ROW - LAND IN DEED | Not Applicable |  | 2022-05-15
325 | 0PT47107 -- AQUIFER SUBSTATION ROAD EASEMENT - PURCHASE EASEMENT | Not Applicable | 5072146 | 2021-09-15 | 5386480.71 |  | 6.197% | Not Applicable
| 0PT43983 -- AQUIFER TAP : (FORMERLY KNOWN AS MCILVAIN) INSTALL 110.4 MVAR 138 KV CAPACITORS | Not Applicable |  | 2021-09-15 |  |  |  | 0
326 | 0PT48344 -- PIN OAK SWITCH ACCESS EASEMENT ACQUISITION | Not Applicable | 9206433 | 2021-06-15 | 10054403.33 |  | 9.211% | Not Applicable
| 0PT44072 -- PIN OAK SWITCH : PURCHASE APPROXIMATELY 35-40 ACRES FOR NEW SWITCHING STATIONS |  |  | 2021-06-15 |  |  |  | 0
| 0PT43961 -- PIN OAK (FORMERLY KNOWN AS BIG BROWN TAP) SWITCH: ESTABLISH 138 KV STATION USING A 5-BREAKER 138 KV BREAKER-AND-A-HALF ARRANGEMENT |  |  | 2021-06-15 |  |  |  | 0
327 | 0PT43949 -- ROWLETT SUB - OATES SUB 138 KV LINE : REBUILD | Not Applicable | 20338645.84 | 2022-08-15 | 19333479.22 |  | -4.942% | Not Applicable
| 0PT46562 -- ROWLETT SUB - OATES SUB 138 KV LINE : REBUILD : ROW ACQUISITION | Not Applicable |  | 2022-08-15 |  |  |  | 0
328 | 0PT46229 -- DUCK COVE TAP #1 - WILLS POINT SUB 69 KV LINE: REBUILD : ROW ACQUISITION | Not Applicable | 7808064 | 2021-09-15 | 8319615.17 |  | 6.552% | Not Applicable
| 0PT43905 -- DUCK COVE TAP #1 - WILLS POINT SUB 69 KV LINE: REBUILD | Not Applicable |  | 2021-09-15 |  |  |  | 0
329 | 0PT43897 -- ESKOTA SWITCH - SWEETWATER NO. 2 SUB 69 KV LINE: REBUILD | Not Applicable | 18576188 | 2022-02-15 | 17048047.66 |  | -8.226% | Not Applicable
| 0PT43896 -- ESKOTA SWITCH - SWEETWATER NO. 2 SUB 69 KV LINE: SOUTH CIRCUIT RETIREMENT ONLY |  |  | 2022-02-15
| 0PT48828 -- ESKOTA SWITCH - SWEETWATER NO. 2 SUB 69 KV LINE : EASEMENT ACQUISITION |  |  | 2022-02-15
330 | 0PT48058 -- WACO EAST SWITCH - BELLMEAD SUB 69 KV LINE : CONVERSION TO 138 KV : ROW ACQUISITION | Not Applicable | 9173498 | 2022-06-15 | 12648795.32 |  | 37.88% | Variance is due to increased material and labor costs. The initial cost estimates provided assumed typical wire pulling and traffic control processes could be utilized. However, the existing wire was in poor condition and had to be removed span-by-span prior to pulling in new wire. Additionally, the rebuild work occurred in a ROW that was in close proximity to residential and commercial buildings and had multiple road and highway crossings. Due to the congested nature of the ROW, additional time precautions were needed, including specialized equipment and traffic control. Matting was required to access the ROW and prevent damage to residential and commercial properties; specifically to driveways, curbs, entrances, and exits along the project ROW.
| 0PT43691 -- WACO EAST SWITCH - BELLMEAD SUB 69 KV LINE : CONVERSION TO 138 KV | Not Applicable |  | 2022-06-15
331 | 0PT47058 -- CROSSROADS SWITCH - ACQUIRE STATION PROPERTY SITE IN DEED | Not Applicable | 4377683 | 2022-02-15 | 4357506.93 |  | -0.4609% | Not Applicable
| 0PT43690 -- CROSSROADS SWITCH : ESTABLISH STATION FOR A POINT-OF-INTERCONNECTION (POI) FOR ESTONIAN SOLAR & STORAGE | Not Applicable |  | 2022-02-15 |  |  |  | 0
332 | 0PT44590 -- NTUSU SL FOR RETIREMENT SL BROWN - BUZZARD DRAW AND VEALMOOR - BUZZARD DRAW 138KV LINES | Not Applicable | 1480819 | 2021-10-15 | 1361946.68 |  | -8.027% | Not Applicable
| 0PT43524 -- SL NTUSU BROWN SUB - KOCH TAP 138 KV LINE : BUZZARD DRAW SWITCH CUT IN | Not Applicable |  | 2021-10-15 |  |  |  | 0
333 | 0PT46560 -- TRINIDAD SWITCH - FAIRFIELD WEST - LONG LAKE SUB 138 KV LINE : REBUILD FROM BIG BROWN TAP TO PIN OAK SWITCH 138 KV : ROW ACQUISITION | Not Applicable | 9101916 | 2022-04-15 | 8399556.75 |  | -7.717% | Not Applicable
| 0PT43447 -- TRINIDAD SWITCH - FAIRFIELD WEST - LONG LAKE SUB 138 KV LINE : REBUILD FROM BIG BROWN TAP TO PIN OAK SWITCH 138 KV | Not Applicable |  | 2022-04-15 |  |  |  | 0
334 | 0PT44208 -- ANTLER HOLLOW SUBSTATION (FKA: STEPHENVILLE NORTH SUBSTATION) ACQUISITION : PURCHASING IN FEE | Not Applicable | 7687918 | 2022-04-15 | 8210469.35 |  | 6.797% | Not Applicable
| 0PT49193 -- ANTLER HOLLOW SUB ACCESS EASEMENT |  |  | 2022-04-15 |  |  |  | 0
| 0PT42928 -- ANTLER HOLLOW SUB : ESTABLISH WITH TWO 47 MVA 138-12 KV TRANSFORMER AND THREE 12.5 KV BREAKERS |  |  | 2022-04-15 |  |  |  | 0
335 | 0PT42151 -- DESERT WIND (FKA GARDEN CITY WEST) SUB : ESTABLISH ONE 47 MVA 138/25 KV TRANSFORMER AND TWO 25 KV FEEDER BREAKERS | Not Applicable | 5753245 | 2021-10-15 | 6566510.91 |  | 14.14% | Variance is due to an increase in land acquisition and labor costs. Property value for the substation, as determined in the condemnation proceeding, exceeded the estimate. Oncor also had to pay to reroute the landowner's irrigation system as a result of the station construction. Non-MSA labor further increased labor costs.
| 0PT42559 -- DESERT WIND SUBSTATION (FKA GARDEN CITY WEST SUB) : PURCHASING SUBSTATION EASEMENT | Not Applicable |  | 2021-10-15
336 | 0PT41809 -- SL NTUSU SU GLASS RANCH SWITCH - SALE RANCH SWITCH 138 KV LINE : RED SAND POD FOR ENDEAVOR'S TIGER SUB | Not Applicable | 2116406 | 2022-06-15 | 1842085.68 |  | -12.96% | Not Applicable
| 0PT47334 -- NTUSU GLASS RANCH SWITCH - SALES RANCH SWITCH 138 KV LINE : RED SAND POD: RETIREMENTS ONLY | Not Applicable |  | 2022-06-15 |  |  |  | 0
337 | 0PT41200 -- CUMBY TAP SWITCH - CUMBY SUB 69 KV LINE : CONVERSION TO 138 KV | Not Applicable | 2367244 | 2022-10-15 | 3314500.69 |  | 40.02% | Variance is due to a change in project scope and increased material and labor costs. A temporary bypass had to be relocated due to tight working conditions at the existing station and to accommodate the landowner’s request. This increased material and labor costs and required access and matting that were not accounted for in the initial estimate. Additionally, wet conditions required higher than anticipated matting costs for the project generally. Mat rentals were also extended due to the associated station project being delayed, which delayed the line work for this project.
| 0PT51456 -- CUMBY TAP SWITCH - CUMBY SUB 69 KV LINE : CONVERSION TO 138 KV : ROW ACQUISITION | Not Applicable |  | 2022-10-15
338 | 0PT41041 -- COURTNEY CREEK (PECOS) SWITCH: ESTABLISH 138/69 KV SWITCHING STATION | Not Applicable | 10020859 | 2021-04-15 | 10263249.15 |  | 2.419% | Not Applicable
| 0PT42306 -- COURTNEY CREEK SWITCH (AKA PECOS SWITCH) - PURCHASE OF EASEMENT | Not Applicable |  | 2021-04-15 |  |  |  | 0
339 | 0PT39815 -- STANTON EAST SWITCH - SPRABERRY SWITCH 69 KV LINE : CMPC LINE HARDENING (STR. 26/11 & 26/12) | Not Applicable | 386820 | 2022-05-15 | 350275.44 |  | -9.447% | Not Applicable
| 0PT43848 -- STANTON EAST SWITCH - SPRABERRY SWITCH 69 KV LINE : CMPC LINE HARDENING (STR. 26/11 & 26/12) : ACKNOWLEDGEMENT OF PAYMENT | Not Applicable |  | 2022-05-15 |  |  |  | 0
340 | 0PT50973 -- GRAIN BELT (FKA MASCH BRANCH SUB): ESTABLISH STATION WITH ONE TRANSFORMER | Not Applicable | 11631211.08 | 2024-08-15 | 10423180.36 |  | -10.39% | Not Applicable
| 0PT50549 -- GRAIN BELT SUB (FKA MASCH BRANCH SUB) - PURCHASE LAND IN FEE | Not Applicable |  | 2024-08-15 |  |  |  | 0
341 | 0PT49102 -- BLOOMDALE SWITCH: ESTABLISH THREE BREAKER 138 KV RING BUS | Not Applicable | 26114264 | 2023-02-15 | 22753321.41 |  | -12.87% | Not Applicable
| 0PT48466 -- BLOOMDALE SWITCH : PURCHASE IN FEE | Not Applicable |  | 2023-02-15 |  |  |  | 0
342 | 19T63016 -- SCURRY COUNTY SOUTH SWITCH: ADD 138 KV LINE TERMINAL FOR CANYON WIND | Not Applicable | 1995325 | 2020-02-15 | 1986328.96 |  | -0.4509% | Not Applicable
343 | 18T65208 -- NORTHAVEN SWITCH - MORRISON LANE SWITCH 138 KV LINE: REBUILD MARSH LN-MORRISON LN | Not Applicable | 10745318 | 2021-08-15 | 8891587.91 |  | -17.25% | Not Applicable
344 | 16T64147 -- LITTLE RIVER-HOLLAND 69 KV LINE: REBUILD | Not Applicable | 11553238 | 2022-03-15 | 11397049.2 |  | -1.352% | Not Applicable
| 0PT49472 -- LITTLE RIVER-HOLLAND 69 KV LINE: REBUILD : ROW ACQUISITION |  |  | 2022-03-15
345 | 0PT47317 -- MARY AVENUE SUBSTATION - PURCHASE OF LAND | Not Applicable | 6881328 | 2022-08-15 | 1303015.09 |  | -81.06% | Not Applicable
346 | 15T64033 -- WACO EAST - WACO WEST 138 KV LINE: CUT-IN TO ESTABLISH MARY AVENUE SWITCH | Not Applicable | 1480576.68 | 2021-06-15 | 1198057.78 |  | -19.08% | Not Applicable
347 | 13T65029 -- LAWRENCE SUB : ESTABLISH WITH ONE 47 MVA 138-25 KV BANK AND TWO 25 KV FEEDER BREAKERS | Not Applicable | 4603754 | 2021-12-15 | 4732307.43 |  | 2.792% | Not Applicable
348 | 0PT53723 -- ALVORD SWITCH - WICHITA FALLS SOUTH SWITCH 138 KV LINE : REPLACE CROSS ARMS | Not Applicable | 246500 | 2024-01-15 | 284856.87 |  | 15.56% | Variance is due to a change in project scope that added three crossarm replacements and associated material and labor costs.
349 | 0PT53436 -- MORGAN CREEK SWITCH - TONKAWA SWITCH 345 KV LINE : UPGRADE BETWEEN 154/5 AND MORGAN CREEK SWITCH | Not Applicable | 822873 | 2024-01-15 | 574503.29 |  | -30.18% | Not Applicable
350 | 0PT52529 -- WHITNEY SWITCH - STEPHENVILLE SWITCH 138 KV LINE : CUT-IN TO ESTABLISH 138KV RING BUS FOR TNMP | Not Applicable | 2177095.48 | 2024-02-15 | 1529453.89 |  | -29.75% | Not Applicable
351 | 0PT52527 -- EULOGY SWITCH: ESTABLISH STATION TO PROVIDE 138 KV POI FOR TNMP (F.K.A. WALNUT SPRINGS SWITCH) | Not Applicable | 6625692.56 | 2023-11-15 | 5142430.99 |  | -22.39% | Not Applicable
352 | 0PT52427 -- RAVEN POI : ESTABLISH 138KV POINT OF INTERCONNECT FOR GSEC | Not Applicable | 1196631.64 | 2023-10-15 | 839273.26 |  | -29.86% | Not Applicable
353 | 0PT52206 -- CEDAR HILL SWITCH - WATERMILL SWITCH SWITCH 138 KV LINE : TEN MILES (FORMERLY GREENE SUB) SUB CUT IN | Not Applicable | 1279087 | 2023-11-15 | 1171901.41 |  | -8.38% | Not Applicable
354 | 0PT52198 -- GRAHAM PLANT SWITCH - COOK FIELD ROAD SWITCH 345 KV LINE: CLEARANCE IMPROVEMENT | Not Applicable | 1418880.13 | 2023-09-15 | 1474634.76 |  | 3.929% | Not Applicable
355 | 0PT52145 -- SANDOW SWITCH : TRANSFER TRIP REPLACEMENT, LINE TERMINAL UPGRADE, FOR THE ADDITION OF BEULAH SWITCH (STONERIDGE SOLAR) | Not Applicable | 723845.96 | 2023-10-15 | 689334.75 |  | -4.768% | Not Applicable
356 | 0PT52141 -- RINGO SWITCH - HARTRING SUB 138 KV LINE : TIE LINE TO EST HARTRING SUB | Not Applicable | 502014 | 2023-11-15 | 424309.99 |  | -15.48% | Not Applicable
357 | 0PT52135 -- ROUND ROCK SOUTHEAST SUB : INSTALL BANK #4 WITH A 138-24.9 KV, 46.7 MVA TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable | 4616659.05 | 2023-11-15 | 4457447.5 |  | -3.449% | Not Applicable
358 | 0PT52129 -- JARRELL EAST SUB: REPLACE TWO 138-12.5 KV 28MVA TRANSFORMERS WITH TWO 138-24.9 KV 46.7MVA TRANSFORMERS | Not Applicable | 4573892.65 | 2023-12-15 | 4551094.99 |  | -0.4984% | Not Applicable
359 | 0PT51967 -- COLLIN SWITCH - STONE CREEK SWITCH 138 KV LINE : INSTALL 138KV POI FOR OUTER LOOP SWITCH FOR RAYBURN'S CELINA SUB | Not Applicable | 2186115 | 2023-10-15 | 1669640.25 |  | -23.63% | Not Applicable
360 | 0PT51966 -- OUTER LOOP SWITCH: ESTABLISH 138KV POINT OF INTERCONNECTION FOR RAYBURN CELINA | Not Applicable | 7680208.8 | 2023-12-15 | 5071006.54 |  | -33.97% | Not Applicable
361 | 0PT51953 -- SANDOW SWITCH - TAYLOR SUB 138 KV LINE : THORNDALE NORTH SUB RE-TERMINATION | Not Applicable | 452731.74 | 2023-08-15 | 267093.2 |  | -41% | Not Applicable
362 | 0PT51772 -- KIRKLAND PARK SWITCH : REPLACE OVER-DUTIED 138KV CIRCUIT BREAKER #55 | Not Applicable | 825696.88 | 2023-10-15 | 595672.46 |  | -27.86% | Not Applicable
363 | 0PT51770 -- BLUE MOUNTAIN SWITCH: ESTABLISH STATION TO PROVIDE 138 KV POD FOR TARGA DELAWARE LLC | Not Applicable | 9999763.31 | 2023-11-15 | 9011884.66 |  | -9.879% | Not Applicable
364 | 0PT51681 -- OWL HILLS SUB : INSTALL BANK #4 WITH A 138-21.6 KV, 47 MVA TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable | 3512732.57 | 2023-11-15 | 2972720.91 |  | -15.37% | Not Applicable
365 | 0PT51638 -- TEMPLE ELM CREEK SWITCH : REPLACE RELAYING AS PART OF ESTABLISHING PEPPERVINE AND PEPPER CREEK SWITCHES | Not Applicable | 265416.98 | 2023-07-15 | 355596.53 |  | 33.98% | Variance is due to a change in project scope to add the installation of one 138 kV breaker control panel that was not part of the initial estimate. These panels are being replaced through an ongoing Oncor program, and adding this replacement to the scope of work for this project allowed for more efficient use of work crews. Material costs increased due to the scope change and price increases for relay panels. Labor costs increased due to the scope change and the need for additional resources for an accelerated schedule.
366 | 0PT51623 -- CENTRALIA SUB: INSTALL 138 KV CAPACITOR BANK #2 | Not Applicable | 3090037.78 | 2023-08-15 | 3005141.92 |  | -2.747% | Not Applicable
367 | 0PT50908 -- ROSEN HEIGHTS SUBSTATION : PURCHASE IN FEE | Not Applicable | 14679351.3 | 2024-05-15 | 393088.46 |  | -97.32% | Not Applicable
368 | 0PT51585 -- PROGRESS PARK SWITCH: ESTABLISH STATION TO PROVIDE 138 KV POD FOR GLOBALWAFERS AMERICA, LLC | Not Applicable | 8156410.6 | 2023-11-15 | 7757975.58 |  | -4.885% | Not Applicable
369 | 0PT51560 -- MELTON BRANCH POD : INSTALL LV METERING ON TWELVE (12) CUSTOMER OWNED TRANSFORMERS | Not Applicable | Not Applicable | Not Applicable | 470938.99 |  | Not Applicable | Not Applicable
370 | 0PT51544 -- LIPAN SUBSTATION: REPLACE TRANSFORMER #1 WITH 28 MVA, 138-12.5 KV TRANSFORMER AND FID | Not Applicable | 1618843.37 | 2023-12-15 | 1760639.67 |  | 8.759% | Not Applicable
371 | 0PT51540 -- TEX HARVEY SUBSTATION: INSTALL BANK #2 WITH A 47 MVA, 138-25 KV TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable | 2951240.79 | 2023-08-15 | 2888137.62 |  | -2.138% | Not Applicable
372 | 0PT51524 -- SL EAST STILES SUB: INSTALL 138 KV CAPACITOR BANK | Not Applicable | 2154873.6 | 2023-08-15 | 2184857.28 |  | 1.391% | Not Applicable
373 | 0PT51483 -- ALLEN SW - ANNA SW 138KV LINE: CUT IN TO ESTABLISH RIDGEVIEW SUB | Not Applicable | 4998391 | 2023-11-15 | 4619323.75 |  | -7.584% | Not Applicable
374 | 0PT51480 -- SHERRY SWITCH – TIMBERVIEW SWITCH 345KV LINE: INSTALL OPGW FROM CENTURY SUB TO SHERRY SW | Not Applicable | 1561889.86 | 2023-12-15 | 1026510.42 |  | -34.28% | Not Applicable
375 | 0PT51479 -- WATERMILL BKR 45 SWITCH - PARKDALE BKR 590 SWITCH 138 KV LINE : INSTALL INSULATOR ON 52 STRUCTURES | Not Applicable | 263564 | 2023-04-15 | 250836.76 |  | -4.829% | Not Applicable
376 | 0PT51478 -- SHERRY SWITCH – TIMBERVIEW SWITCH 345KV LINE: INSTALL OPGW FROM CENTURY SUB TO 10/7 | Not Applicable | 1282290.17 | 2023-12-15 | 775128.14 |  | -39.55% | Not Applicable
377 | 0PT51252 -- LAKE ARROWHEAD TAP - NEWPORT (BEPCO) 138 KV LINE : REPLACE BAD STRUCTURES 47/8, 52/4, 52/6, 52/10, 53/4, 53/5, 53/6, 54/3, 55/6, 63/2, 65/9, 69/9, 71/1, 71/3, 90/3. (GLT) | Not Applicable | 239000 | 2023-07-15 | 391580.9 |  | 63.84% | Variance is due to an increased scope of work and associated labor costs. The initial estimate assumed that Oncor labor would complete the work. Additional contract resources and charges for a Field Construction Coordinator were added, which increased labor costs.
378 | 0PT51225 -- CEDAR CREST SWITCH - WATERMILL SWITCH STATION 138 KV LINE: TEN MILES (FORMERLY GREENE SUB) SUB CUT IN | Not Applicable | 1657454 | 2023-11-15 | 1628685.64 |  | -1.736% | Not Applicable
379 | 0PT51156 -- VINEYARD SWITCH - ROANOKE SWITCH 138 KV LINE : RETERMINATE INTO ROANOKE WEST SUB | Not Applicable | 1521370 | 2023-11-15 | 1222750.77 |  | -19.63% | Not Applicable
380 | 0PT51155 -- SPRABERRY SUB - POLECAT CREEK SUB 138 KV LINE : QUARTZ SAND RETERMINATION | Not Applicable | 1278699 | 2023-10-15 | 1398284.17 |  | 9.352% | Not Applicable
381 | 0PT51143 -- TALL CITY SUB - GLASS RANCH SUB 138 KV LINE : CUT-IN TO ESTABLISH LAZY RANCH SUB | Not Applicable | 1675862.42 | 2023-09-15 | 1346334.39 |  | -19.66% | Not Applicable
382 | 0PT51142 -- DESERT WIND SUB : ADD 138KV 55.2 MVAR THREE STAGE CAPACITOR BANK | Not Applicable | 2943265.39 | 2023-09-15 | 2888344.21 |  | -1.866% | Not Applicable
383 | 0PT51111 -- SHERMAN SOUTH - MEMC SOUTHWEST - VALLEY SWITCH 138 KV LINE: HOWE SUB CUT IN | Not Applicable | 1925159 | 2024-02-15 | 1809636.57 |  | -6.001% | Not Applicable
384 | 0PT51082 -- STONE CREEK SWITCH BKR 15445 AND BKR 15450 - GAINESVILLE EAST TAP 69 SWT 205: REPLACE 27 H-FRAMES (GLT) | Not Applicable | 473611.76 | 2023-05-15 | 682252.24 |  | 44.05% | Variance is due to increased labor costs resulting from the need to use non-MSA labor, material delays, and an accelerated construction schedule. Non-MSA labor was required due to the unavailability of Oncor resources. Material delivery delays postponed the start date of this project, and Oncor resources were unable to perform the work that was originally planned. To meet the original construction timeline, additional contract resources were called in to assist with completing this project.
385 | 0PT51045 -- TIN ROOF POD : ESTABLISH CARRIER BLOCKING TERMINAL | Not Applicable | 475319.7 | 2023-09-15 | 501360.46 |  | 5.479% | Not Applicable
386 | 0PT50972 -- BUCHANAN RANCH SUB: REPLACE TRANSFORMER #1 | Not Applicable | 3034799 | 2024-01-15 | 2893319.68 |  | -4.662% | Not Applicable
387 | 0PT50971 -- CHIRENO SUB: REBUILD STATION WITH ONE TRANSFORMER | Not Applicable | 5349809.18 | 2024-02-15 | 2102725.22 |  | -60.7% | Not Applicable
388 | 0PT50970 -- TAYLOR SUB: REPLACE TRANSFORMER #1 & TRANSFORMER #2 | Not Applicable | 7492171.61 | 2023-09-15 | 6833177.63 |  | -8.796% | Not Applicable
389 | 0PT49606 -- LUND SUBSTATION : PURCHASE IN FEE | Not Applicable | 9606404.63 | 2023-12-15 | 809025.48 |  | -91.58% | Not Applicable
390 | 0PT50966 -- IVY LEAGUE SUB: INSTALL TRANSFORMER #2 | Not Applicable | 2908741.91 | 2023-08-15 | 2290502.24 |  | -21.25% | Not Applicable
391 | 0PT50900 -- WISHBONE POD : ESTABLISH 138KV POINT OF DELIVERY FOR BRAZOS MIDLAND, LLC | Not Applicable | 2354178.17 | 2023-07-15 | 2410500.99 |  | 2.392% | Not Applicable
| 0PT54556 -- WISHBONE POD (BRAZOS MIDSTREAM SUNDANCE SUB): RECEIVE A DEED IN PLACE OF THE EXISTING STATION EASEMENT |  |  | 2023-07-15
392 | 0PT50850 -- BRITTON ROAD SUB: INSTALL STATION #4 WITH ONE 345/26.4 KV, 100 MVA, TRANSFORMER AND ONE FEEDER BREAKER; INSTALL ONE 25 KV FEEDER BREAKER ON # 3 | Not Applicable | 5645752 | 2023-08-15 | 4731543.03 |  | -16.19% | Not Applicable
393 | 0PT50819 -- FAIRFIELD WEST SUB: INSTALL TRANSFORMER #2 | Not Applicable | 4623458.24 | 2024-01-15 | 5287365.13 |  | 14.36% | Variance is primarily due to a change in project scope and increased material and labor costs. A mobile substation was added to the scope of the project. Transformer cost was higher than estimated due to price increases. Labor costs increased due to the need for external protection and control resources, charges for security services due to the project being located in a high-theft area, and multiple remobilizations as a result of multiple work stoppages to remove old equipment and install new equipment in discrete phases, which required coordination of various work crews and schedules beyond what was accounted for in the initial estimate.
394 | 0PT50818 -- SHIFTING SANDS SUB: INSTALL TRANSFORMER #2 | Not Applicable | 3717076.94 | 2023-08-15 | 2684147.56 |  | -27.79% | Not Applicable
395 | 0PT50816 -- KNOTT SUB: INSTALL TRANSFORMER #2 | Not Applicable | 3319771.26 | 2023-09-15 | 2811814.65 |  | -15.3% | Not Applicable
396 | 0PT50815 -- WILLOW WELLS SUB: INSTALL TRANSFORMER #3 | Not Applicable | 4570551.78 | 2023-08-15 | 5173509.47 |  | 13.19% | Variance is due to a change in project scope and increased material and labor costs. Scope change includes additional materials and labor to reroute the existing underground feeder-tie conduits. Material costs increased due to price increases for structural steel, transformers, relay control equipment, and the control center. Costs for transformer rigging, crane, and transportation services increased due to the remote station location. Construction contractor costs increased due to rocky soil conditions; proximity of work to energized equipment; and hand-digging for conduit, grounding, and foundation installations. ERCOT clearance coordination, material delays, and a lack of concrete availability delayed construction, which resulted in additional charges for security services and multiple remobilizations. Additional protection and control resources were required to complete the project ahead of ERCOT's clearance restriction deadline.
397 | 0PT50814 -- CALF TANK SUB: ESTABLISH STATION WITH TWO TRANSFORMERS | Not Applicable | 8642703.74 | 2023-11-15 | 8478753.35 |  | -1.897% | Not Applicable
398 | 0PT50813 -- CRANDALL SUB: INSTALL TRANSFORMER #2 | Not Applicable | 3783842.75 | 2023-08-15 | 4865054.13 |  | 28.57% | Cost variance is due to increased material and labor costs. Material costs for 138/25kV transformer increased and more matting was required than was included in the cost estimates. Construction was delayed for worker safety due to rainy weather and equipment delays occurred, all of which resulted in remobilization charges.
399 | 0PT50811 -- KYLE RANCH SUB: INSTALL TRANSFORMER #3 | Not Applicable | 3184741.5 | 2023-08-15 | 3907530.21 |  | 22.7% | Variance is due to a change in project scope and increased labor costs. A field tie and associated work were added to the project scope. Non-MSA labor was used for construction, and external protection and control resources were required for commissioning to meet the project’s in-service date, which increased labor costs.
400 | 0PT50810 -- MARIENSFIELD SUB: INSTALL TRANSFORMER #2 | Not Applicable | 3102180.57 | 2023-08-15 | 3119853.74 |  | 0.5697% | Not Applicable
401 | 0PT50809 -- COTTONFIELD SUB: INSTALL 138-26.4 KV, 47 MVA TRANSFORMER #2 WITH TWO 25 KV FEEDER BREAKERS | Not Applicable | 2868222.04 | 2023-09-15 | 3085819.12 |  | 7.586% | Not Applicable
402 | 0PT50808 -- ROUND ROCK SWITCH: REPLACE TRANSFORMER #4 | Not Applicable | 2045864.34 | 2024-02-15 | 1715744.97 |  | -16.14% | Not Applicable
403 | 0PT50806 -- ROANOKE WEST SUB: INSTALL TRANSFORMER #3 | Not Applicable | 6276612.67 | 2023-07-15 | 7017674.77 |  | 11.81% | Variance is due to a change in project scope and associated increase in material and labor costs. A Geotech study discovered rockier than expected soil, requiring the removal and replacement of intended ground rods. Conduits thought to be available at the time the estimate was created were actually in use, which required new trenches to be dug and additional conduits to be installed.
404 | 0PT50805 -- KAUFMAN SOUTH SUB: UPGRADE TRANSFORMER #1 AND INSTALL TRANSFORMER #2 | Not Applicable | 5307743.44 | 2023-07-15 | 5675354.47 |  | 6.926% | Not Applicable
405 | 0PT50793 -- WATERMILL TO PARKDALE: 138KV GLT POLE REPLACEMENT - LINE SECTION: SOUTHSIDE FILTRATION TAP WEST - SOUTHSIDE FILTRATION | Not Applicable | 299189 | 2023-02-15 | 330711.82 |  | 10.54% | Variance is due to change in scope to install post insulators on nine structures, which increased material and labor costs.
406 | 0PT50766 -- MIDKIFF SWITCH - SHAW POD 138 KV LINE : SHAW POD FOR ENTERPRISE NAVITAS MIDSTREAM | Not Applicable | 3072883 | 2023-09-15 | 2705196.99 |  | -11.97% | Not Applicable
407 | 0PT50765 -- SHAW POD: ESTABLISH 138KV POINT OF DELIVERY FOR ENTERPRISE NAVITAS MIDSTREAM MIDLAND BASIN, LLC | Not Applicable | 1153081.18 | 2023-09-15 | 1035234.56 |  | -10.22% | Not Applicable
408 | 0PT50638 -- SEYMOUR SUB - MUNDAY SWITCH 69 KV LINE : CUT IN FOR BOMARTON SUB SKID | Not Applicable | 1717608 | 2023-11-15 | 1478249.48 |  | -13.94% | Not Applicable
409 | 0PT50571 -- BEULAH SWITCH : ESTABLISH 345 KV STATION FOR A POINT-OF-INTERCONNECTION (POI) FOR STONERIDGE SOLAR | Not Applicable | 10510829.63 | 2023-09-15 | 10470392.1 |  | -0.3847% | Not Applicable
410 | 0PT50557 -- TERRELL SWITCH - TERRELL SOUTH 138KV LINE : REPLACE 7 POLES (GLT PROJECT) TERRELL SOUTH -- ROSEHILL LINE SECTION | Not Applicable | 255273 | 2023-02-15 | 401283.64 |  | 57.2% | Variance is due to unexpected equipment rental fees and repair costs for vehicular damage to the ROW that increased the cost for pole replacements from the historical costs used to create the estimate.
411 | 0PT50548 -- EAST NETWORK SUB - MEDILL TERMINAL SUB 138 KV LINE : PUMPING PLANT REPLACEMENT | Not Applicable | 1477354 | 2023-11-15 | 1562720.89 |  | 5.778% | Not Applicable
412 | 0PT50529 -- YUCCA DRIVE SWITCH - MOSS SWITCH 138 KV LINE: REPLACE WOOD POLES, INSULATORS AND CROSSARMS (GLT) | Not Applicable | 288106 | 2023-02-15 | 316762.67 |  | 9.947% | Not Applicable
413 | 0PT50485 -- CARROLLTON NORTHWEST: REPLACE OVERDUTIED 138KV CIRCUIT BREAKER 2480 | Not Applicable | 622143.12 | 2023-07-15 | 568141.29 |  | -8.68% | Not Applicable
414 | 0PT50441 -- LAMESA SWITCH - AL PASTOR BESS POI 138 KV LINE : INSTALL LINE FOR AL PASTOR BESS | Not Applicable | 580644 | 2023-08-15 | 475501.68 |  | -18.11% | Not Applicable
415 | 0PT50418 -- BENNETT ROAD SWITCH - KRUM TAP SWITCH 138 KV LINE: CUT-IN DENTON CREEK SWITCH | Not Applicable | 1557404 | 2023-09-15 | 1119932.38 |  | -28.09% | Not Applicable
416 | 0PT50414 -- UPTON SUB - GOODNIGHT SUB 138 KV LINE : ESTABLISH GOODNIGHT SUB | Not Applicable | 949357.32 | 2023-04-15 | 510596.03 |  | -46.22% | Not Applicable
417 | 0PT50394 -- TERRELL SWITCH - KAUFMAN NORTHWEST - SEAGOVILLE: AIRCO TAP - ROSE HILL LINE SECTION 138KV REJECT POLE REPLACEMENTS (GLT) | Not Applicable | 297715 | 2023-02-15 | 441159.13 |  | 48.18% | Variance is due to an underestimation of the amount of materials and supplies needed for the project, unexpected equipment rental fees, and repair costs due to vehicular damages to the ROW.
418 | 0PT50372 -- DOOLEY SUB - WINK SWITCH 69 KV LINE : RE-TERMINATION STRUCTURE 20/8 - WINK SWITCH | Not Applicable | 366194.53 | 2023-04-15 | 315704 |  | -13.79% | Not Applicable
419 | 0PT50371 -- WINK SWITCH AUTOTRANSFORMER #1 - WINK SWITCH 69KV LINE: RE-TERMINATION | Not Applicable | 396687.22 | 2023-04-15 | 615607.82 |  | 55.19% | Variance is due to increased costs for Oncor and Field Construction Coordinator labor resulting from re-sequencing construction to efficiently coordinate the work on this project with other station and line work planned at the same station. This coordination allowed for more efficient use of work crews.
420 | 0PT50347 -- YUCCA DRIVE SWITCH - MOSS SWITCH 138 KV LINE : CUT-IN TO ESTABLISH RACEWAY SWITCH | Not Applicable | 1232895 | 2024-03-15 | 560961.91 |  | -54.5% | Not Applicable
421 | 0PT50335 -- JEWETT SWITCH - ST. JOHNS SWITCH 345 KV LINE : CUT-IN TO ESTABLISH BALE SWITCH 345 KV | Not Applicable | 2464149 | 2023-08-15 | 2127161.57 |  | -13.68% | Not Applicable
422 | 0PT50298 -- ENNIS WEST SWITCH - STERRETT SWITCH 138 KV LINE : REPLACE (13) WOOD POLES, (2) X-ARMS, (4) X-BRACES & (15) INSULATORS. (GLT) | Not Applicable | 312552 | 2023-01-15 | 282585.73 |  | -9.588% | Not Applicable
423 | 0PT50281 -- BROWNWOOD SWITCH - GOLDTHWAITE SUB 138 KV LINE : REPLACE 19 POLES IDENTIFIED DURING GLT | Not Applicable | 387085 | 2023-08-15 | 437886.48 |  | 13.12% | Variance is due to increased labor costs. Initial estimated contemplated internal labor would be sufficient, but due to the project’s complexity contractors were required to complete the work as efficiently as possible.
424 | 0PT50261 -- CARROLL SPRINGS SUB: 69 KV CAPACITOR BANK REPLACEMENT | Not Applicable | 2478415.31 | 2023-09-15 | 2251149.53 |  | -9.17% | Not Applicable
| 0PT50001 -- CARROLL SPRINGS SUB EXPANSION : PURCHASE IN FEE |  |  | 2023-09-15
425 | 0PT50250 -- LEON SWITCH - DUBLIN SUB 69 KV LINE: ESTABLISH ELLISON SPRINGS 69KV POINT OF INTERCONNECT FOR BRAZOS RUCKER SUB | Not Applicable | 2561680.01 | 2023-03-15 | 2443022.43 |  | -4.632% | Not Applicable
426 | 0PT50249 -- ELLISON SPRINGS POI: ESTABLISH 69KV POI FOR BRAZOS RUCKER SUB | Not Applicable | 995389 | 2023-04-15 | 803371.83 |  | -19.29% | Not Applicable
427 | 0PT50080 -- FRANKEL CITY SUB : UPGRADE BANK#1 AND INSTALL BANK #2 WITH A 138-12.5 KV, 47 MVA TRANSFORMER | Not Applicable | 5237672.45 | 2023-07-15 | 5620735.05 |  | 7.314% | Not Applicable
428 | 0PT50079 -- CHINA LAKE SUB : INSTALL BANK #2 WITH 138-21.6 KV, 47 MVA TRANSFORMER AND INSTALL TWO FEEDER BREAKERS | Not Applicable | 3200826.04 | 2023-08-15 | 3208258.25 |  | 0.2322% | Not Applicable
429 | 0PT50077 -- ALCATRAZ SUB : INSTALL BANK #3 WITH 138-21.6 KV, 47 MVA TRANSFORMER AND INSTALL TWO FEEDER BREAKERS | Not Applicable | 4686632.15 | 2023-08-15 | 4863770.17 |  | 3.78% | Not Applicable
430 | 0PT50076 -- MAVERICK DRAW SUB : INSTALL BANK #2 WITH 138-21.6 KV, 47 MVA TRANSFORMER AND INSTALL TWO FEEDER BREAKERS | Not Applicable | 3015513.2 | 2023-08-15 | 3172279.44 |  | 5.199% | Not Applicable
431 | 0PT49982 -- SAM SWITCH - TRADINGHOUSE SWITCH 345 KV LINE : CUT-IN TO ESTABLISH TIGER CREEK SWITCH | Not Applicable | 3540081.65 | 2023-03-15 | 4552191.66 |  | 28.59% | Variance is due to increased labor costs resulting from the need to utilize non-MSA labor. No MSA contractors were available for the project during the period when construction was scheduled.
432 | 0PT49981 -- DENTON CREEK SWITCH: ESTABLISH 138KV STATION FOR POI FOR CONNOLLY STORAGE | Not Applicable | 6036824 | 2023-05-15 | 5673431.78 |  | -6.02% | Not Applicable
433 | 0PT49950 -- MERRICK TAP - MERRICK POD 138 KV LINE : INSTALL POI LINE TO CUSTOMER | Not Applicable | 2858455 | 2023-10-15 | 2678239.77 |  | -6.305% | Not Applicable
434 | 0PT49854 -- KILLEEN CLEAR CREEK SUB : UPGRADE RELAYING TO SUBURBAN IV | Not Applicable | 2926358.35 | 2023-03-15 | 3609375.72 |  | 23.34% | Variance is due to increased material and labor costs. Material costs increased due to the prices for reactors and other materials being higher than the historical costs used to create the estimate. Labor costs increased due to change orders for additional flowable fill, extended security duration, remobilizations, and external protection and control resources being required for commissioning.
435 | 0PT49849 -- MARTIN LAKE SWITCH - STRYKER CREEK SWITCH 345 KV LINE : REPLACE AND RELOCATE TOWER 29/1 | Not Applicable | 665391.75 | 2023-03-15 | 836826.71 |  | 25.76% | Variance is due to increased material and labor costs. Excessive rain before construction increased matting cost and required the installation of permanent casing on structure foundations. Material delivery delays resulted in remobilization charges.
436 | 0PT50008 -- LEAN CLAY SWITCH (FKA COALSON DRAW SWITCH) PURCHASE LAND IN EASEMENT | Not Applicable | 12817097.11 | 2023-10-15 | 682599.46 |  | -94.67% | Not Applicable
437 | 0PT49759 -- BELL COUNTY EAST SWITCH : ESTABLISH 345 KV POI FOR CHILLINGHAM SOLAR AND STORAGE | Not Applicable | 1641833.71 | 2023-03-15 | 1378796.6 |  | -16.02% | Not Applicable
438 | 0PT49662 -- MONTICELLO SWITCH - WOODARD SWITCH 345 KV LINE : CLEARANCE IMPROVEMENT | Not Applicable | 11367782 | 2023-03-15 | 7031412.42 |  | -38.15% | Not Applicable
439 | 0PT49631 -- STEAKLEY DAM SWITCH: ESTABLISH 345 KV RING BUS STATION TO PROVIDE POI FOR BLEVINS SOLAR & STORAGE | Not Applicable | 11781980.77 | 2023-11-15 | 10519524.32 |  | -10.72% | Not Applicable
440 | 0PT49600 -- SL ROCKY ROAD - STILES 138KV LINE: REBUILD | Not Applicable | 11661939 | 2023-12-15 | 9012474.57 |  | -22.72% | Not Applicable
441 | 0PT49594 -- TALL CITY - GLASS RANCH 138KV LINE: REBUILD | Not Applicable | 2421974 | 2023-10-15 | 1073406.55 |  | -55.68% | Not Applicable
442 | 0PT49588 -- CALMONT SWITCH - BENBROOK SWITCH 138 KV LINE : ADD OPGW | Not Applicable | 1721324.86 | 2023-05-15 | 1173836.89 |  | -31.81% | Not Applicable
443 | 0PT49552 -- ROYSE SWITCH - SHAMBURGER SWITCH 345 KV LINE : CUT-IN TO ESTABLISH POETRY SWITCH | Not Applicable | 3498479.93 | 2023-03-15 | 4301256.83 |  | 22.95% | Variance is due to increased material and labor cost. Poor soil conditions required matting to be installed in two separate stages. Additionally, standard bucket trucks were not tall enough for the towers used for the project. Additional costs were incurred to rent taller bucket trucks for several months, and remobilization charges were incurred while waiting for the trucks and matting installation.
444 | 0PT47963 -- WACO WEST SWITCH - MCGREGOR PHILLIPS SWITCH 69 KV LINE : WACO SANGER AVENUE REROUTE | Not Applicable | 3498479.93 | 2023-03-15 | 1249738.77 |  | -64.28% | Not Applicable
445 | 0PT49533 -- WATERMILL SWITCH - CEDAR HILL SWITCH 138 KV LINE: FLOYD BRANCH SUBSTATION CUT-IN | Not Applicable | 692012 | 2023-11-15 | 582564.47 |  | -15.82% | Not Applicable
446 | 0PT49517 -- DRIVER SUB - DJ HUTT SUB 138 KV: STATION TIE LINE BUILD | Not Applicable | 703577.38 | 2023-05-15 | 582801.41 |  | -17.17% | Not Applicable
447 | 0PT49495 -- COLLIN SWITCH : INSTALL TWO 37.5 MVAR REACTORS ON THE TERTIARY OF AUTOTRANSFORMER #2 | Not Applicable | 1352233 | 2023-03-15 | 1282993.63 |  | -5.12% | Not Applicable
448 | 0PT49494 -- ANNA SWITCH : INSTALL TWO 37.5 MVAR REACTORS ON THE TERTIARY OF AUTOTRANSFORMER #2 | Not Applicable | 1679418 | 2023-03-15 | 1586381.21 |  | -5.54% | Not Applicable
449 | 0PT49492 -- ANNA SWITCH : REPLACE EXISTING SSVTS AND UPGRADE GROUNDING GRID | Not Applicable | 1681386 | 2023-07-15 | 1003966.54 |  | -40.29% | Not Applicable
450 | 0PT49486 -- RACEWAY SWITCH: ESTABLISH 138KV, 3 BREAKER RING BUS STATION TO PROVIDE POD FOR 1POINTFIVE P1, LLC (OXY) | Not Applicable | 6002291.05 | 2023-05-15 | 5098283.75 |  | -15.06% | Not Applicable
451 | 0PT49480 -- GRAHAM PLANT SWITCH - BRECKENRIDGE-LEON SWITCH 138 KV LINE : CUT-IN TO SOUTH BEND SUB | Not Applicable | 697097 | 2023-04-15 | 399795.54 |  | -42.65% | Not Applicable
| 0PT54476 -- GRAHAM PLANT SWITCH - BRECKENRIDGE-LEON SWITCH 138 KV LINE : CUT-IN TO SOUTH BEND SUB : ROW ACQUISITION |  |  | 2023-04-15
452 | 0PT49478 -- EDWARDS TAP - EDWARDS SUB 138 KV LINE : CUT IN | Not Applicable | 559671 | 2023-03-15 | 480425.79 |  | -14.16% | Not Applicable
453 | 0PT49446 -- MERRICK TAP: ESTABLISH 138KV POINT OF DELIVERY FOR WTG NORTH PERMIAN MIDSTREAM LLC | Not Applicable | 1100120.75 | 2023-07-15 | 905504.39 |  | -17.69% | Not Applicable
454 | 0PT49440 -- TIN ROOF POD: INSTALL 2ND CAPACITOR BANK FOR POD | Not Applicable | 2398734 | 2022-10-15 | 1906173.77 |  | -20.53% | Not Applicable
455 | 0PT49406 -- LIGGETT SWITCH - HACKBERRY SWITCH 138 KV LINE : REPLACE TRIGAS TAP STRUCTURE 6/3A | Not Applicable | 2038367.24 | 2023-03-15 | 1806441.11 |  | -11.38% | Not Applicable
456 | 0PT49378 -- WICHITA FALLS SOUTH SWITCH - ALVORD SUB 138 KV LINE : REPLACE LAKE ARROWHEAD TAP | Not Applicable | 1963447 | 2023-08-15 | 1684308.52 |  | -14.22% | Not Applicable
457 | 0PT49337 -- DECORDOVA SWITCH – CARMICHAEL BEND SWITCH 138KV LINE: RECONDUCTOR | Not Applicable | 1744456 | 2022-10-15 | 2023259.93 |  | 15.98% | Variance is due to labor costs for non-standard conductor installation, casing on the foundation installation due to a high water table, and a working pad to address safety concerns during tower installation.
458 | 0PT49260 -- VALLEY SOUTH SWITCH: INSTALL TWO 100 MVAR 345 KV REACTORS | Not Applicable | 11479356 | 2023-01-15 | 13027161.9 |  | 13.48% | Variance is due to increased material and labor costs associated with a scope change. The additional scope was to extend the north and south buses to accommodate a planned POI and minimize bus outages during construction of the planned project. This additional scope of work included installing buswork, foundations, steel structures, and air switches. Another scope change occurred when Oncor identified that a new ground grid was required at the station’s east bus. Material costs increased due to the scope change and also due to price increases for high-voltage circuit breakers. Labor costs increased due to several change orders for economic change adjustments, anchor bolt installation, steel casing, Whitaker locates, crane rental to install a shunt reactor, and additional security services.
459 | 0PT49258 -- SL ALIBATES SWITCH - TULE CANYON SWITCH 345 KV LINE: ESTABLISH MIDPOINT SWITCH FOR FGE GOODNIGHT WIND | Not Applicable | 1564121 | 2023-04-15 | 1243396.27 |  | -20.51% | Not Applicable
| 0PT48066 -- NTUSU ALIBATES SWITCH - TULE CANYON SWITCH 345 KV LINE: REMOVAL FOR MIDPOINT SWITCH CUT-IN |  |  | 2023-04-15
460 | 0PT49104 -- LAMESA SWITCH : TERMINAL ADDITION FOR AL PASTOR BESS | Not Applicable | 2206288.95 | 2023-07-15 | 2008437.43 |  | -8.968% | Not Applicable
461 | 0PT49020 -- ROYSE SWITCH - ROWLETT SUB 138 KV LINE : RECONDUCTOR ROCKWALL SUB TO ROWLETT SUB | Not Applicable | 4630726 | 2022-09-15 | 5307431.29 |  | 14.61% | Variance is due to an estimate error. The cost estimate did not capture the entire material cost.
462 | 0PT49001 -- GRAHAM PLANT SWITCH - COOK FIELD ROAD SWITCH 345 KV LINE : RELOCATE STRUCTURE 27/6 | Not Applicable | 577215.86 | 2022-10-15 | 366467.68 |  | -36.51% | Not Applicable
463 | 0PT48983 -- KRUM SWITCH - JACKSBORO SWITCH 345 KV LINE : FIFTY-THREE FOUNDATIONS REMEDIATION | Not Applicable | 459595 | 2022-10-15 | 889582.22 |  | 93.56% | Variance is due to a change in project scope. Oncor discovered that more reveal caps on the structures were cracking and in need of remediation than originally anticipated.
464 | 0PT48976 -- GINDALE SWITCH : ESTABLISH 345 KV STATION FOR A POINT-OF-INTERCONNECTION (POI) FOR STILLHOUSE SOLAR | Not Applicable | 12821750.43 | 2023-11-15 | 11610497.75 |  | -9.447% | Not Applicable
465 | 0PT48973 -- MARTIN LAKE SWITCH - STRYKER CREEK SWITCH 345 KV LINE : REPLACE AND RELOCATE STR. 41/1 | Not Applicable | 2103357.17 | 2022-11-15 | 1546949.37 |  | -26.45% | Not Applicable
466 | 0PT48971 -- STRYKER CREEK SWITCH - LUFKIN SWITCH 345 KV LINE : REPLACE AND RELOCATE TOWER 23/2 | Not Applicable | 2652703 | 2022-10-15 | 1515139.42 |  | -42.88% | Not Applicable
467 | 0PT48967 -- LAVENDER SWITCH – SDC WILMER (FICUS) 138KV LINE: STATION TIE LINES BUILD | Not Applicable | 784840 | 2022-09-15 | 943382.16 |  | 20.2% | Variance is due to increased material and labor costs. Customer delays, delayed material deliveries, and mitigation of unstable soil conditions delayed the construction and resulted in a compressed construction schedule.
468 | 0PT48946 -- SL COYOTE – LUTHER 138 KV LINE: COYOTE RETERMINATION | Not Applicable | 583278 | 2023-01-15 | 461936.7 |  | -20.8% | Not Applicable
469 | 0PT48846 -- ALLEN SWITCH - ANNA SWITCH 138 KV LINE: CUT-IN TO ESTABLISH BLOOMDALE 138 KV SWITCH | Not Applicable | 2144469 | 2023-03-15 | 1569678.61 |  | -26.8% | Not Applicable
470 | 0PT48845 -- DELAWARE RIVER SWITCH - DELAWARE RANCH SUB 138 KV LINE: BUILD TIE LINE | Not Applicable | 543557 | 2022-10-15 | 849114.25 |  | 56.21% | Variance is due to increased material and labor costs resulting from price increases and construction delays for customer readiness.
471 | 0PT48779 -- SL DRIVER SUB : ADDITION OF 138KV LINE TERMINAL | Not Applicable | 1766020 | 2023-01-15 | 2164993.89 |  | 22.59% | Variance is due to an incorrect charge in Commissioning Services, which should have been charged to project 0PT48010 This error is being corrected internally.
472 | 0PT48778 -- GREENVILLE AVENUE SUB: INSTALL TWO 47 MVA, 138/13.8 KV TRANSFORMERS #5 & # 6 | Not Applicable | 6483491.94 | 2023-07-15 | 6244025.74 |  | -3.693% | Not Applicable
473 | 0PT48773 -- SL SOUTH MIDLAND SUB : RECONFIGURE THE 138 KV HIGH SIDE INTO A TAPPED DISTRIBUTION STATION | Not Applicable | 679897 | 2023-04-15 | 711183.62 |  | 4.602% | Not Applicable
474 | 0PT48724 -- BEAR CREEK SUB : UPGRADE RELAYING ON STATION #3 AND #4 | Not Applicable | 2587936.16 | 2023-12-15 | 2447177.11 |  | -5.439% | Not Applicable
475 | 0PT48723 -- WALL STREET SUB : CONVERT CEDAR CREST LINE TERMINAL TO 138 KV OPERATION | Not Applicable | 1278081.55 | 2023-03-15 | 1521642.8 |  | 19.06% | Variance is due to a change in project scope and increased labor costs. Scope change included unplanned deployment of a mobile substation and replacement of structure foundations. Mobile substation increased labor costs and required additional construction matting for transport. Labor costs also increased due after adding removal of pier foundations, backfilling with flow fill, and installation of spread footer foundations to the scope of work. Remobilization charges associated with ERCOT clearance coordination and extended construction schedule resulting from outage further increased labor costs.
476 | 0PT48718 -- BARR RANCH SUB : INSTALL BANK #1 WITH ONE 138-25 KV, 47 MVA TRANSFORMER AND TWO 25 KV FEEDER BREAKERS FOR TARGA, POD | Not Applicable | 4934341 | 2023-03-15 | 5642404.9 |  | 14.35% | Variance is due to a change in project scope that increased labor costs and caused project delays. Scope additions include additional equipment and labor for drilling through rock and installing a different transformer than initially planned. Transformer change was due to a bushing recall and required additional design work, field modifications, and foundation re-design. Contractors were remobilized to ensure timely service to the customer.
477 | 0PT48716 -- EDWARDS SUB : REBUILD STATION WITH REPLACING BANK #1 & INSTALLING NEW BANK #2, 47 MVA, 12.5 KV TRANSFORMER WITH FOUR FEEDER BREAKER ON BANK #1 AND FOUR FEEDER BREAKER ON BANK #2 | Not Applicable | 7746476.38 | 2023-02-15 | 8436114.98 |  | 8.903% | Not Applicable
478 | 0PT48664 -- SUNNYVALE SUB TO MESQUITE TOWN EAST SUB 138KV LINE REBUILD | Not Applicable | 10338011 | 2023-04-15 | 10758771.5 |  | 4.07% | Not Applicable
479 | 0PT48650 -- ODESSA EHV – SPRABERRY 138 KV LINE: SALT LAKE SUBSTATION RETERMINATION | Not Applicable | 807217 | 2022-10-15 | 533744.33 |  | -33.88% | Not Applicable
480 | 0PT48643 -- MCKENZIE DRAW - LAMESA SUB 138KV LINE: LAMESA SUB RETERMINATION | Not Applicable | 386236 | 2022-10-15 | 321583.77 |  | -16.74% | Not Applicable
481 | 0PT48642 -- GETTY VEALMOOR 138 KV TAP LINE: CUT-IN TO EST VINCENT SUB (FKA GETTY VEALMOOR SUB) | Not Applicable | 1700172 | 2022-10-15 | 1435321.68 |  | -15.58% | Not Applicable
482 | 0PT48603 -- ROANOKE SWITCH - EULESS SWITCH 138 KV LINE : RETERMINATION AT ROANOKE SWITCH | Not Applicable | 1593630 | 2022-10-15 | 1388063.1 |  | -12.9% | Not Applicable
483 | 0PT48569 -- SL GRADY TO EXPANSE SWITCH 138 KV LINE: REBUILD | Not Applicable | 14400877 | 2024-02-15 | 11164235.2 |  | -22.48% | Not Applicable
484 | 0PT48556 -- SL EAST STILES – ROCKY ROAD 138 KV LINE: REBUILD | Not Applicable | 13809085 | 2022-11-15 | 8756842.37 |  | -36.59% | Not Applicable
| 0PT48557 -- NTUSU EAST STILES – ROCKY ROAD 138 KV LINE: RETIREMENTS ONLY |  |  | 2022-11-15
485 | 0PT48536 -- SL PRONGHORN - SALT FLAT ROAD 138 KV LINE: REBUILD | Not Applicable | 13100797 | 2022-09-15 | 8575157.09 |  | -34.54% | Not Applicable
| 0PT49159 -- NTUSU PRONGHORN - SALT FLAT ROAD 138 KV LINE: RETIREMENT ONLY |  |  | 2022-09-15
486 | 0PT48531 -- KRUM WEST SWITCH - HUMMINGBIRD STORAGE POI 345 KV LINE: INSTALL LINE FOR HUMMINGBIRD STORAGE | Not Applicable | 1132115 | 2022-09-15 | 997601.62 |  | -11.88% | Not Applicable
487 | 0PT48528 -- BALE SWITCH : ESTABLISH 345 KV RING BUS STATION TO CONNECT TRUE NORTH SOLAR | Not Applicable | 10701854.75 | 2023-07-15 | 9800130.43 |  | -8.426% | Not Applicable
488 | 0PT48522 -- GREENVILLE AVENUE SWITCH - KIRKLAND PARK SWITCH 138 KV LINE : RETERMINATION | Not Applicable | 693018.26 | 2022-12-15 | 495679.89 |  | -28.48% | Not Applicable
489 | 0PT48483 -- MOSS SWITCH : REPLACE OVERDUTIED 138 KV BREAKERS #3970 & 3980 | Not Applicable | 601943 | 2022-11-15 | 538240.4 |  | -10.58% | Not Applicable
490 | 0PT48482 -- KIRKLAND PARK SWITCH : REPLACE OVERDUTIED 138 KV BREAKERS #0012, 0015, 0022, 0052 & 0025 | Not Applicable | 2077589 | 2022-11-15 | 2250893.79 |  | 8.342% | Not Applicable
491 | 0PT48481 -- HUTTO SWITCH : REPLACE OVERDUTIED BREAKERS #7480, 7500, & 7505.REPLACE MDAR RELAYING FOR CB 7500 | Not Applicable | 742830 | 2022-11-15 | 876012.9 |  | 17.93% | Variance is due to two projects being consolidated into one to maximize the efficient use of work crews. This increased the scope of the project and the material and labor costs that were included in the initial estimate. Scope additions include installing 2 MDAR relaying panels and replacing an outdoor yard light due to construction needs.
492 | 0PT48480 -- CARROLLTON NORTHWEST SWITCH : REPLACE OVERDUTIED BREAKERS #1340, 1370, 2600, & 5645 | Not Applicable | 1692321 | 2022-10-15 | 3979300.58 |  | 135.1% | Variance is due to increased material and labor costs and a billing error. Material cost for the high-voltage circuit breakers and control cable were higher than estimated due to price increases. Labor cost increased due delays in removing the existing breakers, which resulted in change orders and standby time for contract resources. Seven breakers were erroneously charged to this project instead of projects 50632, 53677, 51772, 49568, and 48717. This error is being corrected internally.
493 | 0PT48479 -- AROYA SWITCH : REPLACE OVERDUTIED 138 KV BREAKERS #14400, 14405, 14410, 14415, 14420, & 14425 | Not Applicable | 2279147 | 2022-08-15 | 1204805.81 |  | -47.14% | Not Applicable
494 | 0PT48441 -- COTTONFIELD SUB: 138 KV LINE TERMINAL UPGRADE | Not Applicable | 318599.19 | 2022-10-15 | 459861.03 |  | 44.34% | Variance is due to increased material and labor costs. Project required multiple transmission outages and a mobile substation to accommodate work sequencing. Labor costs increased due to delays while waiting on ERCOT clearances.
495 | 0PT48387 -- YARBROUGH SUB : INSTALL BANK #2 WITH A 138-21.6 KV, 47 MVA TRANSFORMER AND UPGRADE BANK #1 WITH 138-21.6 KV, 47 MVA TRANSFORMER FOR ENVY BLOCKCHAIN | Not Applicable | 4684435 | 2023-02-15 | 4468770.7 |  | -4.604% | Not Applicable
496 | 0PT48376 -- HUTTO SWITCH - GILLELAND CREEK SWITCH 138 KV LINE : CUT-IN TO ESTABLISH DOUBLE CREEK SUB | Not Applicable | 2379553 | 2022-11-15 | 2580956.93 |  | 8.464% | Not Applicable
497 | 0PT48361 -- VENUS SWITCH - LIGGETT SWITCH 345 KV LINE : CUT-IN ENDEAVOR SWITCH | Not Applicable | 3114703 | 2023-09-15 | 3399763.34 |  | 9.152% | Not Applicable
498 | 0PT48351 -- STEPHENSON LAKE POD : ESTABLISH 138 KV POINT OF DELIVERY FOR PINNACLE ENERGY TRANSITION OPERATING CO. | Not Applicable | 956969 | 2022-08-15 | 800973.82 |  | -16.3% | Not Applicable
499 | 0PT48310 -- HAGGERTY SWITCH - TI SM1-1 138 KV LINE: BUILD | Not Applicable | 2019065 | 2022-09-15 | 1857223.96 |  | -8.016% | Not Applicable
500 | 0PT48309 -- HAGGERTY SWITCH STATION - MEMC SOUTHWEST SUBSTATION (SOUTH) 138 KV LINE: BUILD | Not Applicable | 1741500 | 2022-10-15 | 2135115.23 |  | 22.6% | Variance is due to increased material and labor costs. ROW acquisition took longer than expected, which delayed the project and required vegetation management, maintenance of the temporary access road, and construction matting for longer than estimated.
501 | 0PT48284 -- TYLER GRANDE SWITCH - OVERTON SUB : 138 KV POLE/ARM REPLACEMENT (2022 SUMMER WORK) | Not Applicable | 237625 | 2022-06-15 | 296213.37 |  | 24.66% | Variance is due to unseasonably rainy summer conditions, which required mats and rock to be installed to gain access to structures.
502 | 0PT48249 -- GOODNIGHT SUB (FKA PECOS TRAIL SUB): ESTABLISH 138/24.9 KV STATION WITH ONE TRANSFORMER AND TWO OH FEEDERS | Not Applicable | 5202980.59 | 2023-01-15 | 6483920.36 |  | 24.62% | Variance is due to a change in project scope and associated material and labor cost increases. Soil conditions discovered at the station site necessitated the use of a ground enhancement material encased ground grid, which entailed substantially more material, labor, and equipment rental costs than a standard ground grid installation. Mobile capacitor bank was initially planned to be installed at a different location and was not included in the initial estimate. Once Oncor determined the capacitor bank needed to be installed at Goodnight Substation, additional material and labor costs for equipment modifications and pad work were required. Rework was required to convert feeders from overhead to underground.
503 | 0PT48235 -- 2022 SUMMER WORK - JEWETT SWITCH - BROWN MAG SUB 69 KV LINE : REPLACE 9 POLES AND 10 CROSS ARMS ENERGIZED | Not Applicable | 372814 | 2022-05-15 | 268119.89 |  | -28.08% | Not Applicable
504 | 0PT48231 -- WINDTHORST SWITCH - RICE SWITCH 138 KV LINE : 2022 SUMMER WORK- REPLACING POLES, CROSS ARMS, AND X- BRACES ON MULTIPLE STRUCTURES | Not Applicable | 319573 | 2022-05-15 | 448911.31 |  | 40.47% | Variance is due to a change in project scope that added material and labor costs to replace 3 crossarms, 6 braces, and 2 poles to the scope of work. Initial assessment of the project discovered the need to replace these assets.
505 | 0PT48230 -- CRANE SWITCH - ODESSA NORTH SUB 69 KV LINE : CUT IN TO ESTABLISH APPLE SUB | Not Applicable | 1491907 | 2022-07-15 | 1315286.81 |  | -11.84% | Not Applicable
| 0PT49393 -- CRANE SWITCH - ODESSA NORTH SUB 69 KV LINE : ROW ACQUISITION |  |  | 2022-07-15
506 | 0PT48200 -- TIGER CREEK SWITCH : ESTABLISH 3 BREAKER 345 KV RING ARRANGEMENT POI STATION | Not Applicable | 11358438.37 | 2022-11-15 | 11480241.68 |  | 1.072% | Not Applicable
507 | 0PT48182 -- MORGAN CREEK SWITCH : UPGRADE 138 KV BARBER LAKE LINE TERMINAL (EAST CIRCUIT) | Not Applicable | 467843.65 | 2023-01-15 | 445529.65 |  | -4.77% | Not Applicable
508 | 0PT48142 -- SAM SWITCH - FORT SMITH SWITCH 345 KV LINE : CUT-IN TO ESTABLISH FILES VALLEY SWITCH | Not Applicable | 2826239 | 2023-09-15 | 2316720.98 |  | -18.03% | Not Applicable
509 | 0PT48124 -- WACO WEST SWITCH: REMOVE 138 KV YARD & RECONFIGURE AUTO CONNECTION | Not Applicable | 1930107 | 2022-11-15 | 754044.58 |  | -60.93% | Not Applicable
510 | 0PT48118 -- MOUNTAIN CREEK SWITCH - WEST LEVEE 138 KV LINE: LINE REROUTE FOR CAMPION 138 KV SUB | Not Applicable | 1401334 | 2022-10-15 | 1192202.37 |  | -14.92% | Not Applicable
511 | 0PT48116 -- MOUNTAIN CREEK SWITCH - NORWOOD SWITCH 138 KV LINE: ESTABLISH TRANSMISSION LOOP FEED FOR CAMPION 138 KV SUB | Not Applicable | 1611278 | 2022-10-15 | 1664681.73 |  | 3.314% | Not Applicable
512 | 0PT48106 -- FILES VALLEY SWITCH: ESTABLISH 345 KV RING BUS STATION TO PROVIDE POI FOR COMPADRE SOLAR | Not Applicable | 9187622.53 | 2023-11-15 | 10126658.99 |  | 10.22% | Variance is due to increased labor costs and an estimation error. Labor costs increased due to the need to use a more costly contractor than was planned at the time of the cost estimate. Costs to commission the project were inadvertently omitted from the estimate, which further contributed to the variance.
| 0PT53764 -- FILES VALLEY SWITCH - LAND BY DEED |  |  | 2023-11-15
513 | 0PT48090 -- CHIMNEY WELL POD : REMOVE EQUIPMENT FOR REPLACEMENT BY NEW DELAWARE RIVER SWITCH FOR CHEVRON USA, INC. | Not Applicable | 291043 | 2022-08-15 | 285942.34 |  | -1.753% | Not Applicable
514 | 0PT48078 -- SALT LAKE SUB : INSTALL TRANSFORMER #4 47 MVA 138/25 KV | Not Applicable | 2721475.03 | 2023-03-15 | 3035062.59 |  | 11.52% | Variance is due to increased material costs resulting from a price increase for power transformers.
515 | 0PT48077 -- SALT LAKE SUB : INSTALL TRANSFORMER #3 47 MVA 138/25 KV | Not Applicable | 5043197 | 2022-10-15 | 5166093.49 |  | 2.437% | Not Applicable
516 | 0PT48075 -- FAIRFIELD WEST - MEXIA MAIN 138 KV LINE: RETERMINATION INTO FAIRFIELD WEST SWITCH | Not Applicable | 858013 | 2022-07-15 | 906429.42 |  | 5.643% | Not Applicable
517 | 0PT48070 -- THORNDALE NORTH SUB: INSTALL 138-12.5 KV 28 MVA STATION 2 WITH TWO (2) UG FEEDERS AND TIE BREAKER | Not Applicable | 5786203.12 | 2022-11-15 | 5698500.63 |  | -1.516% | Not Applicable
518 | 0PT48057 -- BURNETT SWITCH : OIL CONTAINMENT | Not Applicable | 481070 | 2022-05-15 | 465689.53 |  | -3.197% | Not Applicable
519 | 0PT48054 -- COMMERCE SWITCH - SULPHUR SPRINGS SWITCH 138KV LINE: RETERMINATE AT CUMBY TAP | Not Applicable | 996477.52 | 2022-10-15 | 661070.6 |  | -33.66% | Not Applicable
| 0PT48267 -- COMMERCE SWITCH - SULPHUR SPRINGS SWITCH 138KV LINE : EASEMENT ACQUISITION |  |  | 2022-10-15
520 | 0PT48044 -- EVERMAN SWITCH - BURLESON SWITCH 138KV LINE: CUT-IN TO EST RENDON SUB | Not Applicable | 627721.25 | 2023-03-15 | 389878.47 |  | -37.89% | Not Applicable
521 | 0PT48043 -- WEST WACO SWITCH - TEMPLE SUB 69 KV LINE : CASTLEMAN SUB (FKA SOUTH HEWITT SUB) CUT IN | Not Applicable | 1393782.1 | 2023-05-15 | 1121692.82 |  | -19.52% | Not Applicable
522 | 0PT48042 -- SEAGOVILLE SWITCH - MESQUITE EAST 138 KV LINE: NEW VANGUARD SUB (FORMERLY MESQUITE LUCAS SUBSTATION) CUT IN | Not Applicable | 8921442 | 2023-11-15 | 7156220.29 |  | -19.79% | Not Applicable
523 | 0PT48041 -- ENNIS WEST SWITCH - STERRETT SWITCH 138 KV LINE: CUT IN TEMPLETON SUBSTATION | Not Applicable | 1275505 | 2023-04-15 | 1231691.69 |  | -3.435% | Not Applicable
524 | 0PT48029 -- FERRIS SUB - WILMER SUB 69 KV LINE : RETERMINATE AT FERRIS SUB | Not Applicable | 1610298.35 | 2023-03-15 | 1664468.32 |  | 3.364% | Not Applicable
525 | 0PT48019 -- MORGAN CREEK SWITCH - BARBER LAKE SWITCH 138 KV LINE : REBUILD EAST CIRCUIT | Not Applicable | 9436571 | 2024-04-15 | 7317049.57 |  | -22.46% | Not Applicable
| 0PT51558 -- MORGAN CREEK SWITCH - BARBER LAKE SWITCH 138 KV LINE : REBUILD EAST CIRCUIT : ROW ACQUISITION |  |  | 2024-04-15
526 | 0PT48014 -- MATILDA SUB : INSTALL TRANSFORMER #3, #4, AND ASSOCIATED SWITCHGEAR | Not Applicable | 8573178 | 2023-03-15 | 9307608.39 |  | 8.567% | Not Applicable
527 | 0PT48013 -- LEMMON AVE SUB : INSTALL TRANSFORMERS 3 & 4 AND SWITCHGEAR | Not Applicable | 8648622 | 2023-03-15 | 8728004.69 |  | 0.9179% | Not Applicable
528 | 0PT48011 -- GREENVILLE AVE SUB : REBUILD DISTRIBUTION STATION TO INSTALL NEW 138 KV BUS AND TWO 47 MVA, 138/13.8 KV TRANSFORMER #3 & #4 | Not Applicable | 8850144 | 2022-07-15 | 11391294.4 |  | 28.71% | Variance is due to a change in project scope that included the installation of fault interruption devices, additional fiber work, and additional design work to relocate the transformer. Fault interruption devices were added to reduce operational risk. Additional fiber work was identified during construction to reroute an existing fiber line. Also during construction a municipal water line was discovered to be in the path of construction requiring additional design work and remediation for the transformer foundation.
529 | 0PT47990 -- BELL COUNTY EAST SWITCH - TNP ONE SWITCH 345 KV LINE : RAISE STRUCTURES 1/2 AND 1/3 TO ACCOMMODATE FIVE WELLS SOLAR CENTER POI | Not Applicable | 1287749 | 2022-09-15 | 1099096.03 |  | -14.65% | Not Applicable
530 | 0PT47987 -- ROANOKE SWITCH: INSTALL TRANSFORMER #4, 47 MVA, 138-25 KV, TWO FEEDER BREAKERS, AND ONE FEEDER TIE. ESTABLISH DEEN SWITCH LINE TAP FOR STATION #3. | Not Applicable | 3253326 | 2022-06-15 | 4393604.17 |  | 35.05% | Cost variance was due to an increase in material and construction labor costs and a change in project scope. The scope was revised to add transmission line slack span installations inside the station fence, removal of a station deadend structure and foundations, changing the foundation design for underground feeder/tie termination stand to spread footing, and additional conduit and hydro-excavation. These scope additions increased labor costs and required additional costs for job site security. Labor costs also increased due to remobilizations caused by material delays. Material costs increased due to the scope change and a price increase for the power transformer.
531 | 0PT47934 -- MALLARD SWITCH - PINTAIL SWITCH 138 KV LINE : TIE LINES | Not Applicable | 756106 | 2022-07-15 | 674278.33 |  | -10.82% | Not Applicable
532 | 0PT47932 -- MCGUFFEY POD : ESTABLISH 138 KV POINT OF DELIVERY FOR MESSER LLC | Not Applicable | 1132098 | 2023-01-15 | 1245426.6 |  | 10.01% | Variance is due to a change in project scope and increased labor costs. Scope change included additional engineering costs to accommodate a municipal request for a transmission line route modification, which required the relocation of the POD. Labor costs increased due to the need for additional engineering services for the design change to relocate the POD, costs for additional planning and control resources, additional ditching required for conduit installation, and an economic change adjustment for contract labor rates.
533 | 0PT47931 -- BULL HEAD POD: ESTABLISH 138 KV POINT OF DELIVERY FOR DUAL DRIVE TECHNOLOGIES, LTD. | Not Applicable | 1284511.28 | 2023-01-15 | 881294.38 |  | -31.39% | Not Applicable
534 | 0PT47928 -- MOUNTAIN CREEK SWITCH - WEST DALLAS SUB - WEST LEVEE SWITCH 138KV LINE: STRUCTURE REPLACEMENT | Not Applicable | 5393743 | 2023-03-15 | 5791278.46 |  | 7.37% | Not Applicable
| 0PT51113 -- MOUNTAIN CREEK SWITCH - WEST DALLAS SUB - WEST LEVEE SWITCH 138KV LINE: STRUCTURE REPLACEMENT : ROW ACQUISITION |  |  | 2023-03-15
535 | 0PT47905 -- BUCHANAN RANCH SUB - BLUE ACRES SUB 138 KV LINE : REBUILD | Not Applicable | 1156815 | 2023-03-15 | 914271.23 |  | -20.97% | Not Applicable
536 | 0PT47850 -- PEBBLE CREEK SWITCH: INSTALL POD 1 & 2 FOR GOOGLE'S VIOLET SUB | Not Applicable | 3259301.28 | 2023-01-15 | 2129155.38 |  | -34.67% | Not Applicable
537 | 0PT47807 -- BELL COUNTY EAST SWITCH - TNP ONE (TNMP) SWITCH 345 KV LINE : CUT-IN TO ESTABLISH LITTLE POND SWITCH | Not Applicable | 2074518.49 | 2023-06-15 | 1803160.45 |  | -13.08% | Not Applicable
538 | 0PT47806 -- BELL COUNTY EAST SWITCH - TNP ONE (TNMP) SWITCH 345 KV LINE : CUT-IN TO ESTABLISH GIBSON SWITCH | Not Applicable | 1707517.11 | 2023-06-15 | 1804596.77 |  | 5.685% | Not Applicable
539 | 0PT47803 -- WATERMILL SWITCH - PARKDALE SWITCH 138 KV LINE: CUT-IN LAVENDER SWITCH FOR SDC'S WILMER DATA CENTER | Not Applicable | 1675797 | 2022-09-15 | 2062438.7 |  | 23.07% | Variance is due to a change in project scope and supply-chain disruptions that increased labor costs and caused project delays. The scope of work expanded to include casing for foundations due to soil conditions that were causing foundation holes to collapse. Supply-chain disruptions resulted in delays in receiving deadend insulator assemblies, which resulted in additional engineering work.
540 | 0PT47802 -- BELL COUNTY EAST SWITCH - TNP ONE (TNMP) SWITCH 345 KV LINE : CUT-IN TO ESTABLISH BRANGUS SWITCH FOR HALO SOLAR AND BEN MILAM 3 | Not Applicable | 3801745 | 2022-11-15 | 3660609.26 |  | -3.712% | Not Applicable
541 | 0PT47795 -- VALLEY SWITCH - PARIS SWITCH 345 KV LINE : CUT-IN FOR PACIFIC SWITCH | Not Applicable | 2244840.8 | 2022-10-15 | 2150256.68 |  | -4.213% | Not Applicable
542 | 0PT47794 -- TAYLOR SWITCH - SANDOW SWITCH 138 KV LINE : CUT-IN FOR ROOKIE SWITCH | Not Applicable | 2231271 | 2023-04-15 | 2013836.44 |  | -9.745% | Not Applicable
543 | 0PT47792 -- JACKSBORO SWITCH - KRUM WEST SWITCH 345 KV LINE : CUT-IN BIRD DOG SWITCH | Not Applicable | 1381905 | 2022-09-15 | 1247936.2 |  | -9.695% | Not Applicable
544 | 0PT47787 -- HORSESHOE SPRINGS SWITCH - RIVERTON SWITCH 138 KV LINE : CUT-IN FOR DELAWARE RIVER SWITCH | Not Applicable | 2230377 | 2022-10-15 | 2054888.43 |  | -7.868% | Not Applicable
545 | 0PT47778 -- WESTMORELAND NORTH SUB: INSTALL TRANSFORMER #2 AND ONE FEEDER | Not Applicable | 4471785 | 2022-11-15 | 4794368.16 |  | 7.214% | Not Applicable
546 | 0PT47777 -- STAGECOACH SUB: INSTALL TRANSFORMER #2 AND TWO FEEDERS | Not Applicable | 3244911.52 | 2024-02-15 | 2921037.49 |  | -9.981% | Not Applicable
547 | 0PT47775 -- HUTTO SWITCH : REPLACE ELECTROMECHANICAL RELAYS FOR AUTO #1,138KV EAST AND WEST BUS, 345KV EAST AND WEST BUS. REPLACE DFR. | Not Applicable | 2294627.9 | 2023-01-15 | 2263282.79 |  | -1.366% | Not Applicable
548 | 0PT47771 -- TEMPLE SWITCH - LAKE CREEK SWITCH 345 KV LINE : CUT-IN TO ESTABLISH BELFALLS SWITCH FOR BIG ELM SOLAR | Not Applicable | 2642326.09 | 2022-08-15 | 2272251.46 |  | -14.01% | Not Applicable
549 | 0PT47762 -- MCGREGOR PHILLIPS-HARRIS CREEK 138 KV : REBUILD | Not Applicable | 3647064 | 2022-06-15 | 3587515.12 |  | -1.633% | Not Applicable
| 0PT48228 -- MCGREGOR PHILLIPS-HARRIS CREEK 138 KV : REBUILD : EASEMENT ACQUISITION |  |  | 2022-06-15
550 | 0PT47755 -- TEMPLE SWITCH - MINERVA SWITCH 69 KV LINE : CUT-IN TO ESTABLISH MCFALL SWITCH | Not Applicable | 1605399 | 2023-09-15 | 1437388.51 |  | -10.47% | Not Applicable
551 | 0PT47754 -- BELL COUNTY EAST SWITCH - FIVE WELLS POI 345 KV LINE: INSTALL LINE FOR FIVE WELLS SOLAR | Not Applicable | 2176480 | 2022-09-15 | 2023014.03 |  | -7.051% | Not Applicable
552 | 0PT47753 -- BELL COUNTY EAST SWITCH - CHILLINGHAM POI 345 KV LINE: INSTALL LINE FOR CHILLINGHAM SOLAR | Not Applicable | 2842097 | 2022-09-15 | 2079060.62 |  | -26.85% | Not Applicable
553 | 0PT47738 -- BELL COUNTY EAST SWITCH - TNP ONE (TNMP) SWITCH 345 KV LINE : CUT-IN TO ESTABLISH HOG CREEK SWITCH | Not Applicable | 2548516 | 2022-08-15 | 2258334.9 |  | -11.39% | Not Applicable
554 | 0PT47736 -- SANDHILLS SUB : INSTALL BANK #3, 138-21.6 KV, 46.7 MVA TRANSFORMER AND ONE 21.6 KV FEEDER BREAKER | Not Applicable | 3892590 | 2022-05-15 | 4164330.98 |  | 6.981% | Not Applicable
555 | 0PT47713 -- TAYLOR SWITCH - HUTTO SWITCH 138 KV LINE : PINTAIL SWITCH CUT-IN | Not Applicable | 4386190 | 2022-07-15 | 5149762.9 |  | 17.41% | Variance is due to increased material and labor costs. Construction was accelerated to complete the project ahead of ERCOT’s clearance restriction deadline, which increased labor costs. Labor costs also increased due to the need to pour slurry for structure foundations. Construction matting was needed to address wet ROW conditions and allow crews to haul and install materials across a substantial portion of the ROW.
556 | 0PT47711 -- PINTAIL SWITCH - SAS FAB1 138 KV LINE: CONSTRUCT NEW DOUBLE CIRCUIT POD LINE | Not Applicable | 4627932 | 2022-07-15 | 4113353.57 |  | -11.12% | Not Applicable
557 | 0PT47709 -- LAVENDER SWITCH : ESTABLISH A NEW 138 KV, 4 BREAKER RING BUS STATION TO PROVIDE POD FOR SDC PROCUREMENT, LLC | Not Applicable | 6480932 | 2022-06-15 | 6727010.74 |  | 3.797% | Not Applicable
558 | 0PT47706 -- HAGGERTY SWITCH STATION - MEMC SOUTHWEST SUBSTATION (NORTH) 138 KV LINE: BUILD | Not Applicable | 1876123 | 2022-09-15 | 2065136.73 |  | 10.07% | Variance is due to scope changes that increased material and labor costs. Scope additions include permanent casings for structure foundations; a temporary bypass; and vegetation management, construction roads, and matting to access the ROW due to poor soil conditions.
559 | 0PT47705 -- VALLEY-ANNA 138KV LINE: ESTABLISH HAGGERTY 138KV SWITCH | Not Applicable | 3333681 | 2022-09-15 | 3813660.38 |  | 14.4% | Variance is due to increased material and labor costs to address the constrained workspace and poor soil conditions. These conditions extended the construction timeline, which further increased labor costs.
560 | 0PT47702 -- SHERMAN TEXAS INSTRUMENTS : YARD EXPANSION | Not Applicable | 1915057 | 2022-09-15 | 1914193.19 |  | -0.04511% | Not Applicable
561 | 0PT47676 -- HAGGERTY SWITCH STATION: SHERMAN TI 138KV TIE LINE TO XFMR #1 | Not Applicable | 875782 | 2022-09-15 | 793546.98 |  | -9.39% | Not Applicable
562 | 0PT47674 -- HAGGERTY SWITCH STATION: SHERMAN TI 138KV TIE LINE TO XFMR #2 | Not Applicable | 935544 | 2022-09-15 | 776773.4 |  | -16.97% | Not Applicable
563 | 0PT47671 -- POETRY SWITCH - ESTABLISH 345KV, 3200A SWITCH AS POI FOR ELIZA SOLAR | Not Applicable | 8918238 | 2023-01-15 | 10455916.4 |  | 17.24% | Variance is due to increased material and labor costs. After the initial estimate the project was delayed due to customer delays. Increases in material prices and labor rates between the initial estimate and material procurement resulted in a project variance.
564 | 0PT47660 -- RED OAK SUB 138 KV: UPGRADE TERMINALS | Not Applicable | 473635.54 | 2023-07-15 | 751363.04 |  | 58.64% | Variance is due to a change in project scope to install a mobile substation and associated matting and fence removal and add a Field Construction Coordinator to the project. Installing a mobile substation allowed Oncor to take the station out of service without interrupting service to customers.
565 | 0PT47657 -- DESOTO SWITCH 138 KV: TERMINAL WORK REQUIRED | Not Applicable | 455606.82 | 2023-10-15 | 511259.8 |  | 12.22% | Variance is due to increased labor costs due to remobilizations while awaiting ERCOT clearance and delivery of 138 kV breaker.
566 | 0PT47647 -- TAYLOR WEST SUB : INSTALL TRANSFORMER #2 | Not Applicable | 3088708.21 | 2023-03-15 | 3969545.3 |  | 28.52% | Variance is due to increased material and labor costs and a scope change. Material cost for the substation transformer increased due to increased prices for raw materials and labor. Delivery of transformer was delayed. Labor costs increased due to the addition of hand-digging for conduit, grounding, and foundation in proximity to energized equipment to the estimated scope of work. Material delay caused remobilizations, an accelerated construction schedule, and additional security services, which further increased labor costs.
567 | 0PT47633 -- HUTTO SWITCH - GILLELAND CREEK SWITCH 138 KV LINE: CUT-IN TO ESTABLISH STARR RANCH SUB | Not Applicable | 2592531.45 | 2023-04-15 | 2239347.85 |  | -13.62% | Not Applicable
568 | 0PT47631 -- WATERMILL SWITCH - CEDAR CREST SWITCH 138 KV LINE: FLOYD BRANCH SUBSTATION CUT-IN | Not Applicable | 1188645 | 2023-11-15 | 776881.68 |  | -34.64% | Not Applicable
569 | 0PT47618 -- CEDAR HILL SWITCH : REPLACE OVERDUTIED 345 KV CB #312 & CB #315 | Not Applicable | 934417 | 2022-09-15 | 1139943.41 |  | 22% | Variance is due to increased material and labor costs. Material costs increased due to price increases for circuit breakers. Labor costs increased due to the need for hand digging in an energized station, removal and reinstallation of top rock, and additional security services.
570 | 0PT47583 -- BOMARTON SUB : REBUILD EXISTING SUBSTATION WITH A DELTA STAR RURAL SUBSTATION SKID | Not Applicable | 4759559.91 | 2023-12-15 | 5369675.85 |  | 12.82% | Material change order is being corrected through a journal entry at the end of this month; once corrected it will bring the final actual cost down below a 10% variance
571 | 0PT47551 -- PAINT CREEK SWITCH - CHINA GROVE SWITCH 138 KV LINE: INSTALL RAVEN POI | Not Applicable | 2736025 | 2023-08-15 | 2150351.39 |  | -21.41% | Not Applicable
572 | 0PT47545 -- NORTH NETWORK SUB - BRYAN SUB 138 KV LINE : UG TERMINATION REPLACEMENT | Not Applicable | 998077 | 2022-09-15 | 891468.78 |  | -10.68% | Not Applicable
573 | 0PT47543 -- GASLAND SUB : INSTALL TRANSFORMER #2 WITH A 138-21.6 KV 47 MVA TRANSFORMER AND TWO FEEDER BREAKERS ; REPLACE TRANSFORMER #1 WITH A 138-21.6 KV 47 MVA TRANSFORMER | Not Applicable | 5440827 | 2023-03-15 | 4678066.49 |  | -14.02% | Not Applicable
574 | 0PT47542 -- SHAFTER LAKE SUB : ESTABLISH STATIONS #3 & #4 EACH WITH A 138/22.86KV 47MVA TRANSFORMER & (1) ONE 22KV FEEDER BREAKER | Not Applicable | 6718470.06 | 2023-01-15 | 6787214.25 |  | 1.023% | Not Applicable
575 | 0PT47531 -- WACO SANGER AVENUE SUB: INSTALL TRANSFORMER #2 | Not Applicable | 4454481 | 2023-01-15 | 5845511.19 |  | 31.23% | Variance is due to a change in project scope and increased material and labor costs. The scope of work expanded to include replacing an aged fault interrupting device and replacing the station fence. The added scope of work extended the duration of construction by over 2 months and resulted in higher material and labor costs.
576 | 0PT47525 -- SOUTH BEND SUB : REBUILD EXISTING SUBSTATION WITH RURAL SUBSTATION SKID | Not Applicable | 4597592 | 2024-03-15 | 3318926.31 |  | -27.81% | Not Applicable
| 0PT51292 -- SOUTH BEND SUBSTATION - PURCHASE OF AN EXCLUSIVE EASEMENT |  |  | 2024-03-15
577 | 0PT47518 -- WESTERN HILLS SUB: INSTALL FEEDER ON STATION #3, INSTALL FEEDER TIES, AND UPGRADE RELAYING TO SUB IV | Not Applicable | 6000000 | 2023-01-15 | 7869055.85 |  | 31.15% | Variance is due to a change in project scope and increased material and labor costs. The scope of work expanded to include upgrading the low-voltage bus, relocating telecommunications equipment, and replacing 18 aged disconnect switches. The added scope of work resulted in an increase in material and labor costs, including additional charges for demolition work to remove the low-voltage bus and the control center and foundations. Scope changes and material delays contributed to multiple remobilizations. Additional security services were needed due to unauthorized personnel being on-site during construction.
578 | 0PT47513 -- KILLEEN TAFT SUB - KILLEEN SWITCH 138 KV LINE : INSTALL OPGW | Not Applicable | 961314 | 2022-10-15 | 1094683.19 |  | 13.87% | Variance is due to a change in project scope to add the use of a helicopter to remove and replace the OPGW. Standard stringing equipment could not access the ROW. ROW conditions also increased the need for matting and vegetation management above the initial estimate.
579 | 0PT47493 -- SULPHUR SPRINGS SWITCH - CANTON SWITCH 138 KV LINE : REPLACE CROSS ARMS, INSULATORS & POLES. INSTALL GATES. | Not Applicable | 379903 | 2022-04-15 | 430291.96 |  | 13.26% | Variance is due to a change in project scope to replace deteriorating equipment, which increased material and labor costs. Replacements included five poles, three crossarms, and a brace. This work also required construction of a ROW crossing to access the structures.
580 | 0PT47477 -- HOLLIDAY SUB - BOWMAN SWITCH 138 KV LINE : CUT-IN TO ESTABLISH PECAN TREE SUB | Not Applicable | 1579933 | 2022-07-15 | 1677833.54 |  | 6.196% | Not Applicable
581 | 0PT47099 -- DORCHESTER SUBSTATION - PURCHASE IN FEE | Not Applicable | 8436097.96 | 2023-07-15 | 412695.41 |  | -95.11% | Not Applicable
582 | 0PT47439 -- FERRIS SUB: REBUILD STATION | Not Applicable | 7696775.17 | 2023-01-15 | 9511330.79 |  | 23.58% | Variance is due to a scope change and increased material and labor costs due to prolonged and complicated construction sequencing, removals, line bypass coordination, unexpected soil conditions, and an unusual amount of cleanup required after the station rebuild. Soil conditions were much worse than expected which led to almost 100 cubic yards extra of concrete being required, matting, additional time for grading, and an accelerated construction contractor timeline. The overall project continued through a large portion of the year after the in-service date to finish cleanup and open items which increased the construction coordinator and security services required at site significantly.
583 | 0PT47417 -- PRESTON NORTH SUB - MEADOW CREEK SUB 138 KV LINE : PUMPING PLANT REPLACEMENT | Not Applicable | 948838 | 2023-03-15 | 955635.21 |  | 0.7164% | Not Applicable
584 | 0PT47410 -- BUCHANAN RANCH SUB: INSTALL 110.4 MVAR CAPACITOR BANK | Not Applicable | 3137931 | 2022-11-15 | 3101816.56 |  | -1.151% | Not Applicable
585 | 0PT47407 -- RENDON SUB: ESTABLISH STATION | Not Applicable | 9005526.81 | 2023-01-15 | 8321449.86 |  | -7.596% | Not Applicable
586 | 0PT47406 -- TEMPLE PECAN CREEK SWITCH : REPLACE MDAR RELAY PANELS FOR CB #8505, 8520, 8530, & 8545 | Not Applicable | 599952 | 2022-05-15 | 778140.11 |  | 29.7% | Variance is due to increased material and labor costs. Labor costs increased due to the need for conceptual design changes to address non-standard control schemes and the need for protection and control contract resources. Material costs increased due to higher prices for relay panels and control equipment.
587 | 0PT46924 -- BLACKSTOCK SUB (FKA NEVADA SUBSTATION) - PURCHASE OF LAND | Not Applicable | 9675383.63 | 2023-02-15 | 1157007.26 |  | -88.04% | Not Applicable
| 0PT54617 -- BLACKSTOCK SUB (FKA NEVADA SUB) - PURCHASE IN FEE |  |  | 2023-02-15
588 | 0PT47402 -- ROBINSON NORTHWEST SUB: INSTALL BANK #2 AND TWO FEEDER BREAKERS | Not Applicable | 3162926.75 | 2023-02-15 | 3839020.65 |  | 21.38% | Variance is due to increased material and labor costs. Material costs increased due to higher prices for power transformers, conduit, and cable. Labor costs increased due to the addition of hydrovac excavation; redrilling 5 pier holes that were caving in due to wet soil condition; additional concrete, conduit, and control cable removal modifications to designs; and rewiring the panels to align with Oncor standards. In addition, a mobile transformer was required to support testing and commissioning.
589 | 0PT47391 -- WOLF SWITCH - MOSS SWITCH 345 KV LINE : CUT-IN METEOR SWITCH 345 KV FOR GREYHOUND SOLAR | Not Applicable | 1598886 | 2022-09-15 | 1381583.98 |  | -13.59% | Not Applicable
590 | 0PT47380 -- SPRABERRY SWITCH - POLECAT SWITCH 138 KV LINE : INSTALL STEPHENSON LAKE POD FOR PINNACLE ENERGY TRANSITION OPERATING CO. | Not Applicable | 2205610 | 2022-08-15 | 1649550.9 |  | -25.21% | Not Applicable
591 | 0PT47362 -- VENUS SWITCH: REMOVE STATION #4, INSTALL STATION #6 WITH THREE FEEDERS & INSTALL ONE FEEDER ON STATION #5 | Not Applicable | 5066451 | 2023-01-15 | 4831521.65 |  | -4.637% | Not Applicable
592 | 0PT47360 -- SL COYOTE SUB: INSTALL STATION #4 | Not Applicable | 5525519 | 2022-07-15 | 5530543.95 |  | 0.09094% | Not Applicable
593 | 0PT47351 -- MASON SUB: REPLACE TWO TRANSFORMERS | Not Applicable | 3888689 | 2022-11-15 | 4721748.61 |  | 21.42% | Cost variance is due to a change in project scope and increased material and labor costs. Material costs increased due to price increases for transformers and transportation of materials. Scope of work expanded to include removal of spoils discovered on the site and removal of concrete to reroute conduit. Labor costs increased due to removal of spoils and concrete, associated remobilizations, and project commissioning costs.
594 | 0PT47424 -- PALOMA SUBSTATION (FKA: GRAY DOVE SUBSTATION) : PURCHASE IN FEE | Not Applicable | 12003868.83 | 2023-12-15 | 2159566.94 |  | -82.01% | Not Applicable
595 | 0PT47346 -- WACO WEST - WACO EAST - ELM MOTT 138 KV LINE: CUT-IN TO EST CIRCLE POINT SUB (FORMERLY CAMERON PARK SUB) | Not Applicable | 1612601.8 | 2023-11-15 | 1778752.69 |  | 10.3% | Variance is due to increased material and labor costs for additional matting, structure foundation casings, and a vibratory hammer to install structures due to a high water table and unstable soil.
596 | 0PT47344 -- HAGGERTY SWITCH: ESTABLISH 138 KV BREAKER-AND-A-HALF STATION FOR TEXAS INSTRUMENTS | Not Applicable | 17642817 | 2022-03-15 | 18171741.52 |  | 2.998% | Not Applicable
597 | 0PT47325 -- MILLERS FERRY ROAD SUB : INSTALL #2 (138-12.5 KV, 47 MVA), (2) FDRS | Not Applicable | 1732895 | 2022-10-15 | 1407005.54 |  | -18.81% | Not Applicable
598 | 0PT47323 -- FOREST HILL SUB: INSTALL BANK #3 WITH 138-12.5 KV, 47 MVA TRANSFORMER AND THREE FEEDER BREAKERS | Not Applicable | 5634503 | 2023-01-15 | 5631735.38 |  | -0.04912% | Not Applicable
599 | 0PT47322 -- ENNIS SOUTHEAST - INSTALL (1) 28MVA 138-12.5KV TRANSFORMER AND (2) UG FEEDER BREAKERS ON BANK #2 | Not Applicable | 1884960 | 2023-01-15 | 2387859.14 |  | 26.68% | Variance is due to a change in project scope and increased material and labor costs. The scope of work expanded to include additional station access for worker safety and hand-digging due to conduits being located in close proximity to energized equipment. Material delays resulted in re-mobilization fees that further increased labor costs.
| 0PT51464 -- ENNIS SOUTHEAST - ACQUIRE LAND IN FEE FOR STATION ACCESS |  |  | 2023-01-15
600 | 0PT47321 -- MOUNTAIN CREEK SWITCH - WEST LEVEE SWITCH 138 KV LINE : LINE HARDENING | Not Applicable | 1504761 | 2022-07-15 | 827608.08 |  | -45% | Not Applicable
601 | 0PT47315 -- LAKE CREEK SWITCH - JEWETT SWITCH 138 KV LINE : CUT-IN TO ESTABLISH TO RIESEL SWITCH | Not Applicable | 1438247.25 | 2022-08-15 | 1216708.48 |  | -15.4% | Not Applicable
602 | 0PT47310 -- RHOME SUB: REPLACE 138/24.9 KV 10.5 MVA TRANSFORMER WITH A 28 MVA TRANSFORMER | Not Applicable | 3342223 | 2022-08-15 | 3568208.39 |  | 6.762% | Not Applicable
603 | 0PT47295 -- BEALS CREEK SUB: INSTALL 138/25 KV 47 MVA TRANSFORMER #3 AND UG FEEDER | Not Applicable | 2988118 | 2022-08-15 | 4511879.88 |  | 50.99% | Variance is due to a change in project scope and increased material and labor costs. The scope of the project expanded to include additional control cable; bus units; feeder bays with disconnect switches, termination stands, and breakers; distribution work; ground clamps and bus removal; and a feeder tie structure and associated equipment. Modifications were made to the original design of the feeder bays, including the installation of terminal connectors, run and tap connectors, corona bells, straight and angled couplers, and bus support clamps. Material costs increased due to the additional materials required to accommodate the expanded scope of work and price increases after the initial estimate was created. Labor costs increased due to the expanded scope of work, the need for energized work, and multiple material delivery delays that resulted in remobilization charges.
604 | 0PT47279 -- KEMP RANCH SWITCH - SARDIS SWITCH 138 KV LINE : CUT-IN NEWTON BRANCH SUB FOR MARTIN MARIETTA | Not Applicable | 1420628.9 | 2022-09-15 | 1253515.3 |  | -11.76% | Not Applicable
605 | 0PT47250 -- OAKLAND SUB - MEDILL TERMINAL SUB 138 KV LINE : ADD OPGW | Not Applicable | 613962 | 2022-06-15 | 419193.49 |  | -31.72% | Not Applicable
606 | 0PT47231 -- HANDLEY - LANCASTER 138KV: REPLACE STR 2/6 DUE TO EROSION | Not Applicable | 794882 | 2022-10-15 | 665262.63 |  | -16.31% | Not Applicable
607 | 0PT47225 -- NEWTON BRANCH SUB: ESTABLISH STATION WITH A 47 MVA 138-13.2 KV TRANSFORMER AND TWO FEEDERS FOR TXI OPERATIONS DBA MARTIN MARIETTA | Not Applicable | 5567773.71 | 2022-09-15 | 7412292.52 |  | 33.13% | Variance is due to a change in project scope and increased material and labor costs. The scope of work expanded to include installing metal casing for station deadend foundations due to the presence of ground water during construction, installing a ground well to enhance station grounding design, and additional grading costs. Material costs, including the actual costs for transformers and the control enclosure, increased after the final cost estimate was created. Labor costs increased due to the expanded scope of work.
608 | 0PT47207 -- MESQUITE EAST SWITCH : UPGRADE CB #2270 TERMINAL TO 3200A AND ADD TWO NEW TERMINALS | Not Applicable | 2876107 | 2022-10-15 | 3450168.9 |  | 19.96% | Cost variance is due to changes in project scope and increased material and labor costs. The change in scope included the replacement of junction boxes due to moisture being discovered and the redesign of the battery transclosure foundation and electrical drawings per final vendor prints. Costs for high-voltage breakers were higher than initial estimates. Material delivery delays resulted in remobilizations as well as additional labor costs to rebuild an airgap until switches were delivered, then removing it again once the equipment arrived.
609 | 0PT47204 -- MESQUITE TOWN EAST SUB : UPGRADE TERMINAL TO 3200A | Not Applicable | 907830.91 | 2023-03-15 | 1486854.24 |  | 63.78% | Variance is due to a change in project scope to add two additional 138 kV motor operated switches to facilitate construction sequencing, matting services for the mobile transformers, regrading, and erosion control. Switches were needed to transfer load between transformers to execute on the construction sequence. Material and labor costs increased as a result of the scope change.
610 | 0PT47201 -- SUNNYVALE SUB : UPGRADE TERMINALS TO 3200A | Not Applicable | 443757 | 2022-10-15 | 652755.71 |  | 47.1% | Variance is due to a change in project scope to install a temporary bypass and the use of non-MSA labor, which increased labor costs.
611 | 0PT47169 -- QUARRY FIELD SWITCH - WINK SWITCH 138 KV LINE : INSTALL ASHBY POD FOR ENERGY TRANSFER'S WT2 SUB | Not Applicable | 2392691 | 2022-05-15 | 2025669.41 |  | -15.34% | Not Applicable
612 | 0PT47154 -- SHERRY SWITCH: CB 4640 LINE TERMINAL UPGRADE | Not Applicable | 408756 | 2022-09-15 | 402171.98 |  | -1.611% | Not Applicable
613 | 0PT47151 -- ENNIS WEST SWITCH - STERRETT SUB 138 KV LINE : HB4150 CLEARANCE REMEDIATION | Not Applicable | 310599 | 2022-03-15 | 378502.83 |  | 21.86% | Variance is due to the unexpected need for work to be performed during daily/nightly outages. Additionally, the majority of the work was done via helicopter due to access issues. Helicopter work was known to be required at the time of the estimate, but the adjusted plans for daily outages required additional coordination efforts and remobilization charges.
614 | 0PT47126 -- WEATHERFORD WEST SWITCH : UPGRADE CB#4375 TERMINAL TO 3200A | Not Applicable | 712617.31 | 2022-10-15 | 745622.4 |  | 4.632% | Not Applicable
615 | 0PT47097 -- SHERRY SWITCH - FISH CREEK SWITCH 138 KV LINE : GRAND PRAIRIE ASSOCIATED LINE WORK (NORTH CIRCUIT) | Not Applicable | 669782 | 2022-07-15 | 635092.39 |  | -5.179% | Not Applicable
616 | 0PT47089 -- LEON SWITCH - CISCO (ETT) 138 KV LINE: RETERMINATION INTO MOUNTAIN BRANCH SUB | Not Applicable | 499908 | 2022-06-15 | 381383.41 |  | -23.71% | Not Applicable
617 | 0PT47086 -- SOUTHLAKE SUB: INSTALL 138 KV CAPACITOR BANK | Not Applicable | 4439746 | 2022-09-15 | 4504190.57 |  | 1.452% | Not Applicable
618 | 0PT47022 -- TRINIDAD - MEXIA 138 KV LINE: RETERMINATION AT RANCHLAND SWITCH | Not Applicable | 1139613.5 | 2022-12-15 | 1066128.62 |  | -6.448% | Not Applicable
619 | 0PT46988 -- BUCHANAN RANCH SUB : ADD 3-47 MVA 138-24.9 KV TRANSFORMERS WITH 6-24.9 KV FEEDER BREAKERS | Not Applicable | 8788730 | 2022-06-15 | 10083638.87 |  | 14.73% | Variance is due to increased material costs. The actual cost for each of the 3 transformers that were replaced was more than Oncor’s estimate, which was based on historical pricing.
620 | 0PT46985 -- TEMPLE SWITCH - TEMPLE SUB 138 KV LINE : INSTALL OPGW | Not Applicable | 368433 | 2022-10-15 | 267120.56 |  | -27.5% | Not Applicable
621 | 0PT46982 -- MORGAN CREEK SWITCH - MCDONALD ROAD 138 KV LINE : INSTALL NAVIGATION SUB FOR TARGA'S PS4 | Not Applicable | 1138112 | 2022-10-15 | 1225692.46 |  | 7.695% | Not Applicable
622 | 0PT46977 -- PAYNE - VALLEY 138 KV LINE: ADD OPGW | Not Applicable | 2895486 | 2023-08-15 | 2671826.22 |  | -7.724% | Not Applicable
623 | 0PT46976 -- PAYNE – MEMC SOUTHWEST TAP 138 KV LINE: REBUILD | Not Applicable | 6,474,360 | 2023-03-15 | 7116883.38 |  | #VALUE! | Not Applicable
624 | 0PT46975 -- MALLARD SWITCH - SAS FAB1 138KV LINE: CONSTRUCT NEW DOUBLE CIRCUIT POD LINE | Not Applicable | 2664714 | 2022-07-15 | 2392644.68 |  | -10.21% | Not Applicable
625 | 0PT46971 -- PARKER MAXWELL CREEK SUB : INSTALL SECOND 138-25 KV 47 MVA TRANSFORMER WITH TWO FEEDER BREAKER | Not Applicable | 2618162 | 2022-05-15 | 3287910.43 |  | 25.58% | Variance is due to increased material and labor costs. Firm pricing for materials was higher than estimated. Labor costs increased due to unexpected secondary containment costs, the need to reroute feeder conduits, and remobilization charges.
626 | 0PT46970 -- TAYLOR WEST SUB : INSTALL BANK #4 WITH A 138-26.4 KV 47 MVA TRANSFORMER AND TWO FEEDER BREAKERS. | Not Applicable | 3023259 | 2022-04-15 | 3027797.18 |  | 0.1501% | Not Applicable
627 | 0PT46925 -- BARBER LAKE SWITCH - MORGAN CREEK SWITCH 138 KV LINE : INSTALL MOSER CANYON POD FOR PPM DATA'S PROJECT FRONTIER | Not Applicable | 2216404.28 | 2022-07-15 | 2141448.13 |  | -3.382% | Not Applicable
628 | 0PT46909 -- ROCK LAKE POD: ESTABLISH 138KV POINT OF DELIVERY FOR ROBINSON RANCH | Not Applicable | 1125908.8 | 2022-07-15 | 900090.27 |  | -20.06% | Not Applicable
629 | 0PT46888 -- MESQUITE EAST SWITCH TO SUNNYVALE SUB 138KV LINE REBUILD | Not Applicable | 7179241 | 2022-10-15 | 8396730.94 |  | 16.96% | Variance is due to increased material and labor costs. Labor costs increased due to the use of non-MSA contract labor and delays in material delivery that resulted in remobilization charges. After receiving a request from two municipalities crossed by the project, Oncor deemed it necessary to install matting along the entire ROW due to wet conditions and the close proximity of the ROW to a nature walk, housing developments, alleyways, and driveways.
630 | 0PT46883 -- DEEN SWITCH : INSTALL SECURITY MEASURES | Not Applicable | 1444435 | 2022-05-15 | 995297.43 |  | -31.09% | Not Applicable
631 | 0PT46879 -- ADOBE MEADOWS SUB: 138 KV LINE TERMINAL UPGRADE | Not Applicable | 657187 | 2022-10-15 | 782248.11 |  | 19.03% | Variance is due to increased material and labor costs. Material costs increased due to price increases for steel structures, switches, and bus materials. Labor costs increased due to additional resources needed for equipment installations, remobilization fees, additional job site security, and the need for protection and control contract resources to meet project in service deadlines.
632 | 0PT46874 -- MEYERS DRAW POD : ESTABLISH 138 KV POINT OF DELIVERY | Not Applicable | 1120615 | 2022-04-15 | 1893946.01 |  | 69.01% | Variance is due to increased material and labor costs for flood mitigation and erosion control measures and due to a constrained station location that was located within a floodplain and adjacent to an existing pipeline.
633 | 0PT46861 -- WICHITA FALLS PPG SUB: UPGRADE 138 KV LINE TERMINALS AND EQUIPMENT TO 2000 A | Not Applicable | 489484 | 2022-10-15 | 583678.77 |  | 19.24% | Variance is due to increased material and labor costs. Labor costs increased due to material delivery delays, remobilization charges, hauling of spoils, and underground utility location surveys. Material costs increased due to higher prices for commodity items and 138 kV switches.
634 | 0PT46857 -- LIGGETT SWITCH: 138 KV CB 2020 AND 2070 LINE TERMINAL UPGRADES | Not Applicable | 970614 | 2022-09-15 | 1092375.01 |  | 12.54% | Variance is due to a change in project scope to pull new control cable to the new breakers because the existing breakers didn’t have enough conductors to facilitate the protection scheme. This increased material and labor costs.
635 | 0PT46847 -- SPRABERRY SWITCH - POLECAT SWITCH 138 KV LINE: MEYERS DRAW POD FOR ENDEAVOR'S BATTLETEX SUB | Not Applicable | 3375632 | 2022-05-15 | 3050225.13 |  | -9.64% | Not Applicable
636 | 0PT46844 -- SCHUMM POD : ESTABLISH 138 KV POINT OF DELIVERY | Not Applicable | 1091580 | 2022-04-15 | 947890.03 |  | -13.16% | Not Applicable
637 | 0PT46830 -- SANDHILLS TAP - SANDHILLS SUB 138 KV LINE: SCHUMM POD FOR BLACKBEARD OPERATING, LLC WEDDELL SUB | Not Applicable | 2089938 | 2022-05-15 | 2257729.82 |  | 8.029% | Not Applicable
638 | 0PT46828 -- GREY WELL DRAW SWITCH: REBUILD 3-BREAKER RING BUS | Not Applicable | 6108950 | 2022-07-15 | 5373602.63 |  | -12.04% | Not Applicable
639 | 0PT46781 -- FARMERSVILLE SWITCH - MONTICELLO SWITCH 345 KV LINE : CUT-IN SALTILLO SWITCH FOR STAMPEDE SOLAR | Not Applicable | 1656513 | 2022-07-15 | 1396394.58 |  | -15.7% | Not Applicable
640 | 0PT46769 -- CENTERVILLE ROAD SUB: UPGRADE 138 KV CV-014 & CV-024 LINE SWITCHES TO 2000A | Not Applicable | 328861.86 | 2022-10-15 | 346155.03 |  | 5.258% | Not Applicable
641 | 0PT46763 -- LANCASTER SUB - DESOTO PLEASANT RUN 138-KV LINE RECONDUCTOR | Not Applicable | 4973307 | 2022-06-15 | 3560763.75 |  | -28.4% | Not Applicable
6642 | 0PT46762 -- WATERMILL SWITCH - REINDEER SUB 138-KV LINE: OPGW REPLACEMENT | Not Applicable | 757645 | 2022-06-15 | 422904.48 |  | -44.18% | Not Applicable
643 | 0PT46747 -- VENUS SWITCH - SAM SWITCH 345 KV LINE : CUT-IN TO ESTABLISH FORT SMITH SWITCH | Not Applicable | 1317149 | 2022-07-15 | 1849295.53 |  | 40.4% | Variance is due a scope change and unforeseen site conditions that increased material and labor costs. The project scope was modified to add another 345 kV lattice structure. Heavy crane use was required to construct and lift the lattice structure. Additional matting was required to safely ground the transmission line.
644 | 0PT46744 -- CENTERVILLE SWITCH - CENTERVILLE ROAD - LAKE HUBBARD SWITCH 138 KV DOUBLE-CIRCUIT LINE: RECONDUCTOR | Not Applicable | 7913000 | 2022-08-15 | 5534978.76 |  | -30.05% | Not Applicable
645 | 0PT46739 -- BUZZARD DRAW – LAMESA SWITCH 138 KV LINE: INSTALL HARDY MORGAN POI FOR GSEC'S NEW ACKERLY SUB | Not Applicable | 1538675 | 2022-04-15 | 1349303.2 |  | -12.31% | Not Applicable
646 | 0PT46736 -- ROSE HILL SWITCH - ROSE HILL TAP 138 KV LINE: RETERMINATE ROSE HILL STATION | Not Applicable | 1007982 | 2022-02-15 | 1089703.08 |  | 8.107% | Not Applicable
647 | 0PT46726 -- SALT LAKE SUBSTATION : INSTALL BANK #2 WITH ONE 138-25 KV 47 MVA TRANSFORMER AND TWO FEEDER BREAKERS AND DECOMMISSION TRANSFORMER #1 | Not Applicable | 2876816 | 2022-04-15 | 3151952.65 |  | 9.564% | Not Applicable
648 | 0PT46716 -- MOOREHEAD SUB : INSTALL TWO 138-24.9 KV TRANSFORMERS #3 & #4 WITH TWO FEEDER BREAKERS EACH | Not Applicable | 5136068 | 2022-02-15 | 5602305.01 |  | 9.078% | Not Applicable
649 | 0PT46691 -- SHERRY SWITCH - CEDAR HILL SWITCH 138 KV LINE : GRAND PRAIRIE ASSOCIATED LINE WORK (SOUTH CIRCUIT) | Not Applicable | 1583604 | 2022-07-15 | 1351162.05 |  | -14.68% | Not Applicable
650 | 0PT46660 -- TEMPLE SUB - TAYLOR SUB 69 KV LINE : TAYLOR SUB RETERMINATION | Not Applicable | 1002659 | 2022-05-15 | 935381.96 |  | -6.71% | Not Applicable
651 | 0PT46658 -- SANDOW SWITCH - TAYLOR SUB 138 KV LINE : TAYLOR SUB RETERMINATION | Not Applicable | 795232 | 2022-03-15 | 598408.29 |  | -24.75% | Not Applicable
652 | 0PT46646 -- HILLSBORO SWITCH - NAVARRO SWITCH 138 KV LINE : INSTALL ASH CREEK SWITCH FOR PITTS DUDIK SOLAR | Not Applicable | 1163236 | 2022-06-15 | 938000.55 |  | -19.36% | Not Applicable
653 | 0PT46644 -- SALE RANCH SWITCH - NATURAL DAM SWITCH 138 KV LINE : INSTALL ROCK LAKE POD FOR DIAMONDBACK'S ROBINSON RANCH | Not Applicable | 3582498 | 2022-08-15 | 3490923.92 |  | -2.556% | Not Applicable
654 | 0PT46632 -- HORSESHOE SPRINGS SWITCH - THREE MILE DRAW SWITCH 138 KV LINE : INSTALL CRATER ROCK SWITCH FOR HAYHURST TEXAS SOLAR'S ALLEN SUB | Not Applicable | 1437763 | 2022-05-15 | 1033143.58 |  | -28.14% | Not Applicable
655 | 0PT46621 -- DFW SOUTHWEST SUB : RECONFIGURE 138KV LINES AND BUS CONFIGURATION | Not Applicable | 4028834 | 2023-02-15 | 4577427.49 |  | 13.62% | Variance is due to a change in project scope, increased material and labor costs, and construction obstacles related to the proximity of the project to DFW International Airport. The scope change included modifying the existing station layout by installing a 138 kV circuit breaker; installing temporary bypasses and a mobile transformer to maintain service to critical DFW Airport customers; and adding relaying controls to implement Directional Comparison Blocking (DCB) schemes and SONET fiber loop equipment. Material costs increased due to price increases for structural steel, high-voltage breakers, air switches, microprocessor-based line panels, relay control equipment, and control centers. Labor costs increased due to additional demolition work required for existing equipment and foundations; installation of relay controls and fiber equipment; upgrades to buswork; the proximity of work to energized equipment, which required hand-digging and hydrovac excavation for conduit, grounding, and foundation installations; hauling additional equipment and materials; additional security; multiple remobilization charges associated with ERCOT clearances, DFW Airport blackout dates, and material delivery delays; additional site work and matting for the mobile transformer; and additional protection and control contractor resources to meet ERCOT's clearance restriction deadline. The expedited construction schedule further contributed to increased labor costs.
656 | 0PT46620 -- DFW NORTHWEST SUB : RECONFIGURE 138 KV LINES AND BUS CONFIGURATION. | Not Applicable | 3284670 | 2022-06-15 | 5007617.94 |  | 52.45% | Variance is due to a change in project scope and increased material and labor costs. The scope of work was expanded to include a mobile transformer to facilitate the outage schedule required due to the project’s proximity to the DFW Airport; a temporary bypass; three 25 kV disconnect switches; a Station Service Voltage Transformer due to the lack of a backup AC source; two 138 kV motor operators; four control switches; additional relaying controls to implement Directional Comparison Blocking (DCB) schemes and SONET fiber loop equipment; and modifying the station layout to add a 138 kV circuit breaker. Additional scope changes over the course of the project include regrading due to additional site work; matting for the mobile transformer setup; demolition for the additional relay controls, foundations, and other existing equipment; upgrading buswork; hand-digging and hydrovac excavation for conduit, grounding and foundation work in proximity to energized equipment; additional hauling of equipment and materials; and additional security. Material costs increased due the expanded scope of work and increased prices for structural steel, high-voltage breakers, air switches, microprocessor based line panels, relay control equipment and control centers. Labor costs increased due to the expanded scope of work; multiple remobilization charges due to ERCOT clearance issues, DFW Airport blackout dates, and material delivery delays; additional protection and control resources to beat ERCOT's clearance restriction deadline and the customer’s in-service date; and the expedited construction schedule.
657 | 0PT46619 -- NTUSU SL TULE CANYON SWITCH : INSTALL THREE 345KV SSVTS | Not Applicable | 288582 | 2022-03-15 | 386979.69 |  | 34.1% | Variance is due to increased material and labor costs. Labor costs increased due to additional resources needed to complete the station service voltage transformer installations; pricing for equipment installations; hand digging in an energized station; removal and reinstallation of top rock; and West Texas per diem.
658 | 0PT46606 -- DELAWARE RIVER SWITCH: ESTABLISH A 138 KV POI FOR CHEVRON USA, INC | Not Applicable | 8155593 | 2022-05-15 | 8616110.51 |  | 5.647% | Not Applicable
659 | 0PT46587 -- MUSTANG SUB : INSTALL 47 MVA 138-22 KV TRANSFORMER WITH TWO FEEDER BREAKERS ON BANK #2 | Not Applicable | 4065847 | 2022-03-15 | 4427814.15 |  | 8.903% | Not Applicable
660 | 0PT46569 -- BIG SPRING SWITCH - GUNSIGHT SWITCH 138 KV LINE : CROSSARM REPLACEMENT | Not Applicable | 8846141 | 2022-04-15 | 9368516.01 |  | 5.905% | Not Applicable
661 | 0PT46565 -- WATERMILL SWITCH - CEDAR CREST SWITCH 138 KV LINE : RETERMINATE AT CEDAR CREST SUB (WEST) | Not Applicable | 631905 | 2022-07-15 | 444796.11 |  | -29.61% | Not Applicable
662 | 0PT46529 -- TRINIDAD SWITCH - NAVARRO SWITCH 138 KV LINE : CUT-IN FOR LONG PRAIRIE SWITCH | Not Applicable | 1426002 | 2022-06-15 | 1281301.02 |  | -10.15% | Not Applicable
663 | 0PT46514 -- TEMPLE SWITCH : UPGRADE RELAYING ON CAPACITOR BANK #1 | Not Applicable | 609664.58 | 2022-09-15 | 503818.16 |  | -17.36% | Not Applicable
664 | 0PT46511 -- CENTERVILLE I-45 SUB : UPGRADE RELAYING ON CAPACITOR BANK #1 | Not Applicable | 918404.1 | 2022-10-15 | 1007670.56 |  | 9.72% | Not Applicable
665 | 0PT46510 -- GARLAND BOBTOWN ROAD SUB : UPGRADE RELAYING ON CAPACITOR BANK #1 | Not Applicable | 453474 | 2022-09-15 | 545112.48 |  | 20.21% | Variance is due to increased labor costs. Originally in-service date was 2023 but project was delayed to 2024. Labor costs increased due to mobilization charges, economic change adjustments, and the cost of security increasing from the previous year.
666 | 0PT46509 -- ELM MOTT SWITCH : UPGRADE RELAYING FOR CAPACITOR BANK #1 | Not Applicable | 341627 | 2022-08-15 | 779674.34 |  | 128.2% | Variance is due to a change in project scope to trench and install new conduit and cable after it was discovered that the existing conduit was not adequate. This scope change resulted in a longer construction schedule, which increased labor costs. Additionally, contract commissioning crews were needed to complete the work.
667 | 0PT46508 -- DOLLARHIDE SUB : UPGRADE RELAYING ON CAPACITOR BANK #1 | Not Applicable | 683101 | 2022-03-15 | 817950.16 |  | 19.74% | Variance is due a scope change and increased material and labor costs. The number of conductors on the existing cables that were to be reused did not match the station prints. This resulted in additional material and labor costs to pull additional cable to the new RTU from the existing breaker. Material and labor costs also increased to replace the potential transformer located on the existing capacitor bank due to an equipment failure once it was placed back into service.
668 | 0PT46507 -- TWIN OAKS SWITCH: UPGRADE RELAYING ON 345KV NORTH AND SOUTH BUS | Not Applicable | 538402 | 2022-05-15 | 473778.88 |  | -12% | Not Applicable
669 | 0PT46506 -- CEDAR HILL SWITCH : UPGRADE RELAYING ON AUTO #2 | Not Applicable | 1628115.95 | 2023-03-15 | 1349951.01 |  | -17.09% | Not Applicable
670 | 0PT46497 -- PARIS SWITCH - COMMERCE SWITCH 138 KV LINE: CUT-IN TO ESTABLISH CROSSROADS SWITCH | Not Applicable | 1656164 | 2022-06-15 | 987319.87 |  | -40.39% | Not Applicable
671 | 0PT46493 -- ANNA SWITCH: UPGRADE RELAYING ON AUTO #2 | Not Applicable | 1953723 | 2022-09-15 | 1975564.14 |  | 1.118% | Not Applicable
672 | 0PT46491 -- WILMER SWITCH : UPGRADE RELAYING ON AUTO #1 | Not Applicable | 370478 | 2022-06-15 | 462081.85 |  | 24.73% | Variance is due to additional material and labor costs. Additional labor costs include engineering design charges for construction support and unexpected record drawings to capture design changes. Material costs include additional outdoor panels and relay equipment needed due to the poor condition of the existing AC boxes.
673 | 0PT46419 -- CENTRALIA SUB : INSTALL 138-21.6 KV TRANSFORMER #4 WITH TWO FEEDER BREAKERS | Not Applicable | 2780019 | 2022-03-15 | 3247334.41 |  | 16.81% | Variance is due to a change in project scope and increased material and labor costs. Temporarily re-purposing an existing tie breaker to a feeder breaker was added to the scope of work. Material costs increased due to an increase in the price of power transformers. Labor costs were higher than estimated due to increased transportation costs for the transformer, the remote location of the substation, remobilization costs due to equipment delays, and the temporary re-purposing of the tie breaker to a feeder breaker for the adjacent customer during construction, which required substantial panel wiring and relay setting modifications.
674 | 0PT46413 -- MOUNTAIN BRANCH SUB : ESTABLISH (1) 47 MVA 138-12.5KV & (1) 28MVA 138-12.5KV TRANSFORMER AND THREE 12.5KV FEEDERS | Not Applicable | 5755341 | 2022-03-15 | 5761469.01 |  | 0.1065% | Not Applicable
675 | 0PT46403 -- FAIRFIELD WEST SUB: RECONFIGURE HIGH SIDE | Not Applicable | 1458170 | 2022-08-15 | 1792394.07 |  | 22.92% | Variance is due to a change in project scope to regrade the entire station and add fencing that was not included in the initial estimate. Material and labor costs also increased due to the deterioration of existing structures and complicated protection and control work.
676 | 0PT46402 -- RANCHLAND SWITCH: ESTABLISH 138 KV RING BUS | Not Applicable | 5835865 | 2022-08-15 | 5552536.1 |  | -4.855% | Not Applicable
677 | 0PT46386 -- KIRKLAND PARK SWITCH : REPLACE OVERDUTIED BREAKERS #00032 & 00035 | Not Applicable | 696589 | 2021-12-15 | 681996.77 |  | -2.095% | Not Applicable
678 | 0PT46385 -- INDUSTRIAL BLVD SWITCH : REPLACE 138 KV BREAKERS #022, 025 & 045 | Not Applicable | 1511565.61 | 2023-04-15 | 1428610.58 |  | -5.488% | Not Applicable
679 | 0PT46384 -- CARROLLTON NORTHWEST SWITCH : REPLACE OVERDUTIED BREAKERS #2310, 2590, & 3145 | Not Applicable | 1568439 | 2021-12-15 | 1755271.27 |  | 11.91% | Variance is due to increased labor costs. Material delays led to an extended construction timeline and remobilization charges. This increased costs for labor and equipment rentals.
680 | 0PT46378 -- DEALEY STREET SUB : UPGRADE LINE TERMINAL TO 3200A | Not Applicable | 1584343 | 2023-03-15 | 1673229.9 |  | 5.61% | Not Applicable
681 | 0PT46342 -- TIMBERVIEW SWITCH - CEDAR HILL SWITCH 345 KV LINE: INSTALL OPGW FROM CEDAR HILL SWITCH TO STRUCTURE 10/7 | Not Applicable | 2837871 | 2023-10-15 | 1752584.67 |  | -38.24% | Not Applicable
682 | 0PT46340 -- ROOKIE SWITCH : ESTABLISH 138 KV STATION FOR A POINT-OF-INTERCONNECTION (POI) FOR GRANSOLAR TEXAS ONE | Not Applicable | 6446199.16 | 2022-07-15 | 6515299.1 |  | 1.072% | Not Applicable
683 | 0PT46336 -- FARMERSVILLE SWITCH - MONTICELLO SWITCH 345 KV NORTH CIRCUIT LINE : INSTALL A 345 KV POINT-OF-INTERCONNECTION (POI) FOR HOPKINS SOLAR GENERATOR AT BIRTHRIGHT 345 KV SWITCH | Not Applicable | 2122208 | 2021-11-15 | 1998526.24 |  | -5.828% | Not Applicable
684 | 0PT46333 -- ROSE HILL SWITCH : REBUILD ROSE HILL SUB TO 3 BREAKER RING | Not Applicable | 4855264 | 2022-03-15 | 5537355.71 |  | 14.05% | Variance is due to increased material and labor costs and a scope change. The scope change involved a station redesign to avoid a previously undocumented water line discovered by a subsurface survey, which increased engineering and labor costs. Material costs for the control center and steel structures were higher than estimated. Contractor costs increased due to lack of contractor availability and the need for hydrovac excavation of the existing water line. Grading costs increased due to poor soil conditions, which required four feet of soil to be replaced. Regrading costs increased to install ditches and culverts.
685 | 0PT46328 -- CARROLLTON NORTHWEST SWITCH : TERMINATE CARROLLTON EAST AND NORTHLAKE SWITCH AND UPGRADE LINE TERMINALS TO 3200 A | Not Applicable | 1902158.1 | 2022-09-15 | 1862765.42 |  | -2.071% | Not Applicable
686 | 0PT46323 -- VALLEY SOUTH SUB - FARMERSVILLE SWITCH 345 KV LINE: EROSION CONTROL AT STRUCTURE 24/2 | Not Applicable | 819869 | 2022-05-15 | 988447.43 |  | 20.56% | Variance is due to increased material and labor costs. Construction was scheduled for summer when matting was not needed but project was delayed to the fall. Extreme weather caused material and labor cost increases due to the need for matting; a culvert and low-water crossing for work site access; and remobilization charges. The remaining cost increase is due to additional 345 kV grounds being needed, 345 kV wire transfer work, and additional subcontractors being needed to complete lattice lacing.
687 | 0PT46322 -- WOLF SWITCH - GENERAL TIRE SWITCH 138 KV LINE: JUDKINS SUB RETERMINATION | Not Applicable | 1921953 | 2021-11-15 | 1429247.7 |  | -25.64% | Not Applicable
688 | 0PT46319 -- WHITNEY SWITCH - STEPHENVILLE SWITCH 138 KV LINE: ANTLER HOLLOW ASSOCIATED LINE WORK (NORTH CIRCUIT) | Not Applicable | 1003868 | 2022-07-15 | 668104.78 |  | -33.45% | Not Applicable
689 | 0PT46303 -- CUMBY SUB: CONVERT STATION TO 138 KV OPERATION (RURAL DESIGN) | Not Applicable | 3453066.64 | 2022-11-15 | 3561508.27 |  | 3.14% | Not Applicable
690 | 0PT46302 -- CUMBY TAP SWITCH: REMOVE AUTO #1 & 69 KV EQUIPMENT AND RECONFIGURE AS 138 KV RING BUS | Not Applicable | 7014280.55 | 2023-02-15 | 8370533.1 |  | 19.34% | Variance is due to a change in project scope and increased material and labor costs. Installation of wave traps on two lines was added to the project scope, which increased material and labor costs. Material costs also increased due to price increases for structural steel, high-voltage circuit breakers, control cable, and the control house.
| 0PT55515 -- CUMBY TAP SWITCH ACCESS - ACQUIRE LAND IN FEE FOR STATION ACCESS |  |  | Not Applicable
691 | 0PT46293 -- EULESS SOUTH SUB : REPLACE TRANSFORMER #1 AND #2 FAILED HU RELAYS | Not Applicable | 291328 | 2022-11-15 | 289358.05 |  | -0.6762% | Not Applicable
692 | 0PT46242 -- ESTABLISH DRY FORK SUB : ESTABLISH TWO 138-12.5 KV, 28 MVA TRANSFORMERS AND THREE FEEDER BREAKERS | Not Applicable | 7438715 | 2022-08-15 | 7780760.78 |  | 4.598% | Not Applicable
693 | 0PT46207 -- COPPERAS COVE EAST SUB: INSTALL BANK #2 WITH A 138-12.5 KV, 47 MVA | Not Applicable | 2883866 | 2022-03-15 | 2653227.56 |  | -7.998% | Not Applicable
694 | 0PT46203 -- MCFALL SWITCH : ESTABLISH 69 KV STATION FOR A POINT-OF-INTERCONNECTION (POI) FOR JUNGMANN SOLAR | Not Applicable | 5182447.92 | 2023-02-15 | 4805693.96 |  | -7.27% | Not Applicable
695 | 0PT46197 -- SANDOW SWITCH - TEMPLE SWITCH 138 KV LINE: INSTALL TIN ROOF POD FOR TEMPLE DATA | Not Applicable | 1037180 | 2021-12-15 | 909040.77 |  | -12.35% | Not Applicable
696 | 0PT46171 -- RIESEL SWITCH : ESTABLISH 138 KV POINT-OF-INTERCONNECTION (POI) FOR CORAL SOLAR | Not Applicable | 4998964 | 2022-07-15 | 5852935.05 |  | 17.08% | Variance is due to a change in project scope and increased material and labor costs. The scope change included the addition of Wholesale Storage Load facilities at the customer’s request, which extended the construction schedule and increased material and labor costs. Labor costs also increased due to additional commissioning services, security services, and engineering and construction time to coordinate with the customer on the scope change.
697 | 0PT46166 -- TRINIDAD SWITCH 69KV LINE TO POWER PLANT | Not Applicable | 508558 | 2022-04-15 | 453621.94 |  | -10.8% | Not Applicable
698 | 0PT46165 -- TRINIDAD SWITCH 138 KV INTERCONNECTION LINE TO TRINIDAD AUTOTRANSFORMER | Not Applicable | 787396 | 2022-04-15 | 890187.14 |  | 13.05% | Variance is due to increased material and labor costs. Material costs increased due to price increases for structural steel. Labor costs increased due to the need for hydrovac excavation due to congestion in the work area.
699 | 0PT46163 -- CRESLENN RANCH SWITCH - TRINIDAD SWITCH 69 KV LINE : NEW INTERCONNECTION | Not Applicable | 536847 | 2022-04-15 | 465977.59 |  | -13.2% | Not Applicable
700 | 0PT46156 -- SANDOW SWITCH: INSTALL 138 KV AIR CORE REACTORS ON AUTO #1 AND AUTO #2 | Not Applicable | 2964529 | 2022-02-15 | 3285784.26 |  | 10.84% | Variance is due to increased material and labor costs. Material costs increased due to a change in vendor and fees to expedite delivery following a delivery delay with the original vendor. Labor costs increased for engineering and construction to accommodate a design change to accommodate the substitute equipment. Protection and control contract resources were utilized to meet project in service deadlines.
701 | 0PT46155 -- SANDOW SWITCH : INSTALL CAPACITOR BANK #2 | Not Applicable | 2222624 | 2021-12-15 | 1885141.86 |  | -15.18% | Not Applicable
702 | 0PT46153 -- OZARK TRAIL SWITCH : ESTABLISH 345 KV SWITCH STATION IN A 3-BREAKER RING BUS ARRANGEMENT TO PROVIDE 345 KV POI FOR HORNET SOLAR | Not Applicable | 8175933.92 | 2022-05-15 | 8365461.93 |  | 2.318% | Not Applicable
703 | 0PT46145 -- SL AJ SWOPE SUB - ALIBATES SUB 345 KV LINE : GALLOPING DEVICE INSTALLATION | Not Applicable | 1592160 | 2022-08-15 | 1123749.27 |  | -29.42% | Not Applicable
704 | 0PT46134 -- TIN ROOF POD: INSTALL POD AND CAPACITOR BANK IN THE TEMPLE SW - SANDOW SW 138 KV LINE | Not Applicable | 3570723 | 2021-12-15 | 3973953.93 |  | 11.29% | Variance is due to a change in project scope to accommodate future facilities within a constrained workspace. A future capacitor bank was added to the design after the initial cost estimate was created.
705 | 0PT46093 -- GRAFORD SUB : REBUILD EXISTING SUBSTATION TO RURAL SUBSTATION SKID | Not Applicable | 2989585 | 2022-02-15 | 4034044.73 |  | 34.94% | Cost variance is due to Oncor having to rearrange the substation after construction was complete. Due to material delays for components used to construct the first prototype skid substation, a last-minute redesign by the manufacturer was needed to meet the delivery timeline. Upon arrival at the ssite, the redesign contributed to deficiencies in the normal monitoring and maintenance activities required for reliability. Oncor disassembled the skid and reinstalled the equipment in a more traditional arrangement for reliability.
706 | 0PT46052 -- HIGH PLAINS POD: ESTABLISH 138KV POINT OF DELIVERY | Not Applicable | 897944 | 2021-11-15 | 853348.24 |  | -4.966% | Not Applicable
707 | 0PT46033 -- KEMP RANCH SWITCH - SARDIS SWITCH 138 KV LINE : RETERMINATE AT MIDLOTHIAN SOUTH SUB | Not Applicable | 1502626 | 2022-06-15 | 1711168.18 |  | 13.88% | Variance is due to increased labor costs. Material delivery delays and ERCOT clearance coordination resulted in remobilization charges that increased labor costs. Additional costs were incurred to restore the ROW after construction was completed.
708 | 0PT46004 -- WILDHORSE POD: ESTABLISH 138KV POINT OF DELIVERY | Not Applicable | 783746 | 2021-12-15 | 909513.84 |  | 16.05% | Variance is due to an incorrect charge of Other Contract Construction Labor for the installation of a transmission line bypass that was necessary to maintain project energization date after ERCOT declined line outage request. This charge should have gone to project 0PT44895, which is entry 1027 in Schedule VI-M-1&2. This error is being corrected internally.
709 | 0PT46003 -- LAMESA SWITCH : REBUILD/CONVERT EXISTING SUBSTATION TO 138 KV WITH 2-46.7 MVA, 138-12.5 KV TRANSFORMERS | Not Applicable | 7588290 | 2022-10-15 | 9765782.13 |  | 28.7% | Variance is due to a change in project scope and increased material and labor costs. Scope change included work required to accommodate a change in the manufacturer’s design after the foundation for the transformer had already been poured. Material costs increased due to price increases for major equipment, primarily power transformers and the control house. Labor costs increased due to the increased scope of work and associated conduit modifications; additional labor and equipment for rock drilling for structure foundations, remobilizations due to equipment delays for disconnect switches; and 6 months of additional site security.
710 | 0PT45995 -- BIG BROWN SWITCH - RICHLAND CHAMBERS SWITCH 345 KV LINE : RAISE LINE FOR PIN OAK SWITCH 138 KV | Not Applicable | 871651 | 2022-02-15 | 675959.93 |  | -22.45% | Not Applicable
711 | 0PT45941 -- WICHITA FALLS SOUTH SWITCH - BURNETT SWITCH 138 KV LINE : CMPC LINE HARDENING (STR. 7/1 - 7/10) | Not Applicable | 1874557 | 2022-04-15 | 1667044.73 |  | -11.07% | Not Applicable
712 | 0PT45940 -- WICHITA FALLS NORTH SWITCH - PLEASANT VALLEY SWITCH 69 KV LINE : CMPC LINE HARDENING (STR. 2/12 - 2/15) | Not Applicable | 704094 | 2022-06-15 | 508758.56 |  | -27.74% | Not Applicable
713 | 0PT45939 -- BURNETT SWITCH - PLEASANT VALLEY SWITCH 69 KV LINE : CMPC LINE HARDENING (STR. 4/11 - 4/14) | Not Applicable | 1139681 | 2022-06-15 | 1191879.12 |  | 4.58% | Not Applicable
714 | 0PT45887 -- BUZZARD DRAW SWITCH - GETTY VEALMOOR TAP 138 KV LINE: INSTALL HIGH PLAINS POD FOR SURGE ENERGY'S VINCENT SUB | Not Applicable | 1335866 | 2021-09-15 | 1370438.92 |  | 2.588% | Not Applicable
715 | 0PT45886 -- JUDKINS SUB : REPLACE TRANSFORMERS #1 AND #2 WITH TWO 47 MVA TRANSFORMERS | Not Applicable | 5543166 | 2021-11-15 | 5238585.12 |  | -5.495% | Not Applicable
716 | 0PT45742 -- PRAIRIE CREEK SUB : REPLACE TRANSFORMERS #1 AND #2 WITH TWO 47 MVA TRANSFORMERS | Not Applicable | 6444164 | 2021-09-15 | 7435237.51 |  | 15.38% | Variance is due to a change in project scope and increased labor costs. Demolition was added to the project scope, requiring construction contractors to be remobilized. Construction timeline was extended through two seasons due to permitting delays. These resulted in higher than estimated costs for Oncor Labor, Construction Contractor, and Field Construction Coordinator.
717 | 0PT45741 -- WICHITA FALLS RIVERBEND SUB : UPGRADE BOTH TRANSFORMERS WITH TWO 138-12.5 KV 46.7 MVA TRANSFORMERS | Not Applicable | 4940165 | 2021-10-15 | 5016540.54 |  | 1.546% | Not Applicable
718 | 0PT45684 -- D EAST 1- D EAST 2 138 KV LINE: REBUILD CATHODIC PROTECTION | Not Applicable | 347454 | 2022-04-15 | 341809.72 |  | -1.624% | Not Applicable
719 | 0PT45683 -- BIRD DOG SWITCH: ESTABLISH 345 KV RING BUS STATION TO PROVIDE POI FOR PORTER SOLAR | Not Applicable | 7865658 | 2022-05-15 | 7942210.36 |  | 0.9732% | Not Applicable
720 | 0PT45633 -- GRAHAM PLANT SWITCH - BRECKENRIDGE - LEON SWITCH 138KV LINE: CUT-IN GHOST TOWN SWITCH FOR LA CASA WIND POI | Not Applicable | 1522952 | 2023-08-15 | 1218190.9 |  | -20.01% | Not Applicable
721 | 0PT45607 -- LAKE CREEK SWITCH: TRANSFER TRIP ADDITION, LINE TERMINAL UPGRADE, FOR THE ADDITION OF BELFALLS SWITCH (BIG ELM SOLAR) | Not Applicable | 257123.23 | 2023-01-15 | 341635.68 |  | 32.87% | Variance is due to a change in project scope that increased material and labor costs. Scope of work expanded to include commissioning services and rework of existing facilities that was needed to accommodate planned upgrades. During construction, Oncor discovered that existing conduit could not be reused because it was routed through a buried manhole), requiring trenching and the installation of a new conduit run, further increasing the scope of work and associated material and labor costs.
722 | 0PT45580 -- BRECKENRIDGE SUBSTATION: TRANSFER TRIP ADDITION, LINE TERMINAL UPGRADE, FOR THE ADDITION OF GHOST TOWN SWITCH (LA CASA WIND) | Not Applicable | 359022.13 | 2023-12-15 | 308296.48 |  | -14.13% | Not Applicable
723 | 0PT45579 -- LEON SWITCH: TRANSFER TRIP ADDITION, LINE TERMINAL UPGRADE, FOR THE ADDITION OF GHOST TOWN SWITCH (LA CASA WIND) | Not Applicable | 469520 | 2023-12-15 | 358785.1 |  | -23.58% | Not Applicable
724 | 0PT45538 -- AUDELIA TERMINATION- LAKE HIGHLANDS 138 KV LINE: U.G. TERMINATION REPLACEMENT | Not Applicable | 785485 | 2022-06-15 | 659131.77 |  | -16.09% | Not Applicable
725 | 0PT45445 -- SALTILLO SWITCH : ESTABLISH 3 BREAKER RING POI STATION | Not Applicable | 6954657 | 2022-03-15 | 8030802.06 |  | 15.47% | Variance is due to increased material and labor costs. Actuals for materials, transportation and labor increased following initial pricing estimates.
726 | 0PT45437 -- TEMPLE ELM CREEK SWITCH - BELTON SWITCH 138 KV LINE : INSTALL PEPPER CREEK SWITCH FOR PASCA RISE | Not Applicable | 4865246.36 | 2023-01-15 | 4074548.88 |  | -16.25% | Not Applicable
727 | 0PT45420 -- ROYSE SWITCH - TERRELL SWITCH 138/69 KV LINE: RE-TERMINATE AT TERRELL SWITCH | Not Applicable | 2820213 | 2023-03-15 | 1971341.8 |  | -30.1% | Not Applicable
728 | 0PT45417 -- ROYSE SWITCH - TERRELL SWITCH 138/69 KV LINE: RE-TERMINATE AT ROYSE SWITCH | Not Applicable | 2887344.92 | 2023-03-15 | 2342645.4 |  | -18.87% | Not Applicable
729 | 0PT45398 -- FARMERSVILLE SWITCH - ANNA SWITCH 345 KV LINE : INSULATOR REPLACEMENT | Not Applicable | 2244627 | 2021-12-15 | 2344771.82 |  | 4.462% | Not Applicable
730 | 0PT45396 -- GRAHAM SWITCH - BURWICK SWITCH 345 KV LINE : INSULATOR REPLACEMENT | Not Applicable | 1320366 | 2022-07-15 | 1470910.49 |  | 11.4% | Variance is due to a change in project scope and increased material and labor costs. The scope of work increased from replacing 27 insulators to replacing 54, which added to material and labor costs. Material costs also increased due to price increases for insulators. Labor costs increased due to the additional scope of work and due to the need for additional subcontractor ground support for guard structures at a various road crossings and to change the insulator on one structure that was not accessible by helicopter.
731 | 0PT45394 -- MIDLOTHIAN SOUTH SUB : REPLACE TRANSFORMERS #1 AND #2 WITH TWO 47 MVA TRANSFORMERS AND RELAY UPGRADE ON FEEDERS 1003 FOR DA | Not Applicable | 7048748 | 2022-04-15 | 8861908.25 |  | 25.72% | Variance is due to a change in project scope and increased material and labor costs. The scope changes include using a different model of transformer than included in the initial estimate, adding an airbridge to cross an existing pipeline, adding concrete access drives at the station entrance, and adding temporary fencing. Material costs increased due to the use of a different model transformer and price increases for structural steel and other commodity items. Labor costs increased due to the additional grading work required to cross the pipeline and build the access drive, modifications to operation arms on high voltage switches that were required to mount them to the lattice towers, additional site security, and project delays due awaiting completion of related projects. The additional work to mount switches also necessitated crane rental for a longer period than initially planned.
732 | 0PT45387 -- BELL COUNTY EAST SWITCH : ESTABLISH A 345 KV POI FOR FIVE WELLS SOLAR & STORAGE | Not Applicable | 5206702 | 2022-07-15 | 4245140.86 |  | -18.47% | Not Applicable
733 | 0PT45361 -- LONG PRAIRIE SWITCH : ESTABLISH 3 BREAKER RING POI STATION | Not Applicable | 5376538 | 2022-03-15 | 4492144.76 |  | -16.45% | Not Applicable
734 | 0PT45324 -- CHINA GROVE SWITCH - PAINT CREEK SUB 138 KV LINE : INSTALL NEW H-FRAME SWITCH AT RADIUM SUBSTATION | Not Applicable | 996929 | 2021-10-15 | 950512.04 |  | -4.656% | Not Applicable
735 | 0PT45228 -- ROYSE SWITCH - BLACKLAND - TERRELL SWITCH 138 KV LINE: RE-TERMINATION AT TERRELL SWITCH | Not Applicable | 1173408.65 | 2023-03-15 | 891320.84 |  | -24.04% | Not Applicable
736 | 0PT45221 -- LIGGETT SWITCH - NORWOOD SWITCH 138 KV LINE : OPGW | Not Applicable | 826932 | 2021-08-15 | 994439.64 |  | 20.26% | Variance is due to change in project scope and increased labor costs resulting from the greater-than-expected amount of traffic control needed to safely pull wire within close proximity to roads, residential, and commercial properties.
737 | 0PT45165 -- KRUM WEST SWITCH: ADD A NEW 345 KV LINE TERMINAL FOR HUMMINGBIRD STORAGE | Not Applicable | 2035427 | 2022-06-15 | 2314970.39 |  | 13.73% | Variance is due to increased material and labor costs. Pricing for materials and labor increased prior to construction start. Construction schedule was extended due to multiple material delays and customer delays, which further increased labor costs.
738 | 0PT45155 -- MIDPOINT SWITCH : ESTABLISH 3 BREAKER RING ARRANGEMENT POI STATION | Not Applicable | 8256917.48 | 2023-01-15 | 9221857.28 |  | 11.69% | Variance is due to a change in project scope and increased material costs. Scope of work expanded to include installing one 345 kV station service transformer and three circuit breaker platforms. Material costs increased due to scope changes and price increases for structural steel, relay panels, switches and the control center. Labor costs increased due to the scope change and adjustments to field construction coordinator, grading, and material transport costs.
739 | 0PT45138 -- BROWNWOOD - COLEMAN CO. 69 KV AND 138 KV LINE : RETERMINATE 138 KV LINE INTO BANGS SUB DUE TO STATION REBUILD | Not Applicable | 1199052 | 2022-06-15 | 1134423.91 |  | -5.39% | Not Applicable
740 | 0PT45131 -- GRAND PRAIRIE SUB : REBUILD ENTIRE SUBSTATION TO SUBURBAN IV DESIGN STANDARDS. | Not Applicable | 7673504 | 2022-04-15 | 7731476.46 |  | 0.7555% | Not Applicable
741 | 0PT45124 -- LAKECREST SUB : ADD STATION #2 WITH A 47 MVA TRANSFORMER AND 4 - LVCB DISTRIBUTION FEEDERS | Not Applicable | 2582476 | 2021-08-15 | 3056152.65 |  | 18.34% | Variance is due to increased material costs, due to the price for the transformer being higher than the historical cost used to create the initial estimate, and increased labor costs due to the need to use non-MSA labor.
742 | 0PT45123 -- ROSEMONT SUB : ESTABLISH STATION WITH A DOUBLE TAP ARRANGEMENT WITH TWO 47 MVA TRANSFORMERS AND EIGHT LV CIRCUIT BREAKERS. | Not Applicable | 8568084 | 2022-01-15 | 8730988 |  | 1.901% | Not Applicable
743 | 0PT45122 -- CALMONT SUB : ADD TRANSFORMER #8 WITH 3 FEEDERS, REWORK 138 BUS, REMOVE TRANSFORMER #2 AND #3 ALONG WITH SWITCHGEAR AND RELAY UPGRADE ON FEEDERS 0916, 0922, 0927, 0946, 0973 & 0983 FOR DA | Not Applicable | 5218758 | 2021-08-15 | 9771379.37 |  | 87.24% | Variance is due to a change in project scope and increased material and labor costs. The scope of the project was expanded to add distribution automation devices as part of a broader initiative to roll out automation across the system. Consolidating that work into this project allowed for more efficient use of work crews and other resources. Material costs increased due to the scope change, as well as price increases for structural steel, power transformers, and control centers. Labor costs increased due to the scope change, as well as additional costs associated with the installation of the feeder tie cables, cable trench installation, switchgear removal, and grading costs to support the installation of a retaining wall.
744 | 0PT45121 -- WALL STREET SUB : REPLACE STATION #2 TRANSFORMER AND REPLACE EXISTING OIL LV CIRCUIT BREAKERS WITH 10 - NEW LVCB DISTRIBUTION BAYS FOR STATION #1 & #2 | Not Applicable | 4968473 | 2021-10-15 | 7053972.38 |  | 41.97% | Variance is due to increased material and labor costs and an extended, multi-stage construction schedule. Primary contractor labor pricing and material pricing were not available when the cost estimate was created, which was prior to the current MCPR final cost estimate requirement. Costs for Oncor labor, Field Construction Coordinator labor, and security services were higher due to the construction duration and multi-stage sequencing. Material costs increased due to price increases for structural steel, power transformers, and control centers. Additional labor costs were incurred to support the removal of retired equipment and associated foundations.
745 | 0PT45117 -- SL CLEAR CROSSING (ETT) - WILLOW CREEK SWITCH 345 KV LINE: CUT-IN TO ESTABLISH THOMAS PRICE SWITCH | Not Applicable | 2626362 | 2022-03-15 | 2671606.15 |  | 1.723% | Not Applicable
746 | 0PT45108 -- ROYSE SWITCH - ROWLETT SUB 138 KV LINE : RECONDUCTOR ROYSE SWITCH TO FATE SUB | Not Applicable | 4355202 | 2021-09-15 | 4043319.15 |  | -7.161% | Not Applicable
747 | 0PT45103 -- REINDEER SUB - LANCASTER SUB 138-KV LINE RECONDUCTOR | Not Applicable | 3604361 | 2022-06-15 | 4658571.55 |  | 29.25% | Variance is due to increased material and labor costs. Very wet conditions required significant matting that was not included in the initial estimate. Contractor labor costs increased for items including hydrovac excavation, labor and equipment for rock digging, and traffic control.
748 | 0PT45040 -- BRANGUS SWITCH: ESTABLISH 345 KV POI FOR BEN MILAM SOLAR 3, LLC (HALO SOLAR), ORION 3 | Not Applicable | 7734602 | 2022-07-15 | 7526974.17 |  | -2.684% | Not Applicable
749 | 0PT45039 -- GIBSON SWITCH: ESTABLISH 345 KV POI FOR BEN MILAM SOLAR 2, LLC (MANDORLA SOLAR), ORION 2 | Not Applicable | 7823643 | 2022-07-15 | 7378543.85 |  | -5.689% | Not Applicable
750 | 0PT45035 -- LITTLE POND SWITCH: ESTABLISH 345 KV STATION FOR THE BEN MILAM SOLAR 1, LLC - AUREOLA SOLAR, ORION 1 | Not Applicable | 7764705 | 2022-07-15 | 7852209.12 |  | 1.127% | Not Applicable
751 | 0PT45025 -- ODESSA EHV SWITCH : RELAY UPGRADES FOR 138 KV BUS B, 345KV BUS C AND AUTO# 2 | Not Applicable | 732642 | 2021-11-15 | 1137181.4 |  | 55.22% | Variance is due to a change in project scope and increased material and labor costs. Scope change included replacing the autotransformer pump and monitoring equipment that were no longer serviceable. Engineering costs increased due to the large number of interconnected protection panels and the need to create drawings from manufacturer prints. Labor costs increased due to additional resources being needed for equipment installations, the need for hand digging and negotiated per diem.
752 | 0PT45023 -- CEDAR CREST SWITCH - INDUSTRIAL BLVD SWITCH 138 KV LINE : RETERMINATE AT COMPTON SUB | Not Applicable | 679452 | 2022-01-15 | 579363.94 |  | -14.73% | Not Applicable
753 | 0PT45022 -- WATERMILL SWITCH - CEDAR CREST SWITCH 138 KV LINE : RETERMINATE AT CEDAR CREST SUB (EAST) | Not Applicable | 776715 | 2022-07-15 | 691388.44 |  | -10.99% | Not Applicable
754 | 0PT45019 -- CEDAR CREST SWITCH - SARGENT RD SUB 138 KV LINE : RETERMINATE AT CEDAR CREST SW | Not Applicable | 571160.71 | 2023-05-15 | 490662.79 |  | -14.09% | Not Applicable
755 | 0PT45010 -- WINK BASIN TAP NO 1 EAST 69 KV LINE: WINK BASIN SUB - STRUCTURE 3/2 & STRUCTURE 4/1- STRUCTURE 4/8 69 KV SECTION REBUILD TO 138 KV | Not Applicable | 3000000 | 2021-04-15 | 1285761.06 |  | -57.14% | Not Applicable
756 | 0PT44999 -- BOWMAN SWITCH : RELAY UPGRADES FOR 138KV BUS A, AUTO #1 AND REPLACE TERTIARY REACTORS FOR AUTO#1 | Not Applicable | 1228217 | 2021-10-15 | 1506885.35 |  | 22.69% | Variance is due to a change in project scope and increased labor and material costs. Scope was revised to add the replacement of an inoperable manual switch with a new motor-operated switch. This required additional steel, foundation work, and buswork, which increased material and labor costs. Labor costs also increased due to the need for additional resources to complete the relaying upgrades and replace the digital fault recorder.
757 | 0PT44967 -- STERRETT SWITCH - SARDIS SWITCH 138KV LINE: RECONFIGURE STR 31/6 TO 31/11 TO ACCOMODATE DESOTO TO STERRETT REBUILD | Not Applicable | 919869 | 2021-10-15 | 754650.15 |  | -17.96% | Not Applicable
758 | 0PT44966 -- DESOTO SWITCH - STERRETT SWITCH 138KV LINE: REBUILD GLENN HEIGHTS (BEC) TO STERRETT SW | Not Applicable | 9629545 | 2021-10-15 | 7596291.76 |  | -21.11% | Not Applicable
759 | 0PT44949 -- TRINIDAD SWITCH - PALESTINE SWITCH 69 KV LINE : RETERMINATION INTO CRESLENN RANCH SWITICH | Not Applicable | 1121398 | 2022-04-15 | 1342659.49 |  | 19.73% | Variance is due to a change in project scope and increased material and labor costs. Scope was revised to install additional steel poles and re-route the line to avoid impacts to a customer associated with construction sequencing. Material and labor costs increased due to the scope change, foundation costs for the new structures, and the need for hydrovac excavation due to congestion in the work area.
760 | 0PT44895 -- BUZZARD DRAW SWITCH - GETTY VEALMOOR TAP 138 KV LINE: INSTALL WILDHORSE POD FOR HIGHPEAK ENERGY'S SUB | Not Applicable | 1631712 | 2021-09-15 | 1423148.01 |  | -12.78% | Not Applicable
761 | 0PT44873 -- MCDONALD RD SWITCH - SPRABERRY SWITCH 138 KV LINE : CUT-IN TO DESERT WIND SUB | Not Applicable | 545011 | 2021-10-15 | 589047.46 |  | 8.08% | Not Applicable
| 0PT47804 -- MCDONALD RD SWITCH - SPRABERRY SWITCH 138 KV LINE : EASEMENT ACQUISITION |  |  | 2021-10-15
762 | 0PT44870 -- WINK SWITCH : CONVERT 69KV PORTION OF WINK TO 138KV. | Not Applicable | 1335615 | 2022-04-15 | 1582056.49 |  | 18.45% | Variance is due to increased labor costs. Estimate assumed commissioning services would be performed by internal resources. Due to resource constraints and the complexity of the work, contract resources were utilized at a higher cost.
763 | 0PT44863 -- GHOST TOWN SWITCH: ESTABLISH 138KV POI SWITCH FOR LA CASA WIND | Not Applicable | 5546376.54 | 2023-01-15 | 5501398.81 |  | -0.8109% | Not Applicable
764 | 0PT46615 -- GRAHAM - BRECKENRIDGE 138 KV LINE: NORTH GUNSOLUS SUB LINE CONNECTION | Not Applicable | 1861863 | 2021-04-15 | 365372.81 |  | -80.38% | Not Applicable
765 | 0PT44850 -- THOMAS PRICE SWITCH: ESTABLISH A NEW 345 KV, 3 BREAKER RING BUS STATION TO PROVIDE POI FOR YOUNG WIND, LLC | Not Applicable | 7861206 | 2021-11-15 | 7173933.85 |  | -8.743% | Not Applicable
766 | 0PT44767 -- IRON BRIDGE TAP - ABLES SPRINGS TAP WEST 138 KV LINE : KITSEE POI FOR RAYBURN DUCK COVE SUB | Not Applicable | 1483316 | 2021-09-15 | 1014966.19 |  | -31.57% | Not Applicable
767 | 0PT44765 -- MANKIN SWITCH - KAUFMAN NORTHWEST SWITCH 138 KV LINE : INSTALL WILL WHITE POI FOR RAYBURN'S TOOL SUB | Not Applicable | 1730834 | 2021-09-15 | 1421116.47 |  | -17.89% | Not Applicable
768 | 0PT44759 -- BARDWELL SWITCH - ITALY SUB 69 KV LINE : REBUILD | Not Applicable | 11790246 | 2022-04-15 | 9920907.35 |  | -15.85% | Not Applicable
769 | 0PT44731 -- COMANCHE PEAK SWITCH - STEPHENVILLE SWITCH 138 KV LINE: ANTLER HOLLOW ASSOCIATED LINE WORK (SOUTH CIRCUIT) | Not Applicable | 746949 | 2022-07-15 | 436236.01 |  | -41.6% | Not Applicable
770 | 0PT44730 -- CEDAR CREST SWITCH - WALL STREET SUB 138 KV LINE: 69 KV TO 138 KV LINE CONVERSION | Not Applicable | 514751 | 2021-11-15 | 552771.27 |  | 7.386% | Not Applicable
771 | 0PT44681 -- BROWN SWITCH - IP RADIAN POI 345 KV LINE : INSTALL LINE FOR IP RADIAN POI | Not Applicable | 3834123 | 2021-09-15 | 2317510.56 |  | -39.56% | Not Applicable
772 | 0PT44633 -- KITSEE POI : ESTABLISH 138KV POINT OF INTERCONNECTION | Not Applicable | 658784 | 2021-07-15 | 531595.95 |  | -19.31% | Not Applicable
773 | 0PT44632 -- WILL WHITE POI : ESTABLISH 138KV POINT OF INTERCONNECTION FOR RAYBURN TOOL | Not Applicable | 811168 | 2021-07-15 | 545125.16 |  | -32.8% | Not Applicable
774 | 0PT44627 -- JEWETT SWITCH - FAIRFIELD WEST SUB 138 KV LINE: CUT IN BLAIN SUB | Not Applicable | 791401 | 2021-08-15 | 657730.15 |  | -16.89% | Not Applicable
775 | 0PT44585 -- BLACKWATER DRAW – PALEO BESS SOLAR 345 KV LINE: LINE INTERCONNECTION | Not Applicable | 976885 | 2021-06-15 | 770330.18 |  | -21.14% | Not Applicable
776 | 0PT44568 -- HILLSBORO SUB : MODIFY RELAYING FOR CONNECTING TERMINAL TO ASH CREEK SWITCH | Not Applicable | 270503 | 2022-11-15 | 264101.4 |  | -2.367% | Not Applicable
777 | 0PT44559 -- WATERMILL SWITCH - SEAGOVILLE SWITCH 138 KV LINE : REPLACE POLES, XARMS & X-BRACES | Not Applicable | 543752 | 2021-08-15 | 496932.45 |  | -8.61% | Not Applicable
778 | 0PT44557 -- HICKS SWITCH - DEEN SWITCH 138 KV LINE : CUT IN TO HORSEMAN SUB (FORMERLY SAGINAW SE SUB) | Not Applicable | 1594954 | 2023-02-15 | 1727748.2 |  | 8.326% | Not Applicable
| 0PT51515 -- HICKS SWITCH - DEEN SWITCH 138 KV LINE : CUT IN TO HORSEMAN SUB (FORMERLY SAGINAW SE SUB) : ROW ACQUISITION |  |  | 2023-02-15
779 | 0PT44528 -- SL OGALLALA - TULE CANYON 345 KV LINE: KRESS SWITCH INTERCONNECTION | Not Applicable | 1891641 | 2022-06-15 | 1521025.38 |  | -19.59% | Not Applicable
780 | 0PT44514 -- FLINTKOTE SOUTH TAP - FLINTKOTE SWITCH 69 KV LINE : CUT-IN FOR BEACON HILL SUB | Not Applicable | 655834 | 2021-09-15 | 745648.02 |  | 13.69% | Variance is due to a change in project scope. Underground pipelines required moving the rebuild inside of an existing fence, so gates needed to be installed that were not included in the initial estimate and had to be custom made. These changes resulted in additional labor costs to relocate structures and deliver and install 16-foot and 32-foot gates, as well as additional material costs for the gates themselves.
781 | 0PT44505 -- EVERMAN SW. - CLEBURNE SW. 138KV LINE: WILSHIRE SUB CUT-IN | Not Applicable | 1186297.17 | 2023-03-15 | 1107091.35 |  | -6.677% | Not Applicable
| 0PT51476 -- EVERMAN SW. - CLEBURNE SW. 138KV LINE: WILSHIRE SUB CUT-IN : ROW ACQUISITION |  |  | 2023-03-15
782 | 0PT44457 -- TEMPLE PECAN CREEK SWITCH TO TRADINGHOUSE SWITCH AND TEMPLE SWITCH TO LAKE CREEK SWITCH 345 KV DOUBLE-CIRCUIT TRANSMISSION LINE CHANGES | Not Applicable | 749115 | 2021-10-15 | 943770.84 |  | 25.98% | Variance is due to increased material and labor costs. Material cost increased due to price of lattice structure pricing. Construction labor increased due to additional foundation costs and delivery delays that resulted in remobilization charges. Matting became necessary due to unusually wet conditions and short construction window.
783 | 0PT44456 -- TEMPLE PECAN CREEK SWITCH - LAKE CREEK SWITCH 138 KV LINE : MODIFY LINE FOR CONNECTING COW BAYOU SWITCH | Not Applicable | 958849 | 2021-10-15 | 1036807.81 |  | 8.13% | Not Applicable
784 | 0PT44443 -- BLAIN (FORMERLY KNOWN AS DEW) SUB : ESTABLISH SUBSTATION WITH ONE 47 MVA TRANSFORMER AND TWO 25 KV FEEDER BREAKERS | Not Applicable | 4802523 | 2021-05-15 | 4584569.06 |  | -4.538% | Not Applicable
785 | 0PT44435 -- NAVARRO (LONE STAR) SWITCH - LIMESTONE (CENTERPOINT) SWITCH 345 KV LINE : LINE WORK TO CONNECT OUTLAW SWITCH | Not Applicable | 1761913 | 2021-09-15 | 2421166.73 |  | 37.42% | Variance is due to a change in project scope and increased labor costs. Due to material delays, polymer insulators were installed temporarily to meet the in-service date. Crews were remobilized to install permanent glass insulators and re-sag conductor once available. Bad weather necessitated matting for the extended project duration.
786 | 0PT44416 -- HURST SUB: 138 KV LINE TERMINAL UPGRADE | Not Applicable | 486819 | 2022-04-15 | 696605.58 |  | 43.09% | Variance is due to increased material and labor costs. The project required a sequence of outages that resulted in project delays and remobilizations. Material costs increased due to price increases for steel structures and high-voltage switches.
787 | 0PT44414 -- EULESS SOUTH SUB: 138 KV LINE TERMINAL UPGRADE | Not Applicable | 485178 | 2022-04-15 | 459908.74 |  | -5.208% | Not Applicable
788 | 0PT44353 -- 2022 SUMMER WORK - ROYSE SWITCH - SHAMBURGER SWITCH 345 KV LINE : INSTALL BUZZARD DETERRENTS & REPLACE INSULATORS | Not Applicable | 340252 | 2022-03-15 | 356820.72 |  | 4.87% | Not Applicable
789 | 0PT44344 -- CEDAR CREST 138 KV SWITCH : REMOVE AUTO'S AND RECONFIGURE LINE TERMINAL LAYOUT AND UPGRADE CB# 072 TERMINAL TO 3200A | Not Applicable | 6059890.78 | 2023-01-15 | 6268445.91 |  | 3.442% | Not Applicable
790 | 0PT44343 -- CEDAR CREST SUB : CONVERT SUBSTATION TO 138 KV OPERATION AND REBUILD 13.8 KV SUBSTATION | Not Applicable | 5122938 | 2022-03-15 | 6459065.9 |  | 26.08% | Variance is due to a change in project scope and increased material and labor costs. Scope change includes replacing the deteriorating security fence and two 13.8 kV transformer neutral grounding reactors to address safety concerns. Material costs were higher than estimated due to price increases for structural steel, relay control equipment, and control centers. The cost of transformer rigging, a crane, and transportation service to relocate the two existing transformers was higher than expected due to access restrictions and the need to avoid energized overhead circuits. Labor costs increased due to demolition work in proximity to energized equipment, which required hand-digging and hydrovac excavation for conduit, grounding, and foundations; additional hauling of equipment and materials; additional job site security; and multiple remobilization charges associated with ERCOT clearances and material delays. Grading costs were higher than estimated due to additional site work required to mitigate erosion and drainage issues. Additional protection and control resources were required to meet ERCOT's clearance restriction deadline.
791 | 0PT44341 -- BUNTIN DRIVE SUB : CONVERT STATION TO 138 KV OPERATION BY REPLACE 20 MVA TRANSFORMERS WITH 46.7 MVA AND INSTALL EIGHT 13.8 KV FEEDER SWITCHGEAR | Not Applicable | 7608844 | 2022-04-15 | 7878300.67 |  | 3.541% | Not Applicable
792 | 0PT44334 -- ELM MOTT SWITCH: ADD A LINE TERMINAL TO CONVERT 69 KV WACO EAST SWITCH LINE TO 138 KV | Not Applicable | 1150308 | 2023-04-15 | 1281280.32 |  | 11.39% | Variance is due to a change in project scope resulting in increased material and additional labor costs. The scope change included modifying the existing equipment station layout with the installation of 138 kV circuit breaker, a new 138 kV A-frame deadend structure, associated switches, and relaying equipment, including a microprocessor-based relay panel. The estimated material costs were higher than the final cost estimate due to the scope change and price increases for structural steel, high-voltage circuit breakers, air switches, and relay control equipment. Labor costs increased due to additional demolition work, upgrades to existing buswork, hand-digging for conduit, grounding and foundations in proximity to energized equipment, remobilization charges due to material delays, additional buswork upgrades, installation of a new 138 kV deadend structure, additional hauling of equipment and materials, additional job site security and an extended construction schedule. Additional protection and control contractor resources were required to meet the required project in-service date.
793 | 0PT44328 -- ESKOTA SWITCH: CB 1890 LINE TERMINAL UPGRADE | Not Applicable | 372799 | 2023-01-15 | 388451.84 |  | 4.199% | Not Applicable
794 | 0PT44324 -- ITALY SUB: 69 KV LINE TERMINAL UPGRADE | Not Applicable | 1296090 | 2022-05-15 | 1251075.78 |  | -3.473% | Not Applicable
795 | 0PT44322 -- BARDWELL LAKE SWITCH: DISCONNECT TWO 69 KV LINE TERMINALS & UPGRADE LINE TERMINALS | Not Applicable | 274037 | 2022-02-15 | 286623.83 |  | 4.593% | Not Applicable
796 | 0PT44317 -- PECAN TREE SUB: ESTABLISH 138-13.2 KV SUBSTATION AND INSTALL ONE 138-13.2 KV TRANSFORMER WITH THREE 15 KV FEEDER BREAKERS | Not Applicable | 5882174 | 2021-08-15 | 5862540.69 |  | -0.3338% | Not Applicable
797 | 0PT44313 -- SHORT GRASS (FORMERLY ARCHER CITY) SUB: ESTABLISH NEW 138-12.5 KV SUBSTATION | Not Applicable | 3647282 | 2022-03-15 | 3781324.95 |  | 3.675% | Not Applicable
798 | 0PT44304 -- PEPPERVINE SWITCH: 138 KV STATION REBUILD | Not Applicable | 11566138 | 2022-03-15 | 11064958.64 |  | -4.333% | Not Applicable
799 | 0PT44295 -- WEATHERFORD SWITCH : UPGRADE 138 KV LINE TERMINAL TO MEET OR EXCEED 3200 A | Not Applicable | 384571 | 2021-12-15 | 318858.64 |  | -17.09% | Not Applicable
800 | 0PT44280 -- SL SALT FLAT ROAD SUB : INSTALL 55.2 MVAR 138 KV CAPACITOR, ONE 3-18.4 MVAR STAGE | Not Applicable | 2469535 | 2021-08-15 | 2631573.86 |  | 6.562% | Not Applicable
801 | 0PT44279 -- BROWNWOOD SUB - COMANCHE SWITCH 138 KV LINE : PINKNEY SUB CUT IN | Not Applicable | 1674435 | 2021-10-15 | 1433427.18 |  | -14.39% | Not Applicable
802 | 0PT44276 -- PINKNEY SUB: ESTABLISH NEW 138/12.5 KV SUBSTATION | Not Applicable | 4599118 | 2021-08-15 | 5149949.04 |  | 11.98% | Variance is due to a change in project scope to install an additional feeder to serve a customer, replace a CCVT anchor bolt, and fence and gate work. Labor costs also increased due to remobilization charges for the additional scope of work.
803 | 0PT44272 -- ROYSE SWITCH: ESTABLISH NEW 138 KV LINE TERMINAL AND DISCONNECT EXISTING TERRELL 69 KV LINE 2202 | Not Applicable | 1269094.91 | 2023-03-15 | 1192308.42 |  | -6.05% | Not Applicable
804 | 0PT44267 -- ROCKDALE SUB : INSTALL TRANSFORMER #2 WITH 2 FEEDERS | Not Applicable | 2743160 | 2022-03-15 | 3717354.78 |  | 35.51% | Variance is due to increased material and labor costs. Material costs for power transformer were higher than the historical costs used to create the estimate. Labor costs increased due to above-grade work and commissioning being performed by a contractor instead of internal resources.
805 | 0PT44266 -- KILLEEN SWITCH : REPLACE 345/138 KV AUTOTRANSFORMER #1 | Not Applicable | 3243212 | 2021-07-15 | 3095052.06 |  | -4.568% | Not Applicable
806 | 0PT44264 -- BATTLEGROUND (FORMERLY KNOWN AS COUPLAND) SUB : ESTABLISH A 138 KV SUBSTATION WITH ONE 28 MVA, 138-13.2 KV TRANSFORMER | Not Applicable | 4929534 | 2021-08-15 | 5295053.4 |  | 7.415% | Not Applicable
807 | 0PT44263 -- ROYSE SWITCH: 138KV BKR #310 TERMINAL UPGRADE LINE EQUIPMENT TO 2000 A | Not Applicable | 1148524 | 2021-06-15 | 1280162.69 |  | 11.46% | Variance is due to a change in project scope and increased material and labor costs. Scope of work was revised to include installation of a new deadend structure, upgrading relaying controls, and installing a transfer trip panel for increased operational efficiency and system security. Material costs increased due to price increases for structural steel, high-voltage circuit breakers, air switches and relaying control equipment. Labor costs increased due to the scope change; additional demolition work; upgrading existing buswork; hand-digging for conduit, grounding, and foundations in close proximity of energized equipment; remobilization charges due to material delays; additional hauling of equipment and materials; additional job site security; an extended construction schedule; and the need for additional protection and control contractor resources to meet the project in-service date.
808 | 0PT44260 -- ROWLETT SUB: UPGRADE LINE EQUIPMENT TO 2000 A | Not Applicable | 1854298 | 2021-10-15 | 2084156.38 |  | 12.4% | Variance is due to a change in project scope and increased labor costs for grading, secondary containment, leaker management, and a field construction coordinator. Project scope was revised to include an additional 138 kV motor operated sectionalizing switch to eliminate the need for outages during maintenance and accommodate the future installation of two expansion bays. The project also experienced construction delays due to an associated transmission line project falling behind schedule.
809 | 0PT44258 -- TEMPLE SOUTHEAST SUB : REPLACE 138-12.5KV 28 MVA TRANSFORMER #1 WITH A 138-12.5KV 46.7 MVA TRANSFORMER AND REPLACE STATION #1 CIRCUIT BREAKERS AND BUS TIE WITH NEW CIRCUIT BREAKERS. | Not Applicable | 1663935 | 2021-11-15 | 1786792.81 |  | 7.384% | Not Applicable
810 | 0PT44257 -- CLEBURNE WEST SUB : INSTALL BANK #2 WITH A138-12.5 KV 28 MVA TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable | 2080917 | 2022-03-15 | 2214227.91 |  | 6.406% | Not Applicable
811 | 0PT44254 -- DALROCK SUB: UPGRADE LINE EQUIPMENT TO 2000 A | Not Applicable | 889654 | 2021-10-15 | 781727.73 |  | -12.13% | Not Applicable
812 | 0PT44253 -- SL WINDMILL SWITCH - AJ SWOPE SWITCH 345 KV LINE : WALLABY SWITCH CUT IN FOR DAWN SOLAR POI | Not Applicable | 1872222.98 | 2021-10-15 | 1092487.13 |  | -41.65% | Not Applicable
813 | 0PT44246 -- TEMPLE NORTHWEST SUB : REPLACE TWO 138-12.5KV 28 MVA TRANSFORMERS WITH TWO 138-12.5KV 46.7 MVA TRANSFORMERS | Not Applicable | 5313490 | 2021-11-15 | 5702258.33 |  | 7.317% | Not Applicable
814 | 0PT44244 -- INWOOD ROAD SUB: INSTALL TRANSFORMER #3 WITH (1) 47 MVA 138/13.8 KV TRANSFORMER AND (1) 13.8 KV METAL-CLAD SWITCHGEAR | Not Applicable | 4794016 | 2021-06-15 | 5653432.87 |  | 17.93% | Variance is due to a change in project scope and increased material and labor costs. Replacement of electromechanical relay panels was added to the scope of work, which increased material and labor costs. Other material costs were higher than estimated due to price increases for structural steel, power transformers, and metal-clad switchgear equipment. Transformer and switchgear manufacturer rigging, crane, and transportation costs were higher than estimated due to access restrictions and weather conditions that required matting and use of a jack and slide to avoid energized overhead circuits. Labor costs increased due to higher costs for grading and transformer leaker management; the need for hand-digging for conduit, grounding, and foundations in proximity to energized equipment; the need to haul additional equipment and materials; additional job site security; and multiple remobilization charges due to ERCOT clearance coordination, material delays, and an expedited construction schedule to make up for weather delays. Additional protection and control resources were required to meet ERCOT's clearance restriction deadline and due to extensive switchgear designs.
815 | 0PT44243 -- KLEBERG SUB : REPLACE TRANSFORMER #2 WITH ONE 47 MVA 138/13.2 KV AND REBUILD LV BUS WITH (2) BREAKERS PER TRANSFORMER | Not Applicable | 2862907 | 2021-08-15 | 2967212.23 |  | 3.643% | Not Applicable
816 | 0PT44242 -- SABANA SUB : (FORMERLY KNOWN AS PROCTOR SUB) ESTABLISH STATION WITH A 138-12.5 KV 10.5 MVA TRANSFORMER WITH TWO FEEDER BREAKERS | Not Applicable | 4557630 | 2021-10-15 | 4797365.17 |  | 5.26% | Not Applicable
817 | 0PT44234 -- TAYLOR WEST SUB : INSTALL TRANSFORMER #3 WITH A 138-24.9 KV 47 MVA AND TWO FEEDER BREAKERS | Not Applicable | 2381361 | 2021-06-15 | 2316652.08 |  | -2.717% | Not Applicable
818 | 0PT44233 -- BANGS SUB : REBUILD STATION BY INSTALLING TRANSFORMER #2 138-24.9 KV 28 MVA AND TWO FEEDER BREAKERS AND DECOMMISSION TRANSFORMER #1 | Not Applicable | 3676844 | 2022-03-15 | 3800033.24 |  | 3.35% | Not Applicable
819 | 0PT44229 -- TRINITY SUB : INSTALL 2ND 138/12.5 KV 47 MVA TRANSFORMER WITH TWO UG FEEDER BREAKERS | Not Applicable | 2978368 | 2022-04-15 | 3285351.78 |  | 10.31% | Variance is due to a change in project scope and increased material and labor costs. Material costs increased due to price increases for structural steel, power transformers, and relay control equipment. Transformer manufacturer rigging, crane and transportation service costs were also higher than originally estimated. Labor costs increased due to the need for hand-digging associated with the conduit, grounding and foundations in close proximity to energized equipment; additional hauling of equipment and materials; additional job site security; and multiple remobilization charges due to ERCOT clearance coordination and material delays. Additional protection and control resources were required to meet ERCOT's clearance restriction deadline and to replace the existing electromechanical relay panels, which were beyond their serviceable life.
820 | 0PT44228 -- BIRD NEST SUB : INSTALL STATION #2 WITH A 138-24.9 KV 47 MVA TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable | 2170661 | 2021-08-15 | 2029814.45 |  | -6.489% | Not Applicable
821 | 0PT44226 -- WHITE SETTLEMENT WEST SUB : INSTALL 138/25 KV 47 MVA TRANSFORMER #2 WITH ONE FEEDER BREAKER | Not Applicable | 2316447 | 2021-11-15 | 2306673.92 |  | -0.4219% | Not Applicable
822 | 0PT44156 -- SAND LAKE SWITCH - CULBERSON SWITCH 138 KV LINE : CUT-IN TO ESTABLISH CAPACITOR BANK AT AQUIFER TAP | Not Applicable | 1200183 | 2021-09-15 | 942932.53 |  | -21.43% | Not Applicable
823 | 0PT44154 -- MCGREGOR PHILLIPS-HARRIS CREEK 69KV REBUILD | Not Applicable | 711416 | 2021-10-15 | 1572172.65 |  | 121% | Variance is due to a change in project scope resulting from the cut-in to the new Harris Creek Station to a rebuild of 1.35 miles and a temporary bypass, as well as associated access work including matting costs due to right of way conditions. A scope change was required after a fire at McGregor Substation accelerated the need to connect Harris Creek station at 138 kV. This required rebuilding both the 138 kV and the 69 kV line section from the tap to Harris Creek station, including converting the existing H-frame structures to double-circuit monopoles.
824 | 0PT44127 -- WAXAHACHIE SWITCH - BARDWELL SWITCH 69 KV LINE : REBUILD | Not Applicable | 12949145 | 2021-09-15 | 7247209.95 |  | -44.03% | Not Applicable
825 | 0PT44126 -- RATTLESNAKE SWITCH - JEWETT SWITCH 345 KV LINE : LINE MODIFICATION TO CONNECT ST. JOHNS SWITCH | Not Applicable | 1419274 | 2021-09-15 | 1799898.33 |  | 26.82% | Variance is due to increased material and labor costs. Additional construction matting was required due to wet conditions. Material delivery delays resulted in additional crews being deployed to meet ERCOT’s clearance restriction deadline and the generation interconnection timeline.
826 | 0PT44089 -- BEACON HILL SUB : ESTABLISH STATION WITH A 138/69-12.5KV 28MVA TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable | 4266750 | 2021-05-15 | 4373872.99 |  | 2.511% | Not Applicable
827 | 0PT44068 -- STONE CREEK SWITCH - VALLEY SWITCH 138 KV LINE : CUT-IN TO ESTABLISH LOY LAKE 138 KV CAPACITOR BANK | Not Applicable | 900000 | 2021-09-15 | 852297.82 |  | -5.3% | Not Applicable
828 | 0PT44067 -- MCDONALD ROAD SWITCH – SPRABERRY SWITCH 138 KV LINE : CUT-IN TO ESTABLISH CAPACITOR BANK | Not Applicable | 354054 | 2021-10-15 | 279741.88 |  | -20.99% | Not Applicable
829 | 0PT43991 -- SL GRADY: INSTALL 55.2 MVAR 138 KV CAPACITORS | Not Applicable | 2440391 | 2021-08-15 | 2269064.23 |  | -7.02% | Not Applicable
830 | 0PT43989 -- CENTRALIA: INSTALL 55.2 MVAR 138 KV CAPACITOR BANK | Not Applicable | 2141814 | 2021-08-15 | 2338135.89 |  | 9.166% | Not Applicable
831 | 0PT43986 -- KEMP RANCH SWITCH - CEDAR HILL SWITCH 138 KV LINE : CUT-IN TO ESTABLISH SOAP CREEK SWITCH | Not Applicable | 2150000 | 2021-07-15 | 2310869.57 |  | 7.482% | Not Applicable
832 | 0PT43978 -- SL BROWN: INSTALL 55.2 MVAR 138 KV CAPACITORS AND RELAY MODIFICATIONS FOR BUZZARD DRAW SWITCH 138 KV LINE TERMINAL | Not Applicable | 2105080 | 2021-08-15 | 2437897.3 |  | 15.81% | Variance is due to a change in project scope and increased material and labor costs. A temporary bypass was added to the project scope, which increased material and labor costs. Additional protection and control resources were required for commissioning to meet project timelines.
833 | 0PT43970 -- LOY LAKE SUB : ESTABLISH WITH ONE 28 MVA 138-12.5 KV TRANSFORMER AND TWO UG FEEDER BREAKERS AND 3-18.4 MVAR 138 KV CAPACITORS | Not Applicable | 6731530 | 2021-08-15 | 8055748.34 |  | 19.67% | Variance is due to a change in project scope and increased material and labor costs. The scope change includes a pre-cast perimeter wall and concrete driveway, to meet municipal permit requirements. Material costs increased due to price increases for structural steel, power transformers, high-voltage capacitor equipment, relay control equipment, and control centers. The transformer manufacturer rigging, crane, and transportation service costs were higher than originally estimated. Labor costs increased due to poor soil conditions that increased costs for foundation, conduit and grounding installation; municipal surveying, platting, and permitting requirements; additional, protection and control resources required to meet the in-service date ahead of ERCOT's clearance restriction deadline; additional site work required for erosion control and site drainage, the removal of buried trash and debris, requiring additional base materials and site cleanup; increased transformer leaker and oil retention installation costs; remobilization charges due to ERCOT clearance coordination and material delays; and an expedited construction schedule due to weather and permitting delays.
834 | 0PT43964 -- TEX HARVEY SUB: INSTALL 55.2 MVAR 138 KV CAPACITOR BANK | Not Applicable | 1617138 | 2021-09-15 | 2306185.34 |  | 42.61% | Variance is due to a change in project scope that added additional capacitors, nine current-limiting reactors, three coupling capacitors, motor operators, switch, and a static mast. Labor and materials for these items were not included in the estimate.
835 | 0PT43948 -- ROYSE SWITCH - ROWLETT SUB 138 KV LINE : RECONDUCTOR FATE SUB TO ROCKWALL SUB | Not Applicable | 13223812 | 2022-06-15 | 5856999.24 |  | -55.71% | Not Applicable
| 0PT46138 -- ROYSE SWITCH - ROWLETT SUB 138 KV LINE : ROW ACQUISITION |  |  | 2022-06-15
836 | 0PT43900 -- TRINIDAD SWITCH - NAVARRO SWITCH 69 KV LINE: RETERMINATION INTO CRESLENN RANCH | Not Applicable | 1340348 | 2022-04-15 | 1428638.66 |  | 6.587% | Not Applicable
837 | 0PT43899 -- ESKOTA SWITCH - SWEETWATER NO. 2 SUB 69 KV LINE: REBUILD THE FLINTKOTE TAP 69 KV SECTION | Not Applicable | 1300842 | 2021-09-15 | 1536231.21 |  | 18.1% | Variance is due to increased material costs and the discovery of underground utilities during construction. Prices for steel and general hardware increased between the time the estimate was created and the materials were ordered. Underground utilities were found during construction so all structures were hydro-excavated.
838 | 0PT43898 -- ESKOTA SWITCH - SWEETWATER NO. 2 SUB 69 KV LINE: REBUILD THE U.S. GYPSUM SUB TAP SECTION | Not Applicable | 2668839 | 2022-02-15 | 2494910.04 |  | -6.517% | Not Applicable
839 | 0PT43849 -- BUZZARD DRAW SWITCH: INSTALL TWO 138 KV LINE TERMINALS, REMOVE AUTO, AND REMOVE 69 KV YARD | Not Applicable | 1985171 | 2021-07-15 | 2056993.68 |  | 3.618% | Not Applicable
840 | 0PT43825 -- TAYLOR SUB: ESTABLISH 138 KV RING BUS AND UPGRADE DISTRIBUTION STATION HIGH-SIDE | Not Applicable | 6694493 | 2021-12-15 | 8811901.05 |  | 31.63% | Variance is due to a change in project scope to support the expansion of the station with additional drive space, gates, and access to equipment. Estimate did not include the transportation of the 138/69 kV autotransformer. Additional labor was required for the transfer of the autotransformer and installation, equipment removal, station expansion, and expansion of the ground grid.
841 | 0PT43824 -- CRESLENN RANCH (FORMERLY KNOWN AS TRINIDAD 69 KV) SWITCH: REBUILD 69 KV STATION TO A FOUR POSITION RING BUS | Not Applicable | 4354061 | 2021-11-15 | 5662096.08 |  | 30.04% | Variance is due to a change in project scope and increased material and labor costs. Scope of work expanded to include installation of three 12.5 kV potential transformers for accurate feeder relaying, two 240 V fused disconnect switches for protection between distribution and the control center, and a mobile transformer to support the construction timeline, which increased material and labor costs. Due to sandy soil conditions, a slurry mixture was needed to stabilize dead end foundations. Material and labor costs increased due to security fence modifications; price increases for structural steel, potential transformers, conduit, grounding, and control cable multiple; equipment rentals; Field Construction Coordinator labor; and remobilization charges due to ERCOT clearance coordination.
842 | 0PT43721 -- WACO EAST SUB - WACO WEST SWITCH 138 KV LINE : RETERMINATE AT PEPPERVINE SWITCH | Not Applicable | 775379.88 | 2022-06-15 | 716433.34 |  | -7.602% | Not Applicable
843 | 0PT43720 -- LAKE CREEK SWITCH - WACO WEST SWITCH 138 KV LINE : RETERMINATE AT PEPPERVINE SWITCH | Not Applicable | 911267.53 | 2022-06-15 | 846872.43 |  | -7.067% | Not Applicable
844 | 0PT43719 -- WACO WEST SWITCH - MCGREGOR PHILLIPS - TEMPLE ELM CREEK SWITCH 138 KV LINE: RE-TERMINATE AT PEPPERVINE SWITCH | Not Applicable | 931322.69 | 2022-06-15 | 876330.35 |  | -5.905% | Not Applicable
845 | 0PT43718 -- WACO WEST SWITCH - WACO EAST SWITCH - ELM MOTT 138 KV LINE: RE-TERMINATE TO PEPPERVINE SWITCH | Not Applicable | 994911.21 | 2022-06-15 | 822965.49 |  | -17.28% | Not Applicable
846 | 0PT43707 -- SOAP CREEK SWITCH: ESTABLISH A NEW 138 KV, 3 BREAKER RING BUS STATION TO PROVIDE POI FOR ELLIS SOLAR | Not Applicable | 4317006 | 2021-06-15 | 4159181.67 |  | -3.656% | Not Applicable
847 | 0PT43692 -- BELLMEAD SUB - ELM MOTT SWITCH 69 KV LINE : CONVERSION TO 138 KV | Not Applicable | 6597154 | 2021-09-15 | 6177430.38 |  | -6.362% | Not Applicable
848 | 0PT43686 -- FERRIS SWITCH - WAXAHACHIE OCF 69KV LINE: REBUILD FERRIS - STR 28/254 | Not Applicable | 15856613 | 2024-04-15 | 14373914.04 |  | -9.351% | Not Applicable
| 0PT44616 -- FERRIS SWITCH - WAXAHACHIE OCF 69KV LINE: REBUILD FERRIS - STR 28/254 : EASEMENT MODIFICATION AGREEMENTS |  |  | 2020-12-15
849 | 0PT43677 -- STEPHENVILLE SWITCH - COMANCHE SWITCH 138 KV LINE : SABANA SUBSTATION CUT-IN | Not Applicable | 1194221 | 2022-06-15 | 836577.69 |  | -29.95% | Not Applicable
| 0PT48461 -- STEPHENVILLE SWITCH - COMANCHE SWITCH 138 KV LINE : EASEMENT ACQUISITION |  |  | 2022-06-15
850 | 0PT43655 -- LAMESA SWITCH: REPLACE EXISTING 138/69 KV AUTOTRANSFORMER #1 WITH A 86 MVA 138/69 KV AUTOTRANSFORMER | Not Applicable | 867512 | 2021-08-15 | 724583.18 |  | -16.48% | Not Applicable
851 | 0PT43642 -- BLACKWATER DRAW SWITCH : ADD RUNG WITH TWO 345KV BREAKERS | Not Applicable | 3838169 | 2021-07-15 | 4707921.24 |  | 22.66% | Variance is due to increased labor costs. The construction schedule was delayed as a result of material delivery delays and the customer delaying their project multiple times, which resulted in multiple remobilization charges.
852 | 0PT43639 -- MOUNTAIN CREEK SWITCH - WEST DALLAS 138 KV LINE: ESTABLISH TRANSMISSION LOOP FEED FOR CAMPION 138 KV SUB | Not Applicable | 1548979 | 2022-10-15 | 1227715.24 |  | -20.74% | Not Applicable
853 | 0PT43618 -- FARMERSVILLE SWITCH - MONTICELLO SWITCH 345 KV SOUTH CIRCUIT LINE : INSTALL A 345 KV POINT-OF-INTERCONNECTION (POI) FOR HOPKINS SOLAR GENERATOR AT BIRTHRIGHT 345 KV SWITCH | Not Applicable | 2570250 | 2021-11-15 | 2059460.83 |  | -19.87% | Not Applicable
854 | 0PT43598 -- MARLIN SOUTH SUB: INSTALL 27.6 MVAR 69 KV CAPACITORS | Not Applicable | 1983299 | 2021-09-15 | 3109164.91 |  | 56.77% | Variance is due to a change in project scope and increased material and labor costs. A 138 kV bus was added to the scope of work in anticipation of future station upgrades, and the orientation of the 138 kV bus had to be modified to expand the yard more than previously anticipated to accommodate the new equipment. Re-orienting the equipment prevented Oncor from having to expand the station’s footprint, which would have required new fencing, foundations, grounding, and other costs. Lightning arresters and a telecommunications upgrade were added to the project scope for reliability, which increased material and labor costs. Material delays required the contractor to be remobilized to install fence grounding at a later date, resulting in additional labor costs.
855 | 0PT43597 -- DERMOTT SWITCH - ENDURANCE PARK STORAGE POI 138 KV LINE : INSTALL LINE FOR ENDURANCE PARK STORAGE POI | Not Applicable | 1027784 | 2021-02-15 | 786289.65 |  | -23.5% | Not Applicable
856 | 0PT43592 -- DESOTO SWITCH: CB 1635 LINE TERMINAL UPGRADE | Not Applicable | 326944 | 2021-09-15 | 322523.64 |  | -1.352% | Not Applicable
857 | 0PT43554 -- BRUSHY CREEK SWITCH – ELGIN SWITCH 138 KV LINE: CONSTRUCT NEW LINE | Not Applicable | 950469 | 2021-09-15 | 600190.29 |  | -36.85% | Not Applicable
858 | 0PT43553 -- ELGIN SWITCH – TAYLOR 138 KV LINE: BRUSHY CREEK SWITCH RE-TERMINATION | Not Applicable | 1344449 | 2021-09-15 | 1055166.29 |  | -21.52% | Not Applicable
859 | 0PT43552 -- SANDOW SWITCH - ELGIN SWITCH 138 KV LINE: BRUSHY CREEK SWITCH RE-TERMINATION | Not Applicable | 1109985 | 2021-09-15 | 694014.76 |  | -37.48% | Not Applicable
860 | 0PT43551 -- ELGIN SWITCH : MODIFY RELAY AS A PART OF CONNECTING BRUSHY CREEK SWITCH TO THE 138/69 KV AUTOTRANSFORMER | Not Applicable | 313885 | 2021-12-15 | 335745.91 |  | 6.965% | Not Applicable
861 | 0PT43547 -- VENUS SWITCH - NAVARRO SWITCH 345 KV LINE : RELOCATE STRUCTURE 60/1 | Not Applicable | 801019.02 | 2023-12-15 | 1098732.83 |  | 37.17% | Variance is due to unexpected matting costs due to extensive rain in the area before the start of the project. This structure is located near an eroding creek which is why the structure was being relocated. Because of the wet conditions, a permanent casing foundation was also required which increased labor and material costs.
862 | 0PT43543 -- WATERMILL SWITCH - SEAGOVILLE SWITCH 138 KV LINE : RELOCATE STR. 3/3 AND 3/1 | Not Applicable | 1193911 | 2021-03-15 | 1196895.88 |  | 0.25% | Not Applicable
863 | 0PT43542 -- WACO WEST SWITCH - LAKE CREEK SWITCH 138 KV LINE : POLE RELOCATION DUE TO EROSION | Not Applicable | 412325 | 2021-03-15 | 289857.18 |  | -29.7% | Not Applicable
864 | 0PT43514 -- WICKETT (TNMP) SWITCH - WOLF SWITCH 138 KV LINE : TERMINATE LINE FOR TNMP | Not Applicable | 270862 | 2021-10-15 | 276971.98 |  | 2.256% | Not Applicable
865 | 0PT43501 -- BRUSHY CREEK SWITCH - RIVER VALLEY STORAGE 138 KV LINE : LINE WORK TO CONNECT THE BRUSHY CREEK SWITCH TO THE RIVER VALLEY BATTERY STORAGE FACILITIES | Not Applicable | 366675 | 2021-09-15 | 308353.85 |  | -15.91% | Not Applicable
866 | 0PT43477 -- DESOTO SWITCH - STERRETT SWITCH 138 KV LINE: REBUILD DESOTO TO GLENN HEIGHTS (BEC) | Not Applicable | 4013639 | 2022-06-15 | 4001887.19 |  | -0.2928% | Not Applicable
867 | 0PT43468 -- CARROLLTON NORTHWEST SWITCH - CARROLLTON EAST SWITCH 138 KV LINE : LINE TERMINATION AT CARROLLTON NORTHWEST | Not Applicable | 2101040.58 | 2022-10-15 | 1373138.8 |  | -34.64% | Not Applicable
868 | 0PT43467 -- MONTICELLO SWITCH - FARMERSVILLE SWITCH 345 KV LINE : LINE CUT-IN TO CYCLONE SWITCH | Not Applicable | 4594824 | 2021-11-15 | 4202431.88 |  | -8.54% | Not Applicable
869 | 0PT43082 -- DERMOTT SWITCH : ESTABLISH A LINE TERMINAL FOR ENDURANCE PARK STORAGE | Not Applicable | 1325428 | 2021-06-15 | 1101591.26 |  | -16.89% | Not Applicable
870 | 0PT43030 -- BRECKENRIDGE SUB : DECOMMISSION DISTRIBUTION EQUIPMENT AND INSTALLING AN SSVT | Not Applicable | 538487 | 2021-10-15 | 507843.41 |  | -5.691% | Not Applicable
871 | 0PT43028 -- CYCLONE SWITCH : ESTABLISH 3 BREAKER RING BUS STATION | Not Applicable | 9495167 | 2021-09-15 | 9518124.86 |  | 0.2418% | Not Applicable
872 | 0PT43026 -- OUTLAW SWITCH: ESTABLISH FOUR BREAKER RING BUS STATION | Not Applicable | 9503939 | 2021-09-15 | 10292461.43 |  | 8.297% | Not Applicable
873 | 0PT42930 -- ROCKY CREEK SWITCH: INSTALL TRANSFORMER #2 WITH A 138-24.9 KV 46.7 MVA TRANSFORMER AND A 24.9 KV FEEDER BREAKER | Not Applicable | 2137797 | 2021-06-15 | 2577964.54 |  | 20.59% | Variance is due to a change in project scope and an increase in material and labor costs. Project scope was revised to include an additional 24.9 kV feeder breaker for a distribution project set to be constructed in 2023. The addition of the breaker resulted in additional material and labor costs for installation.
874 | 0PT42929 -- COMPTON STREET SUB : REPLACE TRANSFORMERS #1 & #2 WITH 138-13.2 KV 46.7 MVA TRANSFORMERS | Not Applicable | 6133672 | 2022-03-15 | 4508518.79 |  | -26.5% | Not Applicable
875 | 0PT42665 -- AUSTIN RANCH SUB : ESTABLISH A 138 KV POI FOR THE JOSEY (BEC) 138 KV SUBSTATION AT AUSTIN RANCH. | Not Applicable | 256060 | 2020-09-15 | 253402.17 |  | -1.038% | Not Applicable
876 | 0PT42635 -- SHERRY SWITCH : REPLACE MDAR RELAYING PANELS FOR CB #6210 & CB #6220, MODIFY RELAYING FOR CB 6210 TERMINAL TO TIMBERVIEW SWITCH AND MODIFY RELAYING FOR AUTO#1 & 2. | Not Applicable | 335867 | 2021-07-15 | 347646.47 |  | 3.507% | Not Applicable
877 | 0PT42423 -- RIVERCREST SWITCH - PARIS SWITCH 138 KV LINE : EIFFEL SOLAR INTERCONNECT AT HAWK HOLLOW SWITCH | Not Applicable | 2121374 | 2022-06-15 | 1349399.8 |  | -36.39% | Not Applicable
878 | 0PT42336 -- ST. JOHNS SWITCH: ESTABLISH 345 KV SWITCH STATION IN A 3-BREAKER RING BUS ARRANGEMENT TO PROVIDE 345 KV POI FOR ROSELAND SOLAR | Not Applicable | 7163244 | 2021-05-15 | 6153674.57 |  | -14.09% | Not Applicable
879 | 0PT42285 -- BRUSHY CREEK SWITCH : ESTABLISH 138 KV BREAKER-AND-A-HALF STATION AS A PART OF RIVER VALLEY STORAGE FACILITY | Not Applicable | 7576227 | 2021-07-15 | 7757044.59 |  | 2.387% | Not Applicable
880 | 0PT42249 -- HAWK HOLLOW SWITCH : ESTABLISH 5 BREAKER RING POI STATION | Not Applicable | 6613388 | 2022-02-15 | 5929093.01 |  | -10.35% | Not Applicable
881 | 0PT42179 -- CAMPION (FORMERLY BLUEBONNET LAKES) SUB : ESTABLISH SUBSTATION WITH (1) 47 MVA 138/13.8KV AND (1) 28 MVA 138/12.5KV | Not Applicable | 8473410 | 2020-12-15 | 10959698.93 |  | 29.34% | Variance is due to a change in project scope and increased material and labor costs. Scope of work was expanded to include replacing the existing chain-link fence with a masonry wall to address identified safety and security risks. Material costs increased due to the scope change and price increases for power transformers, distribution station equipment, and control centers. Labor costs increased due to the scope change, schedule delays, and increased security services after the security risk was identified.
882 | 0PT42132 -- KRESS SWITCH : ESTABLISH STATION INSTALL THREE 345 KV, 5000 A CIRCUIT BREAKERS IN A RING BUS CONFIGURATION | Not Applicable | 7986575 | 2021-08-15 | 10765815.46 |  | 34.8% | Variance is due to a change in project scope and increased material and labor costs. Scope of work expanded to include a station service voltage transformer and installation of worker platforms at each 345 kV circuit breaker for personnel safety, which required additional material and labor. Contractor service unit costs also increased as a result of receiving firm contractor pricing, including pricing for negotiated items, the installation of 5000 A breakers, switches and bus work, 110' static masts, installation of 500 MCM ground conductor, installation of bus work, concrete escalation and West Texas per diem. Field Construction Coordinator costs were higher due to project delays and schedule shifts extending the duration of construction. Oncor labor costs were also higher due to additional coordination and testing required with the customer.
883 | 0PT42081 -- DFW C EAST - DFW B EAST 138 KV LINE: REBUILD CATHODIC PROTECTION SYSTEM | Not Applicable | 358970 | 2022-02-15 | 348857.6 |  | -2.817% | Not Applicable
884 | 0PT42080 -- DFW C EAST - DFW B EAST 138 KV LINE: PUMPING PLANT REPLACEMENT | Not Applicable | 981132 | 2021-12-15 | 964822.62 |  | -1.662% | Not Applicable
885 | 0PT41807 -- METEOR SWITCH: ESTABLISH 345 KV RING BUS STATION TO PROVIDE POI FOR GREYHOUND SOLAR | Not Applicable | 10779415.5 | 2022-05-15 | 9818322.22 |  | -8.916% | Not Applicable
886 | 0PT41741 -- WALLABY SWITCH : INSTALL THREE 345 KV, 3200 A CIRCUIT BREAKERS IN A RING BUS CONFIGURATION | Not Applicable | 6839311.35 | 2021-06-15 | 8333647.62 |  | 21.85% | Variance is due to a change in project scope and increased material and labor costs. Scope of work was modified to include the addition of an SSVT, communications equipment, and relocation of a breaker to provide continuity to generator during line terminal addition, which increased material and labor costs. Project was placed on hold for approximately 19 months due to delays in the customer's schedule. During that time, material prices and labor rates increased.
887 | 0PT41706 -- RED SAND POD : ESTABLISH 138KV POINT OF DELIVERY | Not Applicable | 1133424 | 2022-05-15 | 1037245.18 |  | -8.486% | Not Applicable
888 | 0PT41468 -- FORT SMITH SWITCH : ESTABLISH 345KV RING BUS STATION FOR POINT-OF-INTERCONNECTION (POI) FILES SOLAR | Not Applicable | 7159942 | 2022-01-15 | 7384844.46 |  | 3.141% | Not Applicable
889 | 0PT41321 -- ROWAN CREEK SWITCH : ESTABLISH 138KV STATION FOR POI FOR AZALEA SPRINGS SOLAR (AZALEA SPRINGS PARK SOLAR, LLC) | Not Applicable | 6578329.42 | 2023-10-15 | 5922121.95 |  | -9.975% | Not Applicable
890 | 0PT41261 -- COW BAYOU SWITCH : ESTABLISH A 138KV POI 4-BREAKER RING BUS SWITCHYARD | Not Applicable | 5992225 | 2021-08-15 | 5677246.44 |  | -5.256% | Not Applicable
891 | 0PT41229 -- BELL MOUNTAIN (FORMERLY HUDSON OAKS) SUB : ESTABLISH SUBSTATION WITH ONE 138-25 KV, 47 MVA TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable | 6859188 | 2021-05-15 | 7060492.04 |  | 2.935% | Not Applicable
892 | 0PT41220 -- WOLF SWITCH: 138 KV LINE TERMINAL ADDITION TO TNMP | Not Applicable | 981337 | 2021-07-15 | 1098089.53 |  | 11.9% | Variance is due to a change in project scope and increased material and labor costs. Scope change added the installation of a new 138 kV deadend structure, associated switches, high-voltage breaker and line relay equipment. Material costs increased due to price increases for structural steel, high-voltage circuit breakers, air switches, and relaying control equipment. Labor costs increased due to additional costs for 138 kV buswork installation; hand-digging for conduit, grounding, and foundation installations in close proximity to energized equipment; remobilization charges due to material delays; installation of the new deadend; additional hauling of equipment and materials; additional job site security; an extended construction schedule; and additional protection and control resources to meet the in-service date.
893 | 0PT41016 -- DUVAL SUB: REMOVE 69 KV STATION AND ESTABLISH 138-12.5 KV STATION | Not Applicable | 8309347 | 2020-10-15 | 11093104.55 |  | 33.5% | Variance is due to a change in project scope and increased material and labor costs. Scope of work expanded to include environmental controls with the addition of Leaker Management and Secondary containment systems and to upgrade existing backhaul communications. Labor costs increased due to additional grading costs for additional erosion control and a retaining wall. Material costs increased due to price increases for structural steel, power transformers, and control centers.
894 | 0PT40880 -- RUSSELL GAP SWITCH : ESTABLISH 3 BREAKER RING POI STATION | Not Applicable | 8089374 | 2022-02-15 | 7849144.5 |  | -2.97% | Not Applicable
895 | 0PT40876 -- SL TRIANGLE SUB : INSTALL 138 KV-12.47 KV 47 MVA TRANSFORMER #2 | Not Applicable | 3625120 | 2019-11-15 | 4078826.98 |  | 12.52% | Variance is due to a change in project scope and increased material and labor costs. The scope expanded to include the rebuild of a high-voltage bus to accommodate a 3200 A rating for another project. This added material and labor costs not accounted for in the original estimate. Material costs also increased due to price increases for structural steel, power transformers, switches, and interrupters.
896 | 0PT40650 -- MANNING POD: ESTABLISH A 138 KV POINT OF DELIVERY (POD) FOR CONCHO'S PEGASUS SUB | Not Applicable | 922339 | 2020-02-15 | 1201712.77 |  | 30.29% | Variance is due to increased labor costs. Construction schedules were longer than anticipated and multiple remobilizations were necessary due to delays related to coordination and construction sequencing with the neighboring utility that was constructing the switching station that would feed this project.
897 | 0PT40648 -- DILLON POD : ESTABLISH 138KV POINT OF DELIVERY DIAMONDBACK CATS | Not Applicable | 764363 | 2020-05-15 | 775141.54 |  | 1.41% | Not Applicable
898 | 0PT40611 -- GRAHAM 345KV SWITCH : AUTO PROTECTION UPGRADE | Not Applicable | 1180134 | 2020-05-15 | 1590426.1 |  | 34.77% | Variance is due to increased labor costs for engineering resources needed to update record drawings to match existing conditions before design work could be finished and additional construction labor that was also required due to poor soil conditions that were encountered during conduit installs.
899 | 0PT40561 -- BIRTHRIGHT SWITCH: ESTABLISH 345 KV 3 BREAKER RING BUS STATION FOR HOPKINS SOLAR | Not Applicable | 6648534 | 2021-05-15 | 7710780.96 |  | 15.98% | Variance is due to a change in project scope and increased material and labor costs. Breaker platforms were added to the project scope to increase worker safety, which increased material and labor costs. Labor costs also increased due to additional grading work, customer delays that extended the construction timeline, and increased construction rates when construction resumed.
900 | 0PT40560 -- FOUR BROTHERS SWITCH : ESTABLISH 3-BREAKER SWITCHING STATION IN A 345 KV RING-BUS ARRANGEMENT FOR INTERCONNECT THE NEW SUN VALLEY SOLAR AND MODIFY RELAYING AT TRADING HOUSE SWITCH FOR THIS STATION | Not Applicable | 6227825 | 2020-10-15 | 5874134.52 |  | -5.679% | Not Applicable
901 | 0PT40543 -- GRAHAM PLANT SWITCH : BUS PROTECTION UPGRADE SCOPE | Not Applicable | 1438785 | 2020-05-15 | 2021646.62 |  | 40.51% | Variance is due to a change in project scope. Installation of three additional capacitor coupled voltage transformers and replacement of a remote terminal unit were added to the scope of work due to a change to the generator’s relaying. These additions resulted in a longer construction schedule and additional material and labor costs.
902 | 0PT40396 -- SAM SWITCH - TRADINGHOUSE SWITCH 345 KV LINE: LINE MODIFICATION TO CONNECT FOUR BROTHERS SWITCH FOR SUN VALLEY SOLAR INTERCONNECT | Not Applicable | 1788914 | 2021-02-15 | 1633748.95 |  | -8.674% | Not Applicable
903 | 0PT40273 -- BROWN SWITCH: PROVIDE A 345 KV POI TO IP RADIAN SOLAR | Not Applicable | 3668033 | 2021-06-15 | 4453112.24 |  | 21.4% | Variance is due to a change in project scope to add redundant breaker failure protection for the generation interconnection.
904 | 0PT40247 -- EPDC SUB - SOUTH MAIN TERMINAL SUB 138 KV LINE : REPLACE TERMINATIONS & REBUILD CATHODIC PROTECTION SYSTEM | Not Applicable | 738236 | 2022-07-15 | 644973.97 |  | -12.63% | Not Applicable
905 | 0PT40139 -- ASH CREEK SWITCH : ESTABLISH 138 KV STATION FOR POINT-OF-INTERCONNECTION (POI) FOR PITTS DUDIK SOLAR | Not Applicable | 4320758 | 2022-02-15 | 4250893.92 |  | -1.617% | Not Applicable
906 | 0PT39833 -- LCRA CRANE – CRANE EAST 138 KV LINE : HAZEL POD FOR CONCHO CHICKADEE NEAL VIA LCRA MOTORMAN SWITCH | Not Applicable | 792076 | 2020-03-15 | 683104.76 |  | -13.76% | Not Applicable
907 | 0PT39816 -- STANTON EAST SWITCH - SPRABERRY SWITCH 69 KV LINE : CMPC LINE HARDENING (STR. 40/7 - 40/9) | Not Applicable | 1191328 | 2021-12-15 | 855660.65 |  | -28.18% | Not Applicable
908 | 0PT39492 -- RICHARDSON SUB : UPGRADE LINE TERMINAL TO 3200 A AS A PART OF UPGRADING THE PLANO WEST SWITCH - RICHARDSON COLLINS 138 KV LINE | Not Applicable | 956152 | 2021-04-15 | 1125057.15 |  | 17.67% | Variance is due to a change in project scope and increased material and labor costs. Material costs increased due to price increases for structural steel, air switches, and relaying control equipment. Labor costs increased due to the need for additional demolition and installation for relaying equipment; unexpected costs for transformer leaker and oil containment system modifications; and the need for additional protection and control contractor resources to meet the in-service date.
909 | 0PT39491 -- WEST PLANO SUB : UPGRADE LINE TERMINAL TO 3200 A AS A PART OF UPGRADING THE PLANO WEST SUB - RICHARDSON 138 KV | Not Applicable | 275909 | 2021-11-15 | 503076.85 |  | 82.33% | Variance is due to increased material and labor costs. Labor costs increased due to tight-turnaround outage times due to bus outages on a connected customer line. Additional material and labor was also needed to interface with the non-standard, older steel line terminal equipment
910 | 0PT39309 -- SYCAMORE CREEK SUB : INSTALL TRANSFORMER #4 WITH TWO FEEDER BREAKERS AND TWO FEEDER BREAKERS ON TRANSFORMER #3 | Not Applicable | 2988557 | 2021-07-15 | 5178290.89 |  | 73.27% | Variance is due to a change in project scope and increased material and labor costs. The scope was expanded to include the connection of all 4 transformers to increase reliability, which extended the project schedule. Labor costs increased due to the need for two additional months of security and because hand-digging was required to install conduits near energized equipment. Material costs increased due to the need for additional equipment to accommodate the scope change, and additional costs were incurred to transport the additional equipment.
911 | 0PT39029 -- HURST - BELL 138 KV LINE: BELL HELICOPTER POD | Not Applicable | 729841 | 2022-06-15 | 608443.9 |  | -16.63% | Not Applicable
912 | 0PT04329 -- LINE WORK TO INSTALL A 138 KV POINT-OF-INTERCONNECTION (POI) FOR CUSTOMER'S GENERATOR (CANYON WIND) | Not Applicable | 1483494 | 2019-07-15 | 885907.43 |  | -40.28% | Not Applicable
913 | 0PT04143 -- MILLERS FERRY SUBSTATION: INSTALL A 138-24.9KV 46.7MVA TRANSFORMER WITH 2 FEEDER BREAKERS ON BANK #3 | Not Applicable | 2127772 | 2021-08-15 | 1730895.54 |  | -18.65% | Not Applicable
914 | 0PT03987 -- MORRISON LANE SWITCH: UPGRADE ALL LINE TERMINAL AND ASSOCIATED EQUIPMENT TO MEET OR EXCEED 3000 A | Not Applicable | 486520 | 2020-12-15 | 466004.09 |  | -4.217% | Not Applicable
915 | 0PT03981 -- SHERRY SWITCH: TWO LINE TERMINAL UPGRADE | Not Applicable | 406246 | 2019-11-15 | 505314.91 |  | 24.39% | Variance is due to a change in project scope and increased material and labor costs. Scope was modified to upgrade the existing bus differential relay controls and convert existing communications to fiber. Material costs increased due to price increases for structural steel, air switches, relay equipment, and communication equipment. Labor costs increased due to the need to relocate surge arrestors for safety purposes; additional demolition work; upgrades to existing buswork; work near energized equipment that required hand-digging; remobilization charges due to ERCOT clearance coordination; additional hauling of equipment and materials; additional job site security; and an extended construction schedule. Additional protection and control resources were required to meet the required project in-service date.
916 | 0PT03978 -- HANDLEY SWITCH: UPGRADE LINE TERMINAL AND ASSOCIATED EQUIPMENT TO MEET OR EXCEED 3200 A | Not Applicable | 580434 | 2020-10-15 | 776836.49 |  | 33.84% | Variance is due to a change in project scope and increased material and labor costs. The original project was to upgrade two 138 kV line terminals. The scope change included upgrading the bus differential relaying controls and converting the existing communications to fiber. Material costs increased due to price increases for structural steel, air switches, relaying equipment, and communication equipment. Labor costs increased due to additional demolition work; upgrades to existing buswork; hand-digging for conduit, grounding, and foundations in close proximity to energized equipment; remobilization charges due to ERCOT clearance coordination; additional hauling of equipment and materials; and additional job site security. Additional protection and control resources were required to meet the in-service date.
917 | 0PT02811 -- DUNCANVILLE SUB: UPGRADE ALL LINE TERMINAL AND ASSOCIATED EQUIPMENT TO MEET OR EXCEED 2000 A | Not Applicable | 954401 | 2021-05-15 | 1492315.72 |  | 56.36% | Variance is due to a change in project scope to include replacement of two fault interrupting devices. Additionally, new relay panels were included to protect the transformer and fault interrupting devices.
918 | 0PT02808 -- CEDAR HILL SWITCH 138 KV LINE - CAMP WISDOM 138 KV LINE: REBUILD CEDAR HILL SWITCH - LOVE BIRD TAP SECTION | Not Applicable | 8189827 | 2021-09-15 | 11392811.03 |  | 39.11% | Cost Variance was due to a significant change of scope at the request of the City of Duncanville to relocate approximately a third of the line section's rebuild into the roadway median. Additional steel pole deadends were needed for construction sequencing and transitioning into median along with significant additional SUE investigations to avoid existing city facilities already in the median. Additionally, Helicopter use work was needed for the Cedar Hill Switch area of the project due access and terrain limitations.
919 | 0PT00208 -- BLACKLAND SWITCH - TERRELL SWITCH 138 KV LINE: ESTABLISH LAWRENCE SUBSTATION | Not Applicable | 1077026 | 2022-07-15 | 947735.92 |  | -12% | Not Applicable
920 | 0PT50868 -- LAWTHER DRIVE SUB : REPLACE 138KV SWITCHES 014 AND 024 | Not Applicable | 315235.3 | 2025-01-15 | 316650.91 |  | 0.4491% | Not Applicable
921 | 0PT51141 -- KRUM TAP SWITCH - SPRING (BEPC) 138 KV LINE: ESTABLISH GRAIN BELT SUBSTATION (FKA MASCH BRANCH SUBSTATION) | Not Applicable | 2287057 | 2024-03-15 | 1220355.3 |  | -46.64% | Not Applicable
922 | 0PT54430 -- CARMELITE SUB: PURCHASE OF ADDITIONAL PROPERTY IN FEE TITLE | Not Applicable | 11144471.85 | 2024-07-15 | 486165.06 |  | -95.64% | Not Applicable
| 0PT50256 -- CARMELITE SUB (BUFFALO SUB REBUILD) ACQUIRE STATION IN FEE TITLE |  |  | 2024-07-15
923 | 0PT53475 -- WACO M&M MARS TAP 2 SWITCH - WACO M&M MARS SWITCH 138 KV LINE: REPLACEMENT OF STRUCTURES 3/7 AND 1/1 | Not Applicable | 1146667.21 | 2024-06-15 | 624530.76 |  | -45.54% | Not Applicable
924 | 0PT51806 -- WINK - QUARRY FIELD SW 138 KV LINE: LINE WORK TO ESTABLISH BLUE MOUNTAIN SWITCH | Not Applicable | 2170788.01 | 2024-03-15 | 1266228.57 |  | -41.67% | Not Applicable
925 | 0PT55498 -- DELEON MAGNOLIA TAP TO OLIVE SPRING POD 69 KV LINE: REPLACING FAILED POLES AND INSULATORS ON STRUCTURES 1/2, 1/6, 1/7, 1/10, 1/17, 1/19, 2/4, 2/6, 2/7, 3/7, 3/11, 3/13, 3/15, 3/17, 3/18, 4/1, 4/2 (BL24) | Not Applicable | 272418.56 | 2025-02-15 | 267325.11 |  | -1.87% | Not Applicable
926 | 0PT51872 -- KILLEEN SWITCH - KILLEEN CLARK ROAD POI 138 KV LINE : ESTABLISH FOUNDERS TRAIL SUBSTATION | Not Applicable | 1623415.48 | 2024-03-15 | 1409392.87 |  | -13.18% | Not Applicable
927 | 0PT51152 -- SALE RANCH SUB - NATURAL DAM SUB 138 KV LINE: CUT-IN TO ESTABLISH CALF TANK SUB | Not Applicable | 1197928.74 | 2024-05-15 | 999189.68 |  | -16.59% | Not Applicable
928 | 0PT52594 -- ROSE HILL SWITCH - KAUFMANN NORTHWEST SWITCH 138 KV LINE : CLEARANCE IMPROVEMENT | Not Applicable | 568769 | 2024-05-15 | 770408.17 |  | 35.45% | Variance is due to a poor soil conditions and a greater number of mats being required for access than were estimated after heavy rainfall during construction.
929 | 0PT55175 -- RIVERCREST SWITCH, BKR 2920, SWT 2922, SULPHUR SPRINGS, BKR 2580, MONTICELLO SWITCH, BKR 3770, SWT 3767, 138KV : REPLACE (7) POLES, (15) CROSS ARMS - (PATROL BACK LOG) (BL24) | Not Applicable | 370122 | 2025-02-15 | 379486.74 |  | 2.53% | Not Applicable
930 | 0PT51298 -- PEPPER CREEK SWITCH - EBERHARDT SUBSTATION 138 KV LINE: CONSTRUCT NEW LINE | Not Applicable | 792923.22 | 2024-06-15 | 455176.69 |  | -42.6% | Not Applicable
931 | 0PT50807 -- EBERHARDT SUB (FORMERLY INDUSTRIAL SUB): ESTABLISH STATION WITH ONE TRANSFORMER | Not Applicable | 6957085.81 | 2024-03-15 | 5815696.35 |  | -16.41% | Not Applicable
932 | 0PT53560 -- LIGGETT SWITCH : INSTALL FIBER OPTIC CABLE | Not Applicable | 350435.75 | 2024-03-15 | 336321.36 |  | -4.028% | Not Applicable
933 | 0PT55642 -- BELL COUNTY SWITCH - GABRIEL SUB 138 KV LINE : REPLACE POLES AND ARMS (BL24) | Not Applicable | 299888.67 | 2025-02-15 | 332784.44 |  | 10.97% | Variance is a result of an estimation error. The original estimate was written for only the cost of labor to replace each structure. It did not include Field Construction Coordinator labor, equipment rentals, per diem, or overtime cost.
934 | 0PT53697 -- STRYKER CREEK SWITCH - PALESTINE SOUTH SUB 138 KV LINE : REPLACING DEFICIENT POLES, CROSSARMS, AND INSULATOR STRINGS (2024) (BL24) | Not Applicable | 335290.72 | 2025-02-15 | 322839.07 |  | -3.714% | Not Applicable
935 | 0PT44614 -- DFW SOUTHWEST - EULESS 138 KV: CUT-IN TO DFW MID CITIES SUB | Not Applicable | 2263392 | 2024-04-15 | 1341179.23 |  | -40.74% | Not Applicable
| 0PT54874 -- LIGGETT SWITCH - EULESS SUB 138 KV LINE : LINE WORK FOR DFW MID CITIES CUT-IN |  |  | 2024-04-15
936 | 0PT51584 -- HAGGERTY SWITCH - VALLEY SWITCH 138 KV LINE: LINE WORK TO ESTABLISH PROGRESS PARK SWITCH FOR GLOBAL WAFERS | Not Applicable | 3174902 | 2024-05-15 | 2811197.17 |  | -11.46% | Not Applicable
937 | 0PT51129 -- BUTTON SUB (FKA NOLANVILLE SUB) - PURCHASE LAND IN FEE TITLE | Not Applicable | 8946156.92 | 2024-09-15 | 658684.15 |  | -92.64% | Not Applicable
938 | 0PT55449 -- SL DRIVER - CANAL ROAD 138KV LINE: CUT IN TO ESTABLISH SAVANNA SUB | Not Applicable | 292463.69 | 2024-08-15 | 282679.55 |  | -3.345% | Not Applicable
939 | 0PT53999 -- ATHENS SWITCH - JACKSONVILLE SWITCH 69 KV LINE : REPLACE POLES AND ARMS (BL24) | Not Applicable | 482666.03 | 2025-02-15 | 460401.19 |  | -4.613% | Not Applicable
940 | 0PT50038 -- WAXAHACHIE NORTH SUB EXPANSION: PURCHASE OF LAND IN FEE | Not Applicable | 12328377.83 | 2024-09-15 | 963042.2 |  | -92.19% | Not Applicable
941 | 0PT53125 -- TREDWAY SWITCH (FKA NEW VEALMOOR SWITCH): ACQUIRE PROPERTY IN FEE TITLE | Not Applicable | 15067477.55 | 2024-07-15 | 1889386.27 |  | -87.46% | Not Applicable
942 | 0PT55248 -- WEATHERFORD SWITCH - SPRINGTOWN SUB 138 KV LINE : REPLACE COMPLETE STRUCTURES, CROSSARMS, AND INSULATORS ON MULTIPLE FRAMES (#BL24) (HOT WORK, RADIAL LINE) | Not Applicable | 299708 | 2025-02-15 | 300672.96 |  | 0.322% | Not Applicable
943 | 0PT55551 -- HUTTO SWITCH BKR 7500/7505 SWITCH - GEORGETOWN SOUTH BKR 27420/27430 SWITCH 138 KV LINE : REPLACE VARIOUS POLES, ARMS & INSULATORS (BL24) | Not Applicable | 368078.52 | 2025-02-15 | 374645.02 |  | 1.784% | Not Applicable
944 | 0PT50812 -- FOUNDERS TRAIL SUB: ESTABLISH STATION WITH TWO TRANSFORMERS | Not Applicable | 10780754.85 | 2024-03-15 | 8261122.22 |  | -23.37% | Not Applicable
945 | 0PT52127 -- PLANO WEST SWITCH - RICHARDSON EAST SUB 138 KV LINE : REPLACE STRUCTURE 4/1 | Not Applicable | 1416322.82 | 2024-03-15 | 1149782.72 |  | -18.82% | Not Applicable
946 | 0PT52025 -- LIGGETT SWITCH - NORWOOD SWITCH 345 KV LINE : RELOCATE STRUCTURE 2/1, 2/2, AND 6/4 DUE TO EROSION ISSUES | Not Applicable | 3720964 | 2024-04-15 | 2493818.25 |  | -32.98% | Not Applicable
947 | 0PT53865 -- JEWETT SWITCH - WORTHAM GULF PUMP 69 KV LINE: REPLACE POLES, CROSSARMS, AND INSULATORS ENERGIZED - CONTRACTOR (2024)(BL24) | Not Applicable | 419117.33 | 2025-02-15 | 392074.66 |  | -6.452% | Not Applicable
948 | 0PT50981 -- PEPPERVINE SWITCH - TEMPLE ELM CREEK SWITCH 138 KV LINE : CUT-IN TO ESTABLISH CENTRAL PARK SWITCH | Not Applicable | 4094060.84 | 2024-06-15 | 3417676.55 |  | -16.52% | Not Applicable
949 | 0PT53065 -- PEPPER CREEK SWITCH - META 1 SUBSTATION 138 KV LINE: INSTALL POD FOR META 1 SUBSTATION | Not Applicable | 2583328.2 | 2024-05-15 | 1203547.99 |  | -53.41% | Not Applicable
950 | 0PT50426 -- GREENVILLE AVENUE SWITCH - MATILDA SUB 138 KV LINE : REPLACE U.G TERMINATIONS | Not Applicable | 1650306 | 2024-03-15 | 1522122.82 |  | -7.767% | Not Applicable
951 | 0PT51216 -- DEEN SWITCH - EULESS SWITCH 138 KV LINE : REPLACE STRUCTURES 5/3 & 5/4 | Not Applicable | 1209901.87 | 2024-04-15 | 632787.03 |  | -47.7% | Not Applicable
952 | 0PT55569 -- LEON SWITCH TO DUBLIN 69KV LINE: REPLACE POLES, INSULATORS AND CROSSARMS ON VARIOUS STRUCTURES (BL24) | Not Applicable | 1405599.94 | 2025-02-15 | 1379254.24 |  | -1.874% | Not Applicable
953 | 0PT55570 -- TEMPLE SWITCH - MINERVA SWITCH 69 KV LINE : REPLACE VARIOUS POLES, ARMS & INSULATORS (BL24) | Not Applicable | 672604.74 | 2025-02-15 | 698575.4 |  | 3.861% | Not Applicable
954 | 0PT55277 -- HANDLEY 138 SWITCH - EVERMAN SWITCH 138 KV LINE : REPLACE MULTIPLE STRUCTURES ON LINE. (BL24) | Not Applicable | 325207.81 | 2025-01-15 | 307756.68 |  | -5.366% | Not Applicable
955 | 0PT51788 -- SANDOW SWITCH - AUSTROP SWITCH 345 KV LINE : LINE WORK TO ESTABLISH BEULAH SWITCH | Not Applicable | 2863348.35 | 2024-03-15 | 1804390.32 |  | -36.98% | Not Applicable
956 | 0PT52050 -- BELFALLS SWITCH - LAKE CREEK SWITCH 345 KV LINE : LINE WORK TO ESTABLISH STEAKLEY DAM SWITCH 345 KV | Not Applicable | 3211361.02 | 2024-03-15 | 3031018.42 |  | -5.616% | Not Applicable
957 | 0PT51237 -- ORAN SWITCH - RW MILLER - MINERAL WELLS SUB 138 KV LINE : CLEARANCE IMPROVEMENT | Not Applicable | 623457.23 | 2024-05-15 | 628666.31 |  | 0.8355% | Not Applicable
958 | 0PT55462 -- HUNTINGTON SUB - ETOILE/ZAVALLA PUMP 138KV IDLE LINE: REPLACE CROSSARMS AND POLES (GLT) (BL24) | Not Applicable | 246446.86 | 2025-02-15 | 252329.72 |  | 2.387% | Not Applicable
959 | 0PT51631 -- PRONG MOSS SWITCH (FKA FALCON SEABOARD SWITCH) - PURCHASE OF LAND IN FEE | Not Applicable | Not Applicable | 2024-11-15 | 949088.03 |  | Not Applicable | Not Applicable
| 0PT48587 -- PRONG MOSS SWITCH (FKA FALCON SEABOARD SWITCH) - PURCHASE OF ROAD ACCESS EASEMENT |  |  | 2024-11-15
960 | 0PT55609 -- PEPPERVINE SWITCH - TEMPLE ELM CREEK SWITCH 138 KV LINE : REPLACE POLES, INSULATORS, CROSS ARMS AND X-BRACES ON MULTIPLE STRUCTURES (BL24) | Not Applicable | 638728.23 | 2025-02-15 | 649663.86 |  | 1.712% | Not Applicable
961 | 0PT47301 -- GRINDSTONE SWITCH (ORAN SWITCH STATION REBUILD) - PURCHASE LAND IN EASEMENT | Not Applicable | 12439612.26 | 2024-06-15 | 425779.8 |  | -96.58% | Not Applicable
962 | 0PT51927 -- BELL COUNTY EAST SWITCH - LITTLE POND SWITCH 345 KV LINE : LINE WORK TO ESTABLISH GINDALE SWITCH 345 KV SWITCH | Not Applicable | 6012310.41 | 2024-03-15 | 6090667.63 |  | 1.303% | Not Applicable
963 | 0PT54210 -- JEWETT-RIESEL 138KV LINE: REPLACING POLES, CROSSARM AND INSULATORS (BL24) | Not Applicable | 488691.97 | 2025-01-15 | 477940.78 |  | -2.2% | Not Applicable
964 | 0PT55467 -- TYLER SWITCH - CANTON SWITCH 138 KV LINE : REPLACE POLES AND INSULATORS (BL24) | Not Applicable | 321287.36 | 2025-01-25 | 324492.93 |  | 0.9977% | Not Applicable
965 | 0PT52098 -- DENISON NORTH SUB : UPGRADE TRANSFORMER #1 AND #2 RELAYING AND CONVERT CELL COMMUNICATION | Not Applicable | 537637.6 | 2024-03-15 | 484073.84 |  | -9.963% | Not Applicable
966 | 0PT54016 -- STRYKER CREEK SWITCH - ELKTON SWITCH 138 KV LINE : REPLACE POLES, ARMS, AND INSULATORS (BL24) | Not Applicable | 253787.85 | 2024-11-15 | 251117.99 |  | -1.052% | Not Applicable
967 | 0PT55553 -- JEWETT SWITCH - PALESTINE SOUTH SWITCH 138 KV LINE : REPLACE POLES, CROSSARMS AND INSULATORS CONTRACTOR (2024) (BL24) | Not Applicable | 496847 | 2025-02-15 | 571917.03 |  | 15.11% | Variance is due to a change in project scope that increased material and labor costs and an estimation error. Maintenance on 3 additional structures was added to the scope of work. The initial estimate also did not estimate costs for contractor resource labor, materials, ROW access, or project cleanup.
968 | 0PT54898 -- TEX HARVEY SUB : UPGRADE THE EXISTING 138 KV, 55.2 MVAR CAPACITOR BANK | Not Applicable | 671822.91 | 2024-07-15 | 611351.29 |  | -9.001% | Not Applicable
969 | 0PT56921 -- KILLEEN SWITCH - KILLEEN FORT HOOD SUB 138 KV LINE : REPLACE POLES, INSULATORS, CROSSARMS AND X-BRACES (BL24) | Not Applicable | 714832 | 2025-02-15 | 714149.22 |  | -0.09552% | Not Applicable
970 | 0PT50093 -- CHICO WEST - ORAN 69KV LINE: RELOCATE TO ACCOMMODATE JUNIPER SUB | Not Applicable | 541329.49 | 2024-06-15 | 436540.51 |  | -19.36% | Not Applicable
971 | 0PT55416 -- SHAMBURGER SWITCH - BLACK FORK SWITCH 138 KV LINE : REPLACE POLES, CROSSARMS AND INSULATORS (BL24) | Not Applicable | 593317.67 | 2024-11-15 | 605170.4 |  | 1.998% | Not Applicable
972 | 0PT50979 -- CENTRAL PARK SWITCH: ESTABLISH 138 KV STATION FOR GRAPHIC PACKAGING INTERNATIONAL, LLC | Not Applicable | 7283442.68 | 2024-02-15 | 5255908.83 |  | -27.84% | Not Applicable
973 | 0PT48311 -- HAGGERTY SWITCH - TI SM1-2 138 KV LINE: BUILD | Not Applicable | 2025804 | 2022-09-15 | 1818466.98 |  | -10.23% | Not Applicable
974 | 0PT54280 -- PLANO SHILOH SUB : ADD TRANSFORMER #4 AND 2 FEEDER BREAKERS | Not Applicable | 987902.67 | 2024-05-15 | 651088.96 |  | -34.09% | Not Applicable
975 | 0PT42965 -- VENUS SW - GERDAU SW 138 KV LINE: INSTALL CHANGE OF OWNERSHIP POINT FOR FURNACE B CIRCUIT | Not Applicable | 479147 | 2021-04-15 | 379005.73 |  | -20.9% | Not Applicable
976 | 0PT50100 -- JUDKINS SUB : INSTALL FEEDER FOR DISTRIBUTED ENERGY STORAGE RESOURCE (DESR) | Not Applicable | 522194.67 | 2023-03-15 | 389114.58 |  | -25.48% | Not Applicable
977 | 0PT55245 -- BONHAM SW-TOCO SW 69KV LINE: REPLACE (9) POLES, CROSSARMS AND INSULATORS (BL24 SPEND) | Not Applicable | 522811.32 | 2025-03-15 | 406245.04 |  | -22.3% | Not Applicable
978 | 0PT46594 -- RIVERCREST SWITCH - CLARKSVILLE SWITCH 69 KV LINE : AGING INFRASTRUCTURE REPLACEMENT | Not Applicable | 4979413 | 2022-03-15 | 6982805.06 |  | 40.23% | The variance is due to changes in the scope of the project and associated increases in material and labor costs. The existing concrete and wood H-frame switch structures had a non-standard switch configuration that limited switching capabilities and created maintenance issues for district personnel. Oncor replaced the switch structures with Oncor’s standard steel H-frame switch structure and corresponding road crossing structures to improve reliability and sectionalizing capabilities. The scope changes include altering the structures at two additional locations due to supply constraints; installing temporary bypasses at both POI locations to keep the customers energized during construction; refurbishing several additional H-frame structures, switches, and platforms that required adjustment, replumbing, or replacement; additional road work to access the stations; additional matting to access sections of the right-of-way due to sustained rainy conditions; and repairing roads near the POI locations that were damaged by the heavy equipment required to complete the POI upgrades. Material costs increased with the expanded scope of work, including additional costs for alternate structures and temporary bypasses. Labor costs also increased with the expanded scope of work, including foundation unit increases to support the structure changes; additional costs for hot work to install the temporary bypasses; increased Field Construction Coordinator costs after the project extended into a second construction season due to weather and material delays; increased right-of-way agent costs due to the scope changes and extended construction schedule, which required additional coordination with landowners; and additional grading costs to regrade the roads that were damaged during construction.
979 | 0PT44564 -- VENUS SWITCH STA. - CEDAR HILL 138KV LINE: PADERA SUB CUT IN | Not Applicable | 1271660.48 | 2022-10-15 | 1184032.58 |  | -6.891% | Not Applicable
980 | 0PT55423 -- TYLER GRANDE SWITCH - OVERTON SUB 138 KV LINE : REPLACES POLES, ARMS AND INSULATORS (BL24) | Not Applicable | 408253 | 2024-12-15 | 398405.65 |  | -2.412% | Not Applicable
981 | 0PT55202 -- RIVERCREST SWITCH BKR 2930 AND SWT 2932 - HAWK HOLLOW SWITCH BKKR 20920 AND BKR 20925 138KV : REPLACE (19) POLES, (16) CROSS ARMS & INSULATORS (PATROL BACK LOG) (BL24) | Not Applicable | 322095.16 | 2024-12-15 | 325367.86 |  | 1.016% | Not Applicable
982 | 0PT55246 -- HILLTOP SWITCH - WEATHERFORD WEST SWITCH 69 KV LINE : REPLACE DEFICIENCIES ON MULTIPLE STRUCTURES (#BL24) | Not Applicable | 307472.73 | 2024-12-15 | 270387.29 |  | -12.06% | Not Applicable
983 | 0PT53460 -- LAWNDALE SUBSTATION (FKA MABANK SUBSTATION EXPANSION) - PURCHASE OF PROPERTY IN FEE TITLE | Not Applicable | Not Applicable | 2024-11-15 | 873454.94 | Not Applicable | Not Applicable | Not Applicable
984 | 0PT47786 -- HARRIS CREEK SUB : ESTABLISH ONE 47 MVA 138-25 KV SUBSTATION, REPLACES FAILED MCGREGOR SUB | Not Applicable | Not Applicable | 2023-02-15 | 3876350.84 | Not Applicable | Not Applicable | Not Applicable
985 | 0PT52262 -- HUTCHINS SUB : INSTALL SETTLEMENT ONLY DISTRIBUTION GENERATOR (SODG) ON FEEDER #1502 | Not Applicable | Not Applicable | Not Applicable | 432717.21 | Not Applicable | Not Applicable | Not Applicable
986 | 0PT46129 -- ELKTON SUB : INSTALL DG ON FEEDER #2503 | Not Applicable | Not Applicable | Not Applicable | 288418.68 | Not Applicable | Not Applicable | Not Applicable
987 | 0PT47885 -- MOORES MILL SUB: INSTALL DG ON FEEDER #3912 AND INSTALL ONE 12.5 KV FEEDER BREAKER ON BANK #2 | Not Applicable | Not Applicable | Not Applicable | 355228.73 | Not Applicable | Not Applicable | Not Applicable
988 | 0PT48748 -- MIDWAY SUB : INSTALL FEEDER FOR DISTRIBUTED ENERGY STORAGE RESOURCE (DESR) | Not Applicable | Not Applicable | Not Applicable | 433311.15 | Not Applicable | Not Applicable | Not Applicable
989 | 0PT49617 -- SIMPSON STUART SUB: INSTALL SODG ON FEEDER #006 | Not Applicable | Not Applicable | Not Applicable | 281684.92 | Not Applicable | Not Applicable | Not Applicable
990 | 0PT49892 -- MINERAL WELLS EAST SUB : INSTALL FEEDER FOR DISTRIBUTED ENERGY STORAGE RESOURCE (DESR) | Not Applicable | Not Applicable | Not Applicable | 358633.13 | Not Applicable | Not Applicable | Not Applicable
991 | 0PT49893 -- GARDEN CITY EAST SUB : INSTALL FEEDER FOR DISTRIBUTED ENERGY STORAGE RESOURCE (DESR) | Not Applicable | Not Applicable | Not Applicable | 499542.55 | Not Applicable | Not Applicable | Not Applicable
992 | 0PT50098 -- PAULINE SUB : INSTALL FEEDER FOR DISTRIBUTED ENERGY STORAGE RESOURCE (DESR) | Not Applicable | Not Applicable | Not Applicable | 369373.16 | Not Applicable | Not Applicable | Not Applicable
993 | 0PT51365 -- LUFKIN SOUTH SUB : INSTALL FEEDER FOR DISTRIBUTED ENERGY STORAGE RESOURCE (DESR) | Not Applicable | Not Applicable | Not Applicable | 387821.86 | Not Applicable | Not Applicable | Not Applicable
994 | 0PT51537 -- RECORD CROSSING SUB: INSTALL SETTLEMENT ONLY DISTRIBUTION GENERATOR (SODG) ON FEEDER #002 | Not Applicable | Not Applicable | Not Applicable | 358358.41 | Not Applicable | Not Applicable | Not Applicable
995 | 0PT40025 -- CARROLLTON JOSEY LANE SUB : INSTALL DISTRIBUTION AUTOMATION ON FEEDERS 1501 1503 1506 | Not Applicable | Not Applicable | Not Applicable | 681407.28 | Not Applicable | Not Applicable | Not Applicable
996 | 0PT43795 -- TEMPLE TAYLORS VALLEY SUB : RELAY UPGRADE ON FEEDER 2404 FOR DA AND FEEDER 2405 | Not Applicable | Not Applicable | Not Applicable | 534328.69 | Not Applicable | Not Applicable | Not Applicable
997 | 0PT46451 -- GRANDVIEW SUB 69KV: RELAY UPGRADE ON FEEDERS 1801 AND 1802 FOR DA | Not Applicable | Not Applicable | Not Applicable | 263411.8 | Not Applicable | Not Applicable | Not Applicable
998 | 0PT47470 -- LANCASTER SUB : UPGRADE SWITCH #600 TO 2000A | Not Applicable | Not Applicable | Not Applicable | 325544.14 | Not Applicable | Not Applicable | Not Applicable
999 | 0PT43794 -- TEMPLE SUB : RELAY UPGRADE ON FEEDERS 1201, 1204, 1205 AND 1206 FOR DA | Not Applicable | Not Applicable | Not Applicable | 575037.39 | Not Applicable | Not Applicable | Not Applicable
1000 | 0PT45790 -- CENTRAL EXPRESSWAY SUB : RELAY UPGRADE ON FEEDERS 0002, 0003, 0004, 0005, 0006 FOR DA | Not Applicable | Not Applicable | Not Applicable | 962454.57 | Not Applicable | Not Applicable | Not Applicable
1001 | 0PT48502 -- TOWNS MILL SWITCH (FKA HUTTO NORTH) : PURCHASE IN FEE | Not Applicable | Not Applicable | Not Applicable | 1401253.29 | Not Applicable | Not Applicable | Not Applicable
1002 | 0PT48904 -- KILLEEN ELMS RD SUB: RELAY UPGRADE ON FEEDERS 2202 FOR DA AND ON FEEDER 2204 | Not Applicable | Not Applicable | Not Applicable | 325918.5 | Not Applicable | Not Applicable | Not Applicable
1003 | 0PT43394 -- MCKINNEY SOUTHWEST SUB : RELAY UPGRADE ON FEEDER 0011, 1604, 2601, & 2602 | Not Applicable | Not Applicable | Not Applicable | 490214.72 | Not Applicable | Not Applicable | Not Applicable
1004 | 0PT44819 -- TEMPLE NORTH SUB : RELAY UPGRADE ON FEEDER 1605 FOR DA | Not Applicable | Not Applicable | Not Applicable | 308501.68 | Not Applicable | Not Applicable | Not Applicable
1005 | 0PT49966 -- MARIGOLD SUBSTATION ( FKA BAYLOR EAST ) : PURCHASE IN FEE | Not Applicable | Not Applicable | Not Applicable | 1257865.21 | Not Applicable | Not Applicable | Not Applicable
1006 | 0PT37930 -- MOCKINGBIRD: INSTALL DISTRIBUTION AUTOMATION ON FEEDERS 5331 | Not Applicable | Not Applicable | Not Applicable | 393275.6 | Not Applicable | Not Applicable | Not Applicable
1007 | 0PT43404 -- WACO COLONIAL AVENUE SUB : RELAY UPGRADE ON FEEDERS 1315 &1316 FOR DA AND ON FEEDERS 1317 | Not Applicable | Not Applicable | Not Applicable | 506116.66 | Not Applicable | Not Applicable | Not Applicable
1008 | 0PT43781 -- RICHARDSON EAST SUB : RELAY UPGRADE ON FEEDERS 1502 & 1505 FOR DA AND FEEDERS 1501, 1503 & 1507 | Not Applicable | Not Applicable | Not Applicable | 471631.57 | Not Applicable | Not Applicable | Not Applicable
1009 | 0PT50502 -- ROLATER ROAD SUB : RELAY UPGRADE ON FEEDER 2912 FOR DA | Not Applicable | Not Applicable | Not Applicable | 324314.34 | Not Applicable | Not Applicable | Not Applicable
1010 | 0PT47427 -- SKYVIEW SWITCH (FKA INTERNATIONAL AIRPORT): ACQUISITION OF EASEMENT | Not Applicable | Not Applicable | Not Applicable | 2061706.87 | Not Applicable | Not Applicable | Not Applicable
1011 | 0PT45773 -- LEMMON AVENUE SUB : RELAY UPGRADE ON FEEDERS 0001, 0006, 0008 FOR DA | Not Applicable | Not Applicable | Not Applicable | 742857.84 | Not Applicable | Not Applicable | Not Applicable
1012 | 0PT46273 -- PARIS NORTH SUB : RELAY UPGRADE ON FEEDER 1406 FOR DA AND ON FEEDERS 1402, 1403, 1404 & 1405 | Not Applicable | Not Applicable | Not Applicable | 740654.16 | Not Applicable | Not Applicable | Not Applicable
1013 | 0PT46478 -- WESTMORELAND NORTH SUB : RELAY UPGRADE ON FEEDER 0001 FOR DA AND ON FEEDERS 0003 AND 0004 | Not Applicable | Not Applicable | Not Applicable | 521550.43 | Not Applicable | Not Applicable | Not Applicable
1014 | 0PT43382 -- GORMAN SUB : RELAY UPGRADE ON FEEDERS 0411 & 0421 FOR DA | Not Applicable | Not Applicable | Not Applicable | 265537.42 | Not Applicable | Not Applicable | Not Applicable
1015 | 0PT43751 -- ELIZABETH CREEK SUB : RELAY UPGRADE ON FEEDER 4912 AND 4921 FOR DA | Not Applicable | Not Applicable | Not Applicable | 261467.24 | Not Applicable | Not Applicable | Not Applicable
1016 | 0PT49730 -- ROCKWALL SOUTH SUB : RELAY UPGRADE ON FEEDER 1854 FOR DA | Not Applicable | Not Applicable | Not Applicable | 718064.88 | Not Applicable | Not Applicable | Not Applicable
1017 | 0PT40047 -- FRANKFORD ROAD SUB : INSTALL DISTRIBUTION AUTOMATION ON FEEDER 0008 (DECOUPLE) | Not Applicable | Not Applicable | Not Applicable | 330466.63 | Not Applicable | Not Applicable | Not Applicable
1018 | 0PT48910 -- PAYNE SUB: RELAY UPGRADE ON FEEDER 1205 FOR DA AND ON FEEDERS 1202 AND 1203 | Not Applicable | Not Applicable | Not Applicable | 658175.2 | Not Applicable | Not Applicable | Not Applicable
1019 | 0PT49321 -- WICHITA FALLS SUB : RELAY UPGRADE ON FEEDERS 0133 AND 0153 FOR DA | Not Applicable | Not Applicable | Not Applicable | 775324.06 | Not Applicable | Not Applicable | Not Applicable
1020 | 0PT45315 -- ANNA SWITCH - SHERMAN SOUTH SUB 138 KV LINE: DAMPER ADDITION | Not Applicable | Not Applicable | Not Applicable | 262795.22 | Not Applicable | Not Applicable | Not Applicable
1021 | 0PT49722 -- EMPIRE CENTRAL SUB : RELAY UPGRADE ON FEEDER 0001, 0002, 0003, 0005, 0006 AND RELAYING FOR TIE BREAKERS T-1 AND T-5. | Not Applicable | Not Applicable | Not Applicable | 691576.38 | Not Applicable | Not Applicable | Not Applicable
1022 | 0PT45829 -- RENNER SWITCH : RELAY UPGRADE ON FEEDER 3124 FOR DA | Not Applicable | Not Applicable | Not Applicable | 407992.44 | Not Applicable | Not Applicable | Not Applicable
1023 | 0PT51680 -- STANTON SUB : UPGRADE BANK #3 WITH 138-21.6 KV, 47 MVA TRANSFORMER | Not Applicable | Not Applicable | Not Applicable | 1577745.48 | Not Applicable | Not Applicable | Not Applicable
1024 | 0PT48733 -- FALLSTOWN SWITCH (FKA BACON SWITCH STATION) - PURCHASE OF LAND IN FEE | Not Applicable | Not Applicable | Not Applicable | 419773.17 | Not Applicable | Not Applicable | Not Applicable
1025 | 0PT43752 -- EULESS SUB : RELAY UPGRADE ON FEEDERS 8722 & 8732 FOR DA AND ON FEEDERS 3128, 8713, 8714, 8723 & 8724 | Not Applicable | Not Applicable | Not Applicable | 568308.1 | Not Applicable | Not Applicable | Not Applicable
1026 | 0PT46462 -- LAKEWOOD SUB : RELAY UPGRADE ON FEEDERS 7411 AND 7432 FOR DA AND FEEDERS 1968, 7421 & 7442 | Not Applicable | Not Applicable | Not Applicable | 842389.13 | Not Applicable | Not Applicable | Not Applicable
1027 | 0PT43754 -- HALTOM SUB : RELAY UPGRADE ON FEEDERS 2461 & 2472 FOR DA AND FEEDERS 2411, 2421, 2431 & 2452. | Not Applicable | Not Applicable | Not Applicable | 495929.81 | Not Applicable | Not Applicable | Not Applicable
1028 | 0PT46463 -- MESQUITE TOWN EAST SUB : RELAY UPGRADE ON FEEDER 1205 FOR DA AND FOR FEEDERS 1204, 1206, 1209, 1211, 1213 & 1215 | Not Applicable | Not Applicable | Not Applicable | 286023.12 | Not Applicable | Not Applicable | Not Applicable
1029 | 0PT47147 -- STERRETT SWITCH: INSTALL UG FEEDER BREAKER ON BANK #2 | Not Applicable | Not Applicable | Not Applicable | 398014 | Not Applicable | Not Applicable | Not Applicable
1030 | 0PT46435 -- BLACKSTONE SUB : RELAY UPGRADE ON FEEDERS 1711, 1721, 1732, 1752, 1771 AND 1781 FOR DA | Not Applicable | Not Applicable | Not Applicable | 678299.85 | Not Applicable | Not Applicable | Not Applicable
1031 | 0PT47587 -- SL SALT FLAT ROAD SUB: CB 5102 LINE TERMINAL UPGRADE | Not Applicable | Not Applicable | Not Applicable | 537978.68 | Not Applicable | Not Applicable | Not Applicable
1032 | 0PT47249 -- EAST NETWORK SUB : CONVERT RELAYING ON SARGENT ROAD AND PARKDALE LINES TO FIBER. | Not Applicable | Not Applicable | Not Applicable | 361954.35 | Not Applicable | Not Applicable | Not Applicable
1033 | 0PT51907 -- CHICO WEST SWITCH - ORAN SWITCH 69 KV LINE : REPLACE MULTIPLE POLES (GLT) | Not Applicable | Not Applicable | Not Applicable | 563517.42 | Not Applicable | Not Applicable | Not Applicable
1034 | 0PT43399 -- RATHGEBER SUB : RELAY UPGRADE ON FEEDERS 1411 & 1421 FOR DA | Not Applicable | Not Applicable | Not Applicable | 268498.38 | Not Applicable | Not Applicable | Not Applicable
1035 | 0PT45774 -- LOMO ALTO SUB : RELAY UPGRADE ON FEEDERS 0003, 0011,0013 FOR DA | Not Applicable | Not Applicable | Not Applicable | 265035.03 | Not Applicable | Not Applicable | Not Applicable
1036 | 0PT46275 -- SHERMAN EAST SUB : RELAY UPGRADE ON FEEDERS 1401, 1403, 1405, 1407 AND 1409 FOR DA | Not Applicable | Not Applicable | Not Applicable | 849008.04 | Not Applicable | Not Applicable | Not Applicable
1037 | 0PT46479 -- WHITE SUB : RELAY UPGRADE ON FEEDER 3511 AND 3531 FOR DA AND FOR FEEDER 0717 | Not Applicable | Not Applicable | Not Applicable | 1224632.17 | Not Applicable | Not Applicable | Not Applicable
1038 | 0PT51332 -- LAMAR BLOSSOM - CLARKSVILLE 138KV: GROUND LINE MAINTENANCE FOR 207 POLES | Not Applicable | Not Applicable | Not Applicable | 578482.42 | Not Applicable | Not Applicable | Not Applicable
1039 | 0PT51590 -- SL SALT FLAT ROAD SUB : CB 5101 LINE TERMINAL UPGRADE | Not Applicable | Not Applicable | Not Applicable | 262817.25 | Not Applicable | Not Applicable | Not Applicable
1040 | 0PT43402 -- TEMPLE NORTHWEST SUB : RELAY UPGRADE ON FEEDERS 1103 & 1105 FOR DA AND ON FEEDER 1102- | Not Applicable | Not Applicable | Not Applicable | 363800.44 | Not Applicable | Not Applicable | Not Applicable
1041 | 0PT45776 -- REAGAN STREET SUB : RELAY UPGRADE ON FEEDERS 0003, 0004 FOR DA | Not Applicable | Not Applicable | Not Applicable | 296797.95 | Not Applicable | Not Applicable | Not Applicable
1042 | 0PT46277 -- SHERMAN NORTHWEST SUB : RELAY UPGRADE ON FEEDERS 1601, 1608,1609,1610 AND 1614 FOR DA AND ON FEEDERS 1611 AND 1612 | Not Applicable | Not Applicable | Not Applicable | 977253.8 | Not Applicable | Not Applicable | Not Applicable
1043 | 0PT45832 -- RICHARDSON SPRING CREEK SUB : RELAY UPGRADE ON FEEDERS 2102, 2104 AND 2132 FOR DA AND ON FEEDER 2103, 2105, 2106 AND 2108 | Not Applicable | Not Applicable | Not Applicable | 880265.57 | Not Applicable | Not Applicable | Not Applicable
1044 | 0PT49671 -- HOLLIDAY SUB: DISCONNECT AND DE-ENERGIZE 12.5KV PORTION OF THE STATION | Not Applicable | Not Applicable | Not Applicable | 369896.56 | Not Applicable | Not Applicable | Not Applicable
1045 | 0PT50852 -- PALESTINE SOUTH SUB: INSTALL ONE 12.5 KV FEEDER BREAKER | Not Applicable | Not Applicable | Not Applicable | 505448.8 | Not Applicable | Not Applicable | Not Applicable
1046 | 0PT51864 -- SL HADACOL CORNER SUB : STATION MODIFICATION FOR LINE TAP CONNECTION | Not Applicable | Not Applicable | Not Applicable | 536499.78 | Not Applicable | Not Applicable | Not Applicable
1047 | 0PT46212 -- PARKDALE SVC : REPLACE SVC 1 AND SVC 2 CONTROLS | Not Applicable | Not Applicable | Not Applicable | 7739666.76 | Not Applicable | Not Applicable | Not Applicable
1048 | 0PT46600 -- MORRISON LANE SWITCH : REPLACE MDAR RELAYING PANEL FOR CB #052 & 062 | Not Applicable | Not Applicable | Not Applicable | 277102.9 | Not Applicable | Not Applicable | Not Applicable
1049 | 0PT47527 -- BOLES SUBSTATION : PURCHASE IN FEE | Not Applicable | Not Applicable | Not Applicable | 260833.12 | Not Applicable | Not Applicable | Not Applicable
1050 | 0PT49707 -- THORNTON EAST SUB : RELAY UPGRADE ON FEEDER 0008 FOR DA | Not Applicable | Not Applicable | Not Applicable | 297267.72 | Not Applicable | Not Applicable | Not Applicable
1051 | 0PT45828 -- PRESTON NORTH SUB : RELAY UPGRADE ON FEEDERS 0005, 0006 AND 0008 FOR DA | Not Applicable | Not Applicable | Not Applicable | 274652.52 | Not Applicable | Not Applicable | Not Applicable
1052 | 0PT50849 -- DOUGLAS SUB: INSTALL ONE 24.9 KV FEEDER BREAKER | Not Applicable | Not Applicable | Not Applicable | 609673.24 | Not Applicable | Not Applicable | Not Applicable
1053 | 18T65180 -- POLK STREET SUBSTATION: DISTRIBUTION AUTOMATION INSTALLATION | Not Applicable | Not Applicable | Not Applicable | 566465.91 | Not Applicable | Not Applicable | Not Applicable
1054 | 0PT37840 -- HIDE-A-WAY LAKE: INSTALL DISTRIBUTION AUTOMATION ON FEEDERS 3001, 3003 | Not Applicable | Not Applicable | Not Applicable | 335991.37 | Not Applicable | Not Applicable | Not Applicable
1055 | 0PT43393 -- MCKINNEY SUB : RELAY UPGRADE ON FEEDERS 1204 & 1206 | Not Applicable | Not Applicable | Not Applicable | 348916.38 | Not Applicable | Not Applicable | Not Applicable
1056 | 0PT43760 -- LIGGETT SWITCH : RELAY UPGRADE ON FEEDERS 1602, 1603 & 1607 FOR DA AND FEEDER 1604 | Not Applicable | Not Applicable | Not Applicable | 691052.59 | Not Applicable | Not Applicable | Not Applicable
1057 | 0PT46258 -- FINK SUB : RELAY UPGRADE ON FEEDERS 1802,1803 AND 1804 FOR DA | Not Applicable | Not Applicable | Not Applicable | 684537.86 | Not Applicable | Not Applicable | Not Applicable
1058 | 0PT46472 -- SIMPSON STUART SUB : RELAY UPGRADE ON FEEDERS 0003 AND 0005 FOR DA AND ON FEEDERS 0007 AND 0008 | Not Applicable | Not Applicable | Not Applicable | 559257.7 | Not Applicable | Not Applicable | Not Applicable
1059 | 0PT38007 -- TEASELVILLE SUB: INSTALL DISTRIBUTION AUTOMATION ON FEEDERS 4008 | Not Applicable | Not Applicable | Not Applicable | 289892.96 | Not Applicable | Not Applicable | Not Applicable
1060 | 0PT43395 -- MINERAL WELLS SUB : RELAY UPGRADE ON FEEDERS 1203 & 1207 FOR DA | Not Applicable | Not Applicable | Not Applicable | 423957.6 | Not Applicable | Not Applicable | Not Applicable
1061 | 0PT43762 -- MESQUITE FORNEY ROAD SUB : RELAY UPGRADE ON FEEDERS 2101, 2102, 2103, 2105 FOR DA AND FEEDER 2107 | Not Applicable | Not Applicable | Not Applicable | 436040.53 | Not Applicable | Not Applicable | Not Applicable
1062 | 0PT46476 -- SPRINGTOWN SUB : RELAY UPGRADE ON FEEDERS 1801 AND 1802 FOR DA | Not Applicable | Not Applicable | Not Applicable | 476263.25 | Not Applicable | Not Applicable | Not Applicable
1063 | 0PT48908 -- PARKERVILLE ROAD SUB : RELAY UPGRADE ON FEEDERS 1051,1053 AND 1054 FOR DA | Not Applicable | Not Applicable | Not Applicable | 414829.53 | Not Applicable | Not Applicable | Not Applicable
1064 | 0PT46252 -- ARTHUR STREET SUB : RELAY UPGRADE ON FEEDERS 0411 AND 0481 FOR DA | Not Applicable | Not Applicable | Not Applicable | 300775.52 | Not Applicable | Not Applicable | Not Applicable
1065 | 0PT46465 -- OAKHILL SUB : RELAY UPGRADE ON FEEDERS 3021, 3052, 3062, 3072 AND 3082 FOR DA | Not Applicable | Not Applicable | Not Applicable | 367774.46 | Not Applicable | Not Applicable | Not Applicable
1066 | 0PT42922 -- EULESS SOUTH SUB : RELAY UPGRADE ON FEEDERS 9112, 9122 & 9131 FOR DA AND ON FEEDER 9132 | Not Applicable | Not Applicable | Not Applicable | 418325.42 | Not Applicable | Not Applicable | Not Applicable
1067 | 0PT45815 -- LAVON SUB : RELAY UPGRADE ON FEEDERS 1401, 1402, 1406 FOR DA AND ON FEEDERS 1401 & 1453 | Not Applicable | Not Applicable | Not Applicable | 551932.52 | Not Applicable | Not Applicable | Not Applicable
1068 | 0PT53381 -- APOLLO RD SUB - COPPELL SWITCH 69 KV LINE : REMOVE GLT STRUCTURES | Not Applicable | Not Applicable | Not Applicable | 550235.26 | Not Applicable | Not Applicable | Not Applicable
1069 | 0PT46244 -- GROESBECK SWITCH : MODIFY RELAYING FOR THE CUT-IN OF RIESEL SWITCH TO INTERCONNECT CORAL SOLAR | Not Applicable | Not Applicable | Not Applicable | 279703.98 | Not Applicable | Not Applicable | Not Applicable
1070 | 0PT42915 -- DALROCK SUB : RELAY UPGRADE ON FEEDERS 1326 & 1358 FOR DA AND ON FEEDER(S) 1301, 1303 & 1305 | Not Applicable | Not Applicable | Not Applicable | 1233746.09 | Not Applicable | Not Applicable | Not Applicable
1071 | 0PT42916 -- DAVIS SUB : RELAY UPGRADE ON FEEDERS 3711,3721, 3723, 3731, 3752 & 3782 FOR DA AND ON FEEDER 3387 | Not Applicable | Not Applicable | Not Applicable | 702846.21 | Not Applicable | Not Applicable | Not Applicable
1072 | 0PT42919 -- DECATUR SUB : RELAY UPGRADE ON FEEDERS 1201,1202 & 1204 FOR DA. | Not Applicable | Not Applicable | Not Applicable | 368979.95 | Not Applicable | Not Applicable | Not Applicable
1073 | 0PT42920 -- DUNCANVILLE SOUTH SUB : RELAY UPGRADE ON FEEDER 1103 FOR DA AND ON FEEDERS 1101, 1102, 1105 & 1106 | Not Applicable | Not Applicable | Not Applicable | 472479.93 | Not Applicable | Not Applicable | Not Applicable
1074 | 0PT43390 -- KILLEEN TAFT SUB : RELAY UPGRADE ON FEEDERS 1801, 1802, 1803, 1805 & 1806 FOR DA | Not Applicable | Not Applicable | Not Applicable | 438832.47 | Not Applicable | Not Applicable | Not Applicable
1075 | 0PT43758 -- KAUFMAN NORTHWEST SUB : RELAY UPGRADE ON FEEDERS 1201 & 1202 FOR DA | Not Applicable | Not Applicable | Not Applicable | 261963.05 | Not Applicable | Not Applicable | Not Applicable
1076 | 0PT44329 -- SWEETWATER SWITCH: CB 1020 LINE TERMINAL UPGRADE | Not Applicable | Not Applicable | Not Applicable | 303499.93 | Not Applicable | Not Applicable | Not Applicable
1077 | 0PT44340 -- FORRESTON SUB: 69 KV LINE TERMINAL UPGRADE | Not Applicable | Not Applicable | Not Applicable | 358571.53 | Not Applicable | Not Applicable | Not Applicable
1078 | 0PT45807 -- FAIR OAKS SUB : RELAY UPGRADE ON FEEDER 0002, 0005 & 0008 FOR DA. | Not Applicable | Not Applicable | Not Applicable | 293437.28 | Not Applicable | Not Applicable | Not Applicable
1079 | 0PT45808 -- FARMERS BRANCH GILLIS SUB : RELAY UPGRADE ON FEEDER 1751 FOR DA AND ON FEEDERS 1701, 1702, 1703, 1704, 1705, 1706, 1707, 1708, 1750, 1753 | Not Applicable | Not Applicable | Not Applicable | 410596.8 | Not Applicable | Not Applicable | Not Applicable
1080 | 0PT45812 -- JUDD COURT SUB : RELAY UPGRADE ON FEEDERS 0002, 0003, 0006, 0007 AND 0008 FOR DA | Not Applicable | Not Applicable | Not Applicable | 277201.94 | Not Applicable | Not Applicable | Not Applicable
1081 | 0PT46329 -- BRECKENRIDGE NORTH SUB : REPLACE 20MVA TRANSFORMER #1 | Not Applicable | Not Applicable | Not Applicable | 1113788.9 | Not Applicable | Not Applicable | Not Applicable
1082 | 0PT46542 -- GROESBECK MAIN SUB : RELAY UPGRADE ON FEEDER 4028 AND 4029 FOR DA AND FOR FEEDERS 3071 AND 3072 | Not Applicable | Not Applicable | Not Applicable | 697347.34 | Not Applicable | Not Applicable | Not Applicable
1083 | 0PT46543 -- HILLSBORO SUB : RELAY UPGRADE ON FEEDERS 1202 AND 1204 FOR DA AND FOR FEEDERS 1201 AND 1203 | Not Applicable | Not Applicable | Not Applicable | 801955.67 | Not Applicable | Not Applicable | Not Applicable
1084 | 0PT46545 -- MEXIA MAIN SUB : RELAY UPGRADE ON FEEDERS 4012 AND 4040 FOR DA | Not Applicable | Not Applicable | Not Applicable | 533121.66 | Not Applicable | Not Applicable | Not Applicable
1085 | 0PT48924 -- VILLAGE CREEK SUB : RELAY UPGRADE ON FEEDER 8011 FOR DA | Not Applicable | Not Applicable | Not Applicable | 332625.86 | Not Applicable | Not Applicable | Not Applicable
1086 | 0PT48927 -- WATSON SUB : RELAY UPGRADE ON FEEDERS 5331, 5342 AND 5352 FOR DA AND ON FEEDERS 1237, 5311, 5321, 5361, 5372, 5382 | Not Applicable | Not Applicable | Not Applicable | 1300677.26 | Not Applicable | Not Applicable | Not Applicable
1087 | 0PT49823 -- MIDKIFF SWITCH: 138 KV CB 12760 LINE TERMINAL UPGRADE | Not Applicable | Not Applicable | Not Applicable | 359187.07 | Not Applicable | Not Applicable | Not Applicable
1088 | 0PT50314 -- WHITESBORO JORDAN BKR 2655 - GAINESVILLE EAST TAP 138 SWT 2945: REPLACE H FRAME 28/1(GLT) | Not Applicable | Not Applicable | Not Applicable | 285431.12 | Not Applicable | Not Applicable | Not Applicable
1089 | 0PT50712 -- CARMICHAEL BEND SWITCH : INSTALL BACKUP GENERATOR | Not Applicable | Not Applicable | Not Applicable | 261091.5 | Not Applicable | Not Applicable | Not Applicable
1090 | 0PT51520 -- STONE CREEK SWITCH BKR 15445 AND BKR 1540 - GAINESVILLE BKR 336: REPLACE 31 H-FRAMES (GLT) | Not Applicable | Not Applicable | Not Applicable | 822201.28 | Not Applicable | Not Applicable | Not Applicable
1091 | 0PT53906 -- FAIRMOUNT SUB : UPGRADE UF SCHEME | Not Applicable | Not Applicable | Not Applicable | 371925.54 | Not Applicable | Not Applicable | Not Applicable
1092 | 0PT56121 -- BOLES SUB EXPANSION : PURCHASE IN FEE | Not Applicable | Not Applicable | Not Applicable | 256958.78 | Not Applicable | Not Applicable | Not Applicable
1093 | 0PT40781 -- MCKINNEY SOUTH SUB : INSTALL DISTRIBUTION AUTOMATION ON FEEDERS 3614 & 3615 | Not Applicable | Not Applicable | Not Applicable | 275099.77 | Not Applicable | Not Applicable | Not Applicable
1094 | 0PT44076 -- IRVING HUNTER FERRELL SUB : RELAY UPGRADE ON FEEDER 2305 FOR DA AND FEEDER 2303 | Not Applicable | Not Applicable | Not Applicable | 265014.32 | Not Applicable | Not Applicable | Not Applicable
1095 | 0PT43374 -- ATHENS NORTHWEST SUB : RELAY UPGRADE ON FEEDERS 1401, 1403, 1404 & 1405 FOR DA | Not Applicable | Not Applicable | Not Applicable | 338284.22 | Not Applicable | Not Applicable | Not Applicable
1096 | 0PT43742 -- BEDFORD WOODSON SUB : RELAY UPGRADE ON FEEDERS 8911, 8912, 8922 & 8941 FOR DA AND ON FEEDERS 8921, 8931, & 8932 | Not Applicable | Not Applicable | Not Applicable | 329478.42 | Not Applicable | Not Applicable | Not Applicable
1097 | 0PT49720 -- DESOTO HAMPTON ROAD SUB: UPGRADE FEEDER RELAYS, REPLACE FEEDERS 1202, 1203, AND 1206, ADD FEEDERS 1205 AND 1207 | Not Applicable | Not Applicable | Not Applicable | 1402692.11 | Not Applicable | Not Applicable | Not Applicable
1098 | 0PT49949 -- BROWN SVC : UPGRADE HMI SYSTEM AND ESTABLISH REMOTE CONNECTIVITY | Not Applicable | Not Applicable | Not Applicable | 939260.13 | Not Applicable | Not Applicable | Not Applicable
1099 | 0PT53749 -- SUNNYVALE SUB : INSTALL TWO 12.5 KV UG FEEDER BREAKERS ON BANK #1 | Not Applicable | Not Applicable | Not Applicable | 325508.58 | Not Applicable | Not Applicable | Not Applicable
1100 | 0PT45821 -- PLANO COIT ROAD SUB : RELAY UPGRADE ON FEEDER 1024 FOR DA AND ON FEEDERS 1002 | Not Applicable | Not Applicable | Not Applicable | 439196.07 | Not Applicable | Not Applicable | Not Applicable
1101 | 0PT53914 -- MISTLETOE HEIGHTS SUB : UPGRADE UF SCHEME | Not Applicable | Not Applicable | Not Applicable | 477771.3 | Not Applicable | Not Applicable | Not Applicable
1102 | 0PT45826 -- PLANO WEST SUB : RELAY UPGRADE ON FEEDERS 1301, 1303, 1304 AND 1311 FOR DA AND ON FEEDERS 1301, 1302, 1305, 1306, 1307, 1308, 1309 AND 1310 | Not Applicable | Not Applicable | Not Applicable | 2151420.25 | Not Applicable | Not Applicable | Not Applicable
1103 | 0PT50848 -- MIDLAND WEST SUB: INSTALL ONE 12.5 KV FEEDER BREAKER | Not Applicable | Not Applicable | Not Applicable | 308574.22 | Not Applicable | Not Applicable | Not Applicable
1104 | 0PT52125 -- SL YOSEMITE SUB : STATION MODIFICATION FOR LINE TAP CONNECTION | Not Applicable | Not Applicable | Not Applicable | 559104.69 | Not Applicable | Not Applicable | Not Applicable
1105 | 0PT43756 -- IRVING SUB : RELAY UPGRADE ON FEEDER 1401 FOR DA AND FEEDERS 1402, 1403, 1404, 1405, 1406, 1407 & 1408 | Not Applicable | Not Applicable | Not Applicable | 1412226.54 | Not Applicable | Not Applicable | Not Applicable
1106 | 0PT43417 -- BROWNWOOD SUB : UPGRADE RELAYING ON FEEDERS 1203, 1205 & 1206. | Not Applicable | Not Applicable | Not Applicable | 908371.31 | Not Applicable | Not Applicable | Not Applicable
1107 | 0PT43786 -- SPRINGDALE SUB : RELAY UPGRADE ON FEEDERS 4811, 4821 & 4831 FOR DA | Not Applicable | Not Applicable | Not Applicable | 540662 | Not Applicable | Not Applicable | Not Applicable
1108 | 0PT45782 -- TERRELL NORTH SUB : RELAY UPGRADE ON FEEDERS 1501, 1504 FOR DA | Not Applicable | Not Applicable | Not Applicable | 375128.15 | Not Applicable | Not Applicable | Not Applicable
1109 | 0PT53330 -- SHERRY SWITCH SUB : OIL CONTAINMENT | Not Applicable | Not Applicable | Not Applicable | 313430.78 | Not Applicable | Not Applicable | Not Applicable
1110 | 0PT49685 -- CENTERVILLE ROAD SUB : RELAY UPGRADE ON FEEDERS 0001 AND 0004 FOR DA | Not Applicable | Not Applicable | Not Applicable | 268026.1 | Not Applicable | Not Applicable | Not Applicable
1111 | 0PT42953 -- ROWLETT SUB : RELAY UPGRADE ON FEEDERS 1102, 1104 & 1106 FOR DA AND ON FEEDERS 1103 & 1105 | Not Applicable | Not Applicable | Not Applicable | 747503.76 | Not Applicable | Not Applicable | Not Applicable
1112 | 0PT45822 -- PLANO CUSTER ROAD SUB : RELAY UPGRADE ON FEEDERS 2007, 2009, 2010 & 2011 FOR DA AND ON FEEDERS 2009, 2010 & 2011 | Not Applicable | Not Applicable | Not Applicable | 475758.88 | Not Applicable | Not Applicable | Not Applicable
1113 | 0PT50846 -- CORSICANA WEST SUB: INSTALL ONE 12.5 KV FEEDER BREAKER | Not Applicable | Not Applicable | Not Applicable | 399611.74 | Not Applicable | Not Applicable | Not Applicable
1114 | 0PT50932 -- CARROLLTON SUB : INSTALL VOLTAGE REDUCTION EQUIPMENT | Not Applicable | Not Applicable | Not Applicable | 409851.44 | Not Applicable | Not Applicable | Not Applicable
1115 | 0PT53915 -- PARIS NORTH SUB : UPGRADE UF SCHEME AND DPU FEEDER RELAYS | Not Applicable | Not Applicable | Not Applicable | 373860.71 | Not Applicable | Not Applicable | Not Applicable
1116 | 0PT37811 -- FERRIS: INSTALL DISTRIBUTION AUTOMATION ON FEEDERS 1101 & 1103 | Not Applicable | Not Applicable | Not Applicable | 411129.55 | Not Applicable | Not Applicable | Not Applicable
1117 | 0PT41935 -- CENTERVILLE ROAD SUB : INSTALL DISTRIBUTION AUTOMATION ON FEEDER 4 | Not Applicable | Not Applicable | Not Applicable | 313098.44 | Not Applicable | Not Applicable | Not Applicable
1118 | 0PT43391 -- LAKE BELTON SUB : RELAY UPGRADE ON FEEDERS 2101, 2102 & 2105 FOR DA | Not Applicable | Not Applicable | Not Applicable | 259877.85 | Not Applicable | Not Applicable | Not Applicable
1119 | 0PT43759 -- LANCASTER SUB : RELAY UPGRADE ON FEEDERS 1601, 1602 & 1605 FOR DA AND FEEDER 1603 | Not Applicable | Not Applicable | Not Applicable | 826848.72 | Not Applicable | Not Applicable | Not Applicable
1120 | 0PT46471 -- SHERRY SWITCH : RELAY UPGRADE ON FEEDERS 6621 & 6622 FOR DA AND FEEDERS 6611, 6631, 6641, 6612 & 2031 | Not Applicable | Not Applicable | Not Applicable | 1132543 | Not Applicable | Not Applicable | Not Applicable
1121 | 0PT46877 -- MIDLAND EAST SWITCH: 138 KV CB 20165/20170 & CB 20180/20185 LINE TERMINAL RELAY MODIFICATIONS | Not Applicable | Not Applicable | Not Applicable | 272706.02 | Not Applicable | Not Applicable | Not Applicable
1122 | 0PT48010 -- SL DRIVER SUB : INSTALL FEEDER TIES | Not Applicable | Not Applicable | Not Applicable | 1688042.6 | Not Applicable | Not Applicable | Not Applicable
1123 | 0PT40733 -- BOOMTOWN SUB : INSTALL DISTRIBUTION AUTOMATION ON FEEDERS 1611 & 1621 | Not Applicable | Not Applicable | Not Applicable | 303366.47 | Not Applicable | Not Applicable | Not Applicable
1124 | 0PT42934 -- GARLAND SUB : RELAY UPGRADE ON FEEDER 1603 | Not Applicable | Not Applicable | Not Applicable | 301261.84 | Not Applicable | Not Applicable | Not Applicable
1125 | 0PT45597 -- LOVEBIRD SUB : RELAY UPGRADE ON FEEDERS 4, 5, AND 8 FOR DA (DECOUPLED) | Not Applicable | Not Applicable | Not Applicable | 435220.23 | Not Applicable | Not Applicable | Not Applicable
1126 | 0PT45818 -- NORTH PARKWAY SUB : RELAY UPGRADE ON FEEDERS 0005 AND 0009 FOR DA | Not Applicable | Not Applicable | Not Applicable | 293217.91 | Not Applicable | Not Applicable | Not Applicable
1127 | 0PT46969 -- FLINT SUB : INSTALL A 46.7 MVA 138-24.9 KV TRANSFORMER ON BANK #2 WITH ONE 25 KV FEEDER BREAKER | Not Applicable | Not Applicable | Not Applicable | 2650499.98 | Not Applicable | Not Applicable | Not Applicable
1128 | 0PT47544 -- CEDAR CREST SUB : REMOVE 69 KV EQUIPMENT | Not Applicable | Not Applicable | Not Applicable | 1422763.64 | Not Applicable | Not Applicable | Not Applicable
1129 | 0PT40740 -- WICHITA FALLS SUB : INSTALL DISTRIBUTION AUTOMATION ON FEEDERS 0174, 0163, 0184 & 0193 | Not Applicable | Not Applicable | Not Applicable | 534530.01 | Not Applicable | Not Applicable | Not Applicable
1130 | 0PT50026 -- WHITE SUB : INSTALL NEW 12.5KV PT'S ON STATION 1 AND 2 | Not Applicable | Not Applicable | Not Applicable | 347623.21 | Not Applicable | Not Applicable | Not Applicable
1131 | 0PT53916 -- PLANO COIT ROAD SUB : UPGRADE UF SCHEME | Not Applicable | Not Applicable | Not Applicable | 256808.45 | Not Applicable | Not Applicable | Not Applicable
1132 | 0PT46927 -- REGENCY SUB (FKA BRADY CREEK SUBSTATION) - PURCHASE LAND IN FEE | Not Applicable | Not Applicable | Not Applicable | 390142.26 | Not Applicable | Not Applicable | Not Applicable
1133 | 0PT49291 -- FOUR BROTHERS SWITCH: INSTALL 34.5 KV WSL METERING FOR SUN VALLEY SOLAR, LLC | Not Applicable | Not Applicable | Not Applicable | 323294.09 | Not Applicable | Not Applicable | Not Applicable
1134 | 0PT43419 -- LAMESA SUB : RELAY UPGRADE ON FEEDERS 1512, 1522 & 1561 FOR DA | Not Applicable | Not Applicable | Not Applicable | 524032.67 | Not Applicable | Not Applicable | Not Applicable
1135 | 0PT43788 -- WATAUGA SUB : RELAY UPGRADE ON FEEDERS 4613, 4631 & 4652 FOR DA | Not Applicable | Not Applicable | Not Applicable | 496516.43 | Not Applicable | Not Applicable | Not Applicable
1136 | 0PT46533 -- CITY VIEW SUB : RELAY UPGRADE ON FEEDER 2222 FOR DA | Not Applicable | Not Applicable | Not Applicable | 425518.48 | Not Applicable | Not Applicable | Not Applicable
1137 | 0PT46538 -- CRANE SUB : RELAY UPGRADE ON FEEDERS 0311 AND 0331 FOR DA | Not Applicable | Not Applicable | Not Applicable | 836829 | Not Applicable | Not Applicable | Not Applicable
1138 | 0PT48890 -- BLACKWELL STREET SUB: RELAY UPGRADE ON FEEDER 0005 FOR DA | Not Applicable | Not Applicable | Not Applicable | 456757.41 | Not Applicable | Not Applicable | Not Applicable
1139 | 0PT48914 -- RICHARDSON SUB : RELAY UPGRADE ON FEEDERS 1201 AND 1207 FOR DA AND ON FEEDERS 1206, AND 1208 | Not Applicable | Not Applicable | Not Applicable | 918207.11 | Not Applicable | Not Applicable | Not Applicable
1140 | 0PT49281 -- DAVIS SUB : RELAY UPGRADE ON FEEDER 3772 FOR DA | Not Applicable | Not Applicable | Not Applicable | 256959.11 | Not Applicable | Not Applicable | Not Applicable
1141 | 0PT49327 -- CHINA GROVE SWITCH EXPANSION : PURCHASE IN FEE | Not Applicable | Not Applicable | Not Applicable | 667676.3 | Not Applicable | Not Applicable | Not Applicable
1142 | 0PT50916 -- SPARTAN SUB (FKA GARDEN ACRES SUBSTATION) : PURCHASE IN FEE | Not Applicable | Not Applicable | Not Applicable | 516379.39 | Not Applicable | Not Applicable | Not Applicable
1143 | 0PT43738 -- ALLEN NORTH SUB : RELAY UPGRADE ON FEEDERS 2832 & 2854 FOR DA | Not Applicable | Not Applicable | Not Applicable | 270907.06 | Not Applicable | Not Applicable | Not Applicable
1144 | 0PT47468 -- DESOTO PLEASANT RUN SUB : UPGRADE SWITCHES #1416, #1417, AND #1419 TO 2000A ON DEADEND | Not Applicable | Not Applicable | Not Applicable | 1008836.25 | Not Applicable | Not Applicable | Not Applicable
1145 | 0PT53233 -- PLANO PARKER ROAD SUB : REPLACE TRANSFORMER #1 AND #2 RELAYING | Not Applicable | Not Applicable | Not Applicable | 255488.16 | Not Applicable | Not Applicable | Not Applicable
1146 | 0PT43373 -- ATHENS SUB : RELAY UPGRADE ON FEEDERS 1201, 1202 & 1203 FOR DA | Not Applicable | Not Applicable | Not Applicable | 327010.33 | Not Applicable | Not Applicable | Not Applicable
1147 | 0PT44197 -- IRVING NORTHEAST SUB : INSTALL NEW FEEDER BREAKER ON TRANSFORMER #3 | Not Applicable | Not Applicable | Not Applicable | 388074.47 | Not Applicable | Not Applicable | Not Applicable
1148 | 0PT40736 -- CRYOVAC EAST SUB : INSTALL DISTRIBUTION AUTOMATION ON FEEDER 3021 | Not Applicable | Not Applicable | Not Applicable | 348073.84 | Not Applicable | Not Applicable | Not Applicable
1149 | 0PT42944 -- MILLERS FERRY ROAD SUB : RELAY UPGRADE ON FEEDERS 2101 AND 2103 FOR DA. | Not Applicable | Not Applicable | Not Applicable | 285552.63 | Not Applicable | Not Applicable | Not Applicable
1150 | 0PT50842 -- ALVARADO SUB: INSTALL ONE 12.5 KV FEEDER BREAKER | Not Applicable | Not Applicable | Not Applicable | 343091.79 | Not Applicable | Not Applicable | Not Applicable
1151 | 0PT53913 -- NACOGDOCHES SOUTH SUB : UPGRADE UF SCHEME | Not Applicable | Not Applicable | Not Applicable | 319536.98 | Not Applicable | Not Applicable | Not Applicable
1152 | 0PT46238 -- LAKE CREEK SWITCH : MODIFY RELAYING FOR THE EXISTING JEWETT SWITCH 138 KV LINE TERMINAL CB 2870 FOR THE CUT-IN OF RIESEL SWITCH TO INTERCONNECT CORAL SOLAR | Not Applicable | Not Applicable | Not Applicable | 379382.33 | Not Applicable | Not Applicable | Not Applicable
1153 | 0PT42884 -- CEDAR HILL SUB : RELAY UPGRADE ON FEEDERS 1613, 1614, 1623 & 1801 FOR DA AND ON FEEDER(S) 1803, 1804, 1805 & 1806 | Not Applicable | Not Applicable | Not Applicable | 551079.76 | Not Applicable | Not Applicable | Not Applicable
1154 | 0PT45804 -- COLONY SUB : RELAY UPGRADE ON FEEDERS 2403 & 2404 FOR DA AND ON FEEDERS 2406 & 2401 | Not Applicable | Not Applicable | Not Applicable | 559527.11 | Not Applicable | Not Applicable | Not Applicable
1155 | 0PT46534 -- COLORADO CITY SUB : RELAY UPGRADE ON FEEDERS 1011,1021 AND 1031 FOR DA | Not Applicable | Not Applicable | Not Applicable | 455596.67 | Not Applicable | Not Applicable | Not Applicable
1156 | 0PT48916 -- ROANOKE WEST SUB : RELAY UPGRADE ON FEEDERS 9512 FOR DA AND ON FEEDERS 9522. | Not Applicable | Not Applicable | Not Applicable | 349672.08 | Not Applicable | Not Applicable | Not Applicable
1157 | 0PT50134 -- FISHER ROAD SUB : RELAY UPGRADE ON FEEDER 2121 FOR DA | Not Applicable | Not Applicable | Not Applicable | 340990.97 | Not Applicable | Not Applicable | Not Applicable
1158 | 0PT45836 -- IRVING VALLEY RANCH SUB : RELAY UPGRADE ON FEEDERS 2953 AND 2955 FOR DA AND FOR FEEDER 2957 | Not Applicable | Not Applicable | Not Applicable | 401218.43 | Not Applicable | Not Applicable | Not Applicable
1159 | 0PT46986 -- FLAT IRON SUB : INSTALL ONE 138-25 KV 46.7 MVA TRANSFORMER WITH TWO FEEDER BREAKERS FOR LEGACY II | Not Applicable | Not Applicable | Not Applicable | 2810428.88 | Not Applicable | Not Applicable | Not Applicable
1160 | 0PT48388 -- ROANOKE SWITCH : REPLACE BANK #1 WITH A 138-24.9 KV, 46.7 MVA TRANSFORMER FOR TELIOS | Not Applicable | Not Applicable | Not Applicable | 3426273.08 | Not Applicable | Not Applicable | Not Applicable
1161 | 0PT49678 -- ABRAMS ROAD SUB : RELAY UPGRADE ON FEEDERS 0002,0004, 0005 AND 0008 FOR DA | Not Applicable | Not Applicable | Not Applicable | 593358.07 | Not Applicable | Not Applicable | Not Applicable
1162 | 0PT50965 -- KILLEEN PARK STREET SUB: INSTALL ONE 12.5 KV FEEDER BREAKER | Not Applicable | Not Applicable | Not Applicable | 639289.38 | Not Applicable | Not Applicable | Not Applicable
1163 | 0PT45606 -- TEMPLE SWITCH: TRANSFER TRIP ADDITION, LINE TERMINAL UPGRADE, FOR THE ADDITION OF BELFALLS SWITCH (BIG ELM SOLAR) | Not Applicable | Not Applicable | Not Applicable | 462869.8 | Not Applicable | Not Applicable | Not Applicable
1164 | 0PT43793 -- OVERTON SUB : RELAY UPGRADE ON FEEDERS 4015 & 4019 FOR DA | Not Applicable | Not Applicable | Not Applicable | 368349.43 | Not Applicable | Not Applicable | Not Applicable
1165 | 0PT45789 -- CARROLLTON TARPLEY ROAD SUB : RELAY UPGRADE ON FEEDERS 2006 & 2007 FOR DA AND ON FEEDERS 2001 2002, 2003, 2004, 2005 & 2054 | Not Applicable | Not Applicable | Not Applicable | 787506.34 | Not Applicable | Not Applicable | Not Applicable
1166 | 0PT49589 -- DIBOLL SUB : INSTALL FEEDER FOR DISTRIBUTED ENERGY STORAGE RESOURCE (DESR) | Not Applicable | Not Applicable | Not Applicable | 612141.06 | Not Applicable | Not Applicable | Not Applicable
1167 | 0PT43401 -- SWEETWATER DOWNTOWN SUB : RELAY UPGRADE ON FEEDERS 1631 & 1641 FOR DA | Not Applicable | Not Applicable | Not Applicable | 558020.44 | Not Applicable | Not Applicable | Not Applicable
1168 | 0PT45775 -- MAPLE SUB : RELAY UPGRADE ON FEEDERS 0002 FOR DA | Not Applicable | Not Applicable | Not Applicable | 459000.83 | Not Applicable | Not Applicable | Not Applicable
1169 | 0PT46276 -- SHERMAN LINE MATERIAL SUB : RELAY UPGRADE ON FEEDERS 1802 FOR DA | Not Applicable | Not Applicable | Not Applicable | 352405.28 | Not Applicable | Not Applicable | Not Applicable
1170 | 0PT45787 -- CARROLLTON COUNTRY CLUB SUB : RELAY UPGRADE ON FEEDER 2704 FOR DA | Not Applicable | Not Applicable | Not Applicable | 283411.35 | Not Applicable | Not Applicable | Not Applicable
1171 | 0PT48896 -- EULESS TRINITY BOULEVARD SUB : RELAY UPGRADE ON FEEDER 5731FOR DA | Not Applicable | Not Applicable | Not Applicable | 507126.49 | Not Applicable | Not Applicable | Not Applicable
1172 | 0PT45817 -- MORRISON LANE SUB : RELAY UPGRADE ON FEEDER 0002 AND 0005 FOR DA | Not Applicable | Not Applicable | Not Applicable | 311835.58 | Not Applicable | Not Applicable | Not Applicable
1173 | 0PT48932 -- WITT ROAD SUBSTATION SUB : RELAY UPGRADE ON FEEDER 1705 FOR DA AND ON FEEDERS 1701, 1703 AND 1707 | Not Applicable | Not Applicable | Not Applicable | 254960.05 | Not Applicable | Not Applicable | Not Applicable
1174 | 0PT50430 -- IRVING NORTHEAST SUB : OIL CONTAINMENT | Not Applicable | Not Applicable | Not Applicable | 269600.36 | Not Applicable | Not Applicable | Not Applicable
1175 | 0PT43420 -- ODESSA NORTH SUB : RELAY UPGRADE ON FEEDERS 2033, 2035 & 2044 FOR DA | Not Applicable | Not Applicable | Not Applicable | 396103.04 | Not Applicable | Not Applicable | Not Applicable
1176 | 0PT45784 -- ADDISON SUB : RELAY UPGRADE ON FEEDERS 1601 FOR DA AND ON FEEDERS 1602, 1603, 1604, 1605, 1606, 1607, 1608 | Not Applicable | Not Applicable | Not Applicable | 1465227.75 | Not Applicable | Not Applicable | Not Applicable
1177 | 0PT48328 -- LONGSHORE 345KV SWITCH EXPANSION (STANTON LOOP) - PURCHASE OF LAND | Not Applicable | Not Applicable | Not Applicable | 385130.88 | Not Applicable | Not Applicable | Not Applicable
1178 | 0PT49282 -- DECORDOVA DAM SUB : RELAY UPGRADE ON FEEDER 2003 FOR DA | Not Applicable | Not Applicable | Not Applicable | 326922.77 | Not Applicable | Not Applicable | Not Applicable
1179 | 0PT51500 -- VANGUARD T-LINE : PURCHASE OF EASEMENT | Not Applicable | Not Applicable | Not Applicable | 433405.5 | Not Applicable | Not Applicable | Not Applicable
1180 | 0PT43790 -- BEAUMONT STREET SUB : RELAY UPGRADE ON FEEDERS 4084 AND 4090 FOR DA | Not Applicable | Not Applicable | Not Applicable | 438969.17 | Not Applicable | Not Applicable | Not Applicable
1181 | 0PT45786 -- BLACKWELL STREET SUB : RELAY UPGRADE ON FEEDER 0002 AND 0007 FOR DA | Not Applicable | Not Applicable | Not Applicable | 608215.79 | Not Applicable | Not Applicable | Not Applicable
1182 | 0PT45816 -- LOMBARDY LANE SUB : RELAY UPGRADE ON FEEDERS 0001 & 0005 FOR DA | Not Applicable | Not Applicable | Not Applicable | 464642.77 | Not Applicable | Not Applicable | Not Applicable
1183 | 0PT48895 -- EDGECLIFF SUB : RELAY UPGRADE ON FEEDERS 2211, 2221, 2231,2241, 2252, 2262, 2272 AND 2282 FOR DA | Not Applicable | Not Applicable | Not Applicable | 1055041.03 | Not Applicable | Not Applicable | Not Applicable
1184 | 0PT48929 -- WEDGEWOOD SUB : RELAY UPGRADE ON FEEDER 1592 FOR DA | Not Applicable | Not Applicable | Not Applicable | 271475.6 | Not Applicable | Not Applicable | Not Applicable
1185 | 0PT49285 -- GLENHAVEN SUB : RELAY UPGRADE ON FEEDERS 3953, 3963, 3973 AND 3992 FOR DA | Not Applicable | Not Applicable | Not Applicable | 434646.19 | Not Applicable | Not Applicable | Not Applicable
1186 | 0PT50820 -- SALT LAKE SUB: INSTALL TRANSFORMER #1 | Not Applicable | Not Applicable | Not Applicable | 2512442.67 | Not Applicable | Not Applicable | Not Applicable
1187 | 0PT52256 -- RICHARDSON SPRING CREEK SUB : INSTALL A FEEDER BREAKER ON BANK #4 | Not Applicable | Not Applicable | Not Applicable | 271521.65 | Not Applicable | Not Applicable | Not Applicable
1188 | 0PT44159 -- 800/900 NETWORK SUB : CONVERT THE RELAYING ON THE GREENVILLE AVENUE LINE TO FIBER | Not Applicable | Not Applicable | Not Applicable | 250294.91 | Not Applicable | Not Applicable | Not Applicable
1189 | 0PT46441 -- COPPERAS COVE SUB : RELAY UPGRADE ON FEEDERS 1401, 1402, 1403, 1404, 1405, 1406 FOR DA AND FEEDER 1407 | Not Applicable | Not Applicable | Not Applicable | 1122303.82 | Not Applicable | Not Applicable | Not Applicable
1190 | 0PT47686 -- ROYSE SWITCH: 345 KV SHAMBURGER LINE CARRIER UPGRADE | Not Applicable | Not Applicable | Not Applicable | 339154.23 | Not Applicable | Not Applicable | Not Applicable
1191 | 0PT43763 -- MESQUITE NORTH SUB : RELAY UPGRADE ON FEEDERS 1501, 1502, 1503, 1504 & 1505 FOR DA AND FEEDERS 1506 & 1507 | Not Applicable | Not Applicable | Not Applicable | 709028.65 | Not Applicable | Not Applicable | Not Applicable
1192 | 0PT45770 -- COLLVILLE SUB : RELAY UPGRADE ON FEEDERS 0003 & 0006 FOR DA | Not Applicable | Not Applicable | Not Applicable | 266852.42 | Not Applicable | Not Applicable | Not Applicable
1193 | 0PT47770 -- HORNE STREET SUB : OIL CONTAINMENT | Not Applicable | Not Applicable | Not Applicable | 846557.27 | Not Applicable | Not Applicable | Not Applicable
1194 | 0PT49366 -- BLUFF CREEK SWITCH EXPANSION - PURCHASE OF LAND IN FEE | Not Applicable | Not Applicable | Not Applicable | 384116.5 | Not Applicable | Not Applicable | Not Applicable
1195 | 0PT39005 -- LAVON SWITCH: PURCHASE AND STORE (ONE) 345/138 KV, 600 MVA AUTOTRANSFORMER | Not Applicable | Not Applicable | Not Applicable | 5391598.02 | Not Applicable | Not Applicable | Not Applicable
1196 | 0PT43403 -- TEMPLE SOUTH SUB : RELAY UPGRADE ON FEEDERS 1402, 1404 & 1408 FOR DA | Not Applicable | Not Applicable | Not Applicable | 253896.87 | Not Applicable | Not Applicable | Not Applicable
1197 | 0PT45777 -- RECORD CROSSING SUB : RELAY UPGRADE ON FEEDERS 0005 FOR DA | Not Applicable | Not Applicable | Not Applicable | 349305.37 | Not Applicable | Not Applicable | Not Applicable
1198 | 0PT47653 -- TEMPLE ELM CREEK SWITCH: MODIFY RELAYING FOR NEW PEPPER CREEK SWITCH LINE TERMINALS | Not Applicable | Not Applicable | Not Applicable | 337846.85 | Not Applicable | Not Applicable | Not Applicable
1199 | 0PT03065 -- DAVIS STREET: DISTRIBUTION AUTOMATION FEEDERS 0007 & 0008 | Not Applicable | Not Applicable | Not Applicable | 632855.31 | Not Applicable | Not Applicable | Not Applicable
1200 | 0PT44218 -- MOORES MILL SUB : INSTALL TRANSFORMER #2 WITH ONE 46.7 MVA, 138-12.5 KV TRANSFORMER AND ONE UG FEEDER BREAKER | Not Applicable | Not Applicable | Not Applicable | 2007281.43 | Not Applicable | Not Applicable | Not Applicable
1201 | 0PT49725 -- LAKE HIGHLAND SUB : RELAY UPGRADE ON FEEDERS 0001, 0002, 0003 AND 0006 FOR DA | Not Applicable | Not Applicable | Not Applicable | 298734.98 | Not Applicable | Not Applicable | Not Applicable
1202 | 0PT46440 -- COLLEYVILLE SUB : RELAY UPGRADE ON FEEDER 9312 FOR DA | Not Applicable | Not Applicable | Not Applicable | 823464.05 | Not Applicable | Not Applicable | Not Applicable
1203 | 0PT48278 -- ELKTON SWITCH - TEASELVILLE SUB 138 KV LINE : 2022 SUMMER WORK: REPLACE STRUCTURE 13/2 | Not Applicable | Not Applicable | Not Applicable | 262384.41 | Not Applicable | Not Applicable | Not Applicable
1204 | 0PT50867 -- ABRAMS ROAD SUB : REPLACE 138KV SWITCH 014 AND 024 | Not Applicable | Not Applicable | Not Applicable | 314201.71 | Not Applicable | Not Applicable | Not Applicable
1205 | 0PT45833 -- RICHARDSON WOODHAVEN SUB : RELAY UPGRADE ON FEEDERS 1905 & 1908 FOR DA AND ON FEEDERS 1901, 1902, 1903, 1904, 1905 & 1906 | Not Applicable | Not Applicable | Not Applicable | 515526.09 | Not Applicable | Not Applicable | Not Applicable
1206 | 0PT51543 -- GOODNIGHT SUBSTATION: INSTALL BANK #2, 138-24.9 KV, 47 MVA TRANSFORMER AND TWO FEEDER BREAKERS | Not Applicable | Not Applicable | Not Applicable | 2589692.98 | Not Applicable | Not Applicable | Not Applicable
1207 | 0PT41277 -- CEDAR HILL SWITCH - SOUTH HAMPTON SUB 138 KV LINE : AVIATION LIGHT MONITOR INSTALLATION | Not Applicable | Not Applicable | Not Applicable | 254474 | Not Applicable | Not Applicable | Not Applicable
1208 | 0PT43745 -- CARROLLTON SUB : RELAY UPGRADE ON FEEDERS 1402, 1406 & 1452 FOR DA AND ON FEEDERS 1401, 1405, 1451 & 1453 | Not Applicable | Not Applicable | Not Applicable | 1005533.65 | Not Applicable | Not Applicable | Not Applicable
1209 | 0PT43406 -- WACO NORTH SUB : RELAY UPGRADE ON FEEDER 1416, 1418,1419, 1420 & 1421 | Not Applicable | Not Applicable | Not Applicable | 322236.16 | Not Applicable | Not Applicable | Not Applicable
1210 | 0PT43409 -- WICHITA RIVER BEND SUB : RELAY UPGRADE ON FEEDERS 2311 & 2322 FOR DA | Not Applicable | Not Applicable | Not Applicable | 279926.62 | Not Applicable | Not Applicable | Not Applicable
1211 | 0PT43783 -- ROSEN HEIGHTS SUB : RELAY UPGRADE ON FEEDERS 1122, 1142, 1152 AND 1171 FOR DA | Not Applicable | Not Applicable | Not Applicable | 342900.31 | Not Applicable | Not Applicable | Not Applicable
1212 | 0PT53328 -- EVERMAN SWITCH : OIL CONTAINMENT | Not Applicable | Not Applicable | Not Applicable | 294976.85 | Not Applicable | Not Applicable | Not Applicable
1213 | 0PT53329 -- DENTON DRIVE SUB SWITCH : OIL CONTAINMENT | Not Applicable | Not Applicable | Not Applicable | 301131.19 | Not Applicable | Not Applicable | Not Applicable