## Under Review
Report Month | Report Year | RPG Project ID | RPG Project Name | Submitted Entity | Tier | Estimated Cost ($ Millions)
January | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
January | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
January | 2020 |  | Corpus North Shore Project | AEPSC | Tier 1 | 259.57
January | 2020 |  | Frio County Transmission Project | 7x Energy | Tier 2 | 23
January | 2020 |  | Quanah Area Improvement Transmission Project | AEPSC | Tier 2 | 10
January | 2020 |  | Farmersville Area Reliability Project | GP&L | Tier 2 | 24.37
January | 2020 |  | W.A. Parish to Westpark Tollway Ckt 09 Rebuild Project | CNP | Tier 3 | 50.77
February | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
February | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
February | 2020 |  | Corpus North Shore Project | AEPSC | Tier 1 | 259.57
February | 2020 |  | Frio County Transmission Project | 7x Energy | Tier 2 | 23
February | 2020 |  | Quanah Area Improvement Transmission Project | AEPSC | Tier 2 | 10
February | 2020 |  | Farmersville Area Reliability Project | GP&L | Tier 2 | 24.37
February | 2020 |  | Smith to Mathis 69-kV Line Rebuild Project | AEPSC | Tier 3 | 38
March | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
March | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
March | 2020 |  | Corpus North Shore Project | AEPSC | Tier 1 | 259.57
March | 2020 |  | Frio County Transmission Project | 7x Energy | Tier 2 | 23
March | 2020 |  | Quanah Area Improvement Transmission Project | AEPSC | Tier 2 | 11.3
March | 2020 |  | Farmersville Area Reliability Project | GP&L | Tier 2 | 24.37
March | 2020 |  | Smith to Mathis 69-kV Line Rebuild Project | AEPSC | Tier 3 | 38
March | 2020 |  | Anna Switch - Royse Switch 138-kV Line Upgrade Project | Oncor | Tier 3 | 91.2
March | 2020 |  | Lookout Substation SVC Project | GP&L | Tier 3 | 25
April | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
April | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
April | 2020 |  | Corpus North Shore Project | AEPSC | Tier 1 | 259.57
April | 2020 |  | Frio County Transmission Project | 7x Energy | Tier 2 | 23
April | 2020 |  | Farmersville Area Reliability Project | GP&L | Tier 2 | 24.37
April | 2020 |  | Anna Switch - Royse Switch 138-kV Line Upgrade Project | Oncor | Tier 3 | 91.2
April | 2020 |  | Lookout Substation SVC Project | GP&L | Tier 3 | 25
April | 2020 |  | Ballinger to San Angelo Concho 69 kV Line Rebuild Project | AEPSC | Tier 3 | 27
April | 2020 |  | Texas City Transmission Improvement Project | TNMP | Tier 2 | 29.3
May | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
May | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
May | 2020 |  | Corpus North Shore Project | AEPSC | Tier 1 | 259.57
May | 2020 |  | Frio County Transmission Project | 7x Energy | Tier 2 | 23
May | 2020 |  | Farmersville Area Reliability Project | GP&L | Tier 2 | 24.37
May | 2020 |  | Lookout Substation SVC Project | GP&L | Tier 3 | 25
May | 2020 |  | Texas City Transmission Improvement Project | TNMP | Tier 2 | 29.3
May | 2020 |  | DeCordova Switching Station Rebuild Project | Oncor | Tier 3 | 37.5
May | 2020 |  | Moffat to Hasse Voltage Conversion Project | BEC | Tier 2 | 55.2
May | 2020 |  | Quarry Field 345-kV Switch Project | Oncor | Tier 3 | 29
June | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
June | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
June | 2020 |  | Corpus North Shore Project | AEPSC | Tier 1 | 259.57
June | 2020 |  | Texas City Transmission Improvement Project | TNMP | Tier 2 | 29.3
June | 2020 |  | Moffat to Hasse Voltage Conversion Project | BEC | Tier 2 | 55.2
June | 2020 |  | Quarry Field 345-kV Switch Project | Oncor | Tier 3 | 29
June | 2020 |  | Big Spring – Buzzard Draw 69-kV Line Conversion to 138-kV Project | Oncor | Tier 3 | 32
June | 2020 |  | Carrollton Northwest 345/138-kV Autotransformer Upgrade Project | Oncor | Tier 3 | 8.5
July | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
July | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
July | 2020 |  | Texas City Transmission Improvement Project | TNMP | Tier 2 | 29.3
July | 2020 |  | Moffat to Hasse Voltage Conversion Project | BEC | Tier 2 | 55.2
July | 2020 |  | Carrollton Northwest 345/138-kV Autotransformer Upgrade Project | Oncor | Tier 3 | 8.5
July | 2020 |  | Eagle Mountain to Saginaw 138-kV Double-Circuit Line Upgrade Project | Oncor | Tier 3 | 32
July | 2020 |  | Horseshoe Springs Switch – Riverton Switch 138-kV Second Circuit Project | Oncor | Tier 3 | 52.3
August | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
August | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
August | 2020 |  | Texas City Transmission Improvement Project | TNMP | Tier 2 | 29.3
August | 2020 |  | Moffat to Hasse Voltage Conversion Project | BEC | Tier 2 | 55.2
August | 2020 |  | Horseshoe Springs Switch – Riverton Switch 138-kV Second Circuit Project | Oncor | Tier 3 | 52.3
August | 2020 |  | Everman Switching Station Rebuild Project | Oncor | Tier 3 | 36
August | 2020 |  | Coleto Creek to Kenedy SS 138-kV Transmission Project | AEPSC | Tier 3 | 54.7
September | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
September | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
September | 2020 |  | Texas City Transmission Improvement Project | TNMP | Tier 2 | 29.3
September | 2020 |  | Moffat to Hasse Voltage Conversion Project | BEC | Tier 2 | 55.2
September | 2020 |  | Everman Switching Station Rebuild Project | Oncor | Tier 3 | 36
September | 2020 |  | Coleto Creek to Kenedy SS 138-kV Transmission Project | AEPSC | Tier 3 | 54.7
September | 2020 |  | Mont Belvieu Reliability Upgrades Project | CNP | Tier 3 | 27.28
September | 2020 |  | Tall City – Telephone Road 138-kV Line Rebuild Project | Oncor | Tier 3 | 23.5
September | 2020 |  | Alamito Creek to Alpine 69-kV Line Rebuild Transmission Project | AEPSC | Tier 3 | 37
October | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
October | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
October | 2020 |  |  | BEC
October | 2020 |  | Tall City – Telephone Road 138-kV Line Rebuild Project | Oncor | Tier 3 | 23.5
October | 2020 |  | Alamito Creek to Alpine 69-kV Line Rebuild Transmission Project | AEPSC | Tier 3 | 37
October | 2020 |  | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
October | 2020 |  | Lake Pauline Area Improvement Project | AEPSC | Tier 3 | 47.5
October | 2020 |  | Wallis to Peters Ckt 65 138-kV Line Rebuild Project | CNP | Tier 3 | 64.78
October | 2020 |  | Burma to Sterling City 69-kV Line Rebuild Project | AEPSC | Tier 3 | 28
November | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
November | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
November | 2020 |  | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
November | 2020 |  | Lake Pauline Area Improvement Project | AEPSC | Tier 3 | 47.5
November | 2020 |  | Wallis to Peters Ckt 65 138-kV Line Rebuild Project | CNP | Tier 3 | 64.78
November | 2020 |  | Burma to Sterling City 69-kV Line Rebuild Project | AEPSC | Tier 3 | 28
November | 2020 |  | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 28
December | 2020 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
December | 2020 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
December | 2020 |  | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
December | 2020 |  | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 28
December | 2020 |  | Royse - Commerce 69 kV Line Conversion to 138 kV Project | Oncor | Tier 3 | 72.1
January | 2021 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
January | 2021 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
January | 2021 |  | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
January | 2021 |  | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34
January | 2021 |  | Royse - Commerce 69-kV Line Conversion to 138-kV Project | Oncor | Tier 3 | 72.1
February | 2021 |  | LRGV Import Project | AEPSC | Tier 1 | 73.4
February | 2021 |  | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
February | 2021 |  | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
February | 2021 |  | Port Lavaca Area Improvement Project | AEPSC | Tier 2 | 97.8
February | 2021 |  | Midland East Area Project | Oncor | Tier 3 | 88.5
February | 2021 |  | Venus Switch - Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3
March | 2021 | 18RPG001 | LRGV Import Project | AEPSC | Tier 1 | 73.4
March | 2021 | 19RPG009 | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
March | 2021 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
March | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 2 | 97.8
March | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Tier 3 | 38.7
April | 2021 | 18RPG001 | LRGV Import Project | AEPSC | Tier 1 | 73.4
April | 2021 | 19RPG009 | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
April | 2021 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
April | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 2 | 97.8
April | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Tier 3 | 38.7
April | 2021 | 21RPG006 | Algoa Corner to La Marque 138 kV ckt 93 Rebuild Project | CNP | Tier 3 | 34.56
April | 2021 | 21RPG007 | Holliday - Seymour 69 kV Line Project | Oncor | Tier 3 | 44.3
May | 2021 | 18RPG001 | LRGV Import Project | AEPSC | Tier 1 | 73.4
May | 2021 | 19RPG009 | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
May | 2021 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
May | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 2 | 97.8
May | 2021 | 21RPG006 | Algoa Corner to La Marque 138-kV ckt 93 Rebuild Project | CNP | Tier 3 | 34.56
May | 2021 | 21RPG007 | Holliday - Seymour 69 kV Line Project | Oncor | Tier 3 | 44.3
May | 2021 | 21RPG008 | Burnett – Bowie 69-kV Line Upgrade Project | Oncor | Tier 3 | 79.7
May | 2021 | 21RPG009 | Waterfowl Substation Addition Project | CNP | Tier 3 | 42.4
June | 2021 | 18RPG001 | LRGV Import Project | AEPSC | Tier 1 | 73.4
June | 2021 | 19RPG009 | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
June | 2021 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
June | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 2 | 97.8
June | 2021 | 21RPG008 | Burnett – Bowie 69-kV Line Upgrade Project | Oncor | Tier 3 | 79.7
June | 2021 | 21RPG009 | Waterfowl Substation Addition Project | CNP | Tier 3 | 42.4
June | 2021 | 21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138 kV Line Project | Oncor | Tier 2 | 50.7
June | 2021 | 21RPG011 | Flewellen to Peters 138 kV ckt 25 Rebuild Project | CNP | Tier 3 | 76.19
July | 2021 | 18RPG001 | LRGV Import Project | AEPSC | Tier 1 | 73.4
July | 2021 | 19RPG009 | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
July | 2021 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
July | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 2 | 97.8
July | 2021 | 21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138 kV Line Project | Oncor | Tier 2 | 50.7
July | 2021 | 21RPG011 | Flewellen to Peters 138 kV ckt 25 Rebuild Project | CNP | Tier 3 | 76.19
August | 2021 | 18RPG001 | LRGV Import Project | AEPSC | Tier 1 | 73.4
August | 2021 | 19RPG009 | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511
August | 2021 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
August | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 2 | 97.8
August | 2021 | 21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138 kV Line Project | Oncor | Tier 2 | 50.7
August | 2021 | 21RPG012 | Andrews North – Mustang – Paul Davis Tap 138-kV Line Section Project | Oncor | Tier 3 | 37
August | 2021 | 21RPG013 | WA Parish to Nash 138-kV Ckt 02 Rebuild Project | CNP | Tier 3 | 71.75
August | 2021 | 21RPG014 | Mason Switch to Yellowjacket 69-kV Line Transmission Project | AEPSC | Tier 3 | 36.9
September | 2021 | 18RPG001 |  | AEPSC
September | 2021 | 19RPG009 |  | STEC
September | 2021 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
September | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 2 | 97.8
September | 2021 | 21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138-kV Line Project | Oncor | Tier 2 | 50.7
September | 2021 | 21RPG013 | WA Parish to Nash 138-kV Ckt 02 Rebuild Project | CNP | Tier 3 | 71.75
September | 2021 | 21RPG014 | Mason Switch to Yellowjacket 69-kV Line Transmission Project | AEPSC | Tier 3 | 36.9
September | 2021 | 21RPG015 | Munday to Throckmorton 69-V and Albany to Throckmorton 69-kV Line Rebuild Project | AEPSC | Tier 3 | 83.4
September | 2021 | 21RPG016 | TH Wharton - White Oak 138-kV Conversion Project | CNP | Tier 3 | 79.9
September | 2021 | 21RPG017 | Lower Rio Grande Valley System Enhancement Project | ERCOT | Tier 1
October | 2021 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
October | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 2 | 97.8
October | 2021 | 21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138-kV Line Project | Oncor | Tier 2 | 50.7
October | 2021 | 21RPG017 | Lower Rio Grande Valley System Enhancement Project | ERCOT | Tier 1
November | 2021 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
November | 2021 | 21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138-kV Line Project | Oncor | Tier 2 | 50.7
November | 2021 | 21RPG017 | Lower Rio Grande Valley System Enhancement Project | ERCOT | Tier 1
November | 2021 | 21RPG018 | Bay City to Lane City 138-kV Line Rebuild Project | AEPSC | Tier 3 | 33
November | 2021 | 21RPG019 | Howard Road 345/138-kV Switching Station Project | CPS | Tier 3 | 56.3
November | 2021 | 21RPG020 | Galena Park Area 138-kV Conversion Project | CNP | Tier 3 | 52.05
December | 2021 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.26
December | 2021 | 21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138-kV Line Project | Oncor | Tier 2 | 50.7
December | 2021 | 21RPG017 | Lower Rio Grande Valley System Enhancement Project | ERCOT | Tier 1
December | 2021 | 21RPG018 | Bay City to Lane City 138-kV Line Rebuild Project | AEPSC | Tier 3 | 33
December | 2021 | 21RPG019 | Howard Road 345/138-kV Switching Station Project | CPS | Tier 3 | 56.3
December | 2021 | 21RPG020 | Galena Park Area 138-kV Conversion Project | CNP | Tier 3 | 52.05
December | 2021 | 21RPG022 | Marshall Ford-Ruther Ford 138-kV Line Rebuild Project | PEC | Tier 3 | 28.8
December | 2021 | 21RPG023 | Barrilla Junction 69-kV Loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44
December | 2021 | 21RPG024 | Tungsten 138/69-kV Station Transmission Project | AEPSC | Tier 3 | 34.9
January | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.3
January | 2022 | 22RPG001 | Greens Bayou to Clinton 138-kV Conversion Project | CNP | Tier 3 | 88.5
January | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138-kV Line Rebuild Project | PEC | Tier 3 | 28.8
January | 2022 | 21RPG023 | Barrilla Junction 69-kV Loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44
January | 2022 | 21RPG024 | Tungsten 138/69-kV Station Transmission Project | AEPSC | Tier 3 | 34.9
February | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.3
February | 2022 | 22RPG001 | Greens Bayou to Clinton 138-kV Conversion Project | CNP | Tier 3 | 88.5
February | 2022 | 22RPG002 | Abilene South to Putnam 138-kV Transmission Line Rebuild Project | AEPSC | Tier 3 | 31.5
February | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9
February | 2022 | 22RPG004 | Pulsar to Victoria 138-kV line Rebuild Project | AEPSC | Tier 3 | 75.7
March | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.3
March | 2022 | 22RPG002 | Abilene South to Putnam 138-kV Transmission Line Rebuild Project | AEPSC | Tier 3 | 31.5
March | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9
March | 2022 | 22RPG004 | Pulsar to Victoria 138-kV Line Rebuild Project | AEPSC | Tier 3 | 75.7
March | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 | 399.9
March | 2022 | 22RPG006 | Consavvy 345/138-kV Switch Project | Oncor | Tier 3 | 90.2
March | 2022 | 22RPG008 | Bowman Switch 345/138-kV Autotransformers Project | Oncor | Tier 3 | 13
March | 2022 | 22RPG009 | Eden to North Brady 69-kV Line Rebuild Project | AEPSC | Tier 3 | 34
April | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345-kV Loop Project | Oncor | Tier 2 | 71.3
April | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9
April | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 | 399.9
April | 2022 | 22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Tier 3 | 77.8
April | 2022 | 22RPG012 | Partial Rebuild 69-kV Deepwater to Clinton Ckt 33 Project | CNP | Tier 3 | 55.91
April | 2022 | 22RPG006 | Consavvy 345/138-kV Switch Project | Oncor | Tier 3 | 90.2
April | 2022 | 22RPG008 | Bowman Switch 345/138-kV Autotransformers Project | Oncor | Tier 3 | 13
April | 2022 | 22RPG009 | Eden to North Brady 69-kV Line Rebuild Project | AEPSC | Tier 3 | 34
May | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9
May | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 | 399.9
May | 2022 | 22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Tier 3 | 77.8
May | 2022 | 22RPG012 | Partial Rebuild 69-kV Deepwater to Clinton Ckt 33 Project | CNP | Tier 3 | 55.91
May | 2022 | 22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 | 56.2
May | 2022 | 22RPG014 | Red Oak Area Upgrades Project | Oncor | Tier 3 | 63
May | 2022 | 22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | Tier 3 | 62.7
June | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9
June | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 | 399.9
June | 2022 | 22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 | 56.2
June | 2022 | 22RPG014 | Red Oak Area Upgrades Project | Oncor | Tier 3 | 63
June | 2022 | 22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | Tier 3 | 62.7
June | 2022 | 22RPG016 |  | Oncor | Tier 3 | 29.7
June | 2022 | 22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | Tier 3 | 38.8
June | 2022 | 22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | Tier 3 | 34.1
June | 2022 | 22RPG019 | Partial Rebuild of 69 kV HOC to Dunlavy Ckt 40 Project | CNP | Tier 3 | 31.39
June | 2022 | 22RPG020 | Belknap to Fort Griffin 69 kV Line Rebuild Project | AEPSC | Tier 3 | 27.6
July | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9
July | 2022 | 22RPG015 | Tyler Switch – Forest Grove Switch 138-kV Line Project | Oncor | Tier 3 | 62.7
July | 2022 | 22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | Tier 3 | 34.1
July | 2022 | 22RPG019 | Partial Rebuild of 69-kV HOC to Dunlavy Ckt 40 Project | CNP | Tier 3 | 31.39
July | 2022 | 22RPG020 | Belknap to Fort Griffin 69-kV Line Rebuild Project | AEPSC | Tier 3 | 27.6
July | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 | 399.9
August | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9
August | 2022 | 22RPG021 | Tawakoni Area Transmission Project | REC | Tier 2 | 27.5
August | 2022 | 22RPG022 | Hondo Creek to Pearson 69 kV Transmission Line Rebuild Project | STEC | Tier 2 | 37.5
August | 2022 | 22RPG023 | Hill Country 345/138 kV Autotransformer Replacement Project | CPS | Tier 3 | 6.9
August | 2022 | 22RPG024 | Wolf-General Tire-Odessa EHV 138 kV Line Rebuild Project | Oncor | Tier 3 | 60.77
August | 2022 | 22RPG025 | Yucca Drive - Courtney Creek 69 kV Line Conversion to 138 kV Project | Oncor | Tier 3 | 65
August | 2022 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 77.32
August | 2022 | 22RPG027 | East Hutto Area 345/138 kV Project | Oncor and LCRA TSC | Tier 3 | 61.6
August | 2022 | 22RPG028 | Ballinger to Santa Anna 69 kV Transmission Line Rebuild Project | AEPSC | Tier 3 | 64.8
September | 2022 | 22RPG021 | Tawakoni Area Transmission Project | REC | Tier 2 | 27.5
September | 2022 | 22RPG022 | Hondo Creek to Pearson 69 kV Transmission Line Rebuild Project | STEC | Tier 2 | 37.5
September | 2022 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 77.32
September | 2022 | 22RPG029 | Fairland – Lago Vista Transmission Line Rehabilitation Project | LCRA TSC | Tier 3 | 26.9
September | 2022 | 22RPG030 | Buchanan CTEC – Pitsburg Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 32.9
September | 2022 | 22RPG024 | Wolf-General Tire-Odessa EHV 138 kV Line Rebuild Project | Oncor | Tier 3 | 60.77
September | 2022 | 22RPG025 | Yucca Drive - Courtney Creek 69 kV Line Conversion to 138 kV Project | Oncor | Tier 3 | 65
September | 2022 | 22RPG028 | Ballinger to Santa Anna 69 kV Transmission Line Rebuild Project | AEPSC | Tier 3 | 64.8
October | 2022 | 22RPG021 | Tawakoni Area Transmission Project | REC | Tier 2 | 27.5
October | 2022 | 22RPG022 | Hondo Creek to Pearson 69 kV Transmission Line Rebuild Project | STEC | Tier 2 | 37.5
October | 2022 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 77.32
October | 2022 | 22RPG029 | Fairland – Lago Vista Transmission Line Rehabilitation Project | LCRA TSC | Tier 3 | 26.9
October | 2022 | 22RPG030 | Buchanan CTEC – Pitsburg Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 32.9
October | 2022 | 22RPG032 | Tesoro 345/138 kV Switch Project | Oncor | Tier 3 | 50.2
October | 2022 | 22RPG033 | Mountain Top – Blanco – Devils Hill Line Rebuild and Voltage Upgrade Project | PEC | Tier 3 | 37
October | 2022 | 22RPG034 | Temple – Minerva 69 kV Line Rebuild Project | Oncor | Tier 3 | 54.92
October | 2022 | 22RPG035 | Palestine - Crockett 69 kV Line Rebuild Project | Oncor | Tier 3 | 50.89
October | 2022 | 22RPG036 | Taylor Switch – Holland 69 kV Line Section Rebuild Project | Oncor | Tier 3 | 60.8
October | 2022 | 22RPG037 | West Columbia to Burke 138 kV ckt 02 Rebuild Project | CNP | Tier 3 | 43.22
November | 2022 | 22RPG021 | Tawakoni Area Transmission Project | REC | Tier 2 | 27.5
November | 2022 | 22RPG022 | Hondo Creek to Pearson 69 kV Transmission Line Rebuild Project | STEC | Tier 2 | 37.5
November | 2022 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 77.32
November | 2022 | 22RPG032 | Tesoro 345/138 kV Switch Project | Oncor | Tier 3 | 50.2
November | 2022 | 22RPG033 | Mountain Top – Blanco – Devils Hill Line Rebuild and Voltage Upgrade Project | PEC | Tier 3 | 37
November | 2022 | 22RPG034 | Temple – Minerva 69 kV Line Rebuild Project | Oncor | Tier 3 | 54.92
November | 2022 | 22RPG035 | Palestine - Crockett 69 kV Line Rebuild Project | Oncor | Tier 3 | 50.89
November | 2022 | 22RPG036 | Taylor Switch – Holland 69 kV Line Section Rebuild Project | Oncor | Tier 3 | 60.8
November | 2022 | 22RPG037 | West Columbia to Burke 138 kV ckt 02 Rebuild Project | CNP | Tier 3 | 43.22
November | 2022 | 22RPG038 | Clute Substation Addition Project Project | CNP | Tier 3 | 46.2
November | 2022 | 22RPG039 | Eagle Mountain 345/138 kV Switch Rebuild Project | Oncor | Tier 3 | 57
November | 2022 | 22RPG040 | Dupont to Joslin 138 kV Line Rebuild Project | AEPSC | Tier 3 | 46.4
November | 2022 | 22RPG041 | Sienna to Dewalt to Missouri City 138 kV ckt 02 Line Rebuild Project | CNP | Tier 3 | 56.03
December | 2022 | 22RPG021 | Tawakoni Area Transmission Project | REC | Tier 2 | 27.5
December | 2022 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 77.32
December | 2022 | 22RPG032 | Tesoro 345/138 kV Switch Project | Oncor | Tier 3 | 50.2
December | 2022 | 22RPG038 | Clute Substation Addition Project Project | CNP | Tier 3 | 46.2
December | 2022 | 22RPG039 | Eagle Mountain 345/138 kV Switch Rebuild Project | Oncor | Tier 3 | 57
December | 2022 | 22RPG040 | Dupont to Joslin 138 kV Line Rebuild Project | AEPSC | Tier 3 | 46.4
December | 2022 | 22RPG041 | Sienna to Dewalt to Missouri City 138 kV ckt 02 Line Rebuild Project | CNP | Tier 3 | 56.03
December | 2022 | 22RPG042 | Carver to Maxwell 138 kV Line Rebuild Project | AEPSC | Tier 3 | 69.1
December | 2022 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Tier 3 | 31
December | 2022 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Tier 3 | 73.5
December | 2022 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Tier 3 | 60.7
December | 2022 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Tier 3 | 36
December | 2022 | 22RPG047 | Peck to Drive 138 kV Line Project | Oncor | Tier 2 | 36.2
December | 2022 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 281
January | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 77.32
January | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Tier 3 | 31
January | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Tier 3 | 73.5
January | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Tier 3 | 60.7
January | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Tier 3 | 36
January | 2023 | 22RPG047 | Peck to Drive 138 kV Line Project | Oncor | Tier 2 | 36.2
January | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 281
January | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Tier 3 | 84.76
February | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 77.32
February | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2
February | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 281
February | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Tier 3 | 84.76
February | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Tier 3 | 33
February | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15
February | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 33.5
March | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2
March | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 281
March | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15
March | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 33.5
March | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Tier 3 | 71.5
March | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild Project | Oncor | Tier 3 | 34.11
April | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2
April | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 281
April | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56
April | 2023 | 23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Tier 3 | 44.9
April | 2023 | 23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9
April | 2023 | 23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52
May | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2
May | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 281
May | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56
May | 2023 | 23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Tier 3 | 44.9
May | 2023 | 23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9
May | 2023 | 23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52
May | 2023 | 23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2
May | 2023 | 23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38
May | 2023 | 23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 299
May | 2023 | 23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8
June | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 281
June | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56
June | 2023 | 23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2
June | 2023 | 23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38
June | 2023 | 23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 299
June | 2023 | 23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8
June | 2023 | 23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | Tier 3 | 25.9
June | 2023 | 23RPG016 | Oncor Tributary Switch to Vincent Rebuild Project | Oncor | Tier 3 | 29.3
July | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 281
July | 2023 | 23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 299
July | 2023 | 23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8
July | 2023 | 23RPG016 | Oncor Tributary Switch to Vincent Rebuild Project | Oncor | Tier 3 | 29.3
July | 2023 | 23RPG017 | Oncor Watermill 345/138-kV Switch Project | Oncor | Tier 3 | 74.9
August | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 281
August | 2023 | 23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 299
August | 2023 | 23RPG016 | Tributary Switch to Vincent Rebuild Project | Oncor | Tier 3 | 29.3
August | 2023 | 23RPG018 | Arlington Reliability Enhancement Project | Oncor | Tier 2 | 72
August | 2023 | 23RPG019 | Stanton Loop South Dynamic Reactive Power Project | Oncor | Tier 3 | 96.9
August | 2023 | 23RPG020 | Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | Tier 3 | 80
August | 2023 | 23RPG021 | West Columbia to Big Creek ckt 89 Reconductor Project | CNP | Tier 3 | 64.17
August | 2023 | 23RPG022 | McLennan County Transmission Project | Oncor | Tier 3 | 42.31
August | 2023 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 108
September | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 281
September | 2023 | 23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 299
September | 2023 | 23RPG018 | Arlington Reliability Enhancement Project | Oncor | Tier 2 | 72
September | 2023 | 23RPG019 | Stanton Loop South Dynamic Reactive Power Project | Oncor | Tier 3 | 96.9
September | 2023 | 23RPG020 | Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | Tier 3 | 80
September | 2023 | 23RPG021 | West Columbia to Big Creek ckt 89 Reconductor Project | CNP | Tier 3 | 64.17
September | 2023 | 23RPG022 | McLennan County Transmission Project | Oncor | Tier 3 | 42.31
September | 2023 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 108
September | 2023 | 23RPG024 | Big Foot to Dilley Switch 138-kV Conversion Project | AEPSC | Tier 3 | 53.1
September | 2023 | 23RPG025 | Britmoore to Bellaire Ckt 24 Upgrade Project | CNP | Tier 3 | 90.1
September | 2023 | 23RPG026 | Synchronous Condensers Project | WETT | Tier 1 | 468
September | 2023 | 23RPG027 | Bakersfield Dynamic Reactive Substation Upgrade Project | LCRA TSC | Tier 1 | 145
September | 2023 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 38
September | 2023 | 23RPG029 | West Texas Synchronous Condenser Project | Oncor | Tier 1 | 280
October | 2023 | 23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 299
October | 2023 | 23RPG018 | Arlington Reliability Enhancement Project | Oncor | Tier 2 | 72
October | 2023 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 108
October | 2023 | 23RPG025 | Britmoore to Bellaire Ckt 24 Upgrade Project | CNP | Tier 3 | 90.1
October | 2023 | 23RPG026 | Synchronous Condensers Project | WETT | Tier 1 | 468
October | 2023 | 23RPG027 | Bakersfield Dynamic Reactive Substation Upgrade Project | LCRA TSC | Tier 1 | 145
October | 2023 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 38
October | 2023 | 23RPG029 | West Texas Synchronous Condenser Project | Oncor | Tier 1 | 280
October | 2023 | 23RPG030 | Walleye Creek 345/138-kV Switch Project | Oncor | Tier 3 | 74
October | 2023 | 23RPG031 | 345-kV Jeanetta Autotransformer Upgrades Project | CNP | Tier 3 | 47.08
October | 2023 | 23RPG032 | San Miguel to Marion 345-KV Project | BEC | Tier 1 | 258.5
October | 2023 | 23RPG033 | Watermill to Seagoville 138 kV Line Project | Oncor | Tier 3 | 33
November | 2023 | 23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 299
November | 2023 | 23RPG018 | Arlington Reliability Enhancement Project | Oncor | Tier 2 | 72
November | 2023 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 108
November | 2023 | 23RPG026 | Synchronous Condensers Project | WETT | Tier 1 | 468
November | 2023 | 23RPG027 | Bakersfield Dynamic Reactive Substation Upgrade Project | LCRA TSC | Tier 1 | 145
November | 2023 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 38
November | 2023 | 23RPG029 | West Texas Synchronous Condenser Project | Oncor | Tier 1 | 280
November | 2023 | 23RPG031 | 345-kV Jeanetta Autotransformer Upgrades Project | CNP | Tier 3 | 47.08
November | 2023 | 23RPG032 | San Miguel to Marion 345-KV Project | BEC | Tier 1 | 258.5
November | 2023 | 23RPG033 | Watermill to Seagoville 138 kV Line Project | Oncor | Tier 3 | 33
November | 2023 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1
December | 2023 | 23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 299
December | 2023 | 23RPG018 | Arlington Reliability Enhancement Project | Oncor | Tier 2 | 72
December | 2023 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 108
December | 2023 | 23RPG026 | Synchronous Condensers Project | WETT | Tier 1 | 468
December | 2023 | 23RPG027 | Bakersfield Dynamic Reactive Substation Upgrade Project | LCRA TSC | Tier 1 | 145
December | 2023 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 38
December | 2023 | 23RPG029 | West Texas Synchronous Condenser Project | Oncor | Tier 1 | 280
December | 2023 | 23RPG032 | San Miguel to Marion 345-KV Project | BEC | Tier 1 | 258.5
December | 2023 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1
January | 2024 | 23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 299
January | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 108
January | 2024 | 23RPG026 | Synchronous Condensers Project | WETT | Tier 1 | 468
January | 2024 | 23RPG027 | Bakersfield Dynamic Reactive Substation Upgrade Project | LCRA TSC | Tier 1 | 145
January | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 38
January | 2024 | 23RPG029 | West Texas Synchronous Condenser Project | Oncor | Tier 1 | 280
January | 2024 | 23RPG032 | San Miguel to Marion 345-KV Project | BEC | Tier 1 | 258.5
January | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1
January | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 120.7
January | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97
January | 2024 | 24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | Tier 1 | 158
January | 2024 | 24RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 42.5
February | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 108
February | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 38
February | 2024 | 23RPG032 | San Miguel to Marion 345-KV Project | BEC | Tier 1 | 258.5
February | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1
February | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 120.7
February | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97
February | 2024 | 24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | Tier 1 | 158
February | 2024 | 24RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 42.5
February | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8
February | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56
March | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 108
March | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 38
March | 2024 | 23RPG032 | San Miguel to Marion 345-KV Project | BEC | Tier 1 | 258.5
March | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1
March | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 120.7
March | 2024 | 24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | Tier 1 | 158
March | 2024 | 24RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 42.5
March | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8
March | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56
March | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 22.61
March | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 387.7
March | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC and BEC | Tier 3 | 76
March | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2
March | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Tier 3 | 34.5
April | 2024 | 23RPG032 | San Miguel to Marion 345-KV Project | BEC | Tier 1 | 258.5
April | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1
April | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 120.7
April | 2024 | 24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | Tier 1 | 158
April | 2024 | 24RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 42.5
April | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56
April | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 22.61
April | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 387.7
April | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC and BEC | Tier 3 | 76
April | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2
April | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Tier 3 | 34.5
April | 2024 | 24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23
April | 2024 | 24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC and AEN | Tier 3 | 60
May | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1
May | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 120.7
May | 2024 | 24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | Tier 1 | 158
May | 2024 | 24RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 42.5
May | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 22.61
May | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 387.7
May | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2
May | 2024 | 24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23
May | 2024 | 24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC and AEN | Tier 3 | 60
May | 2024 | 24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9
May | 2024 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
May | 2024 | 24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2
June | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1
June | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 120.7
June | 2024 | 24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | Tier 1 | 158
June | 2024 | 24RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 42.5
June | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 22.61
June | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 387.7
June | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2
June | 2024 | 24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9
June | 2024 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
June | 2024 | 24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2
June | 2024 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9
June | 2024 | 24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6
June | 2024 | 24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | Tier 3 | 93.04
June | 2024 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
July | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1
July | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 120.7
July | 2024 | 24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | Tier 1 | 158
July | 2024 | 24RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 42.5
July | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 22.61
July | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 387.7
July | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2
July | 2024 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
July | 2024 | 24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2
July | 2024 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9
July | 2024 | 24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6
July | 2024 | 24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | Tier 3 | 93.04
July | 2024 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
July | 2024 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 103.5
July | 2024 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2
August | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 120.7
August | 2024 | 24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | Tier 1 | 158
August | 2024 | 24RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 42.5
August | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 22.61
August | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 387.7
August | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2
August | 2024 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
August | 2024 | 24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2
August | 2024 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9
August | 2024 | 24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6
August | 2024 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
August | 2024 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 103.5
August | 2024 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2
August | 2024 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
August | 2024 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 94
August | 2024 | 24RPG025 | Gunter 345/138-kV Switch Project | Oncor | Tier 3 | 51.2
August | 2024 | 24RPG026 | Jordan/Mont Belvieu Area Improvement Project | CNP | Tier 3 | 76.89
August | 2024 | 24RPG027 | Long Draw Second 345/138-kV Autotransformer Project | WETT | Tier 3 | 28
September | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 387.7
September | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2
September | 2024 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
September | 2024 | 24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2
September | 2024 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9
September | 2024 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
September | 2024 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 103.5
September | 2024 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2
September | 2024 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
September | 2024 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 94
September | 2024 | 24RPG025 | Gunter 345/138-kV Switch Project | Oncor | Tier 3 | 51.2
September | 2024 | 24RPG026 | Jordan/Mont Belvieu Area Improvement Project | CNP | Tier 3 | 76.89
September | 2024 | 24RPG027 | Long Draw Second 345/138-kV Autotransformer Project | WETT | Tier 3 | 28
September | 2024 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
September | 2024 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03
September | 2024 | 24RPG030 | Partial Rebuild of 138-kV Ckt.05A Sienna Tap to Missouri City Tap Project | CNP | Tier 3 | 28.56
October | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 387.7
October | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2
October | 2024 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
October | 2024 | 24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2
October | 2024 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9
October | 2024 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
October | 2024 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 103.5
October | 2024 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2
October | 2024 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
October | 2024 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 94
October | 2024 | 24RPG025 | Gunter 345/138-kV Switch Project | Oncor | Tier 3 | 51.2
October | 2024 | 24RPG026 | Jordan/Mont Belvieu Area Improvement Project | CNP | Tier 3 | 76.89
October | 2024 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
October | 2024 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03
October | 2024 | 24RPG030 | Partial Rebuild of 138-kV Ckt.05A Sienna Tap to Missouri City Tap Project | CNP | Tier 3 | 28.56
October | 2024 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 | 342
October | 2024 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 | 569.32
November | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 387.7
November | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2
November | 2024 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
November | 2024 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9
November | 2024 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
November | 2024 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 103.5
November | 2024 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2
November | 2024 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
November | 2024 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 94
November | 2024 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
November | 2024 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03
November | 2024 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 | 342
November | 2024 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 | 569.32
November | 2024 | 24RPG033 | MINING 69-kV Substation Conversion Project | CNP | Tier 3 | 34.12
November | 2024 | 24RPG034 | Redwood to San Marcos Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 46.4
November | 2024 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 33
December | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 387.7
December | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2
December | 2024 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
December | 2024 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9
December | 2024 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
December | 2024 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 103.5
December | 2024 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2
December | 2024 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
December | 2024 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 94
December | 2024 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
December | 2024 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03
December | 2024 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 | 342
December | 2024 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 | 569.32
December | 2024 | 24RPG033 | MINING 69-kV Substation Conversion Project | CNP | Tier 3 | 34.12
December | 2024 | 24RPG034 | Redwood to San Marcos Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 46.4
December | 2024 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 33
December | 2024 | 24RPG036 | South Padre Island Rebuild Transmission Project | AEPSC | Tier 3 | 44.5
December | 2024 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Tier 3 | 26.2
December | 2024 | 24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC and PEC | Tier 3 | 66.35
December | 2024 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
December | 2024 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 83
January | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
January | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9
January | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
January | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 103.5
January | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2
January | 2025 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
January | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 94
January | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
January | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03
January | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 | 342
January | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 | 569.32
January | 2025 | 24RPG034 | Redwood to San Marcos Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 46.4
January | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 33
January | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Tier 3 | 26.2
January | 2025 | 24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC and PEC | Tier 3 | 66.35
January | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
January | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 83
January | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61
January | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 271.5
January | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Tier 3 | 28.3
February | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
February | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9
February | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
February | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 103.5
February | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2
February | 2025 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
February | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 94
February | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
February | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03
February | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 | 342
February | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 | 569.32
February | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 33
February | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
February | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 83
February | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61
February | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 271.5
February | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Tier 3 | 28.3
February | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 90
February | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
February | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57
February | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6
March | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
March | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
March | 2025 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
March | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 94
March | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
March | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03
March | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 | 342
March | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 | 569.32
March | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 33
March | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
March | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 83
March | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 271.5
March | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 90
March | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
March | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57
March | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6
March | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88
March | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65
March | 2025 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
March | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86
April | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
April | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
April | 2025 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
April | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 94
April | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
April | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03
April | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 | 342
April | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 | 569.32
April | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 33
April | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
April | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 83
April | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 271.5
April | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 90
April | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
April | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88
April | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65
April | 2025 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
April | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86
May | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
May | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
May | 2025 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
May | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 94
May | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
May | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03
May | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 33
May | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
May | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 83
May | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 271.5
May | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 90
May | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
May | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65
May | 2025 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
May | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86
May | 2025 | 25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11
May | 2025 | 25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47
May | 2025 | 25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5
May | 2025 | 25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3
June | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 744.6
June | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
June | 2025 | 24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5
June | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
June | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03
June | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
June | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 83
June | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 271.5
June | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 90
June | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
June | 2025 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
June | 2025 | 25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11
June | 2025 | 25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47
June | 2025 | 25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5
June | 2025 | 25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3
June | 2025 | 25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 36.2
June | 2025 | 25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | Tier 2 | 74
June | 2025 | 25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | Tier 1 | 110
June | 2025 | 25RPG018 | Childress Area Transmission Improvement Project | AEPSC | Tier 2 | 53
June | 2025 | 25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | Tier 3 | 74.5
June | 2025 | 25RPG020 | Large Load Additions Project | CPS Energy | Tier 1 | 333.7
June | 2025 | 25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | Tier 3 | 35.5
July | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
July | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
July | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
July | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 271.5
July | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 90
July | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
July | 2025 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
July | 2025 | 25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47
July | 2025 | 25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5
July | 2025 | 25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | Tier 2 | 74
July | 2025 | 25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | Tier 1 | 110
July | 2025 | 25RPG018 | Childress Area Transmission Improvement Project | AEPSC | Tier 2 | 53
July | 2025 | 25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | Tier 3 | 74.5
July | 2025 | 25RPG020 | Large Load Additions Project | CPS Energy | Tier 1 | 333.7
July | 2025 | 25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | Tier 3 | 35.5
July | 2025 | 25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor and AEPSC | Tier 1 | 742.2
July | 2025 | 25RPG023 | Dunham 345/138-kV Switch Project | Oncor | Tier 3 | 21.3
July | 2025 | 25RPG024 | Blessing Area Improvements Project | AEPSC | Tier 1 | 256
July | 2025 | 25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | Tier 1 | 9384
July | 2025 | 25RPG026 | Paris Switch to Monticello Switch 345-kV Line Rebuild Project | Oncor | Tier 1 | 231.75
July | 2025 | 25RPG027 | Royse Switch to Edgewood 69-kV Line Conversion to 138-kV Project | Oncor | Tier 3 | 44.72
August | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
August | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
August | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
August | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 271.5
August | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 90
August | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
August | 2025 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
August | 2025 | 25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47
August | 2025 | 25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5
August | 2025 | 25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | Tier 2 | 74
August | 2025 | 25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | Tier 1 | 110
August | 2025 | 25RPG018 | Childress Area Transmission Improvement Project | AEPSC | Tier 2 | 53
August | 2025 | 25RPG020 | Large Load Additions Project | CPS Energy | Tier 1 | 333.7
August | 2025 | 25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor and AEPSC | Tier 1 | 742.2
August | 2025 | 25RPG023 | Dunham 345/138-kV Switch Project | Oncor | Tier 3 | 21.3
August | 2025 | 25RPG024 | Blessing Area Improvements Project | AEPSC | Tier 1 | 256
August | 2025 | 25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | Tier 1 | 9384
August | 2025 | 25RPG026 | Paris Switch to Monticello Switch 345-kV Line Rebuild Project | Oncor | Tier 1 | 231.75
August | 2025 | 25RPG027 | Royse Switch to Edgewood 69-kV Line Conversion to 138-kV Project | Oncor | Tier 3 | 44.72
August | 2025 | 25RPG028 | P.H. Robinson to W.A. Parish 345-kV Hardening Project | CNP | Tier 1 | 511.31
August | 2025 | 25RPG029 | Hillsboro Switch to Elm Mott Switch 69-kV Line Rebuild Project | Oncor | Tier 3 | 52.85
August | 2025 | 25RPG030 | Bonham Switch to Toco Switch 69-kV Line Rebuild Project | Oncor | Tier 3 | 72.83
August | 2025 | 25RPG031 | Sam Switch Resiliency Project | LST | Tier 3 | 17
September | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
September | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
September | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
September | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 271.5
September | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 90
September | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
September | 2025 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
September | 2025 | 25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47
September | 2025 | 25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5
September | 2025 | 25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | Tier 2 | 74
September | 2025 | 25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | Tier 1 | 110
September | 2025 | 25RPG018 | Childress Area Transmission Improvement Project | AEPSC | Tier 2 | 53
September | 2025 | 25RPG020 | Large Load Additions Project | CPS Energy | Tier 1 | 333.7
September | 2025 | 25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor and AEPSC | Tier 1 | 742.2
September | 2025 | 25RPG024 | Blessing Area Improvements Project | AEPSC | Tier 1 | 256
September | 2025 | 25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | Tier 1 | 9384
September | 2025 | 25RPG026 | Paris Switch to Monticello Switch 345-kV Line Rebuild Project | Oncor | Tier 1 | 231.75
September | 2025 | 25RPG028 | P.H. Robinson to W.A. Parish 345-kV Hardening Project | CNP | Tier 1 | 511.31
September | 2025 | 25RPG029 | Hillsboro Switch to Elm Mott Switch 69-kV Line Rebuild Project | Oncor | Tier 3 | 52.85
September | 2025 | 25RPG030 | Bonham Switch to Toco Switch 69-kV Line Rebuild Project | Oncor | Tier 3 | 72.83
September | 2025 | 25RPG031 | Sam Switch Resiliency Project | LST | Tier 3 | 17
September | 2025 | 25RPG032 | Fort Stockton Plant 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 25.7
September | 2025 | 25RPG033 | Oncor Skyview 345/138-kV Switch Project | Oncor | Tier 2 | 56.82
September | 2025 | 25RPG034 | Mulberry Creek 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 32
October | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
October | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 141.65
October | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
October | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 271.5
October | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
October | 2025 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
October | 2025 | 25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47
October | 2025 | 25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5
October | 2025 | 25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | Tier 2 | 74
October | 2025 | 25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | Tier 1 | 110
October | 2025 | 25RPG018 | Childress Area Transmission Improvement Project | AEPSC | Tier 2 | 53
October | 2025 | 25RPG020 | Large Load Additions Project | CPS Energy | Tier 1 | 333.7
October | 2025 | 25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor and AEPSC | Tier 1 | 742.2
October | 2025 | 25RPG024 | Blessing Area Improvements Project | AEPSC | Tier 1 | 256
October | 2025 | 25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | Tier 1 | 9384
October | 2025 | 25RPG026 | Paris Switch to Monticello Switch 345-kV Line Rebuild Project | Oncor | Tier 1 | 231.75
October | 2025 | 25RPG028 | P.H. Robinson to W.A. Parish 345-kV Hardening Project | CNP | Tier 1 | 511.31
October | 2025 | 25RPG031 | Sam Switch Resiliency Project | LST | Tier 3 | 17
October | 2025 | 25RPG032 | Fort Stockton Plant 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 25.7
October | 2025 | 25RPG033 | Oncor Skyview 345/138-kV Switch Project | Oncor | Tier 2 | 56.82
October | 2025 | 25RPG034 | Mulberry Creek 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 32
October | 2025 | 25RPG035 | McDonald Road Switch to Polecat Creek Switch 138-kV Line Project | Oncor | Tier 3 | 26.66
October | 2025 | 25RPG036 | Abilene Northwest 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 33
October | 2025 | 25RPG037 | West Loop Project | LP&L | Tier 1 | 309
November | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
November | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
November | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
November | 2025 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
November | 2025 | 25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47
November | 2025 | 25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5
November | 2025 | 25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | Tier 2 | 74
November | 2025 | 25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | Tier 1 | 110
November | 2025 | 25RPG018 | Childress Area Transmission Improvement Project | AEPSC | Tier 2 | 53
November | 2025 | 25RPG020 | Large Load Additions Project | CPS Energy | Tier 1 | 333.7
November | 2025 | 25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor and AEPSC | Tier 1 | 742.2
November | 2025 | 25RPG024 | Blessing Area Improvements Project | AEPSC | Tier 1 | 256
November | 2025 | 25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | Tier 1 | 9384
November | 2025 | 25RPG026 | Paris Switch to Monticello Switch 345-kV Line Rebuild Project | Oncor | Tier 1 | 231.75
November | 2025 | 25RPG028 | P.H. Robinson to W.A. Parish 345-kV Hardening Project | CNP | Tier 1 | 511.31
November | 2025 | 25RPG033 | Oncor Skyview 345/138-kV Switch Project | Oncor | Tier 2 | 56.82
November | 2025 | 25RPG035 | McDonald Road Switch to Polecat Creek Switch 138-kV Line Project | Oncor | Tier 3 | 26.66
November | 2025 | 25RPG036 | Abilene Northwest 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 33
November | 2025 | 25RPG037 | West Loop Project | LP&L | Tier 1 | 309
November | 2025 | 25RPG038 | Navarro and Ellis Area Reliability Project | Oncor and LST | Tier 1 | 759.95
November | 2025 | 25RPG039 | Southeast Brownsville Large Load Transmission System Improvements Project | STEC | Tier 2 | 96.35
November | 2025 | 25RPG040 | Set 1 North & Central Texas Reliability Project | Oncor | Tier 1 | 1798
November | 2025 | 25RPG041 | Set 1 North Central & South Central Texas Reliability Project | Oncor | Tier 1 | 943.92
November | 2025 | 25RPG042 | Set 2 North & Central Texas Reliability Project | Oncor | Tier 1 | 1330
November | 2025 | 25RPG043 | Set 2 North Central & South Central Texas Reliability Project | Oncor | Tier 1 | 440.79
December | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62
December | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
December | 2025 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
December | 2025 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
December | 2025 | 25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47
December | 2025 | 25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5
December | 2025 | 25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | Tier 2 | 74
December | 2025 | 25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | Tier 1 | 110
December | 2025 | 25RPG020 | Large Load Additions Project | CPS Energy | Tier 1 | 333.7
December | 2025 | 25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor and AEPSC | Tier 1 | 742.2
December | 2025 | 25RPG024 | Blessing Area Improvements Project | AEPSC | Tier 1 | 256
December | 2025 | 25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | Tier 1 | 9384
December | 2025 | 25RPG026 | Paris Switch to Monticello Switch 345-kV Line Rebuild Project | Oncor | Tier 1 | 231.75
December | 2025 | 25RPG028 | P.H. Robinson to W.A. Parish 345-kV Hardening Project | CNP | Tier 1 | 511.31
December | 2025 | 25RPG033 | Oncor Skyview 345/138-kV Switch Project | Oncor | Tier 2 | 56.82
December | 2025 | 25RPG037 | West Loop Project | LP&L | Tier 1 | 309
December | 2025 | 25RPG038 | Navarro and Ellis Area Reliability Project | Oncor and LST | Tier 1 | 759.95
December | 2025 | 25RPG039 | Southeast Brownsville Large Load Transmission System Improvements Project | STEC | Tier 2 | 96.35
December | 2025 | 25RPG040 | Set 1 North & Central Texas Reliability Project | Oncor | Tier 1 | 1798
December | 2025 | 25RPG041 | Set 1 North Central & South Central Texas Reliability Project | Oncor | Tier 1 | 943.92
December | 2025 | 25RPG042 | Set 2 North & Central Texas Reliability Project | Oncor | Tier 1 | 1330
December | 2025 | 25RPG043 | Set 2 North Central & South Central Texas Reliability Project | Oncor | Tier 1 | 440.79
December | 2025 | 25RPG044 | Whitney Autotransformer Upgrade Project | BEC | Tier 3 | 33.5
December | 2025 | 25RPG045 | Alice Area Improvements Transmission Project | AEPSC | Tier 3 | 67
January | 2026 | 24RPG039 | Galveston Region Project | TNMP | Tier 1 | 133.73
January | 2026 | 25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219
January | 2026 | 25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83
January | 2026 | 25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47
January | 2026 | 25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5
January | 2026 | 25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | Tier 2 | 74
January | 2026 | 25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | Tier 1 | 110
January | 2026 | 25RPG020 | Large Load Additions Project | CPS Energy | Tier 1 | 333.7
January | 2026 | 25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor and AEPSC | Tier 1 | 742.2
January | 2026 | 25RPG024 | Blessing Area Improvements Project | AEPSC | Tier 1 | 256
January | 2026 | 25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | Tier 1 | 9384
January | 2026 | 25RPG026 | Paris Switch to Monticello Switch 345-kV Line Rebuild Project | Oncor | Tier 1 | 231.75
January | 2026 | 25RPG028 | P.H. Robinson to W.A. Parish 345-kV Hardening Project | CNP | Tier 1 | 511.31
January | 2026 | 25RPG033 | Oncor Skyview 345/138-kV Switch Project | Oncor | Tier 2 | 56.82
January | 2026 | 25RPG037 | West Loop Project | LP&L | Tier 1 | 309
January | 2026 | 25RPG038 | Navarro and Ellis Area Reliability Project | Oncor and LST | Tier 1 | 759.95
January | 2026 | 25RPG039 | Southeast Brownsville Large Load Transmission System Improvements Project | STEC | Tier 2 | 96.35
January | 2026 | 25RPG040 | Set 1 North & Central Texas Reliability Project | Oncor | Tier 1 | 1798
January | 2026 | 25RPG041 | Set 1 North Central & South Central Texas Reliability Project | Oncor | Tier 1 | 943.92
January | 2026 | 25RPG042 | Set 2 North & Central Texas Reliability Project | Oncor | Tier 1 | 1330
January | 2026 | 25RPG043 | Set 2 North Central & South Central Texas Reliability Project | Oncor | Tier 1 | 440.79
January | 2026 | 25RPG044 | Whitney Autotransformer Upgrade Project | BEC | Tier 3 | 33.5
January | 2026 | 25RPG045 | Alice Area Improvements Transmission Project | AEPSC | Tier 3 | 67
January | 2026 | 25RPG046 | Medina County Large Load Additions Project | STEC | Tier 1 | 492
January | 2026 | 26RPG001 | Euclid 765-kV Substation and Transmission Line Addition Project | LCRA TSC and CEHE | Tier 1 | 1830

## Reviews Complete
Report Month | Report Year | RPG Project ID | RPG Project Name | Submitted Entity | Tier | Estimated Cost ($ Millions) | Review Completion Month
March | 2021 | 20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | January
March | 2021 | 20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | January
March | 2021 | 21RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | March
March | 2021 | 21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | March
April | 2021 | 20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | January
April | 2021 | 20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | January
April | 2021 | 21RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | March
April | 2021 | 21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | March
April | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | April
May | 2021 | 20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | January
May | 2021 | 20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | January
May | 2021 | 21RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | March
May | 2021 | 21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | March
May | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | April
May | 2021 | 21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | May
May | 2021 | 21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | May
June | 2021 | 20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | January
June | 2021 | 20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | January
June | 2021 | 21RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | March
June | 2021 | 21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | March
June | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | April
June | 2021 | 21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | May
June | 2021 | 21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | May
June | 2021 | 21RPG008 | Burnett – Bowie 69 kV Line Upgrade Project | Oncor | Tier 3 | 79.7 | June
June | 2021 | 21RPG009 | Waterfowl Substation Addition | CNP | Tier 3 | 42.4 | June
June | 2021 | 21RPG001 | Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | Tier 2 | 83.2 | June
July | 2021 | 20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | January
July | 2021 | 20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | January
July | 2021 | 1RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | March
July | 2021 | 21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | March
July | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | April
July | 2021 | 21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | May
July | 2021 | 21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | May
July | 2021 | 21RPG008 | Burnett – Bowie 69 kV Line Upgrade Project | Oncor | Tier 3 | 79.7 | June
July | 2021 | 21RPG009 | Waterfowl Substation Addition | CNP | Tier 3 | 42.4 | June
July | 2021 | 21RPG001 | Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | Tier 2 | 83.2 | June
July | 2021 | 21RPG011 | Flewellen to Peters 138 kV ckt 25 Rebuild | CNP | Tier 3 | 76.2 | July
August | 2021 | 20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | January
August | 2021 | 20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | January
August | 2021 | 1RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | March
August | 2021 | 21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | March
August | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | April
August | 2021 | 21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | May
August | 2021 | 21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | May
August | 2021 | 21RPG008 | Burnett – Bowie 69 kV Line Upgrade Project | Oncor | Tier 3 | 79.7 | June
August | 2021 | 21RPG009 | Waterfowl Substation Addition | CNP | Tier 3 | 42.4 | June
August | 2021 | 21RPG001 | Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | Tier 2 | 83.2 | June
August | 2021 | 21RPG011 | Flewellen to Peters 138 kV ckt 25 Rebuild | CNP | Tier 3 | 76.2 | July
August | 2021 | 21RPG012 | Andrews North – Mustang – Paul Davis Tap 138 kV Line Section | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 37 | August
September | 2021 | 20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | January
September | 2021 | 20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | January
September | 2021 | 1RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | March
September | 2021 | 21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | March
September | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | April
September | 2021 | 21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | May
September | 2021 | 21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | May
September | 2021 | 21RPG008 | Burnett – Bowie 69-kV Line Upgrade Project | Oncor | Tier 3 | 79.7 | June
September | 2021 | 21RPG009 | Waterfowl Substation Addition | CNP | Tier 3 | 42.4 | June
September | 2021 | 21RPG001 | Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | Tier 2 | 83.2 | June
September | 2021 | 21RPG011 | Flewellen to Peters 138-kV ckt 25 Rebuild | CNP | Tier 3 | 76.2 | July
September | 2021 | 21RPG012 | Andrews North – Mustang – Paul Davis Tap 138-kV Line Section | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 37 | August
September | 2021 | 21RPG013 | WA Parish to Nash 138-kV Ckt 02 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 71.75 | September
September | 2021 | 21RPG014 | Mason Switch to Yellowjacket 69-kV Line Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 36.9 | September
September | 2021 | 21RPG015 | Munday to Throckmorton 69-kV and Albany to Throckmorton 69-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 83.4 | September
September | 2021 | 21RPG016 | TH Wharton - White Oak 138-kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 79.9 | September
October | 2021 | 20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | January
October | 2021 | 20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | January
October | 2021 | 1RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | March
October | 2021 | 21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | March
October | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | April
October | 2021 | 21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | May
October | 2021 | 21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | May
October | 2021 | 21RPG008 | Burnett – Bowie 69-kV Line Upgrade Project | Oncor | Tier 3 | 79.7 | June
October | 2021 | 21RPG009 | Waterfowl Substation Addition | CNP | Tier 3 | 42.4 | June
October | 2021 | 21RPG001 | Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | Tier 2 | 83.2 | June
October | 2021 | 21RPG011 | Flewellen to Peters 138-kV ckt 25 Rebuild | CNP | Tier 3 | 76.2 | July
October | 2021 | 21RPG012 | Andrews North – Mustang – Paul Davis Tap 138-kV Line Section | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 37 | August
October | 2021 | 21RPG013 | WA Parish to Nash 138-kV Ckt 02 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 71.75 | September
October | 2021 | 21RPG014 | Mason Switch to Yellowjacket 69-kV Line Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 36.9 | September
October | 2021 | 21RPG015 | Munday to Throckmorton 69-kV and Albany to Throckmorton 69-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 83.4 | September
October | 2021 | 21RPG016 | TH Wharton - White Oak 138-kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 79.9 | September
October | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 1 | 101.5 | October
November | 2021 | 20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | January
November | 2021 | 20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | January
November | 2021 | 21RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | March
November | 2021 | 21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | March
November | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | April
November | 2021 | 21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | May
November | 2021 | 21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | May
November | 2021 | 21RPG008 | Burnett – Bowie 69-kV Line Upgrade Project | Oncor | Tier 3 | 79.7 | June
November | 2021 | 21RPG009 | Waterfowl Substation Addition | CNP | Tier 3 | 42.4 | June
November | 2021 | 21RPG001 | Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | Tier 2 | 83.2 | June
November | 2021 | 21RPG011 | Flewellen to Peters 138-kV ckt 25 Rebuild | CNP | Tier 3 | 76.2 | July
November | 2021 | 21RPG012 | Andrews North – Mustang – Paul Davis Tap 138-kV Line Section | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 37 | August
November | 2021 | 21RPG013 | WA Parish to Nash 138-kV Ckt 02 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 71.75 | September
November | 2021 | 21RPG014 | Mason Switch to Yellowjacket 69-kV Line Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 36.9 | September
November | 2021 | 21RPG015 | Munday to Throckmorton 69-kV and Albany to Throckmorton 69-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 83.4 | September
November | 2021 | 21RPG016 | TH Wharton - White Oak 138-kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 79.9 | September
November | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 1 | 101.5 | October
December | 2021 | 20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | January
December | 2021 | 20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | January
December | 2021 | 21RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | March
December | 2021 | 21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | March
December | 2021 | 21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | April
December | 2021 | 21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | May
December | 2021 | 21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | May
December | 2021 | 21RPG008 | Burnett – Bowie 69-kV Line Upgrade Project | Oncor | Tier 3 | 79.7 | June
December | 2021 | 21RPG009 | Waterfowl Substation Addition | CNP | Tier 3 | 42.4 | June
December | 2021 | 21RPG001 | Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | Tier 2 | 83.2 | June
December | 2021 | 21RPG011 | Flewellen to Peters 138-kV ckt 25 Rebuild | CNP | Tier 3 | 76.2 | July
December | 2021 | 21RPG012 | Andrews North – Mustang – Paul Davis Tap 138-kV Line Section | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 37 | August
December | 2021 | 21RPG013 | WA Parish to Nash 138-kV Ckt 02 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 71.75 | September
December | 2021 | 21RPG014 | Mason Switch to Yellowjacket 69-kV Line Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 36.9 | September
December | 2021 | 21RPG015 | Munday to Throckmorton 69-kV and Albany to Throckmorton 69-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 83.4 | September
December | 2021 | 21RPG016 | TH Wharton - White Oak 138-kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 79.9 | September
December | 2021 | 21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 1 | 101.5 | October
December | 2021 | 21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138-kV Line Project | Oncor | Tier 2 | 63.1 | December
December | 2021 | 21RPG017 | Lower Rio Grande Valley System Enhancement Project | ERCOT | Tier 1 | 1280 | December
December | 2021 | 21RPG018 | Bay City to Lane City 138-kV Line Rebuild Project | AEPSC | Tier 3 | 33 | December
December | 2021 | 21RPG019 | Howard Road 345/138-kV Switching Station Project | CPS | Tier 3 | 56.3 | December
December | 2021 | 21RPG020 | Galena Park Area 138-kV Conversion Project | CNP | Tier 3 | 52.05 | December
January | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
January | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
January | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
January | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
February | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
February | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
February | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
February | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
February | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
March | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
March | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
March | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
March | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
March | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
March | 2022 | 22RPG002 | Abilene South to Putnam 138-kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | March
March | 2022 | 22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | March
April | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
April | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
April | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
April | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
April | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
April | 2022 | 22RPG002 | Abilene South to Putnam 138 kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | March
April | 2022 | 22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | March
April | 2022 | 22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | April
April | 2022 | 22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | April
April | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | April
April | 2022 | 22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | April
April | 2022 | 22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | April
May | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
May | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
May | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
May | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
May | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
May | 2022 | 22RPG002 | Abilene South to Putnam 138 kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | March
May | 2022 | 22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | March
May | 2022 | 22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | April
May | 2022 | 22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | April
May | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | April
May | 2022 | 22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | April
May | 2022 | 22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | April
May | 2022 | 22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | May
May | 2022 | 22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | May
June | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
June | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
June | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
June | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
June | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
June | 2022 | 22RPG002 | Abilene South to Putnam 138 kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | March
June | 2022 | 22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | March
June | 2022 | 22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | April
June | 2022 | 22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | April
June | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | April
June | 2022 | 22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | April
June | 2022 | 22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | April
June | 2022 | 22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | May
June | 2022 | 22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | May
June | 2022 | 22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.2 | June
June | 2022 | 22RPG014 | Red Oak Area Upgrades project | Oncor | Tier 3 | 63 | June
June | 2022 | 22RPG016 | Hutto East - Brushy Creek 138kV Line Project | Oncor | Tier 3 | 29.7 | June
June | 2022 | 22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 38.8 | June
July | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
July | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
July | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
July | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
July | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
July | 2022 | 22RPG002 | Abilene South to Putnam 138 kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | March
July | 2022 | 22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | March
July | 2022 | 22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | April
July | 2022 | 22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | April
July | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | April
July | 2022 | 22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | April
July | 2022 | 22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | April
July | 2022 | 22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | May
July | 2022 | 22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | May
July | 2022 | 22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.2 | June
July | 2022 | 22RPG014 | Red Oak Area Upgrades project | Oncor | Tier 3 | 63 | June
July | 2022 | 22RPG016 | Hutto East - Brushy Creek 138kV Line Project | Oncor | Tier 3 | 29.7 | June
July | 2022 | 22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 38.8 | June
July | 2022 | 22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 34.1 | July
July | 2022 | 22RPG019 | Partial Rebuild of 69 kV HOC to Dunlavy Ckt 40 Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 31.39 | July
July | 2022 | 22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 62.7 | July
July | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 399.9 | July
July | 2022 | 22RPG020 | Belknap to Fort Griffin 69 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 27.6 | July
August | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
August | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
August | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
August | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
August | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
August | 2022 | 22RPG002 | Abilene South to Putnam 138 kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | March
August | 2022 | 22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | March
August | 2022 | 22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | April
August | 2022 | 22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | April
August | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | April
August | 2022 | 22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | April
August | 2022 | 22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | April
August | 2022 | 22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | May
August | 2022 | 22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | May
August | 2022 | 22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.2 | June
August | 2022 | 22RPG014 | Red Oak Area Upgrades project | Oncor | Tier 3 | 63 | June
August | 2022 | 22RPG016 | Hutto East - Brushy Creek 138kV Line Project | Oncor | Tier 3 | 29.7 | June
August | 2022 | 22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 38.8 | June
August | 2022 | 22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 34.1 | July
August | 2022 | 22RPG019 | Partial Rebuild of 69 kV HOC to Dunlavy Ckt 40 Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 31.39 | July
August | 2022 | 22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 62.7 | July
August | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 399.9 | July
August | 2022 | 22RPG020 | Belknap to Fort Griffin 69 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 27.6 | July
August | 2022 | 22RPG003 | Roanoke Area Upgrades project | Oncor | Tier 1 | 285.9 | August
August | 2022 | 22RPG010 | Bearkat – North McCamey – Sand Lake 345-kV Transmission Line Addition Project | LCRA TSC, Oncor, WETT | Tier 1 | 477.6 | August
August | 2022 | 22RPG023 | Hill Country 345/138 kV Autotransformer Replacement Project | CPS | Tier 3 | 6.9 | August
September | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
September | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
September | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
September | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
September | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
September | 2022 | 22RPG002 | Abilene South to Putnam 138 kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | March
September | 2022 | 22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | March
September | 2022 | 22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | April
September | 2022 | 22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | April
September | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | April
September | 2022 | 22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | April
September | 2022 | 22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | April
September | 2022 | 22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | May
September | 2022 | 22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | May
September | 2022 | 22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.2 | June
September | 2022 | 22RPG014 | Red Oak Area Upgrades project | Oncor | Tier 3 | 63 | June
September | 2022 | 22RPG016 | Hutto East - Brushy Creek 138kV Line Project | Oncor | Tier 3 | 29.7 | June
September | 2022 | 22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 38.8 | June
September | 2022 | 22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 34.1 | July
September | 2022 | 22RPG019 | Partial Rebuild of 69 kV HOC to Dunlavy Ckt 40 Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 31.39 | July
September | 2022 | 22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 62.7 | July
September | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 399.9 | July
September | 2022 | 22RPG020 | Belknap to Fort Griffin 69 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 27.6 | July
September | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9 | August
September | 2022 | 22RPG010 | Bearkat – North McCamey – Sand Lake 345-kV Transmission Line Addition Project | LCRA TSC, Oncor, WETT | Tier 1 | 477.6 | August
September | 2022 | 22RPG023 | Hill Country 345/138 kV Autotransformer Replacement Project | CPS | Tier 3 | 6.9 | August
September | 2022 | 22RPG024 | Wolf-General Tire-Odessa EHV 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.77 | September
September | 2022 | 22RPG025 | Yucca Drive - Courtney Creek 69 kV Line Conversion to 138 kV Project | Oncor | Tier 3 | 65 | September
September | 2022 | 22RPG027 | East Hutto Area 345/138 kV Project | Oncor, LCRA TSC | Tier 3 | 61.6 | September
September | 2022 | 22RPG028 | Ballinger to Santa Anna 69 kV Transmission Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 64.8 | September
October | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
October | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
October | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
October | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
October | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
October | 2022 | 22RPG002 | Abilene South to Putnam 138 kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | March
October | 2022 | 22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | March
October | 2022 | 22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | April
October | 2022 | 22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | April
October | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | April
October | 2022 | 22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | April
October | 2022 | 22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | April
October | 2022 | 22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | May
October | 2022 | 22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | May
October | 2022 | 22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.2 | June
October | 2022 | 22RPG014 | Red Oak Area Upgrades project | Oncor | Tier 3 | 63 | June
October | 2022 | 22RPG016 | Hutto East - Brushy Creek 138kV Line Project | Oncor | Tier 3 | 29.7 | June
October | 2022 | 22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 38.8 | June
October | 2022 | 22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 34.1 | July
October | 2022 | 22RPG019 | Partial Rebuild of 69 kV HOC to Dunlavy Ckt 40 Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 31.39 | July
October | 2022 | 22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 62.7 | July
October | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 399.9 | July
October | 2022 | 22RPG020 | Belknap to Fort Griffin 69 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 27.6 | July
October | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9 | August
October | 2022 | 22RPG010 | Bearkat – North McCamey – Sand Lake 345-kV Transmission Line Addition Project | LCRA TSC, Oncor, WETT | Tier 1 | 477.6 | August
October | 2022 | 22RPG023 | Hill Country 345/138 kV Autotransformer Replacement Project | CPS | Tier 3 | 6.9 | August
October | 2022 | 22RPG024 | Wolf-General Tire-Odessa EHV 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.77 | September
October | 2022 | 22RPG025 | Yucca Drive - Courtney Creek 69 kV Line Conversion to 138 kV Project | Oncor | Tier 3 | 65 | September
October | 2022 | 22RPG027 | East Hutto Area 345/138 kV Project | Oncor, LCRA TSC | Tier 3 | 61.6 | September
October | 2022 | 22RPG028 | Ballinger to Santa Anna 69 kV Transmission Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 64.8 | September
October | 2022 | 22RPG029 | Fairland – Lago Vista Transmission Line Rehabilitation Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 26.9 | October
October | 2022 | 22RPG030 | Buchanan CTEC – Pitsburg Transmission Line Overhaul Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 32.9 | October
November | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
November | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
November | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
November | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
November | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
November | 2022 | 22RPG002 | Abilene South to Putnam 138 kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | March
November | 2022 | 22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | March
November | 2022 | 22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | April
November | 2022 | 22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | April
November | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | April
November | 2022 | 22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | April
November | 2022 | 22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | April
November | 2022 | 22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | May
November | 2022 | 22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | May
November | 2022 | 22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.2 | June
November | 2022 | 22RPG014 | Red Oak Area Upgrades project | Oncor | Tier 3 | 63 | June
November | 2022 | 22RPG016 | Hutto East - Brushy Creek 138kV Line Project | Oncor | Tier 3 | 29.7 | June
November | 2022 | 22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 38.8 | June
November | 2022 | 22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 34.1 | July
November | 2022 | 22RPG019 | Partial Rebuild of 69 kV HOC to Dunlavy Ckt 40 Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 31.39 | July
November | 2022 | 22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 62.7 | July
November | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 399.9 | July
November | 2022 | 22RPG020 | Belknap to Fort Griffin 69 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 27.6 | July
November | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9 | August
November | 2022 | 22RPG010 | Bearkat – North McCamey – Sand Lake 345-kV Transmission Line Addition Project | LCRA TSC, Oncor, WETT | Tier 1 | 477.6 | August
November | 2022 | 22RPG023 | Hill Country 345/138 kV Autotransformer Replacement Project | CPS | Tier 3 | 6.9 | August
November | 2022 | 22RPG024 | Wolf-General Tire-Odessa EHV 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.77 | September
November | 2022 | 22RPG025 | Yucca Drive - Courtney Creek 69 kV Line Conversion to 138 kV Project | Oncor | Tier 3 | 65 | September
November | 2022 | 22RPG027 | East Hutto Area 345/138 kV Project | Oncor, LCRA TSC | Tier 3 | 61.6 | September
November | 2022 | 22RPG028 | Ballinger to Santa Anna 69 kV Transmission Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 64.8 | September
November | 2022 | 22RPG029 | Fairland – Lago Vista Transmission Line Rehabilitation Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 26.9 | October
November | 2022 | 22RPG030 | Buchanan CTEC – Pitsburg Transmission Line Overhaul Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 32.9 | October
November | 2022 | 22RPG031 | Lakeway - Marble Falls Transmission Line Strom Hardening Project | LCRA PEC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 94.2 | November
November | 2022 | 22RPG032 | Tesoro 345/138 kV Switch Project | Oncor | Tier 3 | 50.2 | November
November | 2022 | 22RPG033 | Mountain Top-Blanco-Devils Hill Line Rebuild and Voltage Upgrade Project | PEC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 37 | November
November | 2022 | 22RPG034 | Temple – Minerva 69 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 54.9 | November
November | 2022 | 22RPG035 | Palestine - Crockett 69 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 50.9 | November
November | 2022 | 22RPG036 | Taylor Switch – Holland 69 kV Line Section Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.8 | November
November | 2022 | 22RPG037 | West Columbia to Burke 138 kV ckt 02 Rebuild Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 43.2 | November
December | 2022 | 21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | January
December | 2022 | 21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | January
December | 2022 | 21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | January
December | 2022 | 21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | January
December | 2022 | 22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | February
December | 2022 | 22RPG002 | Abilene South to Putnam 138 kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | March
December | 2022 | 22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | March
December | 2022 | 22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | April
December | 2022 | 22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | April
December | 2022 | 20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | April
December | 2022 | 22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | April
December | 2022 | 22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | April
December | 2022 | 22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | May
December | 2022 | 22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | May
December | 2022 | 22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.2 | June
December | 2022 | 22RPG014 | Red Oak Area Upgrades project | Oncor | Tier 3 | 63 | June
December | 2022 | 22RPG016 | Hutto East - Brushy Creek 138kV Line Project | Oncor | Tier 3 | 29.7 | June
December | 2022 | 22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 38.8 | June
December | 2022 | 22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 34.1 | July
December | 2022 | 22RPG019 | Partial Rebuild of 69 kV HOC to Dunlavy Ckt 40 Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 31.39 | July
December | 2022 | 22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 62.7 | July
December | 2022 | 22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 399.9 | July
December | 2022 | 22RPG020 | Belknap to Fort Griffin 69 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 27.6 | July
December | 2022 | 22RPG003 | Roanoke Area Upgrades Project | Oncor | Tier 1 | 285.9 | August
December | 2022 | 22RPG010 | Bearkat – North McCamey – Sand Lake 345-kV Transmission Line Addition Project | LCRA TSC, Oncor, WETT | Tier 1 | 477.6 | August
December | 2022 | 22RPG023 | Hill Country 345/138 kV Autotransformer Replacement Project | CPS | Tier 3 | 6.9 | August
December | 2022 | 22RPG024 | Wolf-General Tire-Odessa EHV 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.77 | September
December | 2022 | 22RPG025 | Yucca Drive - Courtney Creek 69 kV Line Conversion to 138 kV Project | Oncor | Tier 3 | 65 | September
December | 2022 | 22RPG027 | East Hutto Area 345/138 kV Project | Oncor, LCRA TSC | Tier 3 | 61.6 | September
December | 2022 | 22RPG028 | Ballinger to Santa Anna 69 kV Transmission Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 64.8 | September
December | 2022 | 22RPG029 | Fairland – Lago Vista Transmission Line Rehabilitation Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 26.9 | October
December | 2022 | 22RPG030 | Buchanan CTEC – Pitsburg Transmission Line Overhaul Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 32.9 | October
December | 2022 | 22RPG031 | Lakeway - Marble Falls Transmission Line Strom Hardening Project | LCRA PEC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 94.2 | November
December | 2022 | 22RPG032 | Tesoro 345/138 kV Switch Project | Oncor | Tier 3 | 50.2 | November
December | 2022 | 22RPG033 | Mountain Top-Blanco-Devils Hill Line Rebuild and Voltage Upgrade Project | PEC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 37 | November
December | 2022 | 22RPG034 | Temple – Minerva 69 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 54.9 | November
December | 2022 | 22RPG035 | Palestine - Crockett 69 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 50.9 | November
December | 2022 | 22RPG036 | Taylor Switch – Holland 69 kV Line Section Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.8 | November
December | 2022 | 22RPG037 | West Columbia to Burke 138 kV ckt 02 Rebuild Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 43.2 | November
December | 2022 | 22RPG021 | Tawakoni Area Transmission Project | REC | Tier 2 | 42.4 | December
December | 2022 | 22RPG022 | Hondo Creek to Pearson 69 kV Transmission Line Rebuild Project | STEC | Tier 2 | 37.5 | December
December | 2022 | 22RPG038 | Clute Substation Addition Project | CNP | Tier 3 | 46.2 | December
December | 2022 | 22RPG039 | Eagle Mountain 345/138 kV Switch Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 57 | December
December | 2022 | 22RPG040 | Dupont to Joslin 138 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 46.4 | December
December | 2022 | 22RPG041 | Sienna to Dewalt to Missouri City 138 kV ckt 02 Line Rebuild Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.03 | December
December | 2022 | 22RPG042 | Carver to Maxwell 138 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 69.1 | December
January | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
January | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
January | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
January | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
February | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
February | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
February | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
February | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
February | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
February | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
February | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
March | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
March | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
March | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
March | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
March | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
March | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
March | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
March | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15 | March
March | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33.5 | March
March | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | March
March | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | March
April | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
April | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
April | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
April | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
April | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
April | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
April | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
April | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15 | March
April | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33.5 | March
April | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | March
April | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | March
May | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
May | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
May | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
May | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
May | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
May | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
May | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
May | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15 | March
May | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33.5 | March
May | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | March
May | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | March
May | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2 | May
May | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56 | May
May | 2023 | 23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | May
May | 2023 | 23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9 | May
May | 2023 | 23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52 | May
May | 2023 | 23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2 | May
May | 2023 | 23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38 | May
June | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
June | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
June | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
June | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
June | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
June | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
June | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
June | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15 | March
June | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33.5 | March
June | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | March
June | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | March
June | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2 | May
June | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56 | May
June | 2023 | 23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | May
June | 2023 | 23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9 | May
June | 2023 | 23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52 | May
June | 2023 | 23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2 | May
June | 2023 | 23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38 | May
June | 2023 | 23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8 | June
June | 2023 | 23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 25.9 | June
July | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
July | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
July | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
July | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
July | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
July | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
July | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
July | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15 | March
July | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33.5 | March
July | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | March
July | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | March
July | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2 | May
July | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56 | May
July | 2023 | 23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | May
July | 2023 | 23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9 | May
July | 2023 | 23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52 | May
July | 2023 | 23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2 | May
July | 2023 | 23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38 | May
July | 2023 | 23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8 | June
July | 2023 | 23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 25.9 | June
July | 2023 | 23RPG016 | Oncor Tributary Switch – Vincent Rebuild Project | Oncor | Tier 3 | 29.3 | July
July | 2023 | 23RPG017 | Watermill 345/138-kV Switch Project | Oncor | Tier 3 | 74.9 | July
August | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
August | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
August | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
August | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
August | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
August | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
August | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
August | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15 | March
August | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33.5 | March
August | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | March
August | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | March
August | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2 | May
August | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56 | May
August | 2023 | 23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | May
August | 2023 | 23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9 | May
August | 2023 | 23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52 | May
August | 2023 | 23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2 | May
August | 2023 | 23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38 | May
August | 2023 | 23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8 | June
August | 2023 | 23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 25.9 | June
August | 2023 | 23RPG016 | Tributary Switch – Vincent Rebuild Project | Oncor | Tier 3 | 29.3 | July
August | 2023 | 23RPG017 | Watermill 345/138-kV Switch Project | Oncor | Tier 3 | 74.9 | July
August | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 329.1 | August
August | 2023 | 23RPG019 | Stanton Loop South Dynamic Reactive Power Project | Oncor | Tier 3 | 96.9 | August
August | 2023 | 23RPG020 | Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | Tier 3 | 80 | August
September | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
September | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
September | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
September | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
September | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
September | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
September | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
September | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15 | March
September | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33.5 | March
September | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | March
September | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | March
September | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2 | May
September | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56 | May
September | 2023 | 23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | May
September | 2023 | 23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9 | May
September | 2023 | 23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52 | May
September | 2023 | 23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2 | May
September | 2023 | 23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38 | May
September | 2023 | 23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8 | June
September | 2023 | 23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 25.9 | June
September | 2023 | 23RPG016 | Tributary Switch – Vincent Rebuild Project | Oncor | Tier 3 | 29.3 | July
September | 2023 | 23RPG017 | Watermill 345/138-kV Switch Project | Oncor | Tier 3 | 74.9 | July
September | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 329.1 | August
September | 2023 | 23RPG019 | Stanton Loop South Dynamic Reactive Power Project | Oncor | Tier 3 | 96.9 | August
September | 2023 | 23RPG020 | Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | Tier 3 | 80 | August
September | 2023 | 23RPG021 | West Columbia to Big Creek ckt 89 Reconductor Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 64.17 | September
September | 2023 | 23RPG022 | McLennan County Transmission Project | Oncor | Tier 3 | 42.31 | September
September | 2023 | 23RPG024 | Big Foot to Dilley Switch 138-kV Conversion Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 53.1 | September
September | 2023 | 23RPG025 | Britmoore to Bellaire Ckt 24 Upgrade Project | CNP | Tier 3 | 90.1 | September
October | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
October | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
October | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
October | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
October | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
October | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
October | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
October | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15 | March
October | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33.5 | March
October | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | March
October | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | March
October | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2 | May
October | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56 | May
October | 2023 | 23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | May
October | 2023 | 23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9 | May
October | 2023 | 23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52 | May
October | 2023 | 23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2 | May
October | 2023 | 23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38 | May
October | 2023 | 23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8 | June
October | 2023 | 23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 25.9 | June
October | 2023 | 23RPG016 | Tributary Switch – Vincent Rebuild Project | Oncor | Tier 3 | 29.3 | July
October | 2023 | 23RPG017 | Watermill 345/138-kV Switch Project | Oncor | Tier 3 | 74.9 | July
October | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 329.1 | August
October | 2023 | 23RPG019 | Stanton Loop South Dynamic Reactive Power Project | Oncor | Tier 3 | 96.9 | August
October | 2023 | 23RPG020 | Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | Tier 3 | 80 | August
October | 2023 | 23RPG021 | West Columbia to Big Creek ckt 89 Reconductor Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 64.17 | September
October | 2023 | 23RPG022 | McLennan County Transmission Project | Oncor | Tier 3 | 42.31 | September
October | 2023 | 23RPG024 | Big Foot to Dilley Switch 138-kV Conversion Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 53.1 | September
October | 2023 | 23RPG025 | Britmoore to Bellaire Ckt 24 Upgrade Project | CNP | Tier 3 | 90.1 | September
October | 2023 | 23RPG030 | Walleye Creek 345/138-kV Switch Project | Oncor | Tier 3 | 74 | October
October | 2023 | 23RPG031 | 345-kV Jeanetta Autotransformer Upgrades Project | CNP | Tier 3 | 47.08 | October
November | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
November | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
November | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
November | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
November | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
November | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
November | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
November | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15 | March
November | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33.5 | March
November | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | March
November | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | March
November | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2 | May
November | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56 | May
November | 2023 | 23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | May
November | 2023 | 23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9 | May
November | 2023 | 23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52 | May
November | 2023 | 23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2 | May
November | 2023 | 23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38 | May
November | 2023 | 23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8 | June
November | 2023 | 23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 25.9 | June
November | 2023 | 23RPG016 | Tributary Switch – Vincent Rebuild Project | Oncor | Tier 3 | 29.3 | July
November | 2023 | 23RPG017 | Watermill 345/138-kV Switch Project | Oncor | Tier 3 | 74.9 | July
November | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 329.1 | August
November | 2023 | 23RPG019 | Stanton Loop South Dynamic Reactive Power Project | Oncor | Tier 3 | 96.9 | August
November | 2023 | 23RPG020 | Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | Tier 3 | 80 | August
November | 2023 | 23RPG021 | West Columbia to Big Creek ckt 89 Reconductor Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 64.17 | September
November | 2023 | 23RPG022 | McLennan County Transmission Project | Oncor | Tier 3 | 42.31 | September
November | 2023 | 23RPG024 | Big Foot to Dilley Switch 138-kV Conversion Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 53.1 | September
November | 2023 | 23RPG025 | Britmoore to Bellaire Ckt 24 Upgrade Project | CNP | Tier 3 | 90.1 | September
November | 2023 | 23RPG030 | Walleye Creek 345/138-kV Switch Project | Oncor | Tier 3 | 74 | October
November | 2023 | 23RPG031 | 345-kV Jeanetta Autotransformer Upgrades Project | CNP | Tier 3 | 47.08 | October
November | 2023 | 23RPG033 | Watermill to Seagoville 138 kV Line Project | Oncor | Tier 3 | 33 | November
December | 2023 | 22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | January
December | 2023 | 22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | January
December | 2023 | 22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | January
December | 2023 | 22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | January
December | 2023 | 22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | February
December | 2023 | 23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | February
December | 2023 | 23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | February
December | 2023 | 23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Tier 3 | 35.15 | March
December | 2023 | 23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33.5 | March
December | 2023 | 23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | March
December | 2023 | 23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | March
December | 2023 | 22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2 | May
December | 2023 | 23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56 | May
December | 2023 | 23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | May
December | 2023 | 23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9 | May
December | 2023 | 23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52 | May
December | 2023 | 23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2 | May
December | 2023 | 23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38 | May
December | 2023 | 23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8 | June
December | 2023 | 23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 25.9 | June
December | 2023 | 23RPG016 | Tributary Switch – Vincent Rebuild Project | Oncor | Tier 3 | 29.3 | July
December | 2023 | 23RPG017 | Watermill 345/138-kV Switch Project | Oncor | Tier 3 | 74.9 | July
December | 2023 | 22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 329.1 | August
December | 2023 | 23RPG019 | Stanton Loop South Dynamic Reactive Power Project | Oncor | Tier 3 | 96.9 | August
December | 2023 | 23RPG020 | Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | Tier 3 | 80 | August
December | 2023 | 23RPG021 | West Columbia to Big Creek ckt 89 Reconductor Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 64.17 | September
December | 2023 | 23RPG022 | McLennan County Transmission Project | Oncor | Tier 3 | 42.31 | September
December | 2023 | 23RPG024 | Big Foot to Dilley Switch 138-kV Conversion Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 53.1 | September
December | 2023 | 23RPG025 | Britmoore to Bellaire Ckt 24 Upgrade Project | CNP | Tier 3 | 90.1 | September
December | 2023 | 23RPG030 | Walleye Creek 345/138-kV Switch Project | Oncor | Tier 3 | 74 | October
December | 2023 | 23RPG031 | 345-kV Jeanetta Autotransformer Upgrades Project | CNP | Tier 3 | 47.08 | October
December | 2023 | 23RPG033 | Watermill to Seagoville 138 kV Line Project | Oncor | Tier 3 | 33 | November
December | 2023 | 23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 273.1 | December
December | 2023 | 23RPG018 | Arlington Reliability Enhancement Project | Oncor | Tier 2 | 73 | December
December | 2023 | 23RPG026 | Synchronous Condensers Project | WETT | Tier 1 | 467.7 | December
December | 2023 | 23RPG026 | Bakersfield Dynamic Reactive Substation Upgrade Project | LCRA TSC | Tier 1 | 144.5 | December
December | 2023 | 23RPG029 | West Texas Synchronous Condenser Project | Oncor | Tier 1 | 280 | December
February | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
February | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
February | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
February | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
March | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
March | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
March | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
March | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
March | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | March
April | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
April | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
April | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
April | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
April | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | March
April | 2024 | 23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | April
April | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC & BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | April
April | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | April
May | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
May | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
May | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
May | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
May | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | March
May | 2024 | 23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | April
May | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC & BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | April
May | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | April
May | 2024 | 24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23 | May
May | 2024 | 24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC & AEN | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | May
May | 2024 | 24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9 | May
June | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
June | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
June | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
June | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
June | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | March
June | 2024 | 23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | April
June | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC & BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | April
June | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | April
June | 2024 | 24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23 | May
June | 2024 | 24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC & AEN | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | May
June | 2024 | 24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9 | May
June | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1 | 1120 | June
July | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
July | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
July | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
July | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
July | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | March
July | 2024 | 23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | April
July | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC & BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | April
July | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | April
July | 2024 | 24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23 | May
July | 2024 | 24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC & AEN | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | May
July | 2024 | 24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9 | May
July | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1 | 1120 | June
July | 2024 | 23RPG003 | Energy Eastside 345/138-kV Switching Station Project | CPS Energy | Reclassified from Tier 1 to Tier 3 per Protocol | 47 | July
July | 2024 | 23RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 45.7 | July
July | 2024 | 24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | July
July | 2024 | 24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | Tier 3 | 93.04 | July
August | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
August | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
August | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
August | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
August | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | March
August | 2024 | 23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | April
August | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC & BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | April
August | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | April
August | 2024 | 24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23 | May
August | 2024 | 24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC & AEN | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | May
August | 2024 | 24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9 | May
August | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1 | 1120 | June
August | 2024 | 23RPG003 | Energy Eastside 345/138-kV Switching Station Project | CPS Energy | Reclassified from Tier 1 to Tier 3 per Protocol | 47 | July
August | 2024 | 23RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 45.7 | July
August | 2024 | 24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | July
August | 2024 | 24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | Tier 3 | 93.04 | July
August | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 272.6 | August
August | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 26.03 | August
September | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
September | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
September | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
September | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
September | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | March
September | 2024 | 23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | April
September | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC & BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | April
September | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | April
September | 2024 | 24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23 | May
September | 2024 | 24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC & AEN | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | May
September | 2024 | 24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9 | May
September | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1 | 1120 | June
September | 2024 | 23RPG003 | Energy Eastside 345/138-kV Switching Station Project | CPS Energy | Reclassified from Tier 1 to Tier 3 per Protocol | 47 | July
September | 2024 | 23RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 45.7 | July
September | 2024 | 24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | July
September | 2024 | 24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | Tier 3 | 93.04 | July
September | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 272.6 | August
September | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 26.03 | August
September | 2024 | 24RPG025 | Gunter 345/138-kV Switch Project | Oncor | Tier 3 | 51.2 | September
September | 2024 | 24RPG026 | Jordan/Mont Belvieu Area Improvement Project | CNP | Tier 3 | 76.89 | September
September | 2024 | 24RPG027 | Long Draw Second 345/138-kV Autotransformer Project | WETT | Tier 3 | 28 | September
October | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
October | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
October | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
October | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
October | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | March
October | 2024 | 23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | April
October | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC & BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | April
October | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | April
October | 2024 | 24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23 | May
October | 2024 | 24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC & AEN | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | May
October | 2024 | 24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9 | May
October | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1 | 1120 | June
October | 2024 | 23RPG003 | Energy Eastside 345/138-kV Switching Station Project | CPS Energy | Reclassified from Tier 1 to Tier 3 per Protocol | 47 | July
October | 2024 | 23RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 45.7 | July
October | 2024 | 24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | July
October | 2024 | 24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | Tier 3 | 93.04 | July
October | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 272.6 | August
October | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 26.03 | August
October | 2024 | 24RPG025 | Gunter 345/138-kV Switch Project | Oncor | Tier 3 | 51.2 | September
October | 2024 | 24RPG026 | Jordan/Mont Belvieu Area Improvement Project | CNP | Tier 3 | 76.89 | September
October | 2024 | 24RPG027 | Long Draw Second 345/138-kV Autotransformer Project | WETT | Tier 3 | 28 | September
October | 2024 | 24RPG030 | Partial Rebuild of 138-kV Ckt.05A Sienna Tap to Missouri City Tap Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 28.56 | October
October | 2024 | 24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2 | October
November | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
November | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
November | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
November | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
November | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | March
November | 2024 | 23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | April
November | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC & BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | April
November | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | April
November | 2024 | 24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23 | May
November | 2024 | 24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC & AEN | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | May
November | 2024 | 24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9 | May
November | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1 | 1120 | June
November | 2024 | 23RPG003 | Energy Eastside 345/138-kV Switching Station Project | CPS Energy | Reclassified from Tier 1 to Tier 3 per Protocol | 47 | July
November | 2024 | 23RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 45.7 | July
November | 2024 | 24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | July
November | 2024 | 24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | Tier 3 | 93.04 | July
November | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 272.6 | August
November | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 26.03 | August
November | 2024 | 24RPG025 | Gunter 345/138-kV Switch Project | Oncor | Tier 3 | 51.2 | September
November | 2024 | 24RPG026 | Jordan/Mont Belvieu Area Improvement Project | CNP | Tier 3 | 76.89 | September
November | 2024 | 24RPG027 | Long Draw Second 345/138-kV Autotransformer Project | WETT | Tier 3 | 28 | September
November | 2024 | 24RPG030 | Partial Rebuild of 138-kV Ckt.05A Sienna Tap to Missouri City Tap Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 28.56 | October
November | 2024 | 24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2 | October
December | 2024 | 24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | February
December | 2024 | 23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | February
December | 2024 | 23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | February
December | 2024 | 24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | February
December | 2024 | 24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | March
December | 2024 | 23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | April
December | 2024 | 24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC & BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | April
December | 2024 | 24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | April
December | 2024 | 24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23 | May
December | 2024 | 24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC & AEN | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | May
December | 2024 | 24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9 | May
December | 2024 | 23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1 | 1120 | June
December | 2024 | 23RPG003 | Energy Eastside 345/138-kV Switching Station Project | CPS Energy | Reclassified from Tier 1 to Tier 3 per Protocol | 47 | July
December | 2024 | 23RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 45.7 | July
December | 2024 | 24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | July
December | 2024 | 24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | Tier 3 | 93.04 | July
December | 2024 | 24RPG001 | Temple Area Project | Oncor | Tier 1 | 272.6 | August
December | 2024 | 24RPG007 | Canton Area Loop Project | REC | Tier 2 | 26.03 | August
December | 2024 | 24RPG025 | Gunter 345/138-kV Switch Project | Oncor | Tier 3 | 51.2 | September
December | 2024 | 24RPG026 | Jordan/Mont Belvieu Area Improvement Project | CNP | Tier 3 | 76.89 | September
December | 2024 | 24RPG027 | Long Draw Second 345/138-kV Autotransformer Project | WETT | Tier 3 | 28 | September
December | 2024 | 24RPG030 | Partial Rebuild of 138-kV Ckt.05A Sienna Tap to Missouri City Tap Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 28.56 | October
December | 2024 | 24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2 | October
December | 2024 | 24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 423.8 | December
December | 2024 | 24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2 | December
December | 2024 | 24RPG033 | MINING 69-kV Substation Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.12 | December
December | 2024 | 24RPG034 | Redwood to San Marcos Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 46.4 | December
December | 2024 | 24RPG036 | South Padre Island Rebuild Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.5 | December
January | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
January | 2025 | 24RPG0378 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
January | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
February | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
February | 2025 | 24RPG0378 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
February | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
February | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
February | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
February | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
February | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
March | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
March | 2025 | 24RPG0378 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
March | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
March | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
March | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
March | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
March | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
March | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | March
March | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | March
April | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
April | 2025 | 24RPG0378 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
April | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
April | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
April | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
April | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
April | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
April | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | March
April | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | March
April | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | April
April | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | April
April | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | April
April | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | April
April | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | April
May | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
May | 2025 | 24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
May | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
May | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
May | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
May | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
May | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
May | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | March
May | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | March
May | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | April
May | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | April
May | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | April
May | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | April
May | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | April
May | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor & LCRA TSC | Tier 2 | 97.7 | May
May | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 34 | May
May | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 84.3 | May
May | 2025 | 25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11 | May
June | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
June | 2025 | 24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
June | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
June | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
June | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
June | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
June | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
June | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | March
June | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | March
June | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | April
June | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | April
June | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | April
June | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | April
June | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | April
June | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor & LCRA TSC | Tier 2 | 97.7 | May
June | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 34 | May
June | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 84.3 | May
June | 2025 | 25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11 | May
June | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 855.3 | June
June | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03 | June
June | 2025 | 25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3 | June
June | 2025 | 25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 36.2 | June
July | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
July | 2025 | 24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
July | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
July | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
July | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
July | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
July | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
July | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | March
July | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | March
July | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | April
July | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | April
July | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | April
July | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | April
July | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | April
July | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor & LCRA TSC | Tier 2 | 97.7 | May
July | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 34 | May
July | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 84.3 | May
July | 2025 | 25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11 | May
July | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 855.3 | June
July | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03 | June
July | 2025 | 25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3 | June
July | 2025 | 25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 36.2 | June
July | 2025 | 25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | Tier 3 | 74.5 | July
July | 2025 | 25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | Tier 3 | 35.5 | July
August | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
August | 2025 | 24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
August | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
August | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
August | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
August | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
August | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
August | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | March
August | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | March
August | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | April
August | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | April
August | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | April
August | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | April
August | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | April
August | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor & LCRA TSC | Tier 2 | 97.7 | May
August | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 34 | May
August | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 84.3 | May
August | 2025 | 25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11 | May
August | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 855.3 | June
August | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03 | June
August | 2025 | 25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3 | June
August | 2025 | 25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 36.2 | June
August | 2025 | 25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | Tier 3 | 74.5 | July
August | 2025 | 25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | Tier 3 | 35.5 | July
August | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 84 | August
August | 2025 | 25RPG023 | Dunham 345/138-kV Switch Project | Oncor | Tier 3 | 21.3 | August
August | 2025 | 25RPG027 | Royse Switch to Edgewood 69-kV Line Conversion to 138-kV Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.72 | August
September | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
September | 2025 | 24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
September | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
September | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
September | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
September | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
September | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
September | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | March
September | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | March
September | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | April
September | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | April
September | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | April
September | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | April
September | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | April
September | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor & LCRA TSC | Tier 2 | 97.7 | May
September | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 34 | May
September | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 84.3 | May
September | 2025 | 25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11 | May
September | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 855.3 | June
September | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03 | June
September | 2025 | 25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3 | June
September | 2025 | 25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 36.2 | June
September | 2025 | 25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | Tier 3 | 74.5 | July
September | 2025 | 25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | Tier 3 | 35.5 | July
September | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 84 | August
September | 2025 | 25RPG023 | Dunham 345/138-kV Switch Project | Oncor | Tier 3 | 21.3 | August
September | 2025 | 25RPG027 | Royse Switch to Edgewood 69-kV Line Conversion to 138-kV Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.72 | August
September | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 545.3 | September
September | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 281.2 | September
September | 2025 | 25RPG029 | Hillsboro Switch to Elm Mott Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 52.85 | September
September | 2025 | 25RPG030 | Bonham Switch to Toco Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 72.83 | September
September | 2025 | 25RPG031 | Sam Switch Resiliency Project | LST | Tier 3 | 17 | September
September | 2025 | 25RPG032 | Fort Stockton Plant 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 25.7 | September
October | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
October | 2025 | 24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
October | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
October | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
October | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
October | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
October | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
October | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | March
October | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | March
October | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | April
October | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | April
October | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | April
October | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | April
October | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | April
October | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor & LCRA TSC | Tier 2 | 97.7 | May
October | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 34 | May
October | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 84.3 | May
October | 2025 | 25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11 | May
October | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 855.3 | June
October | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03 | June
October | 2025 | 25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3 | June
October | 2025 | 25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 36.2 | June
October | 2025 | 25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | Tier 3 | 74.5 | July
October | 2025 | 25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | Tier 3 | 35.5 | July
October | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 84 | August
October | 2025 | 25RPG023 | Dunham 345/138-kV Switch Project | Oncor | Tier 3 | 21.3 | August
October | 2025 | 25RPG027 | Royse Switch to Edgewood 69-kV Line Conversion to 138-kV Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.72 | August
October | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 545.3 | September
October | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 281.2 | September
October | 2025 | 25RPG029 | Hillsboro Switch to Elm Mott Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 52.85 | September
October | 2025 | 25RPG030 | Bonham Switch to Toco Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 72.83 | September
October | 2025 | 25RPG031 | Sam Switch Resiliency Project | LST | Tier 3 | 17 | September
October | 2025 | 25RPG032 | Fort Stockton Plant 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 25.7 | September
October | 2025 | 25RPG034 | Mulberry Creek 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 32 | October
October | 2025 | 25RPG035 | McDonald Road Switch to Polecat Creek Switch 138-kV Line Project | Oncor | Tier 3 | 26.66 | October
October | 2025 | 25RPG036 | Abilene Northwest 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 33 | October
November | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
November | 2025 | 24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
November | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
November | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
November | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
November | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
November | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
November | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | March
November | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | March
November | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | April
November | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | April
November | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | April
November | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | April
November | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | April
November | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor & LCRA TSC | Tier 2 | 97.7 | May
November | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 34 | May
November | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 84.3 | May
November | 2025 | 25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11 | May
November | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 855.3 | June
November | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03 | June
November | 2025 | 25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3 | June
November | 2025 | 25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 36.2 | June
November | 2025 | 25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | Tier 3 | 74.5 | July
November | 2025 | 25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | Tier 3 | 35.5 | July
November | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 84 | August
November | 2025 | 25RPG023 | Dunham 345/138-kV Switch Project | Oncor | Tier 3 | 21.3 | August
November | 2025 | 25RPG027 | Royse Switch to Edgewood 69-kV Line Conversion to 138-kV Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.72 | August
November | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 545.3 | September
November | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 281.2 | September
November | 2025 | 25RPG029 | Hillsboro Switch to Elm Mott Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 52.85 | September
November | 2025 | 25RPG030 | Bonham Switch to Toco Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 72.83 | September
November | 2025 | 25RPG031 | Sam Switch Resiliency Project | LST | Tier 3 | 17 | September
November | 2025 | 25RPG032 | Fort Stockton Plant 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 25.7 | September
November | 2025 | 25RPG034 | Mulberry Creek 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 32 | October
November | 2025 | 25RPG035 | McDonald Road Switch to Polecat Creek Switch 138-kV Line Project | Oncor | Tier 3 | 26.66 | October
November | 2025 | 25RPG036 | Abilene Northwest 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 33 | October
November | 2025 | 25RPG018 | Childress Area Transmission Improvement Project | AEPSC | Tier 2 | 77.3 | November
December | 2025 | 24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | January
December | 2025 | 24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC & PEC | Tier 3 | 66.35 | January
December | 2025 | 24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | January
December | 2025 | 24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | February
December | 2025 | 24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | February
December | 2025 | 24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | February
December | 2025 | 25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | February
December | 2025 | 25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | March
December | 2025 | 25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | March
December | 2025 | 24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | April
December | 2025 | 24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | April
December | 2025 | 25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | April
December | 2025 | 25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | April
December | 2025 | 25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | April
December | 2025 | 24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor & LCRA TSC | Tier 2 | 97.7 | May
December | 2025 | 24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 34 | May
December | 2025 | 24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 84.3 | May
December | 2025 | 25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11 | May
December | 2025 | 24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 855.3 | June
December | 2025 | 24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03 | June
December | 2025 | 25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3 | June
December | 2025 | 25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 36.2 | June
December | 2025 | 25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | Tier 3 | 74.5 | July
December | 2025 | 25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | Tier 3 | 35.5 | July
December | 2025 | 25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 84 | August
December | 2025 | 25RPG023 | Dunham 345/138-kV Switch Project | Oncor | Tier 3 | 21.3 | August
December | 2025 | 25RPG027 | Royse Switch to Edgewood 69-kV Line Conversion to 138-kV Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.72 | August
December | 2025 | 24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 545.3 | September
December | 2025 | 25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 281.2 | September
December | 2025 | 25RPG029 | Hillsboro Switch to Elm Mott Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 52.85 | September
December | 2025 | 25RPG030 | Bonham Switch to Toco Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 72.83 | September
December | 2025 | 25RPG031 | Sam Switch Resiliency Project | LST | Tier 3 | 17 | September
December | 2025 | 25RPG032 | Fort Stockton Plant 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 25.7 | September
December | 2025 | 25RPG034 | Mulberry Creek 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 32 | October
December | 2025 | 25RPG035 | McDonald Road Switch to Polecat Creek Switch 138-kV Line Project | Oncor | Tier 3 | 26.66 | October
December | 2025 | 25RPG036 | Abilene Northwest 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 33 | October
December | 2025 | 25RPG018 | Childress Area Transmission Improvement Project | AEPSC | Tier 2 | 77.3 | November
December | 2025 | 24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62 | December
December | 2025 | 24RPG039 | Galveston Region Project | TNMP | Tier 2 | 95.9 | December
December | 2025 | 25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor & AEPSC | Tier 1 | 742.2 | December
December | 2025 | 25RPG024 | Blessing Area Improvements Project | AEPSC | Tier 1 (Withdrawn) | 256 | December
December | 2025 | 25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | Oncor, CPS, CNP & AEP Texas | Tier 1 | 9384 | December
January | 2026 | 25RPG044 | Whitney Autotransformer Upgrade Project | BEC | Tier 3 | 33.5 | January
January | 2026 | 25RPG045 | Alice Area Improvements Transmission Project | AEPSC | Tier 3 | 67 | January

## All Projects
RPG Project ID | RPG Project Name | Submitted Entity | First Report Month | First Report Year | Tier | Estimated Cost ($ Millions) | Status | Review Completion Month | Review Completion Year
18RPG001 | LRGV Import Project | AEPSC | January | 2020 | Tier 1 | 73.4 | Under Review
19RPG009 | Lower Rio Grande Valley Transmission Expansion Project | STEC | January | 2020 | Tier 1 | 511 | Under Review
| Corpus North Shore Project | AEPSC | January | 2020 | Tier 1 | 259.57 | Under Review
| Frio County Transmission Project | 7x Energy | January | 2020 | Tier 2 | 23 | Under Review
| Quanah Area Improvement Transmission Project | AEPSC | January | 2020 | Tier 2 | 11.3 | Under Review
| Farmersville Area Reliability Project | GP&L | January | 2020 | Tier 2 | 24.37 | Under Review
| W.A. Parish to Westpark Tollway Ckt 09 Rebuild Project | CNP | January | 2020 | Tier 3 | 50.77 | Under Review
| Smith to Mathis 69-kV Line Rebuild Project | AEPSC | February | 2020 | Tier 3 | 38 | Under Review
| Anna Switch - Royse Switch 138-kV Line Upgrade Project | Oncor | March | 2020 | Tier 3 | 91.2 | Under Review
| Lookout Substation SVC Project | GP&L | March | 2020 | Tier 3 | 25 | Under Review
| Texas City Transmission Improvement Project | TNMP | April | 2020 | Tier 2 | 29.3 | Under Review
| Ballinger to San Angelo Concho 69 kV Line Rebuild Project | AEPSC | April | 2020 | Tier 3 | 27 | Under Review
| Moffat to Hasse Voltage Conversion Project | BEC | May | 2020 | Tier 2 | 55.2 | Under Review
| Quarry Field 345-kV Switch Project | Oncor | May | 2020 | Tier 3 | 29 | Under Review
| DeCordova Switching Station Rebuild Project | Oncor | May | 2020 | Tier 3 | 37.5 | Under Review
| Big Spring – Buzzard Draw 69-kV Line Conversion to 138-kV Project | Oncor | June | 2020 | Tier 3 | 32 | Under Review
| Carrollton Northwest 345/138-kV Autotransformer Upgrade Project | Oncor | June | 2020 | Tier 3 | 8.5 | Under Review
| Eagle Mountain to Saginaw 138-kV Double-Circuit Line Upgrade Project | Oncor | July | 2020 | Tier 3 | 32 | Under Review
| Horseshoe Springs Switch – Riverton Switch 138-kV Second Circuit Project | Oncor | July | 2020 | Tier 3 | 52.3 | Under Review
| Everman Switching Station Rebuild Project | Oncor | August | 2020 | Tier 3 | 36 | Under Review
| Coleto Creek to Kenedy SS 138-kV Transmission Project | AEPSC | August | 2020 | Tier 3 | 54.7 | Under Review
| Alamito Creek to Alpine 69-kV Line Rebuild Transmission Project | AEPSC | September | 2020 | Tier 3 | 37 | Under Review
| Tall City – Telephone Road 138-kV Line Rebuild Project | Oncor | September | 2020 | Tier 3 | 23.5 | Under Review
| Mont Belvieu Reliability Upgrades Project | CNP | September | 2020 | Tier 3 | 27.28 | Under Review
20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | October | 2020 | Tier 2 | 71.26 | Completed | April | 2022
| Burma to Sterling City 69-kV Line Rebuild Project | AEPSC | October | 2020 | Tier 3 | 28 | Under Review
| Lake Pauline Area Improvement Project | AEPSC | October | 2020 | Tier 3 | 47.5 | Under Review
| Wallis to Peters Ckt 65 138-kV Line Rebuild Project | CNP | October | 2020 | Tier 3 | 64.78 | Under Review
20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | November | 2020 | Tier 3 | 34 | Completed | January | 2021
20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | December | 2020 | Tier 3 | 72.1 | Completed | January | 2021
21RPG002 | Port Lavaca Area Improvement Project | AEPSC | February | 2021 | Tier 1 | 101.5 | Completed | October | 2021
21RPG003 | Midland East Area Projects | Oncor | February | 2021 | Tier 3 | 88.5 | Completed | March | 2021
21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | February | 2021 | Tier 3 | 10.3 | Completed | March | 2021
21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | March | 2021 | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | Completed | April | 2021
21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | April | 2021 | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | Completed | May | 2021
21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | April | 2021 | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | Completed | May | 2021
21RPG009 | Waterfowl Substation Addition | CNP | May | 2021 | Tier 3 | 42.4 | Completed | June | 2021
21RPG008 | Burnett – Bowie 69 kV Line Upgrade Project | Oncor | May | 2021 | Tier 3 | 79.7 | Completed | June | 2021
21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138-kV Line Project | Oncor | June | 2021 | Tier 2 | 63.1 | Completed | December | 2021
21RPG011 | Flewellen to Peters 138 kV ckt 25 Rebuild | CNP | June | 2021 | Tier 3 | 76.2 | Completed | July | 2021
21RPG001 | Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | June | 2021 | Tier 2 | 83.2 | Completed (no UR record) | June | 2021
21RPG013 | WA Parish to Nash 138-kV Ckt 02 Rebuild Project | CNP | August | 2021 | Reclassified from Tier 3 to Tier 4 per Protocol | 71.75 | Completed | September | 2021
21RPG012 | Andrews North – Mustang – Paul Davis Tap 138 kV Line Section | Oncor | August | 2021 | Reclassified from Tier 3 to Tier 4 per Protocol | 37 | Completed | August | 2021
21RPG014 | Mason Switch to Yellowjacket 69-kV Line Transmission Project | AEPSC | August | 2021 | Reclassified from Tier 3 to Tier 4 per Protocol | 36.9 | Completed | September | 2021
21RPG016 | TH Wharton - White Oak 138-kV Conversion Project | CNP | September | 2021 | Reclassified from Tier 3 to Tier 4 per Protocol | 79.9 | Completed | September | 2021
21RPG015 | Munday to Throckmorton 69-kV and Albany to Throckmorton 69-kV Line Rebuild Project | AEPSC | September | 2021 | Reclassified from Tier 3 to Tier 4 per Protocol | 83.4 | Completed | September | 2021
21RPG017 | Lower Rio Grande Valley System Enhancement Project | ERCOT | September | 2021 | Tier 1 | 1280 | Completed | December | 2021
21RPG018 | Bay City to Lane City 138-kV Line Rebuild Project | AEPSC | November | 2021 | Tier 3 | 33 | Completed | December | 2021
21RPG019 | Howard Road 345/138-kV Switching Station Project | CPS | November | 2021 | Tier 3 | 56.3 | Completed | December | 2021
21RPG020 | Galena Park Area 138-kV Conversion Project | CNP | November | 2021 | Tier 3 | 52.05 | Completed | December | 2021
21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | December | 2021 | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | Completed | January | 2022
21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | December | 2021 | Tier 3 | 44 | Completed | January | 2022
21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | December | 2021 | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | Completed | January | 2022
22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | January | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | Completed | February | 2022
21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | January | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | Completed (no UR record) | January | 2022
22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | February | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | Completed | March | 2022
22RPG002 | Abilene South to Putnam 138-kV Transmission Line Rebuild Project | AEPSC | February | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | Completed | March | 2022
22RPG003 | Roanoke Area Upgrades project | Oncor | February | 2022 | Tier 1 | 285.9 | Completed | August | 2022
22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | March | 2022 | Tier 1 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 399.9 | Completed | July | 2022
22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | March | 2022 | Tier 3 | 90.2 | Completed | April | 2022
22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | March | 2022 | Tier 3 | 13 | Completed | April | 2022
22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | March | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | Completed | April | 2022
22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | April | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | Completed | May | 2022
22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | April | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | Completed | May | 2022
22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | April | 2022 | Tier 3 | 45.2 | Completed (no UR record) | April | 2022
22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | May | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.2 | Completed | June | 2022
22RPG014 | Red Oak Area Upgrades project | Oncor | May | 2022 | Tier 3 | 63 | Completed | June | 2022
22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | May | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 62.7 | Completed | July | 2022
22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | June | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 34.1 | Completed | July | 2022
22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | June | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 38.8 | Completed | June | 2022
22RPG020 | Belknap to Fort Griffin 69 kV Line Rebuild Project | AEPSC | June | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 27.6 | Completed | July | 2022
22RPG019 | Partial Rebuild of 69 kV HOC to Dunlavy Ckt 40 Project | CNP | June | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 31.39 | Completed | July | 2022
22RPG016 | Hutto East - Brushy Creek 138kV Line Project | Oncor | June | 2022 | Tier 3 | 29.7 | Completed | June | 2022
22RPG028 | Ballinger to Santa Anna 69 kV Transmission Line Rebuild Project | AEPSC | August | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 64.8 | Completed | September | 2022
22RPG027 | East Hutto Area 345/138 kV Project | Oncor and LCRA TSC | August | 2022 | Tier 3 | 61.6 | Completed | September | 2022
22RPG026 | Wimberley Loop Project | PEC | August | 2022 | Tier 2 | 61.93 | Completed | February | 2023
22RPG024 | Wolf-General Tire-Odessa EHV 138 kV Line Rebuild Project | Oncor | August | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.77 | Completed | September | 2022
22RPG025 | Yucca Drive - Courtney Creek 69 kV Line Conversion to 138 kV Project | Oncor | August | 2022 | Tier 3 | 65 | Completed | September | 2022
22RPG022 | Hondo Creek to Pearson 69 kV Transmission Line Rebuild Project | STEC | August | 2022 | Tier 2 | 37.5 | Completed | December | 2022
22RPG021 | Tawakoni Area Transmission Project | REC | August | 2022 | Tier 2 | 42.4 | Completed | December | 2022
22RPG023 | Hill Country 345/138 kV Autotransformer Replacement Project | CPS | August | 2022 | Tier 3 | 6.9 | Completed | August | 2022
22RPG010 | Bearkat – North McCamey – Sand Lake 345-kV Transmission Line Addition Project | LCRA TSC, Oncor, WETT | August | 2022 | Tier 1 | 477.6 | Completed (no UR record) | August | 2022
22RPG030 | Buchanan CTEC – Pitsburg Transmission Line Overhaul Project | LCRA TSC | September | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 32.9 | Completed | October | 2022
22RPG029 | Fairland – Lago Vista Transmission Line Rehabilitation Project | LCRA TSC | September | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 26.9 | Completed | October | 2022
22RPG035 | Palestine - Crockett 69 kV Line Rebuild Project | Oncor | October | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 50.9 | Completed | November | 2022
22RPG034 | Temple – Minerva 69 kV Line Rebuild Project | Oncor | October | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 54.9 | Completed | November | 2022
22RPG037 | West Columbia to Burke 138 kV ckt 02 Rebuild Project | CNP | October | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 43.2 | Completed | November | 2022
22RPG036 | Taylor Switch – Holland 69 kV Line Section Rebuild Project | Oncor | October | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.8 | Completed | November | 2022
22RPG033 | Mountain Top-Blanco-Devils Hill Line Rebuild and Voltage Upgrade Project | PEC | October | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 37 | Completed | November | 2022
22RPG032 | Tesoro 345/138 kV Switch Project | Oncor | October | 2022 | Tier 3 | 50.2 | Completed | November | 2022
22RPG041 | Sienna to Dewalt to Missouri City 138 kV ckt 02 Line Rebuild Project | CNP | November | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.03 | Completed | December | 2022
22RPG040 | Dupont to Joslin 138 kV Line Rebuild Project | AEPSC | November | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 46.4 | Completed | December | 2022
22RPG039 | Eagle Mountain 345/138 kV Switch Rebuild Project | Oncor | November | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 57 | Completed | December | 2022
22RPG038 | Clute Substation Addition Project | CNP | November | 2022 | Tier 3 | 46.2 | Completed | December | 2022
22RPG031 | Lakeway - Marble Falls Transmission Line Strom Hardening Project | LCRA PEC | November | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 94.2 | Completed (no UR record) | November | 2022
22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | December | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | Completed | January | 2023
22RPG048 | San Antonio South Reliability Project | CPS | December | 2022 | Tier 1 | 329.1 | Completed | August | 2023
22RPG047 | Peck to Driver 138 kV Line Project | Oncor | December | 2022 | Tier 2 | 36.2 | Completed | May | 2023
22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | December | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | Completed | January | 2023
22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | December | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | Completed | January | 2023
22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | December | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | Completed | January | 2023
22RPG042 | Carver to Maxwell 138 kV Line Rebuild Project | AEPSC | December | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 69.1 | Completed | December | 2022
23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | January | 2023 | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | Completed | February | 2023
23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | February | 2023 | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | Completed | February | 2023
23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | February | 2023 | Reclassified from Tier 1 to Tier 3 per Protocol | 47 | Completed | March | 2023
23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | February | 2023 | Tier 2 | 45.7 | Completed | March | 2023
23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | March | 2023 | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | Completed | March | 2023
23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | March | 2023 | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | Completed | March | 2023
23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | April | 2023 | Tier 3 | 56 | Completed | May | 2023
23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | April | 2023 | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | Completed | May | 2023
23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | April | 2023 | Tier 3 | 56.9 | Completed | May | 2023
23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | April | 2023 | Tier 3 | 52 | Completed | May | 2023
23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | May | 2023 | Tier 3 | 36.8 | Completed | June | 2023
23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | May | 2023 | Tier 1 | 273.1 | Completed | December | 2023
23RPG012 | Stone Lake Area Upgrades Project | CNP | May | 2023 | Tier 3 | 74.38 | Completed | May | 2023
23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | May | 2023 | Tier 3 | 40.2 | Completed | May | 2023
23RPG016 | Oncor Tributary Switch – Vincent Rebuild Project | Oncor | June | 2023 | Tier 3 | 29.3 | Completed | July | 2023
23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | June | 2023 | Reclassified from Tier 3 to Tier 4 per Protocol | 25.9 | Completed | June | 2023
23RPG017 | Watermill 345/138-kV Switch Project | Oncor | July | 2023 | Tier 3 | 74.9 | Completed | July | 2023
23RPG023 | Pecos County Transmission Improvement Project | TNMP | August | 2023 | Tier 1 | 114.8 | Completed | February | 2024
23RPG022 | McLennan County Transmission Project | Oncor | August | 2023 | Tier 3 | 42.31 | Completed | September | 2023
23RPG021 | West Columbia to Big Creek ckt 89 Reconductor Project | CNP | August | 2023 | Reclassified from Tier 3 to Tier 4 per Protocol | 64.17 | Completed | September | 2023
23RPG020 | Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | August | 2023 | Tier 3 | 80 | Completed | August | 2023
23RPG018 | Arlington Reliability Enhancement Project | Oncor | August | 2023 | Tier 2 | 73 | Completed | December | 2023
23RPG019 | Stanton Loop South Dynamic Reactive Power Project | Oncor | August | 2023 | Tier 3 | 96.9 | Completed | August | 2023
23RPG024 | Big Foot to Dilley Switch 138-kV Conversion Project | AEPSC | September | 2023 | Reclassified from Tier 3 to Tier 4 per Protocol | 53.1 | Completed | September | 2023
23RPG029 | West Texas Synchronous Condenser Project | Oncor | September | 2023 | Tier 1 | 280 | Completed | December | 2023
23RPG028 | Rio Medina Project | STEC | September | 2023 | Tier 2 | 71.7 | Completed | February | 2024
23RPG027 | Bakersfield Dynamic Reactive Substation Upgrade Project | LCRA TSC | September | 2023 | Tier 1 | 145 | Under Review
23RPG026 | Synchronous Condensers Project | WETT | September | 2023 | Tier 1 | 144.5 | Completed | December | 2023
23RPG025 | Britmoore to Bellaire Ckt 24 Upgrade Project | CNP | September | 2023 | Tier 3 | 90.1 | Completed | September | 2023
23RPG033 | Watermill to Seagoville 138 kV Line Project | Oncor | October | 2023 | Tier 3 | 33 | Completed | November | 2023
23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | October | 2023 | Tier 1 | 435 | Completed | April | 2024
23RPG031 | 345-kV Jeanetta Autotransformer Upgrades Project | CNP | October | 2023 | Tier 3 | 47.08 | Completed | October | 2023
23RPG030 | Walleye Creek 345/138-kV Switch Project | Oncor | October | 2023 | Tier 3 | 74 | Completed | October | 2023
23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | November | 2023 | Tier 1 | 1120 | Completed | June | 2024
24RPG004 | Omicron Reliability Project | CPS Energy | January | 2024 | Tier 2 | 42.5 | Under Review
24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | January | 2024 | Tier 1 | 158 | Under Review
24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | January | 2024 | Tier 3 | 97 | Completed | February | 2024
24RPG001 | Temple Area Project | Oncor | January | 2024 | Tier 1 | 272.6 | Completed | August | 2024
24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | February | 2024 | Tier 3 | 33.8 | Completed | February | 2024
24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | February | 2024 | Tier 3 | 56 | Completed | March | 2024
24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | March | 2024 | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | Completed | April | 2024
24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | March | 2024 | Tier 1 | 202.2 | Completed | December | 2024
24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC and BEC | March | 2024 | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | Completed | April | 2024
24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | March | 2024 | Tier 1 | 423.8 | Completed | December | 2024
24RPG007 | Canton Area Loop Project | REC | March | 2024 | Tier 2 | 26.03 | Completed | August | 2024
24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC and AEN | April | 2024 | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | Completed | May | 2024
24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | April | 2024 | Tier 3 | 68.23 | Completed | May | 2024
24RPG016 | Rand Area Loop Project | REC | May | 2024 | Tier 2 | 32.2 | Completed | October | 2024
24RPG015 | Delaware Basin State 5 Project | Oncor | May | 2024 | Tier 1 | 855.3 | Completed | June | 2025
24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | May | 2024 | Tier 3 | 77.9 | Completed | May | 2024
24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | June | 2024 | Tier 1 | 110.62 | Completed | December | 2025
24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | June | 2024 | Tier 3 | 93.04 | Completed | July | 2024
24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | June | 2024 | Tier 3 | 87.6 | Completed | July | 2024
24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | June | 2024 | Tier 1 | 118.9 | Completed | February | 2025
24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | July | 2024 | Tier 1 | 158.2 | Completed | February | 2025
24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | July | 2024 | Tier 1 | 100.4 | Completed | February | 2025
24RPG027 | Long Draw Second 345/138-kV Autotransformer Project | WETT | August | 2024 | Tier 3 | 28 | Completed | September | 2024
24RPG026 | Jordan/Mont Belvieu Area Improvement Project | CNP | August | 2024 | Tier 3 | 76.89 | Completed | September | 2024
24RPG025 | Gunter 345/138-kV Switch Project | Oncor | August | 2024 | Tier 3 | 51.2 | Completed | September | 2024
24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | August | 2024 | Tier 2 | 97.7 | Completed | May | 2025
24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | August | 2024 | Tier 1 | 305.5 | Under Review
24RPG030 | Partial Rebuild of 138-kV Ckt.05A Sienna Tap to Missouri City Tap Project | CNP | September | 2024 | Reclassified from Tier 3 to Tier 4 per Protocol | 28.56 | Completed | October | 2024
24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | September | 2024 | Tier 1 | 119.03 | Completed | June | 2025
24RPG028 | Baytown Area Load Addition Project | CNP | September | 2024 | Tier 1 | 545.3 | Completed | September | 2025
24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | October | 2024 | Tier 1 (Not Recommend or Endorsed) | 569.32 | Completed | April | 2025
24RPG031 | Central Texas 345-kV Transmission Project | LST | October | 2024 | Tier 1 (Withdrawn) | 342 | Completed | April | 2025
24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | November | 2024 | Tier 2 | 34 | Completed | May | 2025
24RPG034 | Redwood to San Marcos Transmission Line Upgrade Project | LCRA TSC | November | 2024 | Tier 3 | 46.4 | Completed | December | 2024
24RPG033 | MINING 69-kV Substation Conversion Project | CNP | November | 2024 | Reclassified from Tier 3 to Tier 4 per Protocol | 34.12 | Completed | December | 2024
24RPG036 | South Padre Island Rebuild Transmission Project | AEPSC | December | 2024 | Reclassified from Tier 3 to Tier 4 per Protocol | 44.5 | Completed | December | 2024
24RPG039 | Galveston Region Project | TNMP | December | 2024 | Tier 2 | 95.9 | Completed | December | 2025
24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC and PEC | December | 2024 | Tier 3 | 66.35 | Completed | January | 2025
24RPG040 | Roscoe Area Upgrades Project | Oncor | December | 2024 | Tier 2 | 84.3 | Completed | May | 2025
24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | December | 2024 | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | Completed | January | 2025
24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | January | 2025 | Tier 3 | 98.61 | Completed | January | 2025
25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | January | 2025 | Tier 1 | 281.2 | Completed | September | 2025
25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | January | 2025 | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | Completed | February | 2025
25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | February | 2025 | Tier 3 | 87.6 | Completed | March | 2025
25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | February | 2025 | Tier 1 | 1219 | Under Review
25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | February | 2025 | Tier 3 | 57.57 | Completed | March | 2025
25RPG003 | Hamilton County Conversion Project | BEC | February | 2025 | Tier 2 | 84 | Completed | August | 2025
25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | March | 2025 | Tier 3 | 72.86 | Completed | April | 2025
25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | March | 2025 | Tier 3 | 63.88 | Completed | April | 2025
25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | March | 2025 | Tier 3 | 52.65 | Completed | April | 2025
25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | March | 2025 | Tier 1 | 381.83 | Under Review
25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | May | 2025 | Tier 3 | 26.3 | Completed | June | 2025
25RPG013 | Reactive Power Planning Project | CPS Energy | May | 2025 | Tier 1 | 116.5 | Under Review
25RPG012 | Ammonia Plant Load Project | STEC | May | 2025 | Tier 2 | 65.47 | Under Review
25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | May | 2025 | Tier 3 | 95.11 | Completed | May | 2025
25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | June | 2025 | Tier 3 | 36.2 | Completed | June | 2025
25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | June | 2025 | Tier 2 | 74 | Under Review
25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | June | 2025 | Tier 3 | 35.5 | Completed | July | 2025
25RPG018 | Childress Area Transmission Improvement Project | AEPSC | June | 2025 | Tier 2 | 77.3 | Completed | November | 2025
25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | June | 2025 | Tier 3 | 74.5 | Completed | July | 2025
25RPG020 | Large Load Additions Project | CPS Energy | June | 2025 | Tier 1 | 333.7 | Under Review
25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | June | 2025 | Tier 1 | 110 | Under Review
25RPG026 | Paris Switch to Monticello Switch 345-kV Line Rebuild Project | Oncor | July | 2025 | Tier 1 | 231.75 | Under Review
25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | July | 2025 | Tier 1 | 9384 | Completed | December | 2025
25RPG027 | Royse Switch to Edgewood 69-kV Line Conversion to 138-kV Project | Oncor | July | 2025 | Reclassified from Tier 3 to Tier 4 per Protocol | 44.72 | Completed | August | 2025
25RPG024 | Blessing Area Improvements Project | AEPSC | July | 2025 | Tier 1 (Withdrawn) | 256 | Completed | December | 2025
25RPG023 | Dunham 345/138-kV Switch Project | Oncor | July | 2025 | Tier 3 | 21.3 | Completed | August | 2025
25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor and AEPSC | July | 2025 | Tier 1 | 742.2 | Completed | December | 2025
25RPG031 | Sam Switch Resiliency Project | LST | August | 2025 | Tier 3 | 17 | Completed | September | 2025
25RPG029 | Hillsboro Switch to Elm Mott Switch 69-kV Line Rebuild Project | Oncor | August | 2025 | Reclassified from Tier 3 to Tier 4 per Protocol | 52.85 | Completed | September | 2025
25RPG028 | P.H. Robinson to W.A. Parish 345-kV Hardening Project | CNP | August | 2025 | Tier 1 | 511.31 | Under Review
25RPG030 | Bonham Switch to Toco Switch 69-kV Line Rebuild Project | Oncor | August | 2025 | Reclassified from Tier 3 to Tier 4 per Protocol | 72.83 | Completed | September | 2025
25RPG034 | Mulberry Creek 138-kV Transmission Station Rebuild Project | AEPSC | September | 2025 | Tier 3 | 32 | Completed | October | 2025
25RPG032 | Fort Stockton Plant 138-kV Transmission Station Rebuild Project | AEPSC | September | 2025 | Tier 3 | 25.7 | Completed | September | 2025
25RPG033 | Oncor Skyview 345/138-kV Switch Project | Oncor | September | 2025 | Tier 2 | 56.82 | Under Review
25RPG035 | McDonald Road Switch to Polecat Creek Switch 138-kV Line Project | Oncor | October | 2025 | Tier 3 | 26.66 | Completed | October | 2025
25RPG036 | Abilene Northwest 138-kV Transmission Station Rebuild Project | AEPSC | October | 2025 | Tier 3 | 33 | Completed | October | 2025
25RPG037 | West Loop Project | LP&L | October | 2025 | Tier 1 | 309 | Under Review
25RPG043 | Set 2 North Central & South Central Texas Reliability Project | Oncor | November | 2025 | Tier 1 | 440.79 | Under Review
25RPG042 | Set 2 North & Central Texas Reliability Project | Oncor | November | 2025 | Tier 1 | 1330 | Under Review
25RPG039 | Southeast Brownsville Large Load Transmission System Improvements Project | STEC | November | 2025 | Tier 2 | 96.35 | Under Review
25RPG040 | Set 1 North & Central Texas Reliability Project | Oncor | November | 2025 | Tier 1 | 1798 | Under Review
25RPG041 | Set 1 North Central & South Central Texas Reliability Project | Oncor | November | 2025 | Tier 1 | 943.92 | Under Review
25RPG038 | Navarro and Ellis Area Reliability Project | Oncor and LST | November | 2025 | Tier 1 | 759.95 | Under Review
25RPG045 | Alice Area Improvements Transmission Project | AEPSC | December | 2025 | Tier 3 | 67 | Completed | January | 2026
25RPG044 | Whitney Autotransformer Upgrade Project | BEC | December | 2025 | Tier 3 | 33.5 | Completed | January | 2026
25RPG046 | Medina County Large Load Additions Project | STEC | January | 2026 | Tier 1 | 492 | Under Review
26RPG001 | Euclid 765-kV Substation and Transmission Line Addition Project | LCRA TSC and CEHE | January | 2026 | Tier 1 | 1830 | Under Review

## Project Drivers
RPG Project ID | RPG Project Name | Submitted Entity | Tier | Estimated Cost ($M) | First Report Year | Status | Primary Driver | All Drivers | Data Center Load | Large Load Growth | Load Growth | Line Aging/Rebuild | Unit Retirement | Resilience/Hardening | Renewable Integration | Voltage/Reactive | Thermal Overload/Reliability | Key Evidence | Source Documents
18RPG001 | LRGV Import Project | AEPSC | Tier 1 | 73.4 | 2020 | Under Review | Large Load Growth | Large Load Growth, Load Growth, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y |  |  | Y | Y | Y | Y | (projected load growth and potential industrial load additions) (generally large load with limited lead • Continuous load growth is expected in LRGV. In addition, there have  improve resiliency under normal conditions (all components are in load growth in LRGV (LRGV load forecast by 2030 and 2040 are 3.3 GW and 4 GW, respectively) Improve system resilience and operation flexibility Yes Yes | 2021/ERCOT_LRGV_System_Enhancement_Project_RPG_09152021_final.pdf
19RPG009 | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511 | 2020 | Under Review | Large Load Growth | Large Load Growth, Load Growth, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y |  |  | Y | Y | Y | Y | (projected load growth and potential industrial load additions) (generally large load with limited lead Valley load growth • Continuous load growth is expected in LRGV. In addition, there have  improve resiliency under normal conditions (all components are in load growth in LRGV (LRGV load forecast by 2030 and 2040 are 3.3 GW and 4 GW, respectively) Improve system resilience and operation flexibility Yes Yes – Improve system resilience, including • To integrate potential LNG load, potential transmission • Currently, there is no confirmed LNG load in the Valley | 2020/Lower_Rio_Grande_Valley_Transmission_Expansion_-_Jan_21_RPG.PDF 2021/ERCOT_LRGV_System_Enhancement_Project_RPG_09152021_final.pdf 2021/ERCOT_LRGV_System_Enhancement_Project_RPG_10152021_final.pdf
| Corpus North Shore Project | AEPSC | Tier 1 | 259.57 | 2020 | Under Review | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  |  | Y | Y | serve the following new load additions in the Corpus Area Load Growth” Section of AEP Corpus Christi North Shore Report and • Provide sufficient transmission capacity and address the reliability • Reactive compensation upgrades are anticipated to address local area to address reactive improvements | 2020/AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_05_19_2020.pdf 2020/EIR_AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_01_21_2020.pdf 2020/EIR_AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_02_18_2020.pdf 2020/EIR_AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_03_10_2020.pdf 2021/AEPSC_Corpus_North_Shore_reactive_study_v2.pdf
| Frio County Transmission Project | 7x Energy | Tier 2 | 23 | 2020 | Under Review | Renewable Integration | Line Aging/Rebuild, Renewable Integration |  |  |  | Y |  |  | Y |  |  |  Generation identified as retired or mothballed based on the most address the transmission congestion in Frio County associated with the addition  Address local congestion related to the addition of new renewable generators that economic-driven project to address the transmission congestion | 2020/7X_Frio_County_Project_Study_Scope_01_21_2020_RPG.PDF 2020/7X_Frio_County_Project_Study_Update_02_18_2020_RPG.PDF 2020/Frio_County_Project_EIR_05_19_2020_RPG.PDF
| Quanah Area Improvement Transmission Project | AEPSC | Tier 2 | 11.3 | 2020 | Under Review
| Farmersville Area Reliability Project | GP&L | Tier 2 | 24.37 | 2020 | Under Review | Load Growth | Load Growth, Line Aging/Rebuild, Resilience/Hardening, Thermal Overload/Reliability |  |  | Y | Y |  | Y |  |  | Y |  Project need based on TSP’s criteria (Protocol Section 3.11.4.9(4)) flood plain, and the load growth is expected to the east of the city  Addresses GP&L’s Planning criteria violation o ERCOT shall recommend a project that would address the need under TSP’s criteria as well  Project alternatives will be developed and tested to address the GP&L Planning criteria and any | 2020/GPL_Farmersville_Area_Reliability_Project_2_18_2020.pdf 2020/GPL_Farmersville_Area_Reliability_Project_EIR_5_19_2020_RPG.pdf
| W.A. Parish to Westpark Tollway Ckt 09 Rebuild Project | CNP | Tier 3 | 50.77 | 2020 | Under Review | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
| Smith to Mathis 69-kV Line Rebuild Project | AEPSC | Tier 3 | 38 | 2020 | Under Review | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
| Anna Switch - Royse Switch 138-kV Line Upgrade Project | Oncor | Tier 3 | 91.2 | 2020 | Under Review | Load Growth | Load Growth |  |  | Y
| Lookout Substation SVC Project | GP&L | Tier 3 | 25 | 2020 | Under Review | Voltage/Reactive | Voltage/Reactive | [7 empty] | Y
| Texas City Transmission Improvement Project | TNMP | Tier 2 | 29.3 | 2020 | Under Review | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y |  All six options addressed the reliability issues driven by 93  EIR will address reliability issues primarily driven by a potential 50 MW o Retired and mothballed units were consistent with the 2020 RTP.  ERCOT evaluated following six options to address the reliability issues. | 2020/Texas_City_Transmission_Improvement_Project_-_July_21_RPG.pdf 2020/Texas_City_Transmission_Improvement_Project_-_May_19_RPG.pdf
| Ballinger to San Angelo Concho 69 kV Line Rebuild Project | AEPSC | Tier 3 | 27 | 2020 | Under Review | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
| Moffat to Hasse Voltage Conversion Project | BEC | Tier 2 | 55.2 | 2020 | Under Review | Line Aging/Rebuild | Thermal Overload/Reliability | [8 empty] | Y |  Project need based on TSP’s criteria (Protocol Section 3.11.4.9(4))  Addresses NERC, ERCOT and BEC Planning criteria violations  Project alternatives will be developed and tested to address the BEC Planning criteria and any | 2020/BEC_Moffat_to_Hasse_Voltage_Conversion__EIR_Status_7_21_2020.pdf
| Quarry Field 345-kV Switch Project | Oncor | Tier 3 | 29 | 2020 | Under Review
| DeCordova Switching Station Rebuild Project | Oncor | Tier 3 | 37.5 | 2020 | Under Review | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
| Big Spring – Buzzard Draw 69-kV Line Conversion to 138-kV Project | Oncor | Tier 3 | 32 | 2020 | Under Review | Load Growth | Load Growth |  |  | Y
| Carrollton Northwest 345/138-kV Autotransformer Upgrade Project | Oncor | Tier 3 | 8.5 | 2020 | Under Review | Load Growth | Load Growth |  |  | Y
| Eagle Mountain to Saginaw 138-kV Double-Circuit Line Upgrade Project | Oncor | Tier 3 | 32 | 2020 | Under Review | Data Center Load | Data Center Load, Large Load Growth, Load Growth, Voltage/Reactive, Thermal Overload/Reliability | Y | Y | Y |  |  |  |  | Y | Y |  Address rapid load growth in Roanoke area, existing capacity limitations  Based on comments updated scope to include Denton Data Center load  All recent retired or indefinitely mothballed units will be reviewed and turned off, and forecasted thermal and voltage violations. | 2022/Oncor_Roanoke_Area_Upgrades_EIR_Scope_03_15_2022.pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status (1).pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status (2).pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status.pdf
| Horseshoe Springs Switch – Riverton Switch 138-kV Second Circuit Project | Oncor | Tier 3 | 52.3 | 2020 | Under Review | [11 empty] | substations to accommodate the second circuit addition. | 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
| Everman Switching Station Rebuild Project | Oncor | Tier 3 | 36 | 2020 | Under Review | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
| Coleto Creek to Kenedy SS 138-kV Transmission Project | AEPSC | Tier 3 | 54.7 | 2020 | Under Review | Line Aging/Rebuild | Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  | Y | Y | Y | • Upgrades to address aging infrastructures (reliability upgrades) and December 2024 (upgrades for aging  All recent retired or indefinitely mothballed units were turned off, if not and the aging conditions of the existing lines convert to 138 kV, retire the remaining 11.46 miles north to Victoria. ISD: December 2024  Project alternatives will be tested to address the transmission overload • Upgrades to address reliability needs | 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_May_11_RPG_Final.pdf
| Alamito Creek to Alpine 69-kV Line Rebuild Transmission Project | AEPSC | Tier 3 | 37 | 2020 | Under Review | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
| Tall City – Telephone Road 138-kV Line Rebuild Project | Oncor | Tier 3 | 23.5 | 2020 | Under Review | Line Aging/Rebuild | Large Load Growth, Load Growth, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability, Line Aging/Rebuild |  | Y | Y | Y |  |  | Y | Y | Y |  Addresses the reliability issues primarily driven by new confirmed load additions due issues primarily driven by the new confirmed load additions due to the o All recent retired or indefinitely mothballed units will be turned off, if Allow Better Future Load Growth Line Project for RPG review in June 2021 to address the reliability upgrade option to address the reliability issues at the RPG meetings: • To address the reliability issues, ERCOT evaluated five transmission substations to accommodate the second circuit addition. | 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_Sept_15_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Nov_9_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Oct_15_RPG.pdf 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
| Mont Belvieu Reliability Upgrades Project | CNP | Tier 3 | 27.28 | 2020 | Under Review | Load Growth | Load Growth |  |  | Y
20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | 2020 | Completed | Load Growth | Large Load Growth, Load Growth, Unit Retirement, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y |  | Y |  |  | Y | Y |  Addresses thermal violations, load growth, improves dynamic  Generation Retirement Retired/mothballed units in or near the study region were reviewed and none 138 kV line under X-1+N-1) and introduced four options to address | 2020/ERCOT_EIR_Oncor_Nacogdoches_Lufkin_Scope.pdf 2021/ERCOT_EIR_Oncor_Nacogdoches_Lufkin_081721_Status.pdf 2022/ERCOT_EIR_Oncor_Nacogdoches_Lufkin (1).pdf 2022/ERCOT_EIR_Oncor_Nacogdoches_Lufkin.pdf
| Burma to Sterling City 69-kV Line Rebuild Project | AEPSC | Tier 3 | 28 | 2020 | Under Review | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
| Lake Pauline Area Improvement Project | AEPSC | Tier 3 | 47.5 | 2020 | Under Review | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses the voltage violations under planned maintenance outage to address the challenges and accommodate significant and rapid • All recent retired/indefinitely mothballed units will be reviewed load growth in the area. Resource Assessment (TORA) program and is engaging with BEG to New Load Notification (1-2 years) Commitment for New Load | others/EIR-AEP-Childress-Area-Transmission-Improvement-Project-Scope-RPG-July-2025.pdf 2020/Permian_Basin_Area_Improvement_Updates_-_Dec2020RPG.PDF
| Wallis to Peters Ckt 65 138-kV Line Rebuild Project | CNP | Tier 3 | 64.78 | 2020 | Under Review | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | 2020 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Resilience/Hardening |  |  |  | Y |  | Y |  |  |  |  | others/HamiltonRoad-Maxwell_Factsheet_V9.pdf
20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | 2020 | Completed | Load Growth | Load Growth |  |  | Y
21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 1 | 101.5 | 2021 | Completed | Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | review in February 2021 to address reliability need and aging • The three short-listed options address the reliability need and aging  Addresses aging infrastructure • Both thermal overloads and voltage violations in the Pecos and Reeves  Aging transmission infrastructure December of 2024 (upgrades for aging infrastructure)  All recent retired or indefinitely mothballed units will be reviewed Aging Infrastructure Issue line retirement  Provides better prospects for future load growth and voltage conversion | 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Scope_-_April_6_RPG_Final.pdf 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_Aug_17_RPG.pdf 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_June_15_RPG.pdf 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_May_11_RPG_Final.pdf 2023/TNMP - Pecos County Transmission Improvement Project - RPG.pdf
21RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | 2021 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | o Reliability need driven by new confirmed load additions primarily in the oil o Address the reliability issues primarily driven by new confirmed load experiencing rising power demand, driven by o All recent retired or indefinitely mothballed units will be turned off, if performed to identify the need to serve the projected area load using the ‒ The project was submitted to address ✓ Voltage violations on multiple 138-kV buses | 2020/Oncor_IHS_RPG_Presentation_12152020.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2023/EIR - Oncor Peck to Driver 138 kV Line project Scope_Jan2023.pdf
21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | 2021 | Completed | Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Resilience/Hardening, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  | Y |  | Y | Y |  Address rapid load growth in Roanoke area, existing capacity limitations (NERC) and ERCOT Planning Criteria to address thermal overloads on 81.5 miles of  All recent retired or indefinitely mothballed units will be reviewed and turned off, • The purpose of the project is to address the reliability needs in the Key Takeaway: ERCOT studied several options and recommends Option 1 to address the and forecasted thermal and voltage violations. | others/7-2-oncor-venus-switch-to-sam-switch-345-kv-line-project.pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Scope_03_15_2022.pdf 2023/Oncor_Arlington_Reliability_Enhancement_Project.pdf
21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | 2021 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | 2021 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | 2021 | Completed
21RPG009 | Waterfowl Substation Addition | CNP | Tier 3 | 42.4 | 2021 | Completed
21RPG008 | Burnett – Bowie 69 kV Line Upgrade Project | Oncor | Tier 3 | 79.7 | 2021 | Completed | Load Growth | Load Growth |  |  | Y
21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138-kV Line Project | Oncor | Tier 2 | 63.1 | 2021 | Completed | Large Load Growth | Large Load Growth, Load Growth, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y |  |  |  | Y | Y | Y |  Addresses the reliability issues primarily driven by new confirmed load additions due issues primarily driven by the new confirmed load additions due to the o All recent retired or indefinitely mothballed units will be turned off, if Allow Better Future Load Growth Line Project for RPG review in June 2021 to address the reliability upgrade option to address the reliability issues at the RPG meetings: • To address the reliability issues, ERCOT evaluated five transmission • Develop transmission upgrades to address the reliability | 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_Sept_15_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Nov_9_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Oct_15_RPG.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf
21RPG011 | Flewellen to Peters 138 kV ckt 25 Rebuild | CNP | Tier 3 | 76.2 | 2021 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
21RPG001 | Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | Tier 2 | 83.2 | 2021 | Completed (no UR record) | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | ➢ Address the reliability need driven by rapid load growth in the Delaware to address the challenges and accommodate significant and rapid • Due to the significant load growth and because of lack of long-term load and gas load growth in the Delaware Basin area load growth in the area. Resource Assessment (TORA) program and is engaging with BEG to New Load Notification (1-2 years) Commitment for New Load substations to accommodate the second circuit addition. • As part of the efforts to address the challenge, ERCOT completed the | 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf 2022/LCRA_Oncor_WETT_Bearkat_NorthMcCamey_SandLake_Project_06_15_2022.pdf 2020/Permian_Basin_Area_Improvement_Updates_-_Dec2020RPG.PDF
21RPG013 | WA Parish to Nash 138-kV Ckt 02 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 71.75 | 2021 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
21RPG012 | Andrews North – Mustang – Paul Davis Tap 138 kV Line Section | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 37 | 2021 | Completed
21RPG014 | Mason Switch to Yellowjacket 69-kV Line Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 36.9 | 2021 | Completed
21RPG016 | TH Wharton - White Oak 138-kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 79.9 | 2021 | Completed | Load Growth | Load Growth |  |  | Y
21RPG015 | Munday to Throckmorton 69-kV and Albany to Throckmorton 69-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 83.4 | 2021 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
21RPG017 | Lower Rio Grande Valley System Enhancement Project | ERCOT | Tier 1 | 1280 | 2021 | Completed | Large Load Growth | Large Load Growth, Load Growth, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y |  |  | Y | Y | Y | Y | (projected load growth and potential industrial load additions) (generally large load with limited lead Valley load growth • Continuous load growth is expected in LRGV. In addition, there have  improve resiliency under normal conditions (all components are in load growth in LRGV (LRGV load forecast by 2030 and 2040 are 3.3 GW and 4 GW, respectively) Improve system resilience and operation flexibility Yes Yes – Improve system resilience, including • To integrate potential LNG load, potential transmission • Currently, there is no confirmed LNG load in the Valley | 2020/Lower_Rio_Grande_Valley_Transmission_Expansion_-_Jan_21_RPG.PDF 2021/ERCOT_LRGV_System_Enhancement_Project_RPG_09152021_final.pdf 2021/ERCOT_LRGV_System_Enhancement_Project_RPG_10152021_final.pdf
21RPG018 | Bay City to Lane City 138-kV Line Rebuild Project | AEPSC | Tier 3 | 33 | 2021 | Completed | Line Aging/Rebuild | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y |  All six options addressed the reliability issues driven by 93  EIR will address reliability issues primarily driven by a potential 50 MW review in February 2021 to address reliability need and aging • The three short-listed options address the reliability need and aging  Addresses aging infrastructure o Retired and mothballed units were consistent with the 2020 RTP. and December 2024 (aging infrastructure upgrades) Aging Infrastructure Issue line retirement  Provides better prospects for future load growth and voltage conversion | 2020/Texas_City_Transmission_Improvement_Project_-_July_21_RPG.pdf 2020/Texas_City_Transmission_Improvement_Project_-_May_19_RPG.pdf 2020/EIR_AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_01_21_2020.pdf 2020/EIR_AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_03_10_2020.pdf 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_Aug_17_RPG.pdf
21RPG019 | Howard Road 345/138-kV Switching Station Project | CPS | Tier 3 | 56.3 | 2021 | Completed | Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses thermal overloads in the San Antonio South area • All recent retired/indefinitely mothballed units were reviewed and Improves Long-Term Load Serving Capability for future load growth in the area Addresses reliability violation | 2023/EIR - CPS - San Antonio South Reliability Project - Scope - RPG Feb 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG Apr 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG June 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG Mar 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG May 2023.pdf
21RPG020 | Galena Park Area 138-kV Conversion Project | CNP | Tier 3 | 52.05 | 2021 | Completed | Load Growth | Load Growth |  |  | Y
21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | 2021 | Completed
21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | 2021 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | 2021 | Completed | Line Aging/Rebuild | Large Load Growth, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability, Line Aging/Rebuild |  | Y |  | Y |  | Y | Y | Y | Y | 61262A Hunter to McCarty Lane Storm Hardening 4 Apr 2023 PEC,LCRA Hays 61264B Marshall Ford to Trading Post Storm Hardening 4 Dec 2022 PEC Travis 61266 Trading Post to Cedar Valley Storm Hardening 4 Apr 2024 PEC Travis 61274A PEC_MarshallFord_Paleface_StormHardening 4 May-24 PEC Travis 61268 Cedar Valley to Friendship Storm Hardening 4 Apr-25 PEC Travis 61270 Friendship to Rutherford Storm Hardening 4 Apr-26 PEC Travis – Project need based on TSP’s criteria (Protocol Section 3.11.4.9(4)) • All recent retired/indefinitely mothballed units were reviewed and • The project addresses PEC’s transmission planning criteria | 2022/EIR - PEC Wimberley Loop Transmission Scope and Status Update RPG Oct 2022.pdf 2022/EIR - PEC Wimberley Loop Transmission Status Update RPG Nov 2022.pdf 2023/EIR - PEC Wimberley Loop Transmission - Status Update - RPG Jan 2023.pdf
22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | 2022 | Completed | Load Growth | Load Growth |  |  | Y
21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | 2022 | Completed (no UR record)
22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG002 | Abilene South to Putnam 138-kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG003 | Roanoke Area Upgrades project | Oncor | Tier 1 | 285.9 | 2022 | Completed | Data Center Load | Data Center Load, Large Load Growth, Load Growth, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability | Y | Y | Y |  |  |  | Y | Y | Y | – Address rapid load growth in Roanoke area, existing capacity  Based on comments updated scope to include Denton Data Center load Retire Existing Line 1. Adjusted load up in substations identified in “Area Load Growth – Provides better long-term load serving capability for future load growth in  All recent retired or indefinitely mothballed units will be reviewed and turned off, to address overloads on the two existing 345/138-kV transformers at and forecasted thermal and voltage violations. | 2022/Oncor_Roanoke_Area_Upgrades_EIR_07_19_2022.pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Scope_03_15_2022.pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status (1).pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status (2).pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status.pdf
22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 399.9 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Resilience/Hardening, Thermal Overload/Reliability |  |  |  | Y |  | Y |  |  | Y | o Hunter to McCarty Lane Storm Hardening (TPIT 61262A) o Harper Road - Jack Furman Transmission Line Storm Hardening (TPIT 61440) o Hunt - Ingram Transmission Line Storm Hardening (TPIT 61455) ➢ Addresses the need to rehabilitate aging/obsolete conductor ➢ All recent retired or indefinitely mothballed units will be reviewed and turned ➢ Alternatives will be evaluated to address the project need driver | 2022/EIR-LCRA_TSC_Hays_Energy–Kendall_Corridor_Transmission_Line_Rehabilitation_Projects_Scope.pdf
22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | 2022 | Completed
22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | 2022 | Completed | Load Growth | Load Growth, Resilience/Hardening, Voltage/Reactive, Thermal Overload/Reliability |  |  | Y |  |  | Y |  | Y | Y | • Substantial load growth in Oncor’s southern Stanton Loop area introduces • Increase diversity and resiliency in the 138-kV and 345-kV network | 2024/24RPG024 Oncor and LCRATSC RPG Overview for ERCOT 10162024.pdf
22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | 2022 | Completed (no UR record)
22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.2 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG014 | Red Oak Area Upgrades project | Oncor | Tier 3 | 63 | 2022 | Completed | Large Load Growth | Large Load Growth, Load Growth, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y |  |  |  | Y | Y | Y | ➢ Address the reliability need driven by rapid load growth in the Delaware issues primarily driven by the new confirmed load additions due to the o Address the reliability issues primarily driven by new confirmed load  Addresses thermal violations, load growth, improves dynamic performance experiencing rising power demand, driven by o All recent retired or indefinitely mothballed units will be turned off, if Allow Better Future Load Growth • Due to the significant load growth and because of lack of long-term load and gas load growth in the Delaware Basin area Line Project for RPG review in June 2021 to address the reliability | 2020/Oncor_IHS_RPG_Presentation_12152020.pdf 2021/ERCOT_EIR_Oncor_Nacogdoches_Lufkin_081721_Status.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Nov_9_RPG.pdf 2022/LCRA_Oncor_WETT_Bearkat_NorthMcCamey_SandLake_Project_06_15_2022.pdf
22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 62.7 | 2022 | Completed | Large Load Growth | Large Load Growth, Load Growth, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y |  |  |  | Y | Y | Y |  Addresses the reliability issues primarily driven by new confirmed load additions due issues primarily driven by the new confirmed load additions due to the o All recent retired or indefinitely mothballed units will be turned off, if Allow Better Future Load Growth Line Project for RPG review in June 2021 to address the reliability upgrade option to address the reliability issues at the RPG meetings: • To address the reliability issues, ERCOT evaluated five transmission | 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_Sept_15_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Nov_9_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Oct_15_RPG.pdf
22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 34.1 | 2022 | Completed | Resilience/Hardening | Resilience/Hardening | [5 empty] | Y
22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 38.8 | 2022 | Completed | Load Growth | Load Growth |  |  | Y
22RPG020 | Belknap to Fort Griffin 69 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 27.6 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG019 | Partial Rebuild of 69 kV HOC to Dunlavy Ckt 40 Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 31.39 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG016 | Hutto East - Brushy Creek 138kV Line Project | Oncor | Tier 3 | 29.7 | 2022 | Completed
22RPG028 | Ballinger to Santa Anna 69 kV Transmission Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 64.8 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG027 | East Hutto Area 345/138 kV Project | Oncor and LCRA TSC | Tier 3 | 61.6 | 2022 | Completed
22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | 2022 | Completed | Resilience/Hardening | Large Load Growth, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  |  |  | Y | Y | Y | Y | 61262A Hunter to McCarty Lane Storm Hardening 4 Apr 2023 PEC,LCRA Hays 61264B Marshall Ford to Trading Post Storm Hardening 4 Dec 2022 PEC Travis 61266 Trading Post to Cedar Valley Storm Hardening 4 Apr 2024 PEC Travis 61274A PEC_MarshallFord_Paleface_StormHardening 4 May-24 PEC Travis 61268 Cedar Valley to Friendship Storm Hardening 4 Apr-25 PEC Travis 61270 Friendship to Rutherford Storm Hardening 4 Apr-26 PEC Travis – Project need based on TSP’s criteria (Protocol Section 3.11.4.9(4)) • All recent retired/indefinitely mothballed units were reviewed and • The project addresses PEC’s transmission planning criteria | 2022/EIR - PEC Wimberley Loop Transmission Scope and Status Update RPG Oct 2022.pdf 2022/EIR - PEC Wimberley Loop Transmission Status Update RPG Nov 2022.pdf 2023/EIR - PEC Wimberley Loop Transmission - Status Update - RPG Jan 2023.pdf
22RPG024 | Wolf-General Tire-Odessa EHV 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.77 | 2022 | Completed | Line Aging/Rebuild | Large Load Growth, Load Growth, Line Aging/Rebuild, Unit Retirement, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y | Y |  | Y | Y | Y | – Addresses thermal overloads and load growth o Address the reliability issues primarily driven by new confirmed load  Addresses thermal violations, load growth, improves dynamic  Address rapid load growth in Roanoke area, existing capacity limitations o All recent retired or indefinitely mothballed units will be turned off, if  Generation Retirement Retired/mothballed units in or near the study region were reviewed and none • Due to the significant load growth and because of lack of long-term load and forecasted thermal and voltage violations. • As part of the efforts to address this challenge, ERCOT previously | 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2020/ERCOT_EIR_Oncor_Nacogdoches_Lufkin_Scope.pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Scope_03_15_2022.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG March 2024_.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf
22RPG025 | Yucca Drive - Courtney Creek 69 kV Line Conversion to 138 kV Project | Oncor | Tier 3 | 65 | 2022 | Completed | Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y |  | Y | – Addresses thermal overloads and load growth • All recent retired/indefinitely mothballed units were reviewed and turned off, if | 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf
22RPG022 | Hondo Creek to Pearson 69 kV Transmission Line Rebuild Project | STEC | Tier 2 | 37.5 | 2022 | Completed | Line Aging/Rebuild | Large Load Growth, Load Growth, Line Aging/Rebuild, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  | Y | Y | Y | Y | 61453 Ingram - Jack Furman Transmission Line Storm Hardening May-23 Kerr Tier 4 • All options except for Option 4 address the aging transmission – The project serves a new 129 MW load at the new Rio Medina substation o Aging transmission infrastructure Hardening ‒ All recent retired/indefinitely mothballed units will be reviewed and turned off, if not • Option 3 retires the existing transmission line (Hondo Creek – Castroville Switch 69-kV o Better long-term load serving capability for future load growth in the • Retire the Hondo Creek to Castroville Switch 69-kV line • Retire the Castroville Switch to Castroville Sub 69-kV radial line | 2022/EIR - STEC Hondo Creek to Pearson 69-kV Transmission Line Rebuild Project Scope_Sept2022.pdf 2022/EIR - STEC Hondo Creek to Pearson 69-kV Transmission Line Rebuild Project Status Update Nov2022.pdf 2022/EIR - STEC Hondo Creek to Pearson 69-kV Transmission Line Rebuild Project Status Update Oct2022.pdf 2024/EIR - STEC - Rio Medina - RPG Jan2024.pdf
22RPG021 | Tawakoni Area Transmission Project | REC | Tier 2 | 42.4 | 2022 | Completed | Large Load Growth | Large Load Growth, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  |  |  |  | Y | Y | Y | • All recent retired/indefinitely mothballed units were reviewed and August 2022 to address REC’s Planning criteria violation in the Lake  ERCOT shall recommend a project that would address the need under TSP’s criteria – Develop and test project alternatives to address the REC Planning criteria | 2022/EIR - REC - Tawakoni Area Transmission Project - Status Update - RPG Nov 2022.pdf 2022/EIR - REC - Tawakoni Area Transmission Project - Status Update - RPG Oct 2022.pdf 2022/EIR - REC - Tawakoni Area Transmission Project - Status Update - RPG Sep 2022.pdf
22RPG023 | Hill Country 345/138 kV Autotransformer Replacement Project | CPS | Tier 3 | 6.9 | 2022 | Completed | Line Aging/Rebuild | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – Addresses thermal overloads on 345/138-kV autotransformers and 138-kV – Addresses thermal overloads in the San Antonio South area Aging Infrastructures • All recent retired/indefinitely mothballed units were reviewed and o Addresses reliability violations Lake Thermal/Voltage Violations | 2024/EIR - CPS - Eastside 345_138-kV Switching Station Project - RPG Jun 2024.pdf 2024/EIR-CPS-Eastside-345_138-kV-Switching-Station-Project-RPG-Jul-2024.pdf 2024/EIR_CPS_Omicron_Reliability_Project_Status_Update_RPG_July2024.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Scope - RPG Feb 2023.pdf
22RPG010 | Bearkat – North McCamey – Sand Lake 345-kV Transmission Line Addition Project | LCRA TSC, Oncor, WETT | Tier 1 | 477.6 | 2022 | Completed (no UR record) | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | ➢ Address the reliability need driven by rapid load growth in the Delaware – Addresses post-contingency thermal overloads and voltage violations due – The project is needed to address reliability issues (both thermal overloads and voltage violations) – Large Loads with Singed Interconnection Agreement (IA) were added in Total Large Loads in Delaware Basin 3,361 • Due to the significant load growth and because of lack of long-term load and gas load growth in the Delaware Basin area to significant oil and gas load growth • All recent retired/indefinitely mothballed units will be reviewed injection point to support this high load growth area | 2022/LCRA_Oncor_WETT_Bearkat_NorthMcCamey_SandLake_Project_06_15_2022.pdf 2024/EIR_ONCOR_LCRA_Hartring_to_Upland_138kV_Line_and_Benedum_Autotransformer_Addition_Project_Scope_RPG_October_2024.pdf 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2024/EIR - Oncor - Dalaware Basin Stages 3 and 4 Project - Status Update - RPG September 2024.pdf 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
22RPG030 | Buchanan CTEC – Pitsburg Transmission Line Overhaul Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 32.9 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG029 | Fairland – Lago Vista Transmission Line Rehabilitation Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 26.9 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG035 | Palestine - Crockett 69 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 50.9 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG034 | Temple – Minerva 69 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 54.9 | 2022 | Completed | Line Aging/Rebuild | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – Addresses both thermal overloads and aging infrastructure issues in the • All recent retired/indefinitely mothballed units will be reviewed – This project addresses identified thermal violations, provides additional | 2024/EIR - Oncor - Temple Area Project - Scope - RPG February 2024.pdf 2024/Oncor_Temple_Area_Project_RPG_02122024.pdf 2024/EIR - Oncor - Temple Area Project - Status Update - RPG March 2024_.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG June 2024.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG May 2024.pdf
22RPG037 | West Columbia to Burke 138 kV ckt 02 Rebuild Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 43.2 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG036 | Taylor Switch – Holland 69 kV Line Section Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.8 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG033 | Mountain Top-Blanco-Devils Hill Line Rebuild and Voltage Upgrade Project | PEC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 37 | 2022 | Completed | Line Aging/Rebuild | Large Load Growth, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability, Line Aging/Rebuild |  | Y |  | Y |  | Y | Y | Y | Y | 61262A Hunter to McCarty Lane Storm Hardening 4 Apr 2023 PEC,LCRA Hays 61264B Marshall Ford to Trading Post Storm Hardening 4 Dec 2022 PEC Travis 61266 Trading Post to Cedar Valley Storm Hardening 4 Apr 2024 PEC Travis 61274A PEC_MarshallFord_Paleface_StormHardening 4 May-24 PEC Travis 61268 Cedar Valley to Friendship Storm Hardening 4 Apr-25 PEC Travis 61270 Friendship to Rutherford Storm Hardening 4 Apr-26 PEC Travis – Project need based on TSP’s criteria (Protocol Section 3.11.4.9(4)) • All recent retired/indefinitely mothballed units were reviewed and • The project addresses PEC’s transmission planning criteria | 2022/EIR - PEC Wimberley Loop Transmission Status Update RPG Nov 2022.pdf 2023/EIR - PEC Wimberley Loop Transmission - Status Update - RPG Jan 2023.pdf 2022/EIR - PEC Wimberley Loop Transmission Scope and Status Update RPG Oct 2022.pdf
22RPG032 | Tesoro 345/138 kV Switch Project | Oncor | Tier 3 | 50.2 | 2022 | Completed
22RPG041 | Sienna to Dewalt to Missouri City 138 kV ckt 02 Line Rebuild Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.03 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG040 | Dupont to Joslin 138 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 46.4 | 2022 | Completed | Line Aging/Rebuild | Load Growth, Line Aging/Rebuild, Thermal Overload/Reliability |  |  | Y | Y |  |  |  |  | Y | review in February 2021 to address reliability need and aging • The three short-listed options address the reliability need and aging  Addresses aging infrastructure and December 2024 (aging infrastructure upgrades) Aging Infrastructure Issue line retirement  Provides better prospects for future load growth and voltage conversion • December 2024 for upgrades of aging infrastructure North Carbide Retire existing 69-kV line Retire the existing Port Lavaca STEC tap. – North Carbide 69-kV line 9.56 | 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_Aug_17_RPG.pdf 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_June_15_RPG.pdf
22RPG039 | Eagle Mountain 345/138 kV Switch Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 57 | 2022 | Completed | Line Aging/Rebuild | Large Load Growth, Load Growth, Voltage/Reactive, Thermal Overload/Reliability, Line Aging/Rebuild |  | Y | Y | Y |  |  |  | Y | Y |  Address rapid load growth in Roanoke area, existing capacity limitations  All recent retired or indefinitely mothballed units will be reviewed and turned off, and forecasted thermal and voltage violations. | 2022/Oncor_Roanoke_Area_Upgrades_EIR_Scope_03_15_2022.pdf
22RPG038 | Clute Substation Addition Project | CNP | Tier 3 | 46.2 | 2022 | Completed
22RPG031 | Lakeway - Marble Falls Transmission Line Strom Hardening Project | LCRA PEC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 94.2 | 2022 | Completed (no UR record) | Resilience/Hardening | Resilience/Hardening | [5 empty] | Y
22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 329.1 | 2022 | Completed | Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Unit Retirement, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y | Y |  | Y | Y | Y | – Addresses thermal overloads in the San Antonio South area • Driven by new generation additions in areas south and • All recent retired/indefinitely mothballed units were reviewed and Improves Long-Term Load Serving Capability for future load growth in the area area, and generation retirements local to CPS Energy Addresses reliability violation | 2023/EIR - CPS - San Antonio South Reliability Project - Scope - RPG Feb 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG June 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG May 2023.pdf 2023/San Antonio South Reliability Project.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG Apr 2023.pdf
22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2 | 2022 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses thermal overloads and load growth o Reliability need driven by new confirmed load additions primarily in the oil and gas industry ‒ All recent retired/indefinitely mothballed units will be reviewed and turned off, if not ‒ Provides better long-term load serving capability for future load growth in performed to identify the need to serve the projected area load using the ‒ The project was submitted to address ✓ Voltage violations on multiple 138-kV buses ‒ Addresses the reliability criteria violation | 2023/EIR - Oncor Peck to Driver 138 kV Line Project_Status_March2023.pdf 2023/EIR - Oncor Peck to Driver 138 kV Line project Scope_Jan2023.pdf 2023/EIR---Oncor-Peck-to-Driver-138-kV-Line-Project-Status-Update-April2023.pdf 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf
22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | 2022 | Completed | Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses both thermal overloads and aging infrastructure issues in the • All recent retired/indefinitely mothballed units will be reviewed – Improves long-term load serving capability for future load growth in the | 2024/EIR - Oncor - Temple Area Project - Scope - RPG February 2024.pdf 2024/EIR - Oncor - Temple Area Project - Status Update - RPG March 2024_.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG June 2024.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG May 2024.pdf 2024/EIR-Oncor-Temple-Area-Projct-Status-Update-RPG-July-2024.pdf
22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | 2022 | Completed | Large Load Growth | Large Load Growth, Voltage/Reactive, Thermal Overload/Reliability |  | Y | [5 empty] | Y | Y | ✓ Addresses the reliability issues primarily driven by new confirmed load additions due • To address the reliability issues, ERCOT evaluated five transmission | 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Oct_15_RPG.pdf
22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Resilience/Hardening |  |  |  | Y |  | Y |  |  |  |  | others/HamiltonRoad-Maxwell_Factsheet_V9.pdf
22RPG042 | Carver to Maxwell 138 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 69.1 | 2022 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | 2023 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | 2023 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Reclassified from Tier 1 to Tier 3 per Protocol | 47 | 2023 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | • Driven by new 4064 MW large loads in southern DFW that either executed an interconnection agreement – Addresses the thermal overloads and voltage violations due to proposed load – Large Loads including OLLs (approximately 4,046 MW) relevant to the • To improve the accuracy of the study case and compensate for the 4064 MW load, the total 3400 MW comprising of the following The total projected load additions of 4064 MW results in base case 2024 RTP Projects Addressed by Proposed Projects in this RPG Submittal • Voltage Violation • Develop transmission upgrades to address the reliability • Reliability upgrades were identified to address the | 2025/EIR_Oncor_Southern_DFW_Load_Interconnection_Project_StatusUpdate_RPG_Aug_2025.pdf 2025/Oncor_Southern-DFW-Load-Interconnection_Project_RPG_04292025.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_April2021RPG.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf 2021/Permian_Basin_Load_Interconnection_Study_-_Final_Update_-_Oct2021RPG.pdf
23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Tier 2 | 45.7 | 2023 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | 2023 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | 2023 | Completed | Line Aging/Rebuild | Large Load Growth, Load Growth, Renewable Integration, Thermal Overload/Reliability, Line Aging/Rebuild |  | Y | Y | Y |  |  | Y |  | Y | ➢ Address the reliability need driven by rapid load growth in the Delaware • Due to the significant load growth and because of lack of long-term load and gas load growth in the Delaware Basin area • As part of the efforts to address the challenge, ERCOT completed the | 2022/LCRA_Oncor_WETT_Bearkat_NorthMcCamey_SandLake_Project_06_15_2022.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Scope-RPG-Sept-2025.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Status-Update-RPG-Nov-2025.pdf
23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56 | 2023 | Completed | Load Growth | Load Growth |  |  | Y
23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | 2023 | Completed | Data Center Load | Data Center Load, Large Load Growth, Load Growth, Renewable Integration, Thermal Overload/Reliability | Y | Y | Y |  |  |  | Y |  | Y | **Mainly datacenter/crypto load Datacenter Basin region load growth for 2030 • Develop transmission upgrades to address the reliability • Significant progress has been made to address the high demand growth in the | 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf 2024/Permian Basin Reliability Plan Study - Status Update - June 2024 RPG.pdf
23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9 | 2023 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52 | 2023 | Completed | Line Aging/Rebuild | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses thermal overloads and load growth – The project is needed to address reliability issues (both thermal overloads and voltage violations) – To address the post-contingency thermal overloads on Paris Switch • All recent retired/indefinitely mothballed units were reviewed and turned off, if due to significant load growth in the Delaware Basin area, in the Andrews, Borden, Culberson, • Due to the significant load growth and because of lack of long- injection point to support this high load growth area and gas load growth in the Far West Weather Zone, the lack of long- • As part of the efforts to address this challenges, ERCOT | 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf 2025/EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_SCOPE_September2025_RPG.pdf 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG April 2024.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG May 2024.pdf
23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8 | 2023 | Completed | Line Aging/Rebuild | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – The project is needed to address reliability issues (both thermal overloads and voltage – Large Loads with Signed Interconnection Agreement (IA) were added in Total New Large Loads Added 1,194 violations) due to significant load growth in the Delaware Basin area, in the Andrews, injection point to support this high load growth area • Develop transmission upgrades to address the reliability | 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf 2025/EIR - Oncor and WETT - Combined Dalaware Basin Stage 5 Project and Alterntive - Status Update - RPG January 2025.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_April_2025.pdf
23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 273.1 | 2023 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses both thermal overloads and voltage violations in the Reeves • All recent retired/indefinitely mothballed units will be reviewed o Improves long-term load serving capability for future load growth in the area New Load Locations and Integration Outlook o Addresses reliability violation – Provide another source to the IH20 area to address the maintenance outage issues counties in the Far West weather zone addressed be Accommodated Either Remaining Amount of Load | 2023/EIR - TNMP - Silverleaf and Cowpen 345138-kV Stations Project - Scope - RPG July2023.pdf 2023/EIR - TNMP - Silverleaf and Cowpen 345138-kV Stations Project - Status Update - RPG Nov 2023.pdf 2023/EIR - TNMP - Silverleaf and Cowpen 345138-kV Stations Project - Status Update - RPG Oct 2023.pdf 2023/EIR - TNMP - Silverleaf and Cowpen 345138-kV Stations Project - Status Update - RPG Sep 2023.pdf 2023/TNMP - Silverleaf and Cowpen 345138-kV Stations Project.pdf
23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38 | 2023 | Completed | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  |  | Y | Y | – Addresses thermal overloads seen by CNP and 2023 RTP • Develop transmission upgrades to address the reliability | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf
23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2 | 2023 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses thermal overloads and load growth o Reliability need driven by new confirmed load additions primarily in the oil and gas industry – The project is needed to address reliability issues (both thermal overloads and voltage violations) ‒ All recent retired/indefinitely mothballed units will be reviewed and turned off, if not ‒ Provides better long-term load serving capability for future load growth in due to significant load growth in the Delaware Basin area, in the Andrews, Borden, Culberson, • Due to the significant load growth and because of lack of long- injection point to support this high load growth area and gas load growth in the Far West Weather Zone, the lack of long- performed to identify the need to serve the projected area load using the | 2023/EIR - Oncor Peck to Driver 138 kV Line Project_Status_March2023.pdf 2023/EIR - Oncor Peck to Driver 138 kV Line project Scope_Jan2023.pdf 2023/EIR---Oncor-Peck-to-Driver-138-kV-Line-Project-Status-Update-April2023.pdf 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG April 2024.pdf
23RPG016 | Oncor Tributary Switch – Vincent Rebuild Project | Oncor | Tier 3 | 29.3 | 2023 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 25.9 | 2023 | Completed | Load Growth | Load Growth |  |  | Y
23RPG017 | Watermill 345/138-kV Switch Project | Oncor | Tier 3 | 74.9 | 2023 | Completed | Load Growth | Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  | Y | Y |  |  | Y | Y | Y | – Addresses the thermal overloads in the Dallas, Kaufman, and Ellis • All recent retired/indefinitely mothballed units will be reviewed – Option 1 better improves long-term load-serving capability for future load growth in the • ERCOT evaluated four project options to address the identified reliability | 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Scope - RPG Sept2024.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Nov2024.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Oct2024.pdf 2024/eir-oncor-wilmer-345138-kv-switch-project-status-update-rpg-dec2024.pdf
23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | 2023 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  |  | Y | Y | • Both thermal overloads and voltage violations in the Pecos and Reeves Improves long-term load serving capability for future load growth in the area New Load Locations and Integration Outlook counties in the Far West weather zone addressed be Accommodated Either Remaining Amount of Load Addresses reliability violations | 2023/EIR - TNMP - Pecos County Transmission Improvement Project - Status Update - RPG Dec 2023.pdf 2023/EIR - TNMP - Pecos County Transmission Improvement Project - Status Update - RPG Nov 2023.pdf 2023/TNMP - Pecos County Transmission Improvement Project - RPG.pdf 2024/EIR - TNMP - Pecos County Transmission Improvement Project - Status Update - RPG Jan 2024.pdf
23RPG022 | McLennan County Transmission Project | Oncor | Tier 3 | 42.31 | 2023 | Completed
23RPG021 | West Columbia to Big Creek ckt 89 Reconductor Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 64.17 | 2023 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  | Y | Y | Y | – Addresses thermal overloads seen by CNP and 2023 RTP • All recent retired/indefinitely mothballed units will be reviewed economic-driven project to address the local transmission | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf 2024/eir-cnp-southwest-houston-345-kv-reliability-project_scope_december_rpg.pdf 2025/eir-cnp-southwest-houston-345-kv-reliability-project_scope_december_rpg (1).pdf 2020/Frio_County_Project_EIR_05_19_2020_RPG.PDF
23RPG020 | Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | Tier 3 | 80 | 2023 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | • Driven by new 4064 MW large loads in southern DFW that either executed an interconnection agreement – Addresses the thermal overloads and voltage violations due to proposed load – Large Loads including OLLs (approximately 4,046 MW) relevant to the • To improve the accuracy of the study case and compensate for the 4064 MW load, the total 3400 MW comprising of the following load additions in the Southern DFW in the North Central and East Weather The total projected load additions of 4064 MW results in base case 2024 RTP Projects Addressed by Proposed Projects in this RPG Submittal • Voltage Violation | 2025/EIR_Oncor_Southern_DFW_Load_Interconnection_Project_StatusUpdate_RPG_Aug_2025.pdf 2025/EIR_Scope_Oncor_Southern_DFW_Load_Interconnection_Project_-_RPG_April_2025.pdf 2025/EIR_Status_Update_Oncor_Southern_DFW_Load_Interconnection_Project_RPG_July_2025.pdf 2025/Oncor_Southern-DFW-Load-Interconnection_Project_RPG_04292025.pdf
23RPG018 | Arlington Reliability Enhancement Project | Oncor | Tier 2 | 73 | 2023 | Completed | Large Load Growth | Large Load Growth, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  |  |  |  | Y | Y | Y | • All recent retired/indefinitely mothballed units were reviewed and – Addresses particular reliability exposure needs in the Arlington area, | 2023/EIR - Oncor - Arlington Reliability Enhancement Project - Scope and Status Update.pdf 2023/EIR - Oncor - Arlington Reliability Enhancement Project - Status Update - Dec 2023.pdf 2023/Oncor_Arlington_Reliability_Enhancement_Project.pdf
23RPG019 | Stanton Loop South Dynamic Reactive Power Project | Oncor | Tier 3 | 96.9 | 2023 | Completed | Voltage/Reactive | Voltage/Reactive | [7 empty] | Y
23RPG024 | Big Foot to Dilley Switch 138-kV Conversion Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 53.1 | 2023 | Completed | Line Aging/Rebuild | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – The project serves a new 129 MW load at the new Rio Medina substation  Generation identified as retired or mothballed based on the most address the transmission congestion in Frio County associated with the addition  Address local congestion related to the addition of new renewable generators that economic-driven project to address the transmission congestion | 2024/EIR - STEC - Rio Medina - RPG Jan2024.pdf 2020/7X_Frio_County_Project_Study_Scope_01_21_2020_RPG.PDF 2020/7X_Frio_County_Project_Study_Update_02_18_2020_RPG.PDF 2020/Frio_County_Project_EIR_05_19_2020_RPG.PDF
23RPG029 | West Texas Synchronous Condenser Project | Oncor | Tier 1 | 280 | 2023 | Completed | Voltage/Reactive | Large Load Growth, Load Growth, Line Aging/Rebuild, Resilience/Hardening, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  | Y |  | Y | Y | – Addresses low voltages and thermal overloads expected as early as • Provide resilience for IBR control and model uncertainty summer 2025 as a result of significant load growth primarily in oil and gas | others/7.1 West Texas Synchronous Condenser RPG Project - ref page.pdf 2025/EIR-Oncor-Connell-to-Rockhound-RPG-Project_StatusUpdate_July_RPG_Final.pdf 2024/WETT_DB5_Alternative_Overview_RPG_9252024_.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Status-Update-RPG-Nov-2025.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Status-Update-RPG-Oct-2025.pdf
23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | 2023 | Completed | Data Center Load | Data Center Load, Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability | Y | Y | Y | Y |  |  | Y | Y | Y | • The proposed project focuses on serving the Rio Medina data center load but also accommodates – The project serves a new 129 MW load at the new Rio Medina substation service to an additional data center that is currently under evaluation. • All recent retired/indefinitely mothballed units will be reviewed ‒ Improves long-term load serving capability for future load growth in the ‒ Addresses the reliability criteria violations | 2023/EIR - STEC - Rio Medina Project - Scope - RPG Nov 2023.pdf 2023/STEC_Rio Medina Project_.pdf 2024/EIR - STEC - Rio Medina - RPG Feb2024.pdf 2024/EIR - STEC - Rio Medina - RPG Jan2024.pdf
23RPG027 | Bakersfield Dynamic Reactive Substation Upgrade Project | LCRA TSC | Tier 1 | 145 | 2023 | Under Review | Voltage/Reactive | Resilience/Hardening, Voltage/Reactive, Thermal Overload/Reliability | [5 empty] | Y |  | Y | Y | • Provide resilience for IBR control and model uncertainty substations to accommodate the second circuit addition. | 2023/20231018_LCRATSC_Bakersfield_Dynamic_Reactive_Substation_Upgrade.pdf others/7.1 West Texas Synchronous Condenser RPG Project - ref page.pdf 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
23RPG026 | Synchronous Condensers Project | WETT | Tier 1 | 144.5 | 2023 | Completed | Voltage/Reactive | Resilience/Hardening, Voltage/Reactive, Thermal Overload/Reliability | [5 empty] | Y |  | Y | Y | • Provide resilience for IBR control and model uncertainty | others/7.1 West Texas Synchronous Condenser RPG Project - ref page.pdf
23RPG025 | Britmoore to Bellaire Ckt 24 Upgrade Project | CNP | Tier 3 | 90.1 | 2023 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  |  | Y | Y | – Addresses thermal overloads seen by CNP and 2023 RTP | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
23RPG033 | Watermill to Seagoville 138 kV Line Project | Oncor | Tier 3 | 33 | 2023 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  |  | Y | Y | – Addresses Post-contingency thermal overloads seen in steady state – Addresses the thermal overloads in the Dallas, Kaufman, and Ellis Counties – Replace aged infrastructure and address system reliability concerns in Dallas/Forth | 2024/EIR - Oncor - Forney 345_138-kV Switch Rebuild Project_November_RPG.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Nov2024.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Oct2024.pdf 2024/Oncor_Forney345-138 kV Switch_Project_RPG_09252024.pdf 2024/eir-oncor-forney-345_138-kv-switch-rebuild-project_december_rpg.pdf
23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | 2023 | Completed | Resilience/Hardening | Large Load Growth, Line Aging/Rebuild, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  | Y | Y | Y | Y | 73417 LCRATSC_Schumansville_SheriffsPosse_StormHardening Tier 4 25-May 73793 LCRATSC_McCartyLaneEast_Zorn_TL_Storm_Hardening Tier 4 25-May Hays – Addresses thermal overloads in the San Antonio area • All recent retired/indefinitely mothballed units were reviewed and – Addresses the reliability violation | 2024/EIR - San Antonio South Reliability II Project Status Update_April 2024.pdf 2023/EIR - BEC - San Miguel to Marion 345 kV Project Scope.pdf 2024/EIR - BEC - San Miguel to Marion 345 kV Project Status Update_Feb 2024.pdf 2024/EIR - BEC - San Miguel to Marion 345 kV Project Status Update_Jan 2024.pdf 2024/EIR - San Miguel to Marion 345 kV Project Status Update_March 2024.pdf
23RPG031 | 345-kV Jeanetta Autotransformer Upgrades Project | CNP | Tier 3 | 47.08 | 2023 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  |  | Y | Y | – Addresses thermal overloads seen by CNP and 2023 RTP | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
23RPG030 | Walleye Creek 345/138-kV Switch Project | Oncor | Tier 3 | 74 | 2023 | Completed | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – Addresses the thermal overloads and voltage violations due to proposed • All recent retired/indefinitely mothballed units will be reviewed and load additions in the Dallas and Tarrant Counties Thermal Overload | 2025/EIR_Scope_Oncor_Skyview_345138kV_Switch_Project_-_RPG_Oct_2025_Final.pdf
23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1 | 1120 | 2023 | Completed | Line Aging/Rebuild | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y |  | Y | – Addresses thermal overloads and load growth and gas load growth in the Far West Weather Zone, the lack of long- • Due to the significant load growth and because of lack of long-term load • All recent retired/indefinitely mothballed units were reviewed and turned off, if • As part of the efforts to address challenges associated with significant oil | 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG April 2024.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG March 2024_.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG May 2024.pdf 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf 2024/West Texas 345 kV Infrastructure RPG Overview for ERCOT 20240112 (1).pdf
24RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 42.5 | 2024 | Under Review | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  | Y | Y | Y | Y | • Driven by new large loads and system growth in west 73417 LCRATSC_Schumansville_SheriffsPosse_StormHardening Tier 4 15/5/2025 LCRA Guadalupe, Comal 73793 LCRATSC_McCartyLaneEast_Zorn_TL_Storm_Hardening Tier 4 15/5/2025 LCRA Hays, Guadalupe – Addresses both thermal and voltage violations associated with the new 23RPG003 Eagle Ford Large Load Interconnection Project Tier 3 12/4/2025 GVEC DeWitt • All recent retired/indefinitely mothballed units will be reviewed and Aging Infrastructures Lake Thermal/Voltage Violations | 2024/EIR_CPS_Omicron_Reliability_Project_Scope_RPG_March2024.pdf 2024/EIR_CPS_Omicron_Reliability_Project_Status_Update_RPG_July2024.pdf 2024/EIR_CPS_Omicron_Reliability_Project_Status_Update_RPG_June2024.pdf 2024/EIR_CPS_Omicron_Reliability_Project_Status_Update_RPG_May2024_update.pdf 2024/Omicron Reliability Project.pdf
24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | Tier 1 | 158 | 2024 | Under Review | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Unit Retirement, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y | Y | Y | Y | Y | Y | • Driven by generation retirements local to CPS Energy 73417 LCRATSC_Schumansville_SheriffsPosse_StormHardening Tier 4 15/5/2025 LCRA 73793 LCRATSC_McCartyLaneEast_Zorn_TL_Storm_Hardening Tier 4 15/5/2025 LCRA – Addresses thermal overloads on 345/138-kV autotransformers and 138-kV 23RPG003 Eagle Ford Large Load Interconnection Project Tier 3 12/4/2025 GVEC DeWitt • All recent retired/indefinitely mothballed units will be reviewed o Addresses reliability violations | 2024/CPSE Eastside Switching Station (1).pdf 2024/CPSE Eastside Switching Station.pdf 2024/EIR - CPS - Eastside 345_138-kV Switching Station Project - RPG Jun 2024.pdf 2024/EIR - CPS - Eastside 345_138-kV Switching Station Project_May_RPG.pdf 2024/EIR - CPS - Eastside 345_138-kV Switching Station Project_SCOPE_March_RPG_.pdf
24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | 2024 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y |  Addresses the reliability issues primarily driven by new confirmed load additions due – Addresses thermal overloads and load growth o Reliability need driven by new confirmed load additions primarily in the oil – Addresses post-contingency thermal overloads and voltage violations on • All recent retired/indefinitely mothballed units will be reviewed and performed to identify the need to serve the projected area load using the Thermal/Voltage Violations ‒ The project was submitted to address ✓ Voltage violations on multiple 138-kV buses | 2024/EIR_ONCOR_Tredway_Scope_OCT.pdf 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf 2025/EIR_ONCOR_Tredway_Project_JAN2025_2.pdf 2023/EIR - Oncor Peck to Driver 138 kV Line project Scope_Jan2023.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_Sept_15_RPG.pdf
24RPG001 | Temple Area Project | Oncor | Tier 1 | 272.6 | 2024 | Completed | Line Aging/Rebuild | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – Addresses both thermal overloads and aging infrastructure issues in the • All recent retired/indefinitely mothballed units will be reviewed – This project addresses identified thermal violations seen in the Temple area in Bell | 2024/EIR - Oncor - Temple Area Project - Scope - RPG February 2024.pdf 2024/EIR - Oncor - Temple Area Project - Status Update - RPG March 2024_.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG May 2024.pdf 2024/Oncor_Temple_Area_Project_RPG_02122024.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG June 2024.pdf
24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | 2024 | Completed
24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | 2024 | Completed | Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y |  | Y | – Addresses thermal overloads and load growth • All recent retired/indefinitely mothballed units were reviewed and turned off, if | 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf
24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | 2024 | Completed | Voltage/Reactive | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – Addresses both thermal overloads and voltage violations in the Brownsville area upon addition of new large load • All recent retired/indefinitely mothballed units will be reviewed | 2024/EIR - Brownsville Area Improvement_Scope_June 2024.pdf 2024/EIR - Brownsville Area Improvement_Status Update_July 2024.pdf
24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2 | 2024 | Completed | Data Center Load | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability, Data Center Load | Y | Y | Y | Y |  |  | Y | Y | Y | – The project is needed to address reliability issues (both thermal overloads and voltage violations) – Large Loads with Singed Interconnection Agreement (IA) will also be Total Large Loads in Delaware Basin 3,361 • All recent retired/indefinitely mothballed units will be reviewed • Due to the significant load growth and because of lack of long- oil and gas load growth in the Delaware Basin area injection point to support this high load growth area (FW) Weather Zone due to the significant load addition in the FW Weather • All components in Oncor’s project address the scope identified in Stages 3 and • As part of the efforts to address this challenges, ERCOT | 2024/Delaware Basin Stage 3 4 RPG Overview for ERCOT 20240514_.pdf 2024/EIR - Oncor - Dalaware Basin Stages 3 and 4 Project - Scope - RPG May 2024.pdf 2024/EIR - Oncor - Dalaware Basin Stages 3 and 4 Project - Status Update - RPG October 2024.pdf 2024/EIR - Oncor - Dalaware Basin Stages 3 and 4 Project - Status Update - RPG September 2024.pdf 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf
24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC and BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | 2024 | Completed
24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 423.8 | 2024 | Completed | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – Addresses both thermal overloads and voltage violations in the Brownsville addition of new large load • All recent retired/indefinitely mothballed units will be reviewed | 2024/eir-aepsc-brownsville-area-improvement_status-update_sept-2024.pdf 2024/EIR - Brownsville Area Improvement_Scope_June 2024.pdf 2024/EIR - Brownsville Area Improvement_Status Update_July 2024.pdf 2024/eir-brownsville-area-improvement_status-update_august-2024.pdf
24RPG007 | Canton Area Loop Project | REC | Tier 2 | 26.03 | 2024 | Completed | Large Load Growth | Large Load Growth, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  |  |  |  | Y | Y | Y | • All recent retired/indefinitely mothballed units will be reviewed and – To address REC planning criteria to limit radial load to less than 20 MW | 2024/EIR REC - Rayburn Electric Cooperative Canton Loop - Status Update RPG August 2024.pdf 2024/RPG Scope Presentation Rayburn Electric Cooperative Canton Loop v2.pdf 2024/EIR REC - Rayburn Electric Cooperative Canton Loop - Status Update RPG June 2024.pdf
24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC and AEN | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | 2024 | Completed | Line Aging/Rebuild | Voltage/Reactive, Thermal Overload/Reliability, Line Aging/Rebuild |  |  |  | Y |  |  |  | Y | Y | – To address REC planning criteria to limit radial load to less than 20 MW | 2024/EIR - REC - Rand Area Loop Project - RPG Aug 2024.pdf 2024/EIR - REC - Rand Area Loop Project - RPG Sep 2024_ (1).pdf 2024/EIR - REC - Rand Area Loop Project - RPG Sep 2024_.pdf
24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23 | 2024 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  |  | Y | Y | – Addresses thermal overloads seen by CNP and 2023 RTP | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2 | 2024 | Completed | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | • All recent retired/indefinitely mothballed units will be reviewed and – To address REC planning criteria to limit radial load to less than 20 MW | 2024/EIR - REC - Rand Area Loop Project - RPG Aug 2024.pdf 2024/EIR - REC - Rand Area Loop Project - RPG Sep 2024_ (1).pdf 2024/EIR - REC - Rand Area Loop Project - RPG Sep 2024_.pdf 2024/EIR - REC - Rand Area Loop Project - Scope - RPG Jun 2024.pdf 2024/EIR REC - Rayburn Electric Cooperative Canton Loop - Status Update RPG August 2024.pdf
24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 855.3 | 2024 | Completed | Data Center Load | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability, Data Center Load | Y | Y | Y | Y |  |  | Y | Y | Y | – The project is needed to address reliability issues (both thermal overloads and voltage violations) – Large Loads with Signed Interconnection Agreement (IA) were added in Total New Large Loads Added 1,194 due to significant load growth in the Delaware Basin area, in the Andrews, Borden, Culberson, • Due to the significant load growth and because of lack of long- injection point to support this high load growth area • As part of the efforts to address this challenges, ERCOT • All components in Oncor’s project address the scope identified in Stages 3 and | 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2025/EIR - Oncor and WETT - Combined Dalaware Basin Stage 5 Project and Alterntive - Status Update - RPG January 2025.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_April_2025.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_Mar_2025.pdf 2024/Delaware Basin Stage 3 4 RPG Overview for ERCOT 20240514_.pdf
24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9 | 2024 | Completed | Load Growth | Load Growth |  |  | Y
24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62 | 2024 | Completed | Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses low voltages and thermal overloads expected as early as summer 2025 as a result of significant load growth primarily in oil and gas • All recent retired/indefinitely mothballed units will be reviewed | 2024/EIR - Oncor - Connell to Rockhound RPG Project_SCOPE_September_RPG.pdf 2025/EIR-Oncor-Connell-to-Rockhound-RPG-Project_StatusUpdate_July_RPG_Final.pdf 2025/EIR-Oncor-Connell-to-Rockhound-RPG-Project_StatusUpdate_November_RPG.pdf 2025/EIR-Oncor-Connell-to-Rockhound-RPG-Project_StatusUpdate_October_RPG_Final.pdf 2025/EIR-Oncor-Connell-to-Rockhound-RPG-Project_StatusUpdate_September_RPG_Final.pdf
24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | Tier 3 | 93.04 | 2024 | Completed
24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | 2024 | Completed
24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | 2024 | Completed | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  | Y | Y | Y | Y | (NERC) and ERCOT Planning Criteria to address thermal overloads on 81.5 miles of – Addresses post-contingency thermal overloads on the Venus Switch – • All recent retired/indefinitely mothballed units will be reviewed and • The purpose of the project is to address the reliability needs in the Key Takeaway: ERCOT studied several options and recommends Option 1 to address the Thermal/Voltage Violations | others/7-2-oncor-venus-switch-to-sam-switch-345-kv-line-project.pdf 2024/EIR_ONCOR_Venus_Switch_to_Sam_Switch_Project_NOV.pdf 2024/EIR_ONCOR_Venus_Switch_to_Sam_Switch_Project_OCT_Update.pdf 2024/EIR_ONCOR_Venus_Switch_to_Sam_Switch_Project_Scope.pdf 2024/EIR_ONCOR_Venus_Switch_to_Sam_Switch_Project_Update.pdf
24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | 2024 | Completed | Large Load Growth | Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability, Large Load Growth |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses the thermal overloads in the Dallas, Kaufman, and Ellis • All recent retired/indefinitely mothballed units will be reviewed – Option 1 better improves long-term load-serving capability for future load growth in the • ERCOT evaluated four project options to address the identified reliability | 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Scope - RPG Sept2024.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Nov2024.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Oct2024.pdf 2024/eir-oncor-wilmer-345138-kv-switch-project-status-update-rpg-dec2024.pdf 2025/eir-oncor-wilmer-345138-kv-switch-project-status-update-rpg-dec2024 (1).pdf
24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | 2024 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  | Y | Y | Y | – Addresses Post-contingency thermal overloads seen in steady state – Addresses the thermal overloads in the Dallas, Kaufman, and Ellis • All recent retired/indefinitely mothballed units will be reviewed | 2024/EIR - Oncor - Forney 345_138-kV Switch Rebuild Project_November_RPG.pdf 2024/EIR - Oncor - Forney 345_138-kV Switch Rebuild Project_SCOPE_September_RPG.pdf 2024/eir-oncor-forney-345_138-kv-switch-rebuild-project_december_rpg.pdf 2025/eir-oncor-forney-345_138-kv-switch-rebuild-project_december_rpg (1).pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Scope - RPG Sept2024.pdf
24RPG027 | Long Draw Second 345/138-kV Autotransformer Project | WETT | Tier 3 | 28 | 2024 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  | Y | Y | Y | Y | – The project is needed to address reliability issues (both thermal overloads and voltage – Large Loads with Signed Interconnection Agreement (IA) were added in Total New Large Loads Added 1,194 • Substantial load growth in Oncor’s southern Stanton Loop area introduces • Increase diversity and resiliency in the 138-kV and 345-kV network violations) due to significant load growth in the Delaware Basin area, in the Andrews, injection point to support this high load growth area | 2024/24RPG024 Oncor and LCRATSC RPG Overview for ERCOT 10162024.pdf 2025/EIR - Oncor and WETT - Combined Dalaware Basin Stage 5 Project and Alterntive - Status Update - RPG January 2025.pdf 2024/WETT_DB5_Alternative_Overview_RPG_9252024_.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_April_2025.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_Mar_2025.pdf
24RPG026 | Jordan/Mont Belvieu Area Improvement Project | CNP | Tier 3 | 76.89 | 2024 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  |  | Y | Y | – Addresses thermal overloads seen by CNP and 2023 RTP | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
24RPG025 | Gunter 345/138-kV Switch Project | Oncor | Tier 3 | 51.2 | 2024 | Completed
24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 97.7 | 2024 | Completed | Data Center Load | Large Load Growth, Load Growth, Line Aging/Rebuild, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability, Data Center Load | Y | Y | Y | Y |  | Y | Y | Y | Y | – Addresses post-contingency thermal overloads and voltage violations due – Additional Large Loads Provided by TSPs Total Large Loads added 1,328.97 to significant oil and gas load growth • All recent retired/indefinitely mothballed units will be reviewed gas load growth • Substantial load growth in Oncor’s southern Stanton Loop area introduces • Increase diversity and resiliency in the 138-kV and 345-kV network | 2024/EIR_ONCOR_LCRA_Hartring_to_Upland_138kV_Line_and_Benedum_Autotransformer_Addition_Project_Scope_RPG_October_2024.pdf 2025/EIR_StatusUpdat_Hartring_to_Upland_and_BenedumAuto_Project_RPG_Mar_2025.pdf 2025/EIR_StatusUpdate_Hartring_to_Upland_and_BenedumAuto_Project_RPG_April_2025-.pdf 2024/24RPG024 Oncor and LCRATSC RPG Overview for ERCOT 10162024.pdf
24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5 | 2024 | Under Review | Data Center Load | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability, Data Center Load | Y | Y | Y | Y |  |  | Y | Y | Y | – The project is needed to address reliability issues (both thermal overloads and voltage violations) – Large Loads with Signed Interconnection Agreement (IA) were added in Total New Large Loads Added 1,194 violations) due to significant load growth in the Delaware Basin area, in the Andrews, injection point to support this high load growth area • Due to the significant load growth and because of lack of long- oil and gas load growth in the Delaware Basin area • All of components in Oncor’s project address the scope identified in Stage 5 • As part of the efforts to address this challenges, ERCOT | 2024/WETT_DB5_Alternative_Overview_RPG_9252024_.pdf 2025/EIR - Oncor and WETT - Combined Dalaware Basin Stage 5 Project and Alterntive - Status Update - RPG January 2025.pdf 2024/Delaware Basin Stages 5 RPG Overview for ERCOT 09252024.pdf 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_April_2025.pdf
24RPG030 | Partial Rebuild of 138-kV Ckt.05A Sienna Tap to Missouri City Tap Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 28.56 | 2024 | Completed | Line Aging/Rebuild | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – Addresses thermal overloads seen by CNP and 2023 RTP – Addresses the thermal and voltage violations caused by the new 500.5 • All recent retired/indefinitely mothballed units will be reviewed 75856B Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire Tier 4 May-25 Harris the new substation. To serve the new substation and its 500.5 MVA load, 11/12/2024 CNP Baytown Area Load Addition Project load addition in-service date. MVA load addition at the new customer-owned NEWSUB 138-kV – The reliability analysis will be performed to identify the need to serve the new load | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf 2024/CNP_Baytown_Area_Load_Addition_project_20241112.pdf 2024/EIR - CNP - Baytown Area Load Addition RPG Project_SCOPE_November_RPG_Final.pdf 2025/EIR -CNP - Baytown_Area_Load_Addition_Project_February_RPG.pdf
24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03 | 2024 | Completed | Load Growth | Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  | Y | Y |  |  | Y | Y | Y | – Addresses post-contingency thermal overloads and voltage violations on • Load growth in the area introduces post-contingency low voltages and • All recent retired/indefinitely mothballed units will be reviewed and Thermal/Voltage Violations thermal overloads in Oncor’s system • P1.2 and P2.1 contingencies result in low voltages and thermal overloads | 2025/EIR_ONCOR_Tredway_Project_JAN2025_2.pdf 2025/EIR_ONCOR_Tredway_Project_Update_MARCH_v2.pdf 2024/Oncor Tredway 138 kV Switch and Expanse-Tredway 138 kV 2nd Circuit Project RPG Overview for ERCOT 10162024.pdf 2024/EIR_ONCOR_Tredway_Scope_OCT.pdf
24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 545.3 | 2024 | Completed | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – Addresses the thermal and voltage violations caused by the new 500.5 • All recent retired/indefinitely mothballed units will be reviewed 75856B Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire Tier 4 May-25 Harris the new substation. To serve the new substation and its 500.5 MVA load, 11/12/2024 CNP Baytown Area Load Addition Project load addition in-service date. MVA load addition at the new customer-owned NEWSUB 138-kV – The reliability analysis will be performed to identify the need to serve the new load | 2024/CNP_Baytown_Area_Load_Addition_project_20241112.pdf 2024/EIR - CNP - Baytown Area Load Addition RPG Project_SCOPE_November_RPG_Final.pdf 2025/EIR -CNP - Baytown_Area_Load_Addition_Project_February_RPG.pdf 2025/EIR-CNP-Baytown_Area_Load_Addition_Project_April_RPG.pdf 2025/EIR-CNP-Baytown_Area_Load_Addition_Project_July_RPG_Final.pdf
24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | 2024 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  | Y | Y | Y | – Addresses thermal overloads seen by CNP and 2023 RTP • All recent retired/indefinitely mothballed units will be reviewed have thermal overload concerns on multiple planning events as | 2024/24rpg032-_cnp_southwest_houston_345kv_reliability_project_ercot_rpg_presentation.pdf 2025/24rpg032-_cnp_southwest_houston_345kv_reliability_project_ercot_rpg_presentation (1).pdf 2024/eir-cnp-southwest-houston-345-kv-reliability-project_scope_december_rpg.pdf 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | 2024 | Completed | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  |  | Y | Y | – Addresses the thermal overloads and voltage violations in the Bell, Falls, • This is project is needed to address the thermal overloads and voltage violations in the Ellis, Navarro, upgrades that did not meet the reliability need based on the area will have over 16 GW of large loads than the 2025 RTP load level (over 13 GW than review, the study area will have over 19 GW of large loads than the | 2026/10_EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026_Final.pdf 2026/8.-EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Projects-Status-Update-RPG-Apr-2026_Final.pdf 2026/9_EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026.pdf 2026/EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Mar-2026.pdf 2026/EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-Update-RPG-Mar-2026.pdf
24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 34 | 2024 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  | Y | Y | Y | – This project is needed to address post-contingency thermal overloads in • All recent retired/indefinitely mothballed units will be reviewed | 2025/EIR_AEPSC_Aransas_Pass_to_Rincon_Project_Final_Update_RPG_April_2025.pdf 2025/EIR_AEPSC_Aransas_Pass_to_Rincon_Project_Scope_RPG_January_2025.pdf 2025/EIR_AEPSC_Aransas_Pass_to_Rincon_Project_Update_RPG_March_2025.pdf
24RPG034 | Redwood to San Marcos Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 46.4 | 2024 | Completed | Resilience/Hardening | Large Load Growth, Line Aging/Rebuild, Resilience/Hardening, Thermal Overload/Reliability |  | Y |  | Y |  | Y |  |  | Y | 73417 LCRATSC_Schumansville_SheriffsPosse_StormHardening Tier 4 25-May 73793 LCRATSC_McCartyLaneEast_Zorn_TL_Storm_Hardening Tier 4 25-May Hays – Addresses the reliability violation | 2024/EIR - San Antonio South Reliability II Project Status Update_April 2024.pdf
24RPG033 | MINING 69-kV Substation Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.12 | 2024 | Completed | Load Growth | Load Growth |  |  | Y
24RPG036 | South Padre Island Rebuild Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.5 | 2024 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
24RPG039 | Galveston Region Project | TNMP | Tier 2 | 95.9 | 2024 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses the thermal overloads and voltage violations in the Galveston with more flexibility in terms of accommodating some of the large load requests anticipated on • All recent retired/indefinitely mothballed units will be reviewed • TNMP is anticipating a significant amount of load growth on its Galveston region transmission system to assert the load additions in September 2025 • The project is submitted to address the reliability violations under planned • The voltage security of the region will be addressed and the long-term load serving capability will be solution to reliably address the issues identified above | 2025/EIR - TNMP - Galveston Region Project - Scope - RPG Feb 2025.pdf 2025/EIR-TNMP-Galveston-Region-Project-Status-Update-RPG-Dec-2025.pdf 2025/EIR-TNMP-Galveston-Region-Project-Status-Update-RPG-Nov-2025.pdf 2025/TNMP Galveston Region Transmission Improvement Project - EIR.pdf
24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC and PEC | Tier 3 | 66.35 | 2024 | Completed | Load Growth | Load Growth |  |  | Y
24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 84.3 | 2024 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Unit Retirement, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y | Y |  | Y | Y | Y | • Driven by high load growth in the area and increased generation in – Addresses voltage violations seen by Oncor • All recent retired/indefinitely mothballed units will be reviewed – Improves long-term load-serving capability for future load growth in the Roanoke -Euless 474 481 509 516 523 536 546 of new load in the area. Roanoke -Deen 471 478 494 500 504 517 527 • Thermal overloads and voltage | 2025/EIR - Oncor -Roscoe Area Upgrades Project_SCOPE_February_RPG.pdf 2025/EIR-Oncor-Roscoe-Area-Upgrades-Project-StatusUpdate-April_2025_RPG.pdf 2025/EIR-Oncor-Roscoe-Area-Upgrades-Project-StatusUpdate-May_2025_RPG.pdf 2025/8. Roscoe Area Upgrades RPG Overview for ERCOT.pdf 2022/Roanoke_Area_Upgrades_Overview_RPG.pdf
24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | 2024 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | 2025 | Completed | Voltage/Reactive | Line Aging/Rebuild, Resilience/Hardening, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  | Y |  | Y | Y | • Provide resilience for IBR control and model uncertainty substations to accommodate the second circuit addition. | others/7.1 West Texas Synchronous Condenser RPG Project - ref page.pdf 2024/WETT_DB5_Alternative_Overview_RPG_9252024_.pdf 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 281.2 | 2025 | Completed | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – Addresses the thermal overloads and voltage violations due to proposed • All recent retired/indefinitely mothballed units will be reviewed load additions in the Brazos County in the East weather zone | 2025/EIR-BTU-Texas-A-M-University-System-RELLIS-Campus-Reliability-Project-Scope-RPG-Mar-2025.pdf
25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | 2025 | Completed
25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219 | 2025 | Under Review | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – Addresses the thermal overloads and voltage violations due to proposed load additions in • Driven by new 4064 MW large loads in southern DFW that either executed an interconnection agreement – Large Loads including OLLs (approximately 4,046 MW) relevant to the • To improve the accuracy of the study case and compensate for the 4064 MW load, the total 3400 MW comprising of the following load additions in the Southern DFW in the North Central and East Weather The total projected load additions of 4064 MW results in base case 2024 RTP Projects Addressed by Proposed Projects in this RPG Submittal • Voltage Violation | 2025/EIR_Oncor_Southern_DFW_Load_Interconnection_Project_StatusUpdate_RPG_Aug_2025.pdf 2025/EIR_Scope_Oncor_Southern_DFW_Load_Interconnection_Project_-_RPG_April_2025.pdf 2025/EIR_Status_Update_Oncor_Southern_DFW_Load_Interconnection_Project_RPG_July_2025.pdf 2025/Oncor_Southern-DFW-Load-Interconnection_Project_RPG_04292025.pdf 2026/EIR_Oncor_Southern_DFW_Load_Interconnection_Project_StatusUpdate_RPG_Jan_2026_Final.pdf
25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | 2025 | Completed
25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 84 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  | Y | Y | Y | • Retire Poage autotransformer (Installed from Temple Area Improvements RPG). • All recent retired/indefinitely mothballed units will be reviewed | 2025/EIR_BEC_Hamilton_County_Conversion_Project_SCOPE_APRIL.pdf 2025/EIR_BEC_Hamilton_County_Project_Status_Update_August_RPG_Meeting.pdf 2025/EIR_BEC_Hamilton_County_Project_Status_Update_July_RPG_Meeting.pdf 2025/EIR_BEC_Hamilton_County_Project_Status_Update_June_RPG_Meeting.pdf
25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  | Y | Y | Y | – Addresses thermal overloads seen by CNP and 2023 RTP • All recent retired/indefinitely mothballed units will be reviewed | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf 2024/24rpg032-_cnp_southwest_houston_345kv_reliability_project_ercot_rpg_presentation.pdf 2024/eir-cnp-southwest-houston-345-kv-reliability-project_scope_december_rpg.pdf 2025/24rpg032-_cnp_southwest_houston_345kv_reliability_project_ercot_rpg_presentation (1).pdf
25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | 2025 | Completed | Large Load Growth | Large Load Growth, Load Growth, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y |  |  |  | Y | Y | Y |  Addresses the reliability issues primarily driven by new confirmed load additions due issues primarily driven by the new confirmed load additions due to the o All recent retired or indefinitely mothballed units will be turned off, if Allow Better Future Load Growth • To address the reliability issues, ERCOT evaluated five transmission Line Project for RPG review in June 2021 to address the reliability upgrade option to address the reliability issues at the RPG meetings: substations to accommodate the second circuit addition. | 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_Sept_15_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Oct_15_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Nov_9_RPG.pdf 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | 2025 | Completed
25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83 | 2025 | Under Review | Resilience/Hardening | Large Load Growth, Line Aging/Rebuild, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  | Y | Y | Y | Y | • This project is needed to addresses post-contingency and thermal overloads and voltage violations in the 72588A Trading Post to Cedar Valley Storm Hardening Tier 4 May-25 PEC • All recent retired/indefinitely mothballed units will be reviewed • To address the violations identified in Study area 1 – North of Hutto – To address reliability violations seen by Oncor and LCRA TSC | 2026/5_EIR-Oncor-and-LCRA-TSC-Muscovy-Voss-_StatusUpdate_April2026_RPG.pdf 2025/Oncor_Muscovy_Voss-Lake_RPG_05202025.pdf 2025/EIR-Oncor-and-LCRA-TSC-Muscovy-Voss-_SCOPE_May2025_RPG.pdf 2025/EIR-Oncor-and-LCRA-TSC-Muscovy-Voss-_StatusUpdate_July2025_RPG.pdf 2025/EIR-Oncor-and-LCRA-TSC-Muscovy-Voss-_StatusUpdate_Jun2025_RPG.pdf
25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3 | 2025 | Completed | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Resilience/Hardening, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  | Y | Y | Y | Y | – This project is needed to address aging infrastructure and to ensure resilience Aging Infrastructures/Storm – Addresses the thermal and voltage violations caused by the new 500.5 – Addresses thermal overloads seen by CNP and 2023 RTP 75856B Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire Tier 4 May-25 Harris 345-kV Hardening Project – ERCOT 345-kV Hardening Project (25RPG028) for Regional Planning Group • All recent retired/indefinitely mothballed units will be reviewed the new substation. To serve the new substation and its 500.5 MVA load, 11/12/2024 CNP Baytown Area Load Addition Project | 2024/CNP_Baytown_Area_Load_Addition_project_20241112.pdf 2025/EIR -CNP - Baytown_Area_Load_Addition_Project_February_RPG.pdf 2025/EIR_CNP_PHRobinson_to_WAParish_345kV_Hardening_Project_StatusUpdate_RPG_Nov_2025.pdf 2024/EIR - CNP - Baytown Area Load Addition RPG Project_SCOPE_November_RPG_Final.pdf 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf
25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5 | 2025 | Under Review | Voltage/Reactive | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – This project is needed to address post-contingency voltage violations and improve • All recent retired/indefinitely mothballed units will be reviewed | 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Scope_RPG_July_2025.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_August_2025.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_December_2025_FINAL.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_October_2025_FINAL.pdf 2026/3.-EIR-CPS-Energy-Helotes-Reactive-Power-Planning-Project-Recommendation-RPG_April_2026_FINAL.pdf
25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47 | 2025 | Under Review | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Resilience/Hardening, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  | Y |  | Y | Y | STEC evaluated two (2) transmission system improvement options to address reliability issues and support the new load addition. Address the violations under NERC and EPG criteria contingencies and ensure reliable integration of the proposed 300 MW Load It addresses all reliability concerns and supports the integration of the proposed Ammonia Plant Load at its full capacity (1150 MW) Planning Criteria to address thermal overloads on approximately 39 miles of 138-kV – This project is needed to address post-contingency voltage violations in the Dupont Switching station to the new large load and the removal of the double-circuit • Connect the new large load confirmed by Transmission Service Provider (TSP) Large loads in the vicinity were modeled to develop the cases prior to adding the proposed load, per ERCOT LLI team’s input Reliably integrates the proposed 1150 MW load No transmission system stability issues were identified under any planning events with the proposed 1150 MW load connected via Option 2. | others/8-25RPG012-STEC-Ammonia-Plant-Load-Project-Option-1.pdf 2025/STEC_FirstAmmonia_Final_25RPG012 (1).pptx 2025/STEC_FirstAmmonia_Final_25RPG012.pptx 2025/STEC_NuecesGeenAmmonia_Final_25RPG016.pptx 2026/4.-EIR-STEC-Nueces-GreenvAmmonia-Project-Status-Update-RPG-March-2026-FINAL.pdf
25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y |  |  |  | Y | Y | – Addresses thermal overloads seen by CNP and 2023 RTP | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 36.2 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | Tier 2 | 74 | 2025 | Under Review | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Resilience/Hardening, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  | Y |  | Y | Y | STEC evaluated two (2) transmission system improvement options to address reliability issues and support the new load addition. Addresses the violations under NERC and EPG criteria contingencies, and ensures reliable integration of the proposed 1150 MW Load It addresses all reliability concerns and supports the integration of the proposed Ammonia Plant Load at its full capacity (1150 MW) – This project is needed to address post-contingency voltage violations in the Planning Criteria to address thermal overloads on approximately 39 miles of 138-kV Reliably integrates the proposed 1150 MW load No transmission system stability issues were identified under any planning events with the proposed 1150 MW load connected via Option 2. Dupont Switching station to the new large load and the removal of the double-circuit • Connect the new large load confirmed by Transmission Service Provider (TSP) Vice President, System Planning and resilience, the Project has completed Regional Planning | 2026/4.-EIR-STEC-Nueces-GreenvAmmonia-Project-Status-Update-RPG-March-2026-FINAL.pdf 2026/4_EIR_STEC_Nueces_Green_Ammonia_Project_Status_Update_RPG_February_2026_FINAL.pdf 2025/STEC_NuecesGeenAmmonia_Final_25RPG016.pptx others/8-25RPG012-STEC-Ammonia-Plant-Load-Project-Option-1.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_April2021RPG.pdf
25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | Tier 3 | 35.5 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
25RPG018 | Childress Area Transmission Improvement Project | AEPSC | Tier 2 | 77.3 | 2025 | Completed | Load Growth | Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  | Y | Y |  |  | Y | Y | Y | – Addresses the voltage violations under planned maintenance outage • All recent retired/indefinitely mothballed units will be reviewed | others/EIR-AEP-Childress-Area-Transmission-Improvement-Project-Scope-RPG-July-2025.pdf
25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | Tier 3 | 74.5 | 2025 | Completed | Line Aging/Rebuild | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | – The project is needed to address reliability issues (both thermal overloads and voltage violations) – Large Loads with Signed Interconnection Agreement (IA) were added in Total New Large Loads Added 1,194 due to significant load growth in the Delaware Basin area, in the Andrews, Borden, Culberson, • Due to the significant load growth and because of lack of long- injection point to support this high load growth area • As part of the efforts to address this challenges, ERCOT | 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2025/EIR - Oncor and WETT - Combined Dalaware Basin Stage 5 Project and Alterntive - Status Update - RPG January 2025.pdf
25RPG020 | Large Load Additions Project | CPS Energy | Tier 1 | 333.7 | 2025 | Under Review | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | Project set driven by ~2GW of new large loads with varying load CPS Energy submitted the Large Load Additions Project (25RPG020) for Electric ERCOT will perform a combined EIR Study for CPS Energy Large Load Additions Project Contingency Category Unsolved Power Flow Voltage Violations Thermal Overloads Combined – CPS Energy – Large Load CPS Large Load Project – Updated ERCOT approximately 2 GW Load by 2035 CPS ENERGY LARGE LOAD (EIR) into the ongoing EIR for the CPS Large Load Project • All recent retired/indefinitely mothballed units will be reviewed | 2026/6_EIR-CPS-Energy-Large-Load-Additions-Project-and-STEC-Medina-County-Large-Load-Project_StatusUpdate_April2026_RPG.pdf 2026/8_EIR-CPS-Energy-Large-Load-Additions-Project_Updated_SCOPF_Feb2026_RPG.pdf 2025/EIR-CPS-Energy-Large-Load-Additions-Project_SCOPE_Aug2025_RPG.pdf 2025/CPS-Energy-Large-Load-Additions-Project.pdf 2026/7_EIR-STEC-Medina-County-Large-Load-Project_SCOPE_Feb2026_RPG.pdf
25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | Tier 1 | 110 | 2025 | Under Review | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – This project is needed to address post-contingency voltage violations and improve • All recent retired/indefinitely mothballed units will be reviewed | 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Scope_RPG_July_2025.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_August_2025.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_December_2025_FINAL.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_October_2025_FINAL.pdf 2026/3.-EIR-CPS-Energy-Helotes-Reactive-Power-Planning-Project-Recommendation-RPG_April_2026_FINAL.pdf
25RPG026 | Paris Switch to Monticello Switch 345-kV Line Rebuild Project | Oncor | Tier 1 | 231.75 | 2025 | Under Review | Line Aging/Rebuild | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | • The project is needed to addresses post-contingency thermal overloads on Paris Switch to Monticello – To address the post-contingency thermal overloads on Paris Switch • All recent retired/indefinitely mothballed units will be reviewed | 2026/4.-EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_Recommendation_April2026.pdf 2025/EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_SCOPE_September2025_RPG.pdf 2026/3_EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_February2026_RPG.pdf 2026/8.-EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_March2026_RPG.pdf 2026/EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_January2025_RPG.pdf
25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | Tier 1 | 9384 | 2025 | Completed | Large Load Growth | Large Load Growth, Load Growth, Thermal Overload/Reliability |  | Y | Y | [5 empty] | Y | • Ensure transmission system reliability for native & large load customers in Central ERCOT to address the reply comments | 2025/EIR-Joint_AEP_CPS_Oncor_CEHE_Texas_765-kV_STEP_Eastern_Backbone-Status-Update-RPG-Nov_2025_Final.pdf 2025/EIR-Joint_AEP_CPS_Oncor_CEHE_Texas_765-kV_STEP_Eastern_Backbone-Status-Update-RPG-Oct_2025_Final.pdf 2025/EIR-Joint_AEP_CPS_Oncor_CPS_Texas_765-kV_STEP_Eastern_Backbone-Scope-RPG-Sept-2025_Final.pdf 2025/Joint-TSP-Presentation-TX-765-kV-STEP-Eastern-Backbone-RPG.pdf 2026/13.-26RPG001-LCRA-TSC-and-CEHE-Euclid-765-kV-Substation-and-Transmission-Line-Addition-Project_final.pdf
25RPG027 | Royse Switch to Edgewood 69-kV Line Conversion to 138-kV Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.72 | 2025 | Completed | Load Growth | Load Growth |  |  | Y
25RPG024 | Blessing Area Improvements Project | AEPSC | Tier 1 (Withdrawn) | 256 | 2025 | Completed
25RPG023 | Dunham 345/138-kV Switch Project | Oncor | Tier 3 | 21.3 | 2025 | Completed
25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor and AEPSC | Tier 1 | 742.2 | 2025 | Completed | Load Growth | Large Load Growth, Load Growth, Renewable Integration, Thermal Overload/Reliability |  | Y | Y |  |  |  | Y |  | Y | ➢ Address the reliability need driven by rapid load growth in the Delaware • Need based on substantial load growth in the Delaware Basin Region of • Due to the significant load growth and because of lack of long-term load and gas load growth in the Delaware Basin area • As part of the efforts to address the challenge, ERCOT completed the | 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Scope-RPG-Sept-2025.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Status-Update-RPG-Nov-2025.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Status-Update-RPG-Oct-2025.pdf 2025/RPG-Overview-for-Drill-Hole-Sand-Lake-Solstice-765-kV-09252025.pdf 2022/LCRA_Oncor_WETT_Bearkat_NorthMcCamey_SandLake_Project_06_15_2022.pdf
25RPG031 | Sam Switch Resiliency Project | LST | Tier 3 | 17 | 2025 | Completed
25RPG029 | Hillsboro Switch to Elm Mott Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 52.85 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
25RPG028 | P.H. Robinson to W.A. Parish 345-kV Hardening Project | CNP | Tier 1 | 511.31 | 2025 | Under Review | Resilience/Hardening | Line Aging/Rebuild, Resilience/Hardening, Renewable Integration, Thermal Overload/Reliability |  |  |  | Y |  | Y | Y |  | Y | – Addresses the aging transmission infrastructure and storm hardening – This project is needed to address aging infrastructure and to ensure resilience resilience against hurricane-force winds and extreme cold conditions in the Aging Infrastructures/Storm – Based on the need driver (aging transmission infrastructure and storm 345-kV Hardening Project – ERCOT Parish 345-kV Hardening Project (25RPG028) for Regional • All recent retired/indefinitely mothballed units will be reviewed hardening) Hardening Project | 2025/EIR_CNP_PHRobinson_to_WAParish_345kV_Hardening_Project_Scope_RPG_Sep_2025_Final.pdf 2025/EIR_CNP_PHRobinson_to_WAParish_345kV_Hardening_Project_StatusUpdate_RPG_Nov_2025.pdf 2025/EIR_CNP_PHRobinson_to_WAParish_345kV_Hardening_Project_StatusUpdate_RPG_Oct_2025_Final.pdf 2026/EIR_CNP_PHRobinson_to_WAParish_345kV_Hardening_Project_StatusUpdate_RPG_Jan_2026_Final.pdf 2025/CEHE-PHR-WAP-345kV-Hardening-Project20250925.pdf
25RPG030 | Bonham Switch to Toco Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 72.83 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
25RPG034 | Mulberry Creek 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 32 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
25RPG032 | Fort Stockton Plant 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 25.7 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
25RPG033 | Oncor Skyview 345/138-kV Switch Project | Oncor | Tier 2 | 56.82 | 2025 | Under Review | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | – Addresses the thermal overloads and voltage violations due to proposed • All recent retired/indefinitely mothballed units will be reviewed and load additions in the Dallas and Tarrant Counties Thermal Overload Liggett 345/138 kV Autotransformers thermal overload | 2025/EIR_Scope_Oncor_Skyview_345138kV_Switch_Project_-_RPG_Oct_2025_Final.pdf 2025/EIR_Status_Update_Oncor_Skyview_345138kV_Switch_Project_-_RPG_Dec_2025.pdf 2026/EIR_Status_Update_Oncor_Skyview_345138kV_Switch_Project_-_RPG_Jan_2026_Final.pdf 2026/EIR_Status_Update_Oncor_Skyview_345138kV_Switch_Project_-_RPG_Mar_2026.pdf 2025/Oncor_Skyview345-138-kV-Switch_Project_RPG_10282025.pdf
25RPG035 | McDonald Road Switch to Polecat Creek Switch 138-kV Line Project | Oncor | Tier 3 | 26.66 | 2025 | Completed | Large Load Growth | Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y | Y | Y |  |  | Y | Y | Y | o Reliability need driven by new confirmed load additions primarily in the oil and gas industry o Address the reliability issues primarily driven by new confirmed load ‒ All recent retired/indefinitely mothballed units will be reviewed and turned off, if not ‒ Provides better long-term load serving capability for future load growth in performed to identify the need to serve the projected area load using the ‒ The project was submitted to address ✓ Voltage violations on multiple 138-kV buses ‒ Addresses the reliability criteria violation | 2023/EIR - Oncor Peck to Driver 138 kV Line Project_Status_March2023.pdf 2023/EIR - Oncor Peck to Driver 138 kV Line project Scope_Jan2023.pdf 2023/EIR---Oncor-Peck-to-Driver-138-kV-Line-Project-Status-Update-April2023.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf
25RPG036 | Abilene Northwest 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 33 | 2025 | Completed | Line Aging/Rebuild | Line Aging/Rebuild |  |  |  | Y
25RPG037 | West Loop Project | LP&L | Tier 1 | 309 | 2025 | Under Review | Unit Retirement | Line Aging/Rebuild, Unit Retirement, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  |  |  | Y | Y |  | Y | Y | Y | • All recent retired/indefinitely mothballed units will be reviewed Contingency Thermal Violations Voltage Violations • Numerous thermal and voltage violations • This project will solve hundreds of thermal and voltage violations, along with – This project is needed to address post-contingency thermal and voltage | 2026/LP-L-West-Loop-Project-Overview_v2.pdf 2026/EIR_LPL_West_Loop_Project_Scope_RPG_January_2026_FINAL.pdf
25RPG043 | Set 2 North Central & South Central Texas Reliability Project | Oncor | Tier 1 | 440.79 | 2025 | Under Review | Data Center Load | Data Center Load, Large Load Growth, Load Growth, Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability | Y | Y | Y | Y |  |  |  | Y | Y | – Addresses the thermal overloads and voltage violations in the Bell, Falls, upgrades that did not meet the reliability need based on the review, the study area will have over 19 GW of large loads than the have over 19 GW of large loads than the 2025 RTP load level (over 18 GW than the 2024 RTP load 210 GW from data centers Over 16 GW of load from various other industrial sectors Oncor submitted five RPG submittals to address these reliability projects based on ERCOT’s recommendation: Proposed upgrades will address thermal and voltage planning criteria violations identified by ERCOT in the 2024 RTP and 2025 RTP | 2026/10_EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026_Final.pdf 2026/EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Mar-2026.pdf 2026/9.-EIR-Status-Update-Oncor-Combined-Set-1-Set-2-North-Central-South-Central-TX-Reliability-Project_RPG-Apr_2026_Final.pdf 2026/Set-1-Set-2-and-Navarro-and-Ellis-Area-Reliability-Project-Overviews-01162026_Final.pptx 2026/9_EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026.pdf
25RPG042 | Set 2 North & Central Texas Reliability Project | Oncor | Tier 1 | 1330 | 2025 | Under Review | Data Center Load | Data Center Load, Large Load Growth, Load Growth, Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability | Y | Y | Y | Y |  |  |  | Y | Y | – Addresses the thermal overloads and voltage violations in the Ellis, Navarro, • This is project is needed to address the thermal overloads and voltage violations in the Ellis, Navarro, upgrades that did not meet the reliability need based on the review, the study area will have over 16 GW of large loads than the 210 GW from data centers Over 16 GW of load from various other industrial sectors area will have over 16 GW of large loads than the 2025 RTP load level (over 13 GW than Oncor submitted five RPG submittals to address these reliability projects based on ERCOT’s recommendation: Proposed upgrades will address thermal and voltage planning criteria violations identified by ERCOT in the 2024 RTP and 2025 RTP | 2026/9_EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026.pdf 2026/EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-Update-RPG-Mar-2026.pdf 2026/Set-1-Set-2-and-Navarro-and-Ellis-Area-Reliability-Project-Overviews-01162026_Final.pptx 2026/8.-EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Projects-Status-Update-RPG-Apr-2026_Final.pdf 2026/10_EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026_Final.pdf
25RPG039 | Southeast Brownsville Large Load Transmission System Improvements Project | STEC | Tier 2 | 96.35 | 2025 | Under Review | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | Large loads in the vicinity were modeled to develop the cases prior to adding the proposed load, per ERCOT LLI team’s input - ~1166 MW of large load additions were included based on input from ERCOT LLI Team. Address the violations under NERC TPL-001-5 and EPG criteria contingencies and ensure reliable integration of the proposed 250 MW Load Thermal Overloads Voltage Violations Unsolved Power Flow Southeast Brownsville Large Load The proposed project aims to support a new 250 MW load connecting to STEC’s proposed 138 kV Boca Chica* substation in Cameron County The interconnection study for the proposed 250 MW load has identified transmission system reliability criteria violations per Section 4 of the ERCOT Planning Guide (EPG). • All recent retired/indefinitely mothballed units will be reviewed • This project is needed to address the thermal violations seen by STEC in Cameron County in the South STEC evaluated four (4) transmission system improvement options to address reliability issues observed in the load interconnection study. Thermal Overloads (Exhibiting loading >100% of the 2-hr Emergency rating) | 2026/7.-EIR-Status-Update-STEC-Southeast-Brownsville-Large-Load-Project-RPG_April_2026_Final.pdf 2026/12.-EIR-STEC-Brownsville-Project-Scope-RPG-March-2026-FINAL.pdf 2026/12_EIR_STEC_Brownsville_Project_Scope_RPG_February_2026_FINAL (1).pdf 2026/12_EIR_STEC_Brownsville_Project_Scope_RPG_February_2026_FINAL.pdf 2026/STEC_Southeast-Brownsville-Load-_RPG_final.pptx
25RPG040 | Set 1 North & Central Texas Reliability Project | Oncor | Tier 1 | 1798 | 2025 | Under Review | Data Center Load | Data Center Load, Large Load Growth, Load Growth, Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability | Y | Y | Y | Y |  |  |  | Y | Y | – Addresses the thermal overloads and voltage violations in the Ellis, Navarro, • This is project is needed to address the thermal overloads and voltage violations in the Ellis, Navarro, upgrades that did not meet the reliability need based on the review, the study area will have over 16 GW of large loads than the 210 GW from data centers Over 16 GW of load from various other industrial sectors area will have over 16 GW of large loads than the 2025 RTP load level (over 13 GW than Oncor submitted five RPG submittals to address these reliability projects based on ERCOT’s recommendation: Proposed upgrades will address thermal and voltage planning criteria violations identified by ERCOT in the 2024 RTP and 2025 RTP | 2026/9_EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026.pdf 2026/EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-Update-RPG-Mar-2026.pdf 2026/Set-1-Set-2-and-Navarro-and-Ellis-Area-Reliability-Project-Overviews-01162026_Final.pptx 2026/8.-EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Projects-Status-Update-RPG-Apr-2026_Final.pdf 2026/10_EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026_Final.pdf
25RPG041 | Set 1 North Central & South Central Texas Reliability Project | Oncor | Tier 1 | 943.92 | 2025 | Under Review | Data Center Load | Data Center Load, Large Load Growth, Load Growth, Line Aging/Rebuild, Voltage/Reactive, Thermal Overload/Reliability | Y | Y | Y | Y |  |  |  | Y | Y | • Addresses the thermal overloads and voltage violations in the Bell, Falls, Henderson, Hill, Limestone, upgrades that did not meet the reliability need based on the have over 19 GW of large loads than the 2025 RTP load level (over 18 GW than the 2024 RTP load review, the study area will have over 19 GW of large loads than the 210 GW from data centers Over 16 GW of load from various other industrial sectors Oncor submitted five RPG submittals to address these reliability projects based on ERCOT’s recommendation: Proposed upgrades will address thermal and voltage planning criteria violations identified by ERCOT in the 2024 RTP and 2025 RTP | 2026/9.-EIR-Status-Update-Oncor-Combined-Set-1-Set-2-North-Central-South-Central-TX-Reliability-Project_RPG-Apr_2026_Final.pdf 2026/10_EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026_Final.pdf 2026/EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Mar-2026.pdf 2026/Set-1-Set-2-and-Navarro-and-Ellis-Area-Reliability-Project-Overviews-01162026_Final.pptx 2026/9_EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026.pdf
25RPG038 | Navarro and Ellis Area Reliability Project | Oncor and LST | Tier 1 | 759.95 | 2025 | Under Review | Data Center Load | Data Center Load, Large Load Growth, Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability | Y | Y | Y | Y |  |  | Y | Y | Y | – This project is needed to address post-contingency thermal and voltage violations – Addresses post-contingency thermal overloads on the Venus Switch – 210 GW from data centers Over 16 GW of load from various other industrial sectors caused by load growth in the Dallas, Ellis, Freestone, Hill and Navarro Counties • All recent retired/indefinitely mothballed units will be reviewed Oncor submitted five RPG submittals to address these reliability projects based on ERCOT’s recommendation: Proposed upgrades will address thermal and voltage planning criteria violations identified by ERCOT in the 2024 RTP and 2025 RTP – To address REC planning criteria to limit radial load to less than 20 MW Thermal/Voltage Violations | 2026/11_EIR_Oncor_Lone_Star_Navarro_and_Ellis_Area_Reliability_Project_Scope_RPG_February_2026.pdf 2026/Set-1-Set-2-and-Navarro-and-Ellis-Area-Reliability-Project-Overviews-01162026_Final.pptx 2024/EIR - REC - Rand Area Loop Project - Scope - RPG Jun 2024.pdf 2024/EIR_ONCOR_Venus_Switch_to_Sam_Switch_Project_Update.pdf
25RPG045 | Alice Area Improvements Transmission Project | AEPSC | Tier 3 | 67 | 2025 | Completed
25RPG044 | Whitney Autotransformer Upgrade Project | BEC | Tier 3 | 33.5 | 2025 | Completed | Load Growth | Load Growth |  |  | Y
25RPG046 | Medina County Large Load Additions Project | STEC | Tier 1 | 492 | 2026 | Under Review | Large Load Growth | Large Load Growth, Line Aging/Rebuild, Renewable Integration, Voltage/Reactive, Thermal Overload/Reliability |  | Y |  | Y |  |  | Y | Y | Y | Firmly committed large loads in the vicinity were modeled to develop the base cases prior to adding the proposed load. A total of 259.5 MW of large load additions were included. CPS Energy submitted the Large Load Additions Project (25RPG020) for Electric ERCOT will perform a combined EIR Study for CPS Energy Large Load Additions Project Address the violations under NERC TPL-001-5 and EPG criteria contingencies and ensure reliable integration of the proposed 980 MW Load Contingency Category Unsolved Power Flow Voltage Violations Thermal Overloads STEC Medina County Large Load Project (25RPG046) Combined – CPS Energy – Large Load CPS Large Load Project – Updated ERCOT approximately 2 GW Load by 2035 (EIR) into the ongoing EIR for the CPS Large Load Project | 2026/6_STEC_Medina-County-Large-Load-_RPG_final.pptx 2026/6_EIR-CPS-Energy-Large-Load-Additions-Project-and-STEC-Medina-County-Large-Load-Project_StatusUpdate_April2026_RPG.pdf 2026/8_EIR-CPS-Energy-Large-Load-Additions-Project_Updated_SCOPF_Feb2026_RPG.pdf 2026/7_EIR-STEC-Medina-County-Large-Load-Project_SCOPE_Feb2026_RPG.pdf 2025/EIR-CPS-Energy-Large-Load-Additions-Project_SCOPE_Aug2025_RPG.pdf
26RPG001 | Euclid 765-kV Substation and Transmission Line Addition Project | LCRA TSC and CEHE | Tier 1 | 1830 | 2026 | Under Review | Large Load Growth | Large Load Growth, Load Growth, Thermal Overload/Reliability |  | Y | Y | [5 empty] | Y | • Ensure transmission system reliability for native & large load customers in Central | 2026/13.-26RPG001-LCRA-TSC-and-CEHE-Euclid-765-kV-Substation-and-Transmission-Line-Addition-Project_final.pdf 2026/EIR-Euclid-765-kV-Substation-and-Transmission-Line-Addition-Status-Update-RPG-April_2026.pdf 2026/EIR-Euclid-765-kV-Substation-and-Transmission-Line-Addition-Scope-RPG-March_2026.pdf

## Driver Summary
Category (Primary) | Count | Total Cost ($M) | Avg Cost ($M) | Share
Data Center Load | 13 | 7167.9 | 551.4 | 18.6%
Large Load Growth | 49 | 19824.2 | 404.6 | 51.4%
Load Growth | 32 | 2795.4 | 87.4 | 7.2%
Line Aging/Rebuild | 83 | 5934 | 71.5 | 15.4%
Unit Retirement | 1 | 309 | 309 | 0.8%
Resilience/Hardening | 7 | 1564.8 | 223.5 | 4.1%
Renewable Integration | 1 | 23 | 23 | 0.1%
Voltage/Reactive | 8 | 941 | 117.6 | 2.4%
Thermal Overload/Reliability | 0 | 0 | 0 | 0.0%
Total | 194 | 38559.2
Data Center / Large Load Detail
Project Name | Entity | Cost ($M) | Year | Tier | Primary Driver | DC? | Key Evidence
Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | 9384 | 2025 | Tier 1 | Large Load Growth |  | • Ensure transmission system reliability for native & large load customers in Central ERCOT to address the reply comments
Euclid 765-kV Substation and Transmission Line Addition Project | LCRA TSC and CEHE | 1830 | 2026 | Tier 1 | Large Load Growth |  | • Ensure transmission system reliability for native & large load customers in Central
Set 1 North & Central Texas Reliability Project | Oncor | 1798 | 2025 | Tier 1 | Data Center Load | Y | – Addresses the thermal overloads and voltage violations in the Ellis, Navarro, • This is project is needed to address the thermal overloads and voltage violations in the Ellis, Navarro, upgrades that did not meet the reliability need based on the review, the study area will have over 16 GW of large loads than the 210 GW from data centers Over 16 GW of load from various other industrial sectors area will have over 16 GW of large loads than the 2025 RTP load level (over 13 GW than Oncor submitted five RPG submittals to address these reliability projects based on ERCOT’s recommendation: Proposed upgrades will address thermal and voltage planning criteria violations identified by ERCOT in the 2024 RTP and 2025 RTP
Set 2 North & Central Texas Reliability Project | Oncor | 1330 | 2025 | Tier 1 | Data Center Load | Y | – Addresses the thermal overloads and voltage violations in the Ellis, Navarro, • This is project is needed to address the thermal overloads and voltage violations in the Ellis, Navarro, upgrades that did not meet the reliability need based on the review, the study area will have over 16 GW of large loads than the 210 GW from data centers Over 16 GW of load from various other industrial sectors area will have over 16 GW of large loads than the 2025 RTP load level (over 13 GW than Oncor submitted five RPG submittals to address these reliability projects based on ERCOT’s recommendation: Proposed upgrades will address thermal and voltage planning criteria violations identified by ERCOT in the 2024 RTP and 2025 RTP
Lower Rio Grande Valley System Enhancement Project | ERCOT | 1280 | 2021 | Tier 1 | Large Load Growth |  | (projected load growth and potential industrial load additions) (generally large load with limited lead Valley load growth • Continuous load growth is expected in LRGV. In addition, there have  improve resiliency under normal conditions (all components are in load growth in LRGV (LRGV load forecast by 2030 and 2040 are 3.3 GW and 4 GW, respectively) Improve system resilience and operation flexibility Yes Yes – Improve system resilience, including • To integrate potential LNG load, potential transmission • Currently, there is no confirmed LNG load in the Valley
Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | 1219 | 2025 | Tier 1 | Large Load Growth |  | – Addresses the thermal overloads and voltage violations due to proposed load additions in • Driven by new 4064 MW large loads in southern DFW that either executed an interconnection agreement – Large Loads including OLLs (approximately 4,046 MW) relevant to the • To improve the accuracy of the study case and compensate for the 4064 MW load, the total 3400 MW comprising of the following load additions in the Southern DFW in the North Central and East Weather The total projected load additions of 4064 MW results in base case 2024 RTP Projects Addressed by Proposed Projects in this RPG Submittal • Voltage Violation
Set 1 North Central & South Central Texas Reliability Project | Oncor | 943.92 | 2025 | Tier 1 | Data Center Load | Y | • Addresses the thermal overloads and voltage violations in the Bell, Falls, Henderson, Hill, Limestone, upgrades that did not meet the reliability need based on the have over 19 GW of large loads than the 2025 RTP load level (over 18 GW than the 2024 RTP load review, the study area will have over 19 GW of large loads than the 210 GW from data centers Over 16 GW of load from various other industrial sectors Oncor submitted five RPG submittals to address these reliability projects based on ERCOT’s recommendation: Proposed upgrades will address thermal and voltage planning criteria violations identified by ERCOT in the 2024 RTP and 2025 RTP
Delaware Basin State 5 Project | Oncor | 855.3 | 2024 | Tier 1 | Data Center Load | Y | – The project is needed to address reliability issues (both thermal overloads and voltage violations) – Large Loads with Signed Interconnection Agreement (IA) were added in Total New Large Loads Added 1,194 due to significant load growth in the Delaware Basin area, in the Andrews, Borden, Culberson, • Due to the significant load growth and because of lack of long- injection point to support this high load growth area • As part of the efforts to address this challenges, ERCOT • All components in Oncor’s project address the scope identified in Stages 3 and
Navarro and Ellis Area Reliability Project | Oncor and LST | 759.95 | 2025 | Tier 1 | Data Center Load | Y | – This project is needed to address post-contingency thermal and voltage violations – Addresses post-contingency thermal overloads on the Venus Switch – 210 GW from data centers Over 16 GW of load from various other industrial sectors caused by load growth in the Dallas, Ellis, Freestone, Hill and Navarro Counties • All recent retired/indefinitely mothballed units will be reviewed Oncor submitted five RPG submittals to address these reliability projects based on ERCOT’s recommendation: Proposed upgrades will address thermal and voltage planning criteria violations identified by ERCOT in the 2024 RTP and 2025 RTP – To address REC planning criteria to limit radial load to less than 20 MW Thermal/Voltage Violations
Baytown Area Load Addition Project | CNP | 545.3 | 2024 | Tier 1 | Large Load Growth |  | – Addresses the thermal and voltage violations caused by the new 500.5 • All recent retired/indefinitely mothballed units will be reviewed 75856B Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire Tier 4 May-25 Harris the new substation. To serve the new substation and its 500.5 MVA load, 11/12/2024 CNP Baytown Area Load Addition Project load addition in-service date. MVA load addition at the new customer-owned NEWSUB 138-kV – The reliability analysis will be performed to identify the need to serve the new load
Lower Rio Grande Valley Transmission Expansion Project | STEC | 511 | 2020 | Tier 1 | Large Load Growth |  | (projected load growth and potential industrial load additions) (generally large load with limited lead Valley load growth • Continuous load growth is expected in LRGV. In addition, there have  improve resiliency under normal conditions (all components are in load growth in LRGV (LRGV load forecast by 2030 and 2040 are 3.3 GW and 4 GW, respectively) Improve system resilience and operation flexibility Yes Yes – Improve system resilience, including • To integrate potential LNG load, potential transmission • Currently, there is no confirmed LNG load in the Valley
Medina County Large Load Additions Project | STEC | 492 | 2026 | Tier 1 | Large Load Growth |  | Firmly committed large loads in the vicinity were modeled to develop the base cases prior to adding the proposed load. A total of 259.5 MW of large load additions were included. CPS Energy submitted the Large Load Additions Project (25RPG020) for Electric ERCOT will perform a combined EIR Study for CPS Energy Large Load Additions Project Address the violations under NERC TPL-001-5 and EPG criteria contingencies and ensure reliable integration of the proposed 980 MW Load Contingency Category Unsolved Power Flow Voltage Violations Thermal Overloads STEC Medina County Large Load Project (25RPG046) Combined – CPS Energy – Large Load CPS Large Load Project – Updated ERCOT approximately 2 GW Load by 2035 (EIR) into the ongoing EIR for the CPS Large Load Project
Bearkat – North McCamey – Sand Lake 345-kV Transmission Line Addition Project | LCRA TSC, Oncor, WETT | 477.6 | 2022 | Tier 1 | Large Load Growth |  | ➢ Address the reliability need driven by rapid load growth in the Delaware – Addresses post-contingency thermal overloads and voltage violations due – The project is needed to address reliability issues (both thermal overloads and voltage violations) – Large Loads with Singed Interconnection Agreement (IA) were added in Total Large Loads in Delaware Basin 3,361 • Due to the significant load growth and because of lack of long-term load and gas load growth in the Delaware Basin area to significant oil and gas load growth • All recent retired/indefinitely mothballed units will be reviewed injection point to support this high load growth area
Set 2 North Central & South Central Texas Reliability Project | Oncor | 440.79 | 2025 | Tier 1 | Data Center Load | Y | – Addresses the thermal overloads and voltage violations in the Bell, Falls, upgrades that did not meet the reliability need based on the review, the study area will have over 19 GW of large loads than the have over 19 GW of large loads than the 2025 RTP load level (over 18 GW than the 2024 RTP load 210 GW from data centers Over 16 GW of load from various other industrial sectors Oncor submitted five RPG submittals to address these reliability projects based on ERCOT’s recommendation: Proposed upgrades will address thermal and voltage planning criteria violations identified by ERCOT in the 2024 RTP and 2025 RTP
Brownsville Area Improvements Transmission Project | AEPSC | 423.8 | 2024 | Tier 1 | Large Load Growth |  | – Addresses both thermal overloads and voltage violations in the Brownsville addition of new large load • All recent retired/indefinitely mothballed units will be reviewed
Large Load Additions Project | CPS Energy | 333.7 | 2025 | Tier 1 | Large Load Growth |  | Project set driven by ~2GW of new large loads with varying load CPS Energy submitted the Large Load Additions Project (25RPG020) for Electric ERCOT will perform a combined EIR Study for CPS Energy Large Load Additions Project Contingency Category Unsolved Power Flow Voltage Violations Thermal Overloads Combined – CPS Energy – Large Load CPS Large Load Project – Updated ERCOT approximately 2 GW Load by 2035 CPS ENERGY LARGE LOAD (EIR) into the ongoing EIR for the CPS Large Load Project • All recent retired/indefinitely mothballed units will be reviewed
WETT Delaware Basin Stage 5 Project Alternative | WETT | 305.5 | 2024 | Tier 1 | Data Center Load | Y | – The project is needed to address reliability issues (both thermal overloads and voltage violations) – Large Loads with Signed Interconnection Agreement (IA) were added in Total New Large Loads Added 1,194 violations) due to significant load growth in the Delaware Basin area, in the Andrews, injection point to support this high load growth area • Due to the significant load growth and because of lack of long- oil and gas load growth in the Delaware Basin area • All of components in Oncor’s project address the scope identified in Stage 5 • As part of the efforts to address this challenges, ERCOT
Roanoke Area Upgrades project | Oncor | 285.9 | 2022 | Tier 1 | Data Center Load | Y | – Address rapid load growth in Roanoke area, existing capacity  Based on comments updated scope to include Denton Data Center load Retire Existing Line 1. Adjusted load up in substations identified in “Area Load Growth – Provides better long-term load serving capability for future load growth in  All recent retired or indefinitely mothballed units will be reviewed and turned off, to address overloads on the two existing 345/138-kV transformers at and forecasted thermal and voltage violations.
Texas A&M University System RELLIS Campus Reliability Project | BTU | 281.2 | 2025 | Tier 1 | Large Load Growth |  | – Addresses the thermal overloads and voltage violations due to proposed • All recent retired/indefinitely mothballed units will be reviewed load additions in the Brazos County in the East weather zone
Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | 273.1 | 2023 | Tier 1 | Large Load Growth |  | – Addresses both thermal overloads and voltage violations in the Reeves • All recent retired/indefinitely mothballed units will be reviewed o Improves long-term load serving capability for future load growth in the area New Load Locations and Integration Outlook o Addresses reliability violation – Provide another source to the IH20 area to address the maintenance outage issues counties in the Far West weather zone addressed be Accommodated Either Remaining Amount of Load
Corpus North Shore Project | AEPSC | 259.57 | 2020 | Tier 1 | Large Load Growth |  | serve the following new load additions in the Corpus Area Load Growth” Section of AEP Corpus Christi North Shore Report and • Provide sufficient transmission capacity and address the reliability • Reactive compensation upgrades are anticipated to address local area to address reactive improvements
Delaware Basin Stages 3 and 4 Project | Oncor | 202.2 | 2024 | Tier 1 | Data Center Load | Y | – The project is needed to address reliability issues (both thermal overloads and voltage violations) – Large Loads with Singed Interconnection Agreement (IA) will also be Total Large Loads in Delaware Basin 3,361 • All recent retired/indefinitely mothballed units will be reviewed • Due to the significant load growth and because of lack of long- oil and gas load growth in the Delaware Basin area injection point to support this high load growth area (FW) Weather Zone due to the significant load addition in the FW Weather • All components in Oncor’s project address the scope identified in Stages 3 and • As part of the efforts to address this challenges, ERCOT
Wilmer 345/138-kV Switch Project | Oncor | 158.2 | 2024 | Tier 1 | Large Load Growth |  | – Addresses the thermal overloads in the Dallas, Kaufman, and Ellis • All recent retired/indefinitely mothballed units will be reviewed – Option 1 better improves long-term load-serving capability for future load growth in the • ERCOT evaluated four project options to address the identified reliability
Eastside 345/138-kV Switching Station Project | CPS Energy | 158 | 2024 | Tier 1 | Large Load Growth |  | • Driven by generation retirements local to CPS Energy 73417 LCRATSC_Schumansville_SheriffsPosse_StormHardening Tier 4 15/5/2025 LCRA 73793 LCRATSC_McCartyLaneEast_Zorn_TL_Storm_Hardening Tier 4 15/5/2025 LCRA – Addresses thermal overloads on 345/138-kV autotransformers and 138-kV 23RPG003 Eagle Ford Large Load Interconnection Project Tier 3 12/4/2025 GVEC DeWitt • All recent retired/indefinitely mothballed units will be reviewed o Addresses reliability violations
Venus Switch to Sam Switch 345-kV Line Project | Oncor | 118.9 | 2024 | Tier 1 | Large Load Growth |  | (NERC) and ERCOT Planning Criteria to address thermal overloads on 81.5 miles of – Addresses post-contingency thermal overloads on the Venus Switch – • All recent retired/indefinitely mothballed units will be reviewed and • The purpose of the project is to address the reliability needs in the Key Takeaway: ERCOT studied several options and recommends Option 1 to address the Thermal/Voltage Violations
Pecos County Transmission Improvement Project | TNMP | 114.8 | 2023 | Tier 1 | Large Load Growth |  | • Both thermal overloads and voltage violations in the Pecos and Reeves Improves long-term load serving capability for future load growth in the area New Load Locations and Integration Outlook counties in the Far West weather zone addressed be Accommodated Either Remaining Amount of Load Addresses reliability violations
Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | 110 | 2025 | Tier 1 | Large Load Growth |  | – This project is needed to address post-contingency voltage violations and improve • All recent retired/indefinitely mothballed units will be reviewed
Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | 97.7 | 2024 | Tier 2 | Data Center Load | Y | – Addresses post-contingency thermal overloads and voltage violations due – Additional Large Loads Provided by TSPs Total Large Loads added 1,328.97 to significant oil and gas load growth • All recent retired/indefinitely mothballed units will be reviewed gas load growth • Substantial load growth in Oncor’s southern Stanton Loop area introduces • Increase diversity and resiliency in the 138-kV and 345-kV network
Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | 97 | 2024 | Tier 3 | Large Load Growth |  |  Addresses the reliability issues primarily driven by new confirmed load additions due – Addresses thermal overloads and load growth o Reliability need driven by new confirmed load additions primarily in the oil – Addresses post-contingency thermal overloads and voltage violations on • All recent retired/indefinitely mothballed units will be reviewed and performed to identify the need to serve the projected area load using the Thermal/Voltage Violations ‒ The project was submitted to address ✓ Voltage violations on multiple 138-kV buses
Southeast Brownsville Large Load Transmission System Improvements Project | STEC | 96.35 | 2025 | Tier 2 | Large Load Growth |  | Large loads in the vicinity were modeled to develop the cases prior to adding the proposed load, per ERCOT LLI team’s input - ~1166 MW of large load additions were included based on input from ERCOT LLI Team. Address the violations under NERC TPL-001-5 and EPG criteria contingencies and ensure reliable integration of the proposed 250 MW Load Thermal Overloads Voltage Violations Unsolved Power Flow Southeast Brownsville Large Load The proposed project aims to support a new 250 MW load connecting to STEC’s proposed 138 kV Boca Chica* substation in Cameron County The interconnection study for the proposed 250 MW load has identified transmission system reliability criteria violations per Section 4 of the ERCOT Planning Guide (EPG). • All recent retired/indefinitely mothballed units will be reviewed • This project is needed to address the thermal violations seen by STEC in Cameron County in the South STEC evaluated four (4) transmission system improvement options to address reliability issues observed in the load interconnection study. Thermal Overloads (Exhibiting loading >100% of the 2-hr Emergency rating)
Galveston Region Project | TNMP | 95.9 | 2024 | Tier 2 | Large Load Growth |  | – Addresses the thermal overloads and voltage violations in the Galveston with more flexibility in terms of accommodating some of the large load requests anticipated on • All recent retired/indefinitely mothballed units will be reviewed • TNMP is anticipating a significant amount of load growth on its Galveston region transmission system to assert the load additions in September 2025 • The project is submitted to address the reliability violations under planned • The voltage security of the region will be addressed and the long-term load serving capability will be solution to reliably address the issues identified above
Midland East Area Projects | Oncor | 88.5 | 2021 | Tier 3 | Large Load Growth |  | o Reliability need driven by new confirmed load additions primarily in the oil o Address the reliability issues primarily driven by new confirmed load experiencing rising power demand, driven by o All recent retired or indefinitely mothballed units will be turned off, if performed to identify the need to serve the projected area load using the ‒ The project was submitted to address ✓ Voltage violations on multiple 138-kV buses
Roscoe Area Upgrades Project | Oncor | 84.3 | 2024 | Tier 2 | Large Load Growth |  | • Driven by high load growth in the area and increased generation in – Addresses voltage violations seen by Oncor • All recent retired/indefinitely mothballed units will be reviewed – Improves long-term load-serving capability for future load growth in the Roanoke -Euless 474 481 509 516 523 536 546 of new load in the area. Roanoke -Deen 471 478 494 500 504 517 527 • Thermal overloads and voltage
Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | 83.2 | 2021 | Tier 2 | Large Load Growth |  | ➢ Address the reliability need driven by rapid load growth in the Delaware to address the challenges and accommodate significant and rapid • Due to the significant load growth and because of lack of long-term load and gas load growth in the Delaware Basin area load growth in the area. Resource Assessment (TORA) program and is engaging with BEG to New Load Notification (1-2 years) Commitment for New Load substations to accommodate the second circuit addition. • As part of the efforts to address the challenge, ERCOT completed the
Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | 80 | 2023 | Tier 3 | Large Load Growth |  | • Driven by new 4064 MW large loads in southern DFW that either executed an interconnection agreement – Addresses the thermal overloads and voltage violations due to proposed load – Large Loads including OLLs (approximately 4,046 MW) relevant to the • To improve the accuracy of the study case and compensate for the 4064 MW load, the total 3400 MW comprising of the following load additions in the Southern DFW in the North Central and East Weather The total projected load additions of 4064 MW results in base case 2024 RTP Projects Addressed by Proposed Projects in this RPG Submittal • Voltage Violation
Stone Lake Area Upgrades Project | CNP | 74.38 | 2023 | Tier 3 | Large Load Growth |  | – Addresses thermal overloads seen by CNP and 2023 RTP • Develop transmission upgrades to address the reliability
Walleye Creek 345/138-kV Switch Project | Oncor | 74 | 2023 | Tier 3 | Large Load Growth |  | – Addresses the thermal overloads and voltage violations due to proposed • All recent retired/indefinitely mothballed units will be reviewed and load additions in the Dallas and Tarrant Counties Thermal Overload
Nueces Green Ammonia Load Interconnection Project | STEC | 74 | 2025 | Tier 2 | Large Load Growth |  | STEC evaluated two (2) transmission system improvement options to address reliability issues and support the new load addition. Addresses the violations under NERC and EPG criteria contingencies, and ensures reliable integration of the proposed 1150 MW Load It addresses all reliability concerns and supports the integration of the proposed Ammonia Plant Load at its full capacity (1150 MW) – This project is needed to address post-contingency voltage violations in the Planning Criteria to address thermal overloads on approximately 39 miles of 138-kV Reliably integrates the proposed 1150 MW load No transmission system stability issues were identified under any planning events with the proposed 1150 MW load connected via Option 2. Dupont Switching station to the new large load and the removal of the double-circuit • Connect the new large load confirmed by Transmission Service Provider (TSP) Vice President, System Planning and resilience, the Project has completed Regional Planning
LRGV Import Project | AEPSC | 73.4 | 2020 | Tier 1 | Large Load Growth |  | (projected load growth and potential industrial load additions) (generally large load with limited lead • Continuous load growth is expected in LRGV. In addition, there have  improve resiliency under normal conditions (all components are in load growth in LRGV (LRGV load forecast by 2030 and 2040 are 3.3 GW and 4 GW, respectively) Improve system resilience and operation flexibility Yes Yes
Arlington Reliability Enhancement Project | Oncor | 73 | 2023 | Tier 2 | Large Load Growth |  | • All recent retired/indefinitely mothballed units were reviewed and – Addresses particular reliability exposure needs in the Arlington area,
Rio Medina Project | STEC | 71.7 | 2023 | Tier 2 | Data Center Load | Y | • The proposed project focuses on serving the Rio Medina data center load but also accommodates – The project serves a new 129 MW load at the new Rio Medina substation service to an additional data center that is currently under evaluation. • All recent retired/indefinitely mothballed units will be reviewed ‒ Improves long-term load serving capability for future load growth in the ‒ Addresses the reliability criteria violations
Ammonia Plant Load Project | STEC | 65.47 | 2025 | Tier 2 | Large Load Growth |  | STEC evaluated two (2) transmission system improvement options to address reliability issues and support the new load addition. Address the violations under NERC and EPG criteria contingencies and ensure reliable integration of the proposed 300 MW Load It addresses all reliability concerns and supports the integration of the proposed Ammonia Plant Load at its full capacity (1150 MW) Planning Criteria to address thermal overloads on approximately 39 miles of 138-kV – This project is needed to address post-contingency voltage violations in the Dupont Switching station to the new large load and the removal of the double-circuit • Connect the new large load confirmed by Transmission Service Provider (TSP) Large loads in the vicinity were modeled to develop the cases prior to adding the proposed load, per ERCOT LLI team’s input Reliably integrates the proposed 1150 MW load No transmission system stability issues were identified under any planning events with the proposed 1150 MW load connected via Option 2.
Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | 63.88 | 2025 | Tier 3 | Large Load Growth |  |  Addresses the reliability issues primarily driven by new confirmed load additions due issues primarily driven by the new confirmed load additions due to the o All recent retired or indefinitely mothballed units will be turned off, if Allow Better Future Load Growth • To address the reliability issues, ERCOT evaluated five transmission Line Project for RPG review in June 2021 to address the reliability upgrade option to address the reliability issues at the RPG meetings: substations to accommodate the second circuit addition.
Flat Iron – Barr Ranch – Pegasus South 138-kV Line Project | Oncor | 63.1 | 2021 | Tier 2 | Large Load Growth |  |  Addresses the reliability issues primarily driven by new confirmed load additions due issues primarily driven by the new confirmed load additions due to the o All recent retired or indefinitely mothballed units will be turned off, if Allow Better Future Load Growth Line Project for RPG review in June 2021 to address the reliability upgrade option to address the reliability issues at the RPG meetings: • To address the reliability issues, ERCOT evaluated five transmission • Develop transmission upgrades to address the reliability
Red Oak Area Upgrades project | Oncor | 63 | 2022 | Tier 3 | Large Load Growth |  | ➢ Address the reliability need driven by rapid load growth in the Delaware issues primarily driven by the new confirmed load additions due to the o Address the reliability issues primarily driven by new confirmed load  Addresses thermal violations, load growth, improves dynamic performance experiencing rising power demand, driven by o All recent retired or indefinitely mothballed units will be turned off, if Allow Better Future Load Growth • Due to the significant load growth and because of lack of long-term load and gas load growth in the Delaware Basin area Line Project for RPG review in June 2021 to address the reliability
Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | 62.7 | 2022 | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | Large Load Growth |  |  Addresses the reliability issues primarily driven by new confirmed load additions due issues primarily driven by the new confirmed load additions due to the o All recent retired or indefinitely mothballed units will be turned off, if Allow Better Future Load Growth Line Project for RPG review in June 2021 to address the reliability upgrade option to address the reliability issues at the RPG meetings: • To address the reliability issues, ERCOT evaluated five transmission
Yucca to Moss 138 kV Line Project | Oncor | 60.7 | 2022 | Reclassified from Tier 3 to Tier 4 per Protocol | Large Load Growth |  | ✓ Addresses the reliability issues primarily driven by new confirmed load additions due • To address the reliability issues, ERCOT evaluated five transmission
Oncor Skyview 345/138-kV Switch Project | Oncor | 56.82 | 2025 | Tier 2 | Large Load Growth |  | – Addresses the thermal overloads and voltage violations due to proposed • All recent retired/indefinitely mothballed units will be reviewed and load additions in the Dallas and Tarrant Counties Thermal Overload Liggett 345/138 kV Autotransformers thermal overload
Lake Pauline Area Improvement Project | AEPSC | 47.5 | 2020 | Tier 3 | Large Load Growth |  | – Addresses the voltage violations under planned maintenance outage to address the challenges and accommodate significant and rapid • All recent retired/indefinitely mothballed units will be reviewed load growth in the area. Resource Assessment (TORA) program and is engaging with BEG to New Load Notification (1-2 years) Commitment for New Load
Eagle Ford Large Load Interconnection Project | GVEC | 47 | 2023 | Reclassified from Tier 1 to Tier 3 per Protocol | Large Load Growth |  | • Driven by new 4064 MW large loads in southern DFW that either executed an interconnection agreement – Addresses the thermal overloads and voltage violations due to proposed load – Large Loads including OLLs (approximately 4,046 MW) relevant to the • To improve the accuracy of the study case and compensate for the 4064 MW load, the total 3400 MW comprising of the following The total projected load additions of 4064 MW results in base case 2024 RTP Projects Addressed by Proposed Projects in this RPG Submittal • Voltage Violation • Develop transmission upgrades to address the reliability • Reliability upgrades were identified to address the
Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | 44.9 | 2023 | Reclassified from Tier 3 to Tier 4 per Protocol | Data Center Load | Y | **Mainly datacenter/crypto load Datacenter Basin region load growth for 2030 • Develop transmission upgrades to address the reliability • Significant progress has been made to address the high demand growth in the
Omicron Reliability Project | CPS Energy | 42.5 | 2024 | Tier 2 | Large Load Growth |  | • Driven by new large loads and system growth in west 73417 LCRATSC_Schumansville_SheriffsPosse_StormHardening Tier 4 15/5/2025 LCRA Guadalupe, Comal 73793 LCRATSC_McCartyLaneEast_Zorn_TL_Storm_Hardening Tier 4 15/5/2025 LCRA Hays, Guadalupe – Addresses both thermal and voltage violations associated with the new 23RPG003 Eagle Ford Large Load Interconnection Project Tier 3 12/4/2025 GVEC DeWitt • All recent retired/indefinitely mothballed units will be reviewed and Aging Infrastructures Lake Thermal/Voltage Violations
Tawakoni Area Transmission Project | REC | 42.4 | 2022 | Tier 2 | Large Load Growth |  | • All recent retired/indefinitely mothballed units were reviewed and August 2022 to address REC’s Planning criteria violation in the Lake  ERCOT shall recommend a project that would address the need under TSP’s criteria – Develop and test project alternatives to address the REC Planning criteria
Morgan Creek to McDonald Road 138-kV Line Project | Oncor | 40.2 | 2023 | Tier 3 | Large Load Growth |  | – Addresses thermal overloads and load growth o Reliability need driven by new confirmed load additions primarily in the oil and gas industry – The project is needed to address reliability issues (both thermal overloads and voltage violations) ‒ All recent retired/indefinitely mothballed units will be reviewed and turned off, if not ‒ Provides better long-term load serving capability for future load growth in due to significant load growth in the Delaware Basin area, in the Andrews, Borden, Culberson, • Due to the significant load growth and because of lack of long- injection point to support this high load growth area and gas load growth in the Far West Weather Zone, the lack of long- performed to identify the need to serve the projected area load using the
Peck to Driver 138 kV Line Project | Oncor | 36.2 | 2022 | Tier 2 | Large Load Growth |  | – Addresses thermal overloads and load growth o Reliability need driven by new confirmed load additions primarily in the oil and gas industry ‒ All recent retired/indefinitely mothballed units will be reviewed and turned off, if not ‒ Provides better long-term load serving capability for future load growth in performed to identify the need to serve the projected area load using the ‒ The project was submitted to address ✓ Voltage violations on multiple 138-kV buses ‒ Addresses the reliability criteria violation
Rand Area Loop Project | REC | 32.2 | 2024 | Tier 2 | Large Load Growth |  | • All recent retired/indefinitely mothballed units will be reviewed and – To address REC planning criteria to limit radial load to less than 20 MW
Eagle Mountain to Saginaw 138-kV Double-Circuit Line Upgrade Project | Oncor | 32 | 2020 | Tier 3 | Data Center Load | Y |  Address rapid load growth in Roanoke area, existing capacity limitations  Based on comments updated scope to include Denton Data Center load  All recent retired or indefinitely mothballed units will be reviewed and turned off, and forecasted thermal and voltage violations.
Texas City Transmission Improvement Project | TNMP | 29.3 | 2020 | Tier 2 | Large Load Growth |  |  All six options addressed the reliability issues driven by 93  EIR will address reliability issues primarily driven by a potential 50 MW o Retired and mothballed units were consistent with the 2020 RTP.  ERCOT evaluated following six options to address the reliability issues.
Long Draw Second 345/138-kV Autotransformer Project | WETT | 28 | 2024 | Tier 3 | Large Load Growth |  | – The project is needed to address reliability issues (both thermal overloads and voltage – Large Loads with Signed Interconnection Agreement (IA) were added in Total New Large Loads Added 1,194 • Substantial load growth in Oncor’s southern Stanton Loop area introduces • Increase diversity and resiliency in the 138-kV and 345-kV network violations) due to significant load growth in the Delaware Basin area, in the Andrews, injection point to support this high load growth area
McDonald Road Switch to Polecat Creek Switch 138-kV Line Project | Oncor | 26.66 | 2025 | Tier 3 | Large Load Growth |  | o Reliability need driven by new confirmed load additions primarily in the oil and gas industry o Address the reliability issues primarily driven by new confirmed load ‒ All recent retired/indefinitely mothballed units will be reviewed and turned off, if not ‒ Provides better long-term load serving capability for future load growth in performed to identify the need to serve the projected area load using the ‒ The project was submitted to address ✓ Voltage violations on multiple 138-kV buses ‒ Addresses the reliability criteria violation
Cedar Bayou Autotransformer Upgrades Project | CNP | 26.3 | 2025 | Tier 3 | Large Load Growth |  | – This project is needed to address aging infrastructure and to ensure resilience Aging Infrastructures/Storm – Addresses the thermal and voltage violations caused by the new 500.5 – Addresses thermal overloads seen by CNP and 2023 RTP 75856B Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire Tier 4 May-25 Harris 345-kV Hardening Project – ERCOT 345-kV Hardening Project (25RPG028) for Regional Planning Group • All recent retired/indefinitely mothballed units will be reviewed the new substation. To serve the new substation and its 500.5 MVA load, 11/12/2024 CNP Baytown Area Load Addition Project
Canton Area Loop Project | REC | 26.03 | 2024 | Tier 2 | Large Load Growth |  | • All recent retired/indefinitely mothballed units will be reviewed and – To address REC planning criteria to limit radial load to less than 20 MW
Primary Driver by Year
Category | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Data Center Load | 1 |  | 1 | 2 | 4 | 5
Large Load Growth | 5 | 4 | 6 | 8 | 12 | 12 | 2
Load Growth | 7 | 6 | 6 | 3 | 6 | 4
Line Aging/Rebuild | 12 | 8 | 26 | 15 | 9 | 13
Unit Retirement | [5 empty] | 1
Resilience/Hardening |  |  | 3 | 1 | 1 | 2
Renewable Integration | 1
Voltage/Reactive | 1 |  |  | 4 | 1 | 2
Thermal Overload/Reliability

## Project-File Mapping
RPG Project ID | RPG Project Name | Submitted Entity | Tier | Estimated Cost ($M) | First Report Year | Status | Matched Files Count | Matched Files
18RPG001 | LRGV Import Project | AEPSC | Tier 1 | 73.4 | 2020 | Under Review | 1 | 2021/ERCOT_LRGV_System_Enhancement_Project_RPG_09152021_final.pdf
19RPG009 | Lower Rio Grande Valley Transmission Expansion Project | STEC | Tier 1 | 511 | 2020 | Under Review | 3 | 2020/Lower_Rio_Grande_Valley_Transmission_Expansion_-_Jan_21_RPG.PDF 2021/ERCOT_LRGV_System_Enhancement_Project_RPG_09152021_final.pdf 2021/ERCOT_LRGV_System_Enhancement_Project_RPG_10152021_final.pdf
| Corpus North Shore Project | AEPSC | Tier 1 | 259.57 | 2020 | Under Review | 5 | 2020/AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_05_19_2020.pdf 2020/EIR_AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_01_21_2020.pdf 2020/EIR_AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_02_18_2020.pdf 2020/EIR_AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_03_10_2020.pdf 2021/AEPSC_Corpus_North_Shore_reactive_study_v2.pdf
| Frio County Transmission Project | 7x Energy | Tier 2 | 23 | 2020 | Under Review | 3 | 2020/7X_Frio_County_Project_Study_Scope_01_21_2020_RPG.PDF 2020/7X_Frio_County_Project_Study_Update_02_18_2020_RPG.PDF 2020/Frio_County_Project_EIR_05_19_2020_RPG.PDF
| Quanah Area Improvement Transmission Project | AEPSC | Tier 2 | 11.3 | 2020 | Under Review | 0
| Farmersville Area Reliability Project | GP&L | Tier 2 | 24.37 | 2020 | Under Review | 2 | 2020/GPL_Farmersville_Area_Reliability_Project_2_18_2020.pdf 2020/GPL_Farmersville_Area_Reliability_Project_EIR_5_19_2020_RPG.pdf
| W.A. Parish to Westpark Tollway Ckt 09 Rebuild Project | CNP | Tier 3 | 50.77 | 2020 | Under Review | 0
| Smith to Mathis 69-kV Line Rebuild Project | AEPSC | Tier 3 | 38 | 2020 | Under Review | 0
| Anna Switch - Royse Switch 138-kV Line Upgrade Project | Oncor | Tier 3 | 91.2 | 2020 | Under Review | 0
| Lookout Substation SVC Project | GP&L | Tier 3 | 25 | 2020 | Under Review | 0
| Texas City Transmission Improvement Project | TNMP | Tier 2 | 29.3 | 2020 | Under Review | 2 | 2020/Texas_City_Transmission_Improvement_Project_-_July_21_RPG.pdf 2020/Texas_City_Transmission_Improvement_Project_-_May_19_RPG.pdf
| Ballinger to San Angelo Concho 69 kV Line Rebuild Project | AEPSC | Tier 3 | 27 | 2020 | Under Review | 0
| Moffat to Hasse Voltage Conversion Project | BEC | Tier 2 | 55.2 | 2020 | Under Review | 1 | 2020/BEC_Moffat_to_Hasse_Voltage_Conversion__EIR_Status_7_21_2020.pdf
| Quarry Field 345-kV Switch Project | Oncor | Tier 3 | 29 | 2020 | Under Review | 0
| DeCordova Switching Station Rebuild Project | Oncor | Tier 3 | 37.5 | 2020 | Under Review | 0
| Big Spring – Buzzard Draw 69-kV Line Conversion to 138-kV Project | Oncor | Tier 3 | 32 | 2020 | Under Review | 0
| Carrollton Northwest 345/138-kV Autotransformer Upgrade Project | Oncor | Tier 3 | 8.5 | 2020 | Under Review | 0
| Eagle Mountain to Saginaw 138-kV Double-Circuit Line Upgrade Project | Oncor | Tier 3 | 32 | 2020 | Under Review | 4 | 2022/Oncor_Roanoke_Area_Upgrades_EIR_Scope_03_15_2022.pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status (1).pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status (2).pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status.pdf
| Horseshoe Springs Switch – Riverton Switch 138-kV Second Circuit Project | Oncor | Tier 3 | 52.3 | 2020 | Under Review | 1 | 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
| Everman Switching Station Rebuild Project | Oncor | Tier 3 | 36 | 2020 | Under Review | 0
| Coleto Creek to Kenedy SS 138-kV Transmission Project | AEPSC | Tier 3 | 54.7 | 2020 | Under Review | 1 | 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_May_11_RPG_Final.pdf
| Alamito Creek to Alpine 69-kV Line Rebuild Transmission Project | AEPSC | Tier 3 | 37 | 2020 | Under Review | 0
| Tall City – Telephone Road 138-kV Line Rebuild Project | Oncor | Tier 3 | 23.5 | 2020 | Under Review | 5 | 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_Sept_15_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Nov_9_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Oct_15_RPG.pdf 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
| Mont Belvieu Reliability Upgrades Project | CNP | Tier 3 | 27.28 | 2020 | Under Review | 0
20RPG019 | Nacogdoches Southeast Switch – Redland Switch – Lufkin Switch 345 kV Loop | Oncor | Tier 2 | 71.26 | 2020 | Completed | 4 | 2020/ERCOT_EIR_Oncor_Nacogdoches_Lufkin_Scope.pdf 2021/ERCOT_EIR_Oncor_Nacogdoches_Lufkin_081721_Status.pdf 2022/ERCOT_EIR_Oncor_Nacogdoches_Lufkin (1).pdf 2022/ERCOT_EIR_Oncor_Nacogdoches_Lufkin.pdf
| Burma to Sterling City 69-kV Line Rebuild Project | AEPSC | Tier 3 | 28 | 2020 | Under Review | 0
| Lake Pauline Area Improvement Project | AEPSC | Tier 3 | 47.5 | 2020 | Under Review | 2 | others/EIR-AEP-Childress-Area-Transmission-Improvement-Project-Scope-RPG-July-2025.pdf 2020/Permian_Basin_Area_Improvement_Updates_-_Dec2020RPG.PDF
| Wallis to Peters Ckt 65 138-kV Line Rebuild Project | CNP | Tier 3 | 64.78 | 2020 | Under Review | 0
20RPG022 | Hamilton Road to Maxwell 138-kV Line Rebuild Project | AEPSC | Tier 3 | 34 | 2020 | Completed | 1 | others/HamiltonRoad-Maxwell_Factsheet_V9.pdf
20RPG023 | Royse - Commerce 69-kV Line Conversion to 138-kV | Oncor | Tier 3 | 72.1 | 2020 | Completed | 0
21RPG002 | Port Lavaca Area Improvement Project | AEPSC | Tier 1 | 101.5 | 2021 | Completed | 5 | 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Scope_-_April_6_RPG_Final.pdf 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_Aug_17_RPG.pdf 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_June_15_RPG.pdf 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_May_11_RPG_Final.pdf 2023/TNMP - Pecos County Transmission Improvement Project - RPG.pdf
21RPG003 | Midland East Area Projects | Oncor | Tier 3 | 88.5 | 2021 | Completed | 3 | 2020/Oncor_IHS_RPG_Presentation_12152020.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2023/EIR - Oncor Peck to Driver 138 kV Line project Scope_Jan2023.pdf
21RPG004 | Venus Switch-Cedar Hill Switch 345-kV Line Project | Oncor | Tier 3 | 10.3 | 2021 | Completed | 3 | others/7-2-oncor-venus-switch-to-sam-switch-345-kv-line-project.pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Scope_03_15_2022.pdf 2023/Oncor_Arlington_Reliability_Enhancement_Project.pdf
21RPG005 | Angleton to West Columbia 138-kV ckt 04 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 38.7 | 2021 | Completed | 0
21RPG006 | Algoa Corner to La Marque 138 138-kV ckt 93 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.56 | 2021 | Completed | 0
21RPG007 | Holliday - Seymour 69-kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.3 | 2021 | Completed | 0
21RPG009 | Waterfowl Substation Addition | CNP | Tier 3 | 42.4 | 2021 | Completed | 0
21RPG008 | Burnett – Bowie 69 kV Line Upgrade Project | Oncor | Tier 3 | 79.7 | 2021 | Completed | 0
21RPG010 | Flat Iron – Barr Ranch – Pegasus South 138-kV Line Project | Oncor | Tier 2 | 63.1 | 2021 | Completed | 5 | 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_Sept_15_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Nov_9_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Oct_15_RPG.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf
21RPG011 | Flewellen to Peters 138 kV ckt 25 Rebuild | CNP | Tier 3 | 76.2 | 2021 | Completed | 0
21RPG001 | Bakersfield to Big Hill 345‐kV Second Circuit Addition Project | STEC & LCRA TSC | Tier 2 | 83.2 | 2021 | Completed (no UR record) | 3 | 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf 2022/LCRA_Oncor_WETT_Bearkat_NorthMcCamey_SandLake_Project_06_15_2022.pdf 2020/Permian_Basin_Area_Improvement_Updates_-_Dec2020RPG.PDF
21RPG013 | WA Parish to Nash 138-kV Ckt 02 Rebuild Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 71.75 | 2021 | Completed | 0
21RPG012 | Andrews North – Mustang – Paul Davis Tap 138 kV Line Section | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 37 | 2021 | Completed | 0
21RPG014 | Mason Switch to Yellowjacket 69-kV Line Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 36.9 | 2021 | Completed | 0
21RPG016 | TH Wharton - White Oak 138-kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 79.9 | 2021 | Completed | 0
21RPG015 | Munday to Throckmorton 69-kV and Albany to Throckmorton 69-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 83.4 | 2021 | Completed | 0
21RPG017 | Lower Rio Grande Valley System Enhancement Project | ERCOT | Tier 1 | 1280 | 2021 | Completed | 3 | 2020/Lower_Rio_Grande_Valley_Transmission_Expansion_-_Jan_21_RPG.PDF 2021/ERCOT_LRGV_System_Enhancement_Project_RPG_09152021_final.pdf 2021/ERCOT_LRGV_System_Enhancement_Project_RPG_10152021_final.pdf
21RPG018 | Bay City to Lane City 138-kV Line Rebuild Project | AEPSC | Tier 3 | 33 | 2021 | Completed | 5 | 2020/Texas_City_Transmission_Improvement_Project_-_July_21_RPG.pdf 2020/Texas_City_Transmission_Improvement_Project_-_May_19_RPG.pdf 2020/EIR_AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_01_21_2020.pdf 2020/EIR_AEPSC_Corpus_Christi_North_Shore_Study_StatusUpdate_03_10_2020.pdf 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_Aug_17_RPG.pdf
21RPG019 | Howard Road 345/138-kV Switching Station Project | CPS | Tier 3 | 56.3 | 2021 | Completed | 5 | 2023/EIR - CPS - San Antonio South Reliability Project - Scope - RPG Feb 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG Apr 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG June 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG Mar 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG May 2023.pdf
21RPG020 | Galena Park Area 138-kV Conversion Project | CNP | Tier 3 | 52.05 | 2021 | Completed | 0
21RPG024 | Tungsten 138/69 kV Station Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.9 | 2021 | Completed | 0
21RPG023 | Barrilla Junction 69 kV loop Rebuild and Conversion Project | AEPSC | Tier 3 | 44 | 2021 | Completed | 0
21RPG022 | Marshall Ford-Ruther Ford 138 kV Line Rebuild Project | PEC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.8 | 2021 | Completed | 3 | 2022/EIR - PEC Wimberley Loop Transmission Scope and Status Update RPG Oct 2022.pdf 2022/EIR - PEC Wimberley Loop Transmission Status Update RPG Nov 2022.pdf 2023/EIR - PEC Wimberley Loop Transmission - Status Update - RPG Jan 2023.pdf
22RPG001 | Greens Bayou to Clinton 138 kV Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 88.5 | 2022 | Completed | 0
21RPG021 | Mulberry Creek 345 kV Station Improvements Project | AEPSC/Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 49.2 | 2022 | Completed (no UR record) | 0
22RPG004 | Pulsar to Victoria 138 kV Line Rebuild project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 75.7 | 2022 | Completed | 0
22RPG002 | Abilene South to Putnam 138-kV Transmission Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31.5 | 2022 | Completed | 0
22RPG003 | Roanoke Area Upgrades project | Oncor | Tier 1 | 285.9 | 2022 | Completed | 5 | 2022/Oncor_Roanoke_Area_Upgrades_EIR_07_19_2022.pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Scope_03_15_2022.pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status (1).pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status (2).pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Status.pdf
22RPG005 | Hays Energy – Kendall Corridor Transmission Line Rehabilitation Projects | LCRA TSC | Tier 1 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 399.9 | 2022 | Completed | 1 | 2022/EIR-LCRA_TSC_Hays_Energy–Kendall_Corridor_Transmission_Line_Rehabilitation_Projects_Scope.pdf
22RPG006 | Consavvy 345/138 kV Switch Project | Oncor | Tier 3 | 90.2 | 2022 | Completed | 0
22RPG008 | Bowman Switch 345/138 kV Autotransformers Project | Oncor | Tier 3 | 13 | 2022 | Completed | 1 | 2024/24RPG024 Oncor and LCRATSC RPG Overview for ERCOT 10162024.pdf
22RPG009 | Eden to North Brady 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34 | 2022 | Completed | 0
22RPG011 | Fayetteville – Salem Transmission Line Rehabilitation Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 77.8 | 2022 | Completed | 0
22RPG012 | Partial Rebuild 69 kV Deepwater to Clinton Ckt 33 Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 55.91 | 2022 | Completed | 0
22RPG007 | Lenorah Area 345/138 kV Project | Oncor/WETT | Tier 3 | 45.2 | 2022 | Completed (no UR record) | 0
22RPG013 | Wolf Switch - Moss Switch 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.2 | 2022 | Completed | 0
22RPG014 | Red Oak Area Upgrades project | Oncor | Tier 3 | 63 | 2022 | Completed | 5 | 2020/Oncor_IHS_RPG_Presentation_12152020.pdf 2021/ERCOT_EIR_Oncor_Nacogdoches_Lufkin_081721_Status.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Nov_9_RPG.pdf 2022/LCRA_Oncor_WETT_Bearkat_NorthMcCamey_SandLake_Project_06_15_2022.pdf
22RPG015 | Tyler Switch – Forest Grove Switch 138 kV Line Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 62.7 | 2022 | Completed | 4 | 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_Sept_15_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Nov_9_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Oct_15_RPG.pdf
22RPG018 | Marshall Ford – McNeil Transmission Line Storm Hardening Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 34.1 | 2022 | Completed | 0
22RPG017 | McGregor Phillips – Waco West 69 kV Line Conversion Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 38.8 | 2022 | Completed | 0
22RPG020 | Belknap to Fort Griffin 69 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 27.6 | 2022 | Completed | 0
22RPG019 | Partial Rebuild of 69 kV HOC to Dunlavy Ckt 40 Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 31.39 | 2022 | Completed | 0
22RPG016 | Hutto East - Brushy Creek 138kV Line Project | Oncor | Tier 3 | 29.7 | 2022 | Completed | 0
22RPG028 | Ballinger to Santa Anna 69 kV Transmission Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 64.8 | 2022 | Completed | 0
22RPG027 | East Hutto Area 345/138 kV Project | Oncor and LCRA TSC | Tier 3 | 61.6 | 2022 | Completed | 0
22RPG026 | Wimberley Loop Project | PEC | Tier 2 | 61.93 | 2022 | Completed | 3 | 2022/EIR - PEC Wimberley Loop Transmission Scope and Status Update RPG Oct 2022.pdf 2022/EIR - PEC Wimberley Loop Transmission Status Update RPG Nov 2022.pdf 2023/EIR - PEC Wimberley Loop Transmission - Status Update - RPG Jan 2023.pdf
22RPG024 | Wolf-General Tire-Odessa EHV 138 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.77 | 2022 | Completed | 5 | 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2020/ERCOT_EIR_Oncor_Nacogdoches_Lufkin_Scope.pdf 2022/Oncor_Roanoke_Area_Upgrades_EIR_Scope_03_15_2022.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG March 2024_.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf
22RPG025 | Yucca Drive - Courtney Creek 69 kV Line Conversion to 138 kV Project | Oncor | Tier 3 | 65 | 2022 | Completed | 1 | 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf
22RPG022 | Hondo Creek to Pearson 69 kV Transmission Line Rebuild Project | STEC | Tier 2 | 37.5 | 2022 | Completed | 4 | 2022/EIR - STEC Hondo Creek to Pearson 69-kV Transmission Line Rebuild Project Scope_Sept2022.pdf 2022/EIR - STEC Hondo Creek to Pearson 69-kV Transmission Line Rebuild Project Status Update Nov2022.pdf 2022/EIR - STEC Hondo Creek to Pearson 69-kV Transmission Line Rebuild Project Status Update Oct2022.pdf 2024/EIR - STEC - Rio Medina - RPG Jan2024.pdf
22RPG021 | Tawakoni Area Transmission Project | REC | Tier 2 | 42.4 | 2022 | Completed | 3 | 2022/EIR - REC - Tawakoni Area Transmission Project - Status Update - RPG Nov 2022.pdf 2022/EIR - REC - Tawakoni Area Transmission Project - Status Update - RPG Oct 2022.pdf 2022/EIR - REC - Tawakoni Area Transmission Project - Status Update - RPG Sep 2022.pdf
22RPG023 | Hill Country 345/138 kV Autotransformer Replacement Project | CPS | Tier 3 | 6.9 | 2022 | Completed | 4 | 2024/EIR - CPS - Eastside 345_138-kV Switching Station Project - RPG Jun 2024.pdf 2024/EIR-CPS-Eastside-345_138-kV-Switching-Station-Project-RPG-Jul-2024.pdf 2024/EIR_CPS_Omicron_Reliability_Project_Status_Update_RPG_July2024.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Scope - RPG Feb 2023.pdf
22RPG010 | Bearkat – North McCamey – Sand Lake 345-kV Transmission Line Addition Project | LCRA TSC, Oncor, WETT | Tier 1 | 477.6 | 2022 | Completed (no UR record) | 5 | 2022/LCRA_Oncor_WETT_Bearkat_NorthMcCamey_SandLake_Project_06_15_2022.pdf 2024/EIR_ONCOR_LCRA_Hartring_to_Upland_138kV_Line_and_Benedum_Autotransformer_Addition_Project_Scope_RPG_October_2024.pdf 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2024/EIR - Oncor - Dalaware Basin Stages 3 and 4 Project - Status Update - RPG September 2024.pdf 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
22RPG030 | Buchanan CTEC – Pitsburg Transmission Line Overhaul Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 32.9 | 2022 | Completed | 0
22RPG029 | Fairland – Lago Vista Transmission Line Rehabilitation Project | LCRA TSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 26.9 | 2022 | Completed | 0
22RPG035 | Palestine - Crockett 69 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 50.9 | 2022 | Completed | 0
22RPG034 | Temple – Minerva 69 kV Line Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 54.9 | 2022 | Completed | 5 | 2024/EIR - Oncor - Temple Area Project - Scope - RPG February 2024.pdf 2024/Oncor_Temple_Area_Project_RPG_02122024.pdf 2024/EIR - Oncor - Temple Area Project - Status Update - RPG March 2024_.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG June 2024.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG May 2024.pdf
22RPG037 | West Columbia to Burke 138 kV ckt 02 Rebuild Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 43.2 | 2022 | Completed | 0
22RPG036 | Taylor Switch – Holland 69 kV Line Section Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 60.8 | 2022 | Completed | 0
22RPG033 | Mountain Top-Blanco-Devils Hill Line Rebuild and Voltage Upgrade Project | PEC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 37 | 2022 | Completed | 3 | 2022/EIR - PEC Wimberley Loop Transmission Status Update RPG Nov 2022.pdf 2023/EIR - PEC Wimberley Loop Transmission - Status Update - RPG Jan 2023.pdf 2022/EIR - PEC Wimberley Loop Transmission Scope and Status Update RPG Oct 2022.pdf
22RPG032 | Tesoro 345/138 kV Switch Project | Oncor | Tier 3 | 50.2 | 2022 | Completed | 0
22RPG041 | Sienna to Dewalt to Missouri City 138 kV ckt 02 Line Rebuild Project | CNP | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 56.03 | 2022 | Completed | 0
22RPG040 | Dupont to Joslin 138 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 46.4 | 2022 | Completed | 2 | 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_Aug_17_RPG.pdf 2021/AEPSC_-_Port_Lavaca_Area_Improvement_Project_Status_Update_-_June_15_RPG.pdf
22RPG039 | Eagle Mountain 345/138 kV Switch Rebuild Project | Oncor | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 57 | 2022 | Completed | 1 | 2022/Oncor_Roanoke_Area_Upgrades_EIR_Scope_03_15_2022.pdf
22RPG038 | Clute Substation Addition Project | CNP | Tier 3 | 46.2 | 2022 | Completed | 0
22RPG031 | Lakeway - Marble Falls Transmission Line Strom Hardening Project | LCRA PEC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 94.2 | 2022 | Completed (no UR record) | 0
22RPG043 | Haskell to Munday 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 31 | 2022 | Completed | 0
22RPG048 | San Antonio South Reliability Project | CPS | Tier 1 | 329.1 | 2022 | Completed | 5 | 2023/EIR - CPS - San Antonio South Reliability Project - Scope - RPG Feb 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG June 2023.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG May 2023.pdf 2023/San Antonio South Reliability Project.pdf 2023/EIR - CPS - San Antonio South Reliability Project - Status Update - RPG Apr 2023.pdf
22RPG047 | Peck to Driver 138 kV Line Project | Oncor | Tier 2 | 36.2 | 2022 | Completed | 4 | 2023/EIR - Oncor Peck to Driver 138 kV Line Project_Status_March2023.pdf 2023/EIR - Oncor Peck to Driver 138 kV Line project Scope_Jan2023.pdf 2023/EIR---Oncor-Peck-to-Driver-138-kV-Line-Project-Status-Update-April2023.pdf 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf
22RPG046 | Peppervine to Temple 69 kV Line Conversion Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 36 | 2022 | Completed | 5 | 2024/EIR - Oncor - Temple Area Project - Scope - RPG February 2024.pdf 2024/EIR - Oncor - Temple Area Project - Status Update - RPG March 2024_.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG June 2024.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG May 2024.pdf 2024/EIR-Oncor-Temple-Area-Projct-Status-Update-RPG-July-2024.pdf
22RPG045 | Yucca to Moss 138 kV Line Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 60.7 | 2022 | Completed | 1 | 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Oct_15_RPG.pdf
22RPG044 | Escondido to Hamilton Road 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 73.5 | 2022 | Completed | 1 | others/HamiltonRoad-Maxwell_Factsheet_V9.pdf
22RPG042 | Carver to Maxwell 138 kV Line Rebuild Project | AEPSC | Tier 3 to Tier 4 Pursuant to the Protocol Section 3.11.4.3.1 (d) | 69.1 | 2022 | Completed | 0
23RPG001 | Bessel to Falfurrias 138 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 84.76 | 2023 | Completed | 0
23RPG002 | Hamlin to Roby 69 kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 33 | 2023 | Completed | 0
23RPG003 | Eagle Ford Large Load Interconnection Project | GVEC | Reclassified from Tier 1 to Tier 3 per Protocol | 47 | 2023 | Completed | 5 | 2025/EIR_Oncor_Southern_DFW_Load_Interconnection_Project_StatusUpdate_RPG_Aug_2025.pdf 2025/Oncor_Southern-DFW-Load-Interconnection_Project_RPG_04292025.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_April2021RPG.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf 2021/Permian_Basin_Load_Interconnection_Study_-_Final_Update_-_Oct2021RPG.pdf
23RPG004 | Lockhart to Luling 69-kV Transmission Line Overhaul Project | LCRA TSC | Tier 2 | 45.7 | 2023 | Completed | 0
23RPG005 | La Palma to Stewart Road Rebuild and Conversion to 138-kV Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 71.5 | 2023 | Completed | 0
23RPG006 | North Lake 138 kV Switch Rebuild | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 34.11 | 2023 | Completed | 3 | 2022/LCRA_Oncor_WETT_Bearkat_NorthMcCamey_SandLake_Project_06_15_2022.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Scope-RPG-Sept-2025.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Status-Update-RPG-Nov-2025.pdf
23RPG007 | Asherton to Uvalde 138-kV Conversion Project | AEPSC | Tier 3 | 56 | 2023 | Completed | 0
23RPG008 | Fort Stockton Plant to Lynx 138-kV Line Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.9 | 2023 | Completed | 2 | 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf 2024/Permian Basin Reliability Plan Study - Status Update - June 2024 RPG.pdf
23RPG009 | Spraberry to Polecat 138-kV Line Rebuild Project | Oncor | Tier 3 | 56.9 | 2023 | Completed | 0
23RPG010 | Big Spring West to Stanton East 138-kV Line Rebuild Project | Oncor | Tier 3 | 52 | 2023 | Completed | 5 | 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf 2025/EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_SCOPE_September2025_RPG.pdf 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG April 2024.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG May 2024.pdf
23RPG014 | Lamesa to Jim Payne POI to Paul Davis Tap 138-kV Line Rebuild Project | Oncor | Tier 3 | 36.8 | 2023 | Completed | 3 | 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf 2025/EIR - Oncor and WETT - Combined Dalaware Basin Stage 5 Project and Alterntive - Status Update - RPG January 2025.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_April_2025.pdf
23RPG013 | Silverleaf and Cowpen 345/138-kV Stations Project | TNMP | Tier 1 | 273.1 | 2023 | Completed | 5 | 2023/EIR - TNMP - Silverleaf and Cowpen 345138-kV Stations Project - Scope - RPG July2023.pdf 2023/EIR - TNMP - Silverleaf and Cowpen 345138-kV Stations Project - Status Update - RPG Nov 2023.pdf 2023/EIR - TNMP - Silverleaf and Cowpen 345138-kV Stations Project - Status Update - RPG Oct 2023.pdf 2023/EIR - TNMP - Silverleaf and Cowpen 345138-kV Stations Project - Status Update - RPG Sep 2023.pdf 2023/TNMP - Silverleaf and Cowpen 345138-kV Stations Project.pdf
23RPG012 | Stone Lake Area Upgrades Project | CNP | Tier 3 | 74.38 | 2023 | Completed | 3 | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_June2021RPG.pdf
23RPG011 | Morgan Creek to McDonald Road 138-kV Line Project | Oncor | Tier 3 | 40.2 | 2023 | Completed | 5 | 2023/EIR - Oncor Peck to Driver 138 kV Line Project_Status_March2023.pdf 2023/EIR - Oncor Peck to Driver 138 kV Line project Scope_Jan2023.pdf 2023/EIR---Oncor-Peck-to-Driver-138-kV-Line-Project-Status-Update-April2023.pdf 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG April 2024.pdf
23RPG016 | Oncor Tributary Switch – Vincent Rebuild Project | Oncor | Tier 3 | 29.3 | 2023 | Completed | 0
23RPG015 | Cuero Substation Upgrade Project | LCRA TSC | Reclassified from Tier 3 to Tier 4 per Protocol | 25.9 | 2023 | Completed | 0
23RPG017 | Watermill 345/138-kV Switch Project | Oncor | Tier 3 | 74.9 | 2023 | Completed | 4 | 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Scope - RPG Sept2024.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Nov2024.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Oct2024.pdf 2024/eir-oncor-wilmer-345138-kv-switch-project-status-update-rpg-dec2024.pdf
23RPG023 | Pecos County Transmission Improvement Project | TNMP | Tier 1 | 114.8 | 2023 | Completed | 4 | 2023/EIR - TNMP - Pecos County Transmission Improvement Project - Status Update - RPG Dec 2023.pdf 2023/EIR - TNMP - Pecos County Transmission Improvement Project - Status Update - RPG Nov 2023.pdf 2023/TNMP - Pecos County Transmission Improvement Project - RPG.pdf 2024/EIR - TNMP - Pecos County Transmission Improvement Project - Status Update - RPG Jan 2024.pdf
23RPG022 | McLennan County Transmission Project | Oncor | Tier 3 | 42.31 | 2023 | Completed | 0
23RPG021 | West Columbia to Big Creek ckt 89 Reconductor Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 64.17 | 2023 | Completed | 5 | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf 2024/eir-cnp-southwest-houston-345-kv-reliability-project_scope_december_rpg.pdf 2025/eir-cnp-southwest-houston-345-kv-reliability-project_scope_december_rpg (1).pdf 2020/Frio_County_Project_EIR_05_19_2020_RPG.PDF
23RPG020 | Hackberry Switch to DFW D East 2 138-kV Double-Circuit Line Section Project | Oncor | Tier 3 | 80 | 2023 | Completed | 4 | 2025/EIR_Oncor_Southern_DFW_Load_Interconnection_Project_StatusUpdate_RPG_Aug_2025.pdf 2025/EIR_Scope_Oncor_Southern_DFW_Load_Interconnection_Project_-_RPG_April_2025.pdf 2025/EIR_Status_Update_Oncor_Southern_DFW_Load_Interconnection_Project_RPG_July_2025.pdf 2025/Oncor_Southern-DFW-Load-Interconnection_Project_RPG_04292025.pdf
23RPG018 | Arlington Reliability Enhancement Project | Oncor | Tier 2 | 73 | 2023 | Completed | 3 | 2023/EIR - Oncor - Arlington Reliability Enhancement Project - Scope and Status Update.pdf 2023/EIR - Oncor - Arlington Reliability Enhancement Project - Status Update - Dec 2023.pdf 2023/Oncor_Arlington_Reliability_Enhancement_Project.pdf
23RPG019 | Stanton Loop South Dynamic Reactive Power Project | Oncor | Tier 3 | 96.9 | 2023 | Completed | 0
23RPG024 | Big Foot to Dilley Switch 138-kV Conversion Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 53.1 | 2023 | Completed | 4 | 2024/EIR - STEC - Rio Medina - RPG Jan2024.pdf 2020/7X_Frio_County_Project_Study_Scope_01_21_2020_RPG.PDF 2020/7X_Frio_County_Project_Study_Update_02_18_2020_RPG.PDF 2020/Frio_County_Project_EIR_05_19_2020_RPG.PDF
23RPG029 | West Texas Synchronous Condenser Project | Oncor | Tier 1 | 280 | 2023 | Completed | 5 | others/7.1 West Texas Synchronous Condenser RPG Project - ref page.pdf 2025/EIR-Oncor-Connell-to-Rockhound-RPG-Project_StatusUpdate_July_RPG_Final.pdf 2024/WETT_DB5_Alternative_Overview_RPG_9252024_.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Status-Update-RPG-Nov-2025.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Status-Update-RPG-Oct-2025.pdf
23RPG028 | Rio Medina Project | STEC | Tier 2 | 71.7 | 2023 | Completed | 4 | 2023/EIR - STEC - Rio Medina Project - Scope - RPG Nov 2023.pdf 2023/STEC_Rio Medina Project_.pdf 2024/EIR - STEC - Rio Medina - RPG Feb2024.pdf 2024/EIR - STEC - Rio Medina - RPG Jan2024.pdf
23RPG027 | Bakersfield Dynamic Reactive Substation Upgrade Project | LCRA TSC | Tier 1 | 145 | 2023 | Under Review | 3 | 2023/20231018_LCRATSC_Bakersfield_Dynamic_Reactive_Substation_Upgrade.pdf others/7.1 West Texas Synchronous Condenser RPG Project - ref page.pdf 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
23RPG026 | Synchronous Condensers Project | WETT | Tier 1 | 144.5 | 2023 | Completed | 1 | others/7.1 West Texas Synchronous Condenser RPG Project - ref page.pdf
23RPG025 | Britmoore to Bellaire Ckt 24 Upgrade Project | CNP | Tier 3 | 90.1 | 2023 | Completed | 2 | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
23RPG033 | Watermill to Seagoville 138 kV Line Project | Oncor | Tier 3 | 33 | 2023 | Completed | 5 | 2024/EIR - Oncor - Forney 345_138-kV Switch Rebuild Project_November_RPG.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Nov2024.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Oct2024.pdf 2024/Oncor_Forney345-138 kV Switch_Project_RPG_09252024.pdf 2024/eir-oncor-forney-345_138-kv-switch-rebuild-project_december_rpg.pdf
23RPG032 | San Antonio South Reliability II Project (San Miguel to Marion 345-KV Project) | BEC | Tier 1 | 435 | 2023 | Completed | 5 | 2024/EIR - San Antonio South Reliability II Project Status Update_April 2024.pdf 2023/EIR - BEC - San Miguel to Marion 345 kV Project Scope.pdf 2024/EIR - BEC - San Miguel to Marion 345 kV Project Status Update_Feb 2024.pdf 2024/EIR - BEC - San Miguel to Marion 345 kV Project Status Update_Jan 2024.pdf 2024/EIR - San Miguel to Marion 345 kV Project Status Update_March 2024.pdf
23RPG031 | 345-kV Jeanetta Autotransformer Upgrades Project | CNP | Tier 3 | 47.08 | 2023 | Completed | 2 | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
23RPG030 | Walleye Creek 345/138-kV Switch Project | Oncor | Tier 3 | 74 | 2023 | Completed | 1 | 2025/EIR_Scope_Oncor_Skyview_345138kV_Switch_Project_-_RPG_Oct_2025_Final.pdf
23RPG034 | West Texas 345-kV Infrastructure Rebuild Project | Oncor | Tier 1 | 1120 | 2023 | Completed | 5 | 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG April 2024.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG March 2024_.pdf 2024/EIR_Oncor_West Texas 345-kV Infrastructure Rebuild Project - Status Update RPG May 2024.pdf 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf 2024/West Texas 345 kV Infrastructure RPG Overview for ERCOT 20240112 (1).pdf
24RPG004 | Omicron Reliability Project | CPS Energy | Tier 2 | 42.5 | 2024 | Under Review | 5 | 2024/EIR_CPS_Omicron_Reliability_Project_Scope_RPG_March2024.pdf 2024/EIR_CPS_Omicron_Reliability_Project_Status_Update_RPG_July2024.pdf 2024/EIR_CPS_Omicron_Reliability_Project_Status_Update_RPG_June2024.pdf 2024/EIR_CPS_Omicron_Reliability_Project_Status_Update_RPG_May2024_update.pdf 2024/Omicron Reliability Project.pdf
24RPG003 | Eastside 345/138-kV Switching Station Project | CPS Energy | Tier 1 | 158 | 2024 | Under Review | 5 | 2024/CPSE Eastside Switching Station (1).pdf 2024/CPSE Eastside Switching Station.pdf 2024/EIR - CPS - Eastside 345_138-kV Switching Station Project - RPG Jun 2024.pdf 2024/EIR - CPS - Eastside 345_138-kV Switching Station Project_May_RPG.pdf 2024/EIR - CPS - Eastside 345_138-kV Switching Station Project_SCOPE_March_RPG_.pdf
24RPG002 | Rockhound 345/138-kV Switch and Grey Well Draw to Buffalo 2nd 138-kV Circuit Project | Oncor | Tier 3 | 97 | 2024 | Completed | 5 | 2024/EIR_ONCOR_Tredway_Scope_OCT.pdf 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf 2025/EIR_ONCOR_Tredway_Project_JAN2025_2.pdf 2023/EIR - Oncor Peck to Driver 138 kV Line project Scope_Jan2023.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_Sept_15_RPG.pdf
24RPG001 | Temple Area Project | Oncor | Tier 1 | 272.6 | 2024 | Completed | 5 | 2024/EIR - Oncor - Temple Area Project - Scope - RPG February 2024.pdf 2024/EIR - Oncor - Temple Area Project - Status Update - RPG March 2024_.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG May 2024.pdf 2024/Oncor_Temple_Area_Project_RPG_02122024.pdf 2024/EIR Oncor - Temple Area Projct - Status Update - RPG June 2024.pdf
24RPG005 | Montfort Switch to Shankle Switch 138-kV Line Project | Oncor | Tier 3 | 33.8 | 2024 | Completed | 0
24RPG006 | Prairieland 345/138-kV Switch and Prairieland Switch to Quartz Sand Switch/Hog Mountain Pod 138-kV Line Project | Oncor | Tier 3 | 56 | 2024 | Completed | 1 | 2024/Oncor Scope_West Texas 345-kV Infrastructure Rebuild Project_02122024.pdf
24RPG011 | Gonzales STATCOM Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 34.5 | 2024 | Completed | 2 | 2024/EIR - Brownsville Area Improvement_Scope_June 2024.pdf 2024/EIR - Brownsville Area Improvement_Status Update_July 2024.pdf
24RPG010 | Delaware Basin Stages 3 and 4 Project | Oncor | Tier 1 | 202.2 | 2024 | Completed | 5 | 2024/Delaware Basin Stage 3 4 RPG Overview for ERCOT 20240514_.pdf 2024/EIR - Oncor - Dalaware Basin Stages 3 and 4 Project - Scope - RPG May 2024.pdf 2024/EIR - Oncor - Dalaware Basin Stages 3 and 4 Project - Status Update - RPG October 2024.pdf 2024/EIR - Oncor - Dalaware Basin Stages 3 and 4 Project - Status Update - RPG September 2024.pdf 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf
24RPG009 | Sonora to Uvalde to Campwood to Bandera Area Transmission Project | AEPSC, LCRA TSC and BEC | Reclassified from Tier 3 to Tier 4 per Protocol | 76 | 2024 | Completed | 0
24RPG008 | Brownsville Area Improvements Transmission Project | AEPSC | Tier 1 | 423.8 | 2024 | Completed | 4 | 2024/eir-aepsc-brownsville-area-improvement_status-update_sept-2024.pdf 2024/EIR - Brownsville Area Improvement_Scope_June 2024.pdf 2024/EIR - Brownsville Area Improvement_Status Update_July 2024.pdf 2024/eir-brownsville-area-improvement_status-update_august-2024.pdf
24RPG007 | Canton Area Loop Project | REC | Tier 2 | 26.03 | 2024 | Completed | 3 | 2024/EIR REC - Rayburn Electric Cooperative Canton Loop - Status Update RPG August 2024.pdf 2024/RPG Scope Presentation Rayburn Electric Cooperative Canton Loop v2.pdf 2024/EIR REC - Rayburn Electric Cooperative Canton Loop - Status Update RPG June 2024.pdf
24RPG013 | FPP Yard 2 to Lytton Springs Transmission Line Overhaul Project | LCRA TSC and AEN | Reclassified from Tier 3 to Tier 4 per Protocol | 60 | 2024 | Completed | 3 | 2024/EIR - REC - Rand Area Loop Project - RPG Aug 2024.pdf 2024/EIR - REC - Rand Area Loop Project - RPG Sep 2024_ (1).pdf 2024/EIR - REC - Rand Area Loop Project - RPG Sep 2024_.pdf
24RPG012 | Clute to Velasco ckt 26 Upgrades Project | CNP | Tier 3 | 68.23 | 2024 | Completed | 2 | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
24RPG016 | Rand Area Loop Project | REC | Tier 2 | 32.2 | 2024 | Completed | 5 | 2024/EIR - REC - Rand Area Loop Project - RPG Aug 2024.pdf 2024/EIR - REC - Rand Area Loop Project - RPG Sep 2024_ (1).pdf 2024/EIR - REC - Rand Area Loop Project - RPG Sep 2024_.pdf 2024/EIR - REC - Rand Area Loop Project - Scope - RPG Jun 2024.pdf 2024/EIR REC - Rayburn Electric Cooperative Canton Loop - Status Update RPG August 2024.pdf
24RPG015 | Delaware Basin State 5 Project | Oncor | Tier 1 | 855.3 | 2024 | Completed | 5 | 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2025/EIR - Oncor and WETT - Combined Dalaware Basin Stage 5 Project and Alterntive - Status Update - RPG January 2025.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_April_2025.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_Mar_2025.pdf 2024/Delaware Basin Stage 3 4 RPG Overview for ERCOT 20240514_.pdf
24RPG014 | Sim Gideon to Cedar Hill Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 77.9 | 2024 | Completed | 0
24RPG020 | Connell 345/138-kV Switch and Connell to Rockhound 345-kV Double-Circuit Line Project | Oncor | Tier 1 | 110.62 | 2024 | Completed | 5 | 2024/EIR - Oncor - Connell to Rockhound RPG Project_SCOPE_September_RPG.pdf 2025/EIR-Oncor-Connell-to-Rockhound-RPG-Project_StatusUpdate_July_RPG_Final.pdf 2025/EIR-Oncor-Connell-to-Rockhound-RPG-Project_StatusUpdate_November_RPG.pdf 2025/EIR-Oncor-Connell-to-Rockhound-RPG-Project_StatusUpdate_October_RPG_Final.pdf 2025/EIR-Oncor-Connell-to-Rockhound-RPG-Project_StatusUpdate_September_RPG_Final.pdf
24RPG019 | Vineyard Switch to Cypress Waters 138-kV Circuit Addition Project | Oncor | Tier 3 | 93.04 | 2024 | Completed | 0
24RPG018 | Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | 2024 | Completed | 0
24RPG017 | Venus Switch to Sam Switch 345-kV Line Project | Oncor | Tier 1 | 118.9 | 2024 | Completed | 5 | others/7-2-oncor-venus-switch-to-sam-switch-345-kv-line-project.pdf 2024/EIR_ONCOR_Venus_Switch_to_Sam_Switch_Project_NOV.pdf 2024/EIR_ONCOR_Venus_Switch_to_Sam_Switch_Project_OCT_Update.pdf 2024/EIR_ONCOR_Venus_Switch_to_Sam_Switch_Project_Scope.pdf 2024/EIR_ONCOR_Venus_Switch_to_Sam_Switch_Project_Update.pdf
24RPG022 | Wilmer 345/138-kV Switch Project | Oncor | Tier 1 | 158.2 | 2024 | Completed | 5 | 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Scope - RPG Sept2024.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Nov2024.pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Status Update - RPG Oct2024.pdf 2024/eir-oncor-wilmer-345138-kv-switch-project-status-update-rpg-dec2024.pdf 2025/eir-oncor-wilmer-345138-kv-switch-project-status-update-rpg-dec2024 (1).pdf
24RPG021 | Forney 345/138-kV Switch Rebuild Project | Oncor | Tier 1 | 100.4 | 2024 | Completed | 5 | 2024/EIR - Oncor - Forney 345_138-kV Switch Rebuild Project_November_RPG.pdf 2024/EIR - Oncor - Forney 345_138-kV Switch Rebuild Project_SCOPE_September_RPG.pdf 2024/eir-oncor-forney-345_138-kv-switch-rebuild-project_december_rpg.pdf 2025/eir-oncor-forney-345_138-kv-switch-rebuild-project_december_rpg (1).pdf 2024/EIR - Oncor - Wilmer 345138-kV Switch Project - Scope - RPG Sept2024.pdf
24RPG027 | Long Draw Second 345/138-kV Autotransformer Project | WETT | Tier 3 | 28 | 2024 | Completed | 5 | 2024/24RPG024 Oncor and LCRATSC RPG Overview for ERCOT 10162024.pdf 2025/EIR - Oncor and WETT - Combined Dalaware Basin Stage 5 Project and Alterntive - Status Update - RPG January 2025.pdf 2024/WETT_DB5_Alternative_Overview_RPG_9252024_.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_April_2025.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_Mar_2025.pdf
24RPG026 | Jordan/Mont Belvieu Area Improvement Project | CNP | Tier 3 | 76.89 | 2024 | Completed | 2 | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
24RPG025 | Gunter 345/138-kV Switch Project | Oncor | Tier 3 | 51.2 | 2024 | Completed | 0
24RPG024 | Hartring to Upland 138-kV Line and Benedum Autotransformer Addition Project | Oncor and LCRA TSC | Tier 2 | 97.7 | 2024 | Completed | 4 | 2024/EIR_ONCOR_LCRA_Hartring_to_Upland_138kV_Line_and_Benedum_Autotransformer_Addition_Project_Scope_RPG_October_2024.pdf 2025/EIR_StatusUpdat_Hartring_to_Upland_and_BenedumAuto_Project_RPG_Mar_2025.pdf 2025/EIR_StatusUpdate_Hartring_to_Upland_and_BenedumAuto_Project_RPG_April_2025-.pdf 2024/24RPG024 Oncor and LCRATSC RPG Overview for ERCOT 10162024.pdf
24RPG023 | WETT Delaware Basin Stage 5 Project Alternative | WETT | Tier 1 | 305.5 | 2024 | Under Review | 5 | 2024/WETT_DB5_Alternative_Overview_RPG_9252024_.pdf 2025/EIR - Oncor and WETT - Combined Dalaware Basin Stage 5 Project and Alterntive - Status Update - RPG January 2025.pdf 2024/Delaware Basin Stages 5 RPG Overview for ERCOT 09252024.pdf 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2025/EIR_StatusUpdate_Combined_Dalaware_Basin_Stage_5_Project_and_Alterntive_RPG_April_2025.pdf
24RPG030 | Partial Rebuild of 138-kV Ckt.05A Sienna Tap to Missouri City Tap Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 28.56 | 2024 | Completed | 5 | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf 2024/CNP_Baytown_Area_Load_Addition_project_20241112.pdf 2024/EIR - CNP - Baytown Area Load Addition RPG Project_SCOPE_November_RPG_Final.pdf 2025/EIR -CNP - Baytown_Area_Load_Addition_Project_February_RPG.pdf
24RPG029 | Tredway 138-kV Switch and Expanse to Tredway 138-kV 2nd Circuit Project | Oncor | Tier 1 | 119.03 | 2024 | Completed | 4 | 2025/EIR_ONCOR_Tredway_Project_JAN2025_2.pdf 2025/EIR_ONCOR_Tredway_Project_Update_MARCH_v2.pdf 2024/Oncor Tredway 138 kV Switch and Expanse-Tredway 138 kV 2nd Circuit Project RPG Overview for ERCOT 10162024.pdf 2024/EIR_ONCOR_Tredway_Scope_OCT.pdf
24RPG028 | Baytown Area Load Addition Project | CNP | Tier 1 | 545.3 | 2024 | Completed | 5 | 2024/CNP_Baytown_Area_Load_Addition_project_20241112.pdf 2024/EIR - CNP - Baytown Area Load Addition RPG Project_SCOPE_November_RPG_Final.pdf 2025/EIR -CNP - Baytown_Area_Load_Addition_Project_February_RPG.pdf 2025/EIR-CNP-Baytown_Area_Load_Addition_Project_April_RPG.pdf 2025/EIR-CNP-Baytown_Area_Load_Addition_Project_July_RPG_Final.pdf
24RPG032 | Southwest Houston 345-kV Reliability Project | CNP | Tier 1 (Not Recommend or Endorsed) | 569.32 | 2024 | Completed | 5 | 2024/24rpg032-_cnp_southwest_houston_345kv_reliability_project_ercot_rpg_presentation.pdf 2025/24rpg032-_cnp_southwest_houston_345kv_reliability_project_ercot_rpg_presentation (1).pdf 2024/eir-cnp-southwest-houston-345-kv-reliability-project_scope_december_rpg.pdf 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
24RPG031 | Central Texas 345-kV Transmission Project | LST | Tier 1 (Withdrawn) | 342 | 2024 | Completed | 5 | 2026/10_EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026_Final.pdf 2026/8.-EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Projects-Status-Update-RPG-Apr-2026_Final.pdf 2026/9_EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026.pdf 2026/EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Mar-2026.pdf 2026/EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-Update-RPG-Mar-2026.pdf
24RPG035 | Aransas Pass to Rincon 69-kV Line Rebuild Project | AEPSC | Tier 2 | 34 | 2024 | Completed | 3 | 2025/EIR_AEPSC_Aransas_Pass_to_Rincon_Project_Final_Update_RPG_April_2025.pdf 2025/EIR_AEPSC_Aransas_Pass_to_Rincon_Project_Scope_RPG_January_2025.pdf 2025/EIR_AEPSC_Aransas_Pass_to_Rincon_Project_Update_RPG_March_2025.pdf
24RPG034 | Redwood to San Marcos Transmission Line Upgrade Project | LCRA TSC | Tier 3 | 46.4 | 2024 | Completed | 1 | 2024/EIR - San Antonio South Reliability II Project Status Update_April 2024.pdf
24RPG033 | MINING 69-kV Substation Conversion Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 34.12 | 2024 | Completed | 0
24RPG036 | South Padre Island Rebuild Transmission Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 44.5 | 2024 | Completed | 0
24RPG039 | Galveston Region Project | TNMP | Tier 2 | 95.9 | 2024 | Completed | 4 | 2025/EIR - TNMP - Galveston Region Project - Scope - RPG Feb 2025.pdf 2025/EIR-TNMP-Galveston-Region-Project-Status-Update-RPG-Dec-2025.pdf 2025/EIR-TNMP-Galveston-Region-Project-Status-Update-RPG-Nov-2025.pdf 2025/TNMP Galveston Region Transmission Improvement Project - EIR.pdf
24RPG038 | Bergheim Substation Upgrade Project | LCRA TSC and PEC | Tier 3 | 66.35 | 2024 | Completed | 0
24RPG040 | Roscoe Area Upgrades Project | Oncor | Tier 2 | 84.3 | 2024 | Completed | 5 | 2025/EIR - Oncor -Roscoe Area Upgrades Project_SCOPE_February_RPG.pdf 2025/EIR-Oncor-Roscoe-Area-Upgrades-Project-StatusUpdate-April_2025_RPG.pdf 2025/EIR-Oncor-Roscoe-Area-Upgrades-Project-StatusUpdate-May_2025_RPG.pdf 2025/8. Roscoe Area Upgrades RPG Overview for ERCOT.pdf 2022/Roanoke_Area_Upgrades_Overview_RPG.pdf
24RPG037 | Partial Rebuild of 138-kV Ckt.63 West Galveston to Moody Project | CNP | Reclassified from Tier 3 to Tier 4 per Protocol | 26.2 | 2024 | Completed | 0
24RPG041 | Buck Canyon and Binturong 345-kV Synchronous Condenser Stations Project | WETT | Tier 3 | 98.61 | 2025 | Completed | 3 | others/7.1 West Texas Synchronous Condenser RPG Project - ref page.pdf 2024/WETT_DB5_Alternative_Overview_RPG_9252024_.pdf 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
25RPG001 | Texas A&M University System RELLIS Campus Reliability Project | BTU | Tier 1 | 281.2 | 2025 | Completed | 1 | 2025/EIR-BTU-Texas-A-M-University-System-RELLIS-Campus-Reliability-Project-Scope-RPG-Mar-2025.pdf
25RPG002 | East Munday 138-kV Station Rebuild Project | AEPSC | Reclassified from Tier 3 to Tier 4 per Protocol | 28.3 | 2025 | Completed | 0
25RPG006 | Resubmission for Salado Switch to Hutto Switch 138-kV Line Project | Oncor | Tier 3 | 87.6 | 2025 | Completed | 0
25RPG004 | Southern DFW Load Interconnection and General Grid Strengthening Project | Oncor | Tier 1 | 1219 | 2025 | Under Review | 5 | 2025/EIR_Oncor_Southern_DFW_Load_Interconnection_Project_StatusUpdate_RPG_Aug_2025.pdf 2025/EIR_Scope_Oncor_Southern_DFW_Load_Interconnection_Project_-_RPG_April_2025.pdf 2025/EIR_Status_Update_Oncor_Southern_DFW_Load_Interconnection_Project_RPG_July_2025.pdf 2025/Oncor_Southern-DFW-Load-Interconnection_Project_RPG_04292025.pdf 2026/EIR_Oncor_Southern_DFW_Load_Interconnection_Project_StatusUpdate_RPG_Jan_2026_Final.pdf
25RPG005 | Pitchfork 345-kV Substation Addition Project | WETT | Tier 3 | 57.57 | 2025 | Completed | 0
25RPG003 | Hamilton County Conversion Project | BEC | Tier 2 | 84 | 2025 | Completed | 4 | 2025/EIR_BEC_Hamilton_County_Conversion_Project_SCOPE_APRIL.pdf 2025/EIR_BEC_Hamilton_County_Project_Status_Update_August_RPG_Meeting.pdf 2025/EIR_BEC_Hamilton_County_Project_Status_Update_July_RPG_Meeting.pdf 2025/EIR_BEC_Hamilton_County_Project_Status_Update_June_RPG_Meeting.pdf
25RPG010 | 138-kV Flewellen to Fort Bend Upgrades Project | CNP | Tier 3 | 72.86 | 2025 | Completed | 5 | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf 2024/24rpg032-_cnp_southwest_houston_345kv_reliability_project_ercot_rpg_presentation.pdf 2024/eir-cnp-southwest-houston-345-kv-reliability-project_scope_december_rpg.pdf 2025/24rpg032-_cnp_southwest_houston_345kv_reliability_project_ercot_rpg_presentation (1).pdf
25RPG007 | Salt Flat Road to Barr Ranch to Reiter 138-kV Second Circuit Project | Oncor | Tier 3 | 63.88 | 2025 | Completed | 5 | 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_Sept_15_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Oct_15_RPG.pdf 2021/Oncor_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_Nov_9_RPG.pdf 2021/Bakersfield_to_Big_Hill_345-kV_Second_Circuit_Addition_April_RPG_2021.pdf
25RPG008 | Wolf Switch to Reiter Switch 138-kV Line Project | Oncor | Tier 3 | 52.65 | 2025 | Completed | 0
25RPG009 | Muscovy and Voss Lake 345/138-kV Project | Oncor and LCRA TSC | Tier 1 | 381.83 | 2025 | Under Review | 5 | 2026/5_EIR-Oncor-and-LCRA-TSC-Muscovy-Voss-_StatusUpdate_April2026_RPG.pdf 2025/Oncor_Muscovy_Voss-Lake_RPG_05202025.pdf 2025/EIR-Oncor-and-LCRA-TSC-Muscovy-Voss-_SCOPE_May2025_RPG.pdf 2025/EIR-Oncor-and-LCRA-TSC-Muscovy-Voss-_StatusUpdate_July2025_RPG.pdf 2025/EIR-Oncor-and-LCRA-TSC-Muscovy-Voss-_StatusUpdate_Jun2025_RPG.pdf
25RPG014 | Cedar Bayou Autotransformer Upgrades Project | CNP | Tier 3 | 26.3 | 2025 | Completed | 5 | 2024/CNP_Baytown_Area_Load_Addition_project_20241112.pdf 2025/EIR -CNP - Baytown_Area_Load_Addition_Project_February_RPG.pdf 2025/EIR_CNP_PHRobinson_to_WAParish_345kV_Hardening_Project_StatusUpdate_RPG_Nov_2025.pdf 2024/EIR - CNP - Baytown Area Load Addition RPG Project_SCOPE_November_RPG_Final.pdf 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf
25RPG013 | Reactive Power Planning Project | CPS Energy | Tier 1 | 116.5 | 2025 | Under Review | 5 | 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Scope_RPG_July_2025.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_August_2025.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_December_2025_FINAL.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_October_2025_FINAL.pdf 2026/3.-EIR-CPS-Energy-Helotes-Reactive-Power-Planning-Project-Recommendation-RPG_April_2026_FINAL.pdf
25RPG012 | Ammonia Plant Load Project | STEC | Tier 2 | 65.47 | 2025 | Under Review | 5 | others/8-25RPG012-STEC-Ammonia-Plant-Load-Project-Option-1.pdf 2025/STEC_FirstAmmonia_Final_25RPG012 (1).pptx 2025/STEC_FirstAmmonia_Final_25RPG012.pptx 2025/STEC_NuecesGeenAmmonia_Final_25RPG016.pptx 2026/4.-EIR-STEC-Nueces-GreenvAmmonia-Project-Status-Update-RPG-March-2026-FINAL.pdf
25RPG011 | 138-kV West Columbia to Needville Upgrades Project | CNP | Tier 3 | 95.11 | 2025 | Completed | 2 | 2025/EIR - CNP - Southwest Houston 345-kV Reliability Project_February_RPG.pdf 2025/EIR-CNP-Southwest-Houston-345-kV-Reliability-Project_March_RPG.pdf
25RPG015 | Buchanan to Burnet Transmission Line Overhaul Project | LCRA TSC | Tier 3 | 36.2 | 2025 | Completed | 0
25RPG016 | Nueces Green Ammonia Load Interconnection Project | STEC | Tier 2 | 74 | 2025 | Under Review | 5 | 2026/4.-EIR-STEC-Nueces-GreenvAmmonia-Project-Status-Update-RPG-March-2026-FINAL.pdf 2026/4_EIR_STEC_Nueces_Green_Ammonia_Project_Status_Update_RPG_February_2026_FINAL.pdf 2025/STEC_NuecesGeenAmmonia_Final_25RPG016.pptx others/8-25RPG012-STEC-Ammonia-Plant-Load-Project-Option-1.pdf 2021/Permian_Basin_Load_Interconnection_Status_Update__-_April2021RPG.pdf
25RPG021 | Victoria to Warburton 138-kV Line Rebuild Project | AEPSC | Tier 3 | 35.5 | 2025 | Completed | 0
25RPG018 | Childress Area Transmission Improvement Project | AEPSC | Tier 2 | 77.3 | 2025 | Completed | 1 | others/EIR-AEP-Childress-Area-Transmission-Improvement-Project-Scope-RPG-July-2025.pdf
25RPG019 | Lamesa Switch to Willow Valley Switch 138-kV Line Rebuild Project | Oncor | Tier 3 | 74.5 | 2025 | Completed | 2 | 2024/EIR - Oncor - Dalaware Basin Stage 5 Project - Scope - RPG September 2024.pdf 2025/EIR - Oncor and WETT - Combined Dalaware Basin Stage 5 Project and Alterntive - Status Update - RPG January 2025.pdf
25RPG020 | Large Load Additions Project | CPS Energy | Tier 1 | 333.7 | 2025 | Under Review | 5 | 2026/6_EIR-CPS-Energy-Large-Load-Additions-Project-and-STEC-Medina-County-Large-Load-Project_StatusUpdate_April2026_RPG.pdf 2026/8_EIR-CPS-Energy-Large-Load-Additions-Project_Updated_SCOPF_Feb2026_RPG.pdf 2025/EIR-CPS-Energy-Large-Load-Additions-Project_SCOPE_Aug2025_RPG.pdf 2025/CPS-Energy-Large-Load-Additions-Project.pdf 2026/7_EIR-STEC-Medina-County-Large-Load-Project_SCOPE_Feb2026_RPG.pdf
25RPG017 | Helotes 345/138-kV Switching Station and Autotransformer Addition at Eastside Switching Station Project | CPS Energy | Tier 1 | 110 | 2025 | Under Review | 5 | 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Scope_RPG_July_2025.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_August_2025.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_December_2025_FINAL.pdf 2025/EIR_CPS_Energy_Helotes_Reactive_Power_Planning_Project_Status_Update_RPG_October_2025_FINAL.pdf 2026/3.-EIR-CPS-Energy-Helotes-Reactive-Power-Planning-Project-Recommendation-RPG_April_2026_FINAL.pdf
25RPG026 | Paris Switch to Monticello Switch 345-kV Line Rebuild Project | Oncor | Tier 1 | 231.75 | 2025 | Under Review | 5 | 2026/4.-EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_Recommendation_April2026.pdf 2025/EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_SCOPE_September2025_RPG.pdf 2026/3_EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_February2026_RPG.pdf 2026/8.-EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_March2026_RPG.pdf 2026/EIR-Oncor-Paris-Switch-to-Monticello-Switch-345-kV-Line-Rebuild-Project_January2025_RPG.pdf
25RPG025 | Texas 765-kV-STEP Eastern Backbone Project | AEP Texas, CPS Energy, Oncor and CNP | Tier 1 | 9384 | 2025 | Completed | 5 | 2025/EIR-Joint_AEP_CPS_Oncor_CEHE_Texas_765-kV_STEP_Eastern_Backbone-Status-Update-RPG-Nov_2025_Final.pdf 2025/EIR-Joint_AEP_CPS_Oncor_CEHE_Texas_765-kV_STEP_Eastern_Backbone-Status-Update-RPG-Oct_2025_Final.pdf 2025/EIR-Joint_AEP_CPS_Oncor_CPS_Texas_765-kV_STEP_Eastern_Backbone-Scope-RPG-Sept-2025_Final.pdf 2025/Joint-TSP-Presentation-TX-765-kV-STEP-Eastern-Backbone-RPG.pdf 2026/13.-26RPG001-LCRA-TSC-and-CEHE-Euclid-765-kV-Substation-and-Transmission-Line-Addition-Project_final.pdf
25RPG027 | Royse Switch to Edgewood 69-kV Line Conversion to 138-kV Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 44.72 | 2025 | Completed | 0
25RPG024 | Blessing Area Improvements Project | AEPSC | Tier 1 (Withdrawn) | 256 | 2025 | Completed | 0
25RPG023 | Dunham 345/138-kV Switch Project | Oncor | Tier 3 | 21.3 | 2025 | Completed | 0
25RPG022 | Drill Hole to Sand Lake to Solstice 765-kV Line Project | Oncor and AEPSC | Tier 1 | 742.2 | 2025 | Completed | 5 | 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Scope-RPG-Sept-2025.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Status-Update-RPG-Nov-2025.pdf 2025/EIR-Oncor-and-AEPSC-Drill-Hole-to-Sand-Lake-to-Solstice-765-kV-Line-Project-Status-Update-RPG-Oct-2025.pdf 2025/RPG-Overview-for-Drill-Hole-Sand-Lake-Solstice-765-kV-09252025.pdf 2022/LCRA_Oncor_WETT_Bearkat_NorthMcCamey_SandLake_Project_06_15_2022.pdf
25RPG031 | Sam Switch Resiliency Project | LST | Tier 3 | 17 | 2025 | Completed | 0
25RPG029 | Hillsboro Switch to Elm Mott Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 52.85 | 2025 | Completed | 0
25RPG028 | P.H. Robinson to W.A. Parish 345-kV Hardening Project | CNP | Tier 1 | 511.31 | 2025 | Under Review | 5 | 2025/EIR_CNP_PHRobinson_to_WAParish_345kV_Hardening_Project_Scope_RPG_Sep_2025_Final.pdf 2025/EIR_CNP_PHRobinson_to_WAParish_345kV_Hardening_Project_StatusUpdate_RPG_Nov_2025.pdf 2025/EIR_CNP_PHRobinson_to_WAParish_345kV_Hardening_Project_StatusUpdate_RPG_Oct_2025_Final.pdf 2026/EIR_CNP_PHRobinson_to_WAParish_345kV_Hardening_Project_StatusUpdate_RPG_Jan_2026_Final.pdf 2025/CEHE-PHR-WAP-345kV-Hardening-Project20250925.pdf
25RPG030 | Bonham Switch to Toco Switch 69-kV Line Rebuild Project | Oncor | Reclassified from Tier 3 to Tier 4 per Protocol | 72.83 | 2025 | Completed | 0
25RPG034 | Mulberry Creek 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 32 | 2025 | Completed | 0
25RPG032 | Fort Stockton Plant 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 25.7 | 2025 | Completed | 0
25RPG033 | Oncor Skyview 345/138-kV Switch Project | Oncor | Tier 2 | 56.82 | 2025 | Under Review | 5 | 2025/EIR_Scope_Oncor_Skyview_345138kV_Switch_Project_-_RPG_Oct_2025_Final.pdf 2025/EIR_Status_Update_Oncor_Skyview_345138kV_Switch_Project_-_RPG_Dec_2025.pdf 2026/EIR_Status_Update_Oncor_Skyview_345138kV_Switch_Project_-_RPG_Jan_2026_Final.pdf 2026/EIR_Status_Update_Oncor_Skyview_345138kV_Switch_Project_-_RPG_Mar_2026.pdf 2025/Oncor_Skyview345-138-kV-Switch_Project_RPG_10282025.pdf
25RPG035 | McDonald Road Switch to Polecat Creek Switch 138-kV Line Project | Oncor | Tier 3 | 26.66 | 2025 | Completed | 4 | 2023/EIR - Oncor Peck to Driver 138 kV Line Project_Status_March2023.pdf 2023/EIR - Oncor Peck to Driver 138 kV Line project Scope_Jan2023.pdf 2023/EIR---Oncor-Peck-to-Driver-138-kV-Line-Project-Status-Update-April2023.pdf 2021/Oncor_-_Flat_Iron_-_Barr_Ranch_-_Pegasus_South_138-kV_Line_Project_-_August_17_RPG.pdf
25RPG036 | Abilene Northwest 138-kV Transmission Station Rebuild Project | AEPSC | Tier 3 | 33 | 2025 | Completed | 0
25RPG037 | West Loop Project | LP&L | Tier 1 | 309 | 2025 | Under Review | 2 | 2026/LP-L-West-Loop-Project-Overview_v2.pdf 2026/EIR_LPL_West_Loop_Project_Scope_RPG_January_2026_FINAL.pdf
25RPG043 | Set 2 North Central & South Central Texas Reliability Project | Oncor | Tier 1 | 440.79 | 2025 | Under Review | 5 | 2026/10_EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026_Final.pdf 2026/EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Mar-2026.pdf 2026/9.-EIR-Status-Update-Oncor-Combined-Set-1-Set-2-North-Central-South-Central-TX-Reliability-Project_RPG-Apr_2026_Final.pdf 2026/Set-1-Set-2-and-Navarro-and-Ellis-Area-Reliability-Project-Overviews-01162026_Final.pptx 2026/9_EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026.pdf
25RPG042 | Set 2 North & Central Texas Reliability Project | Oncor | Tier 1 | 1330 | 2025 | Under Review | 5 | 2026/9_EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026.pdf 2026/EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-Update-RPG-Mar-2026.pdf 2026/Set-1-Set-2-and-Navarro-and-Ellis-Area-Reliability-Project-Overviews-01162026_Final.pptx 2026/8.-EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Projects-Status-Update-RPG-Apr-2026_Final.pdf 2026/10_EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026_Final.pdf
25RPG039 | Southeast Brownsville Large Load Transmission System Improvements Project | STEC | Tier 2 | 96.35 | 2025 | Under Review | 5 | 2026/7.-EIR-Status-Update-STEC-Southeast-Brownsville-Large-Load-Project-RPG_April_2026_Final.pdf 2026/12.-EIR-STEC-Brownsville-Project-Scope-RPG-March-2026-FINAL.pdf 2026/12_EIR_STEC_Brownsville_Project_Scope_RPG_February_2026_FINAL (1).pdf 2026/12_EIR_STEC_Brownsville_Project_Scope_RPG_February_2026_FINAL.pdf 2026/STEC_Southeast-Brownsville-Load-_RPG_final.pptx
25RPG040 | Set 1 North & Central Texas Reliability Project | Oncor | Tier 1 | 1798 | 2025 | Under Review | 5 | 2026/9_EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026.pdf 2026/EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-Update-RPG-Mar-2026.pdf 2026/Set-1-Set-2-and-Navarro-and-Ellis-Area-Reliability-Project-Overviews-01162026_Final.pptx 2026/8.-EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Projects-Status-Update-RPG-Apr-2026_Final.pdf 2026/10_EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026_Final.pdf
25RPG041 | Set 1 North Central & South Central Texas Reliability Project | Oncor | Tier 1 | 943.92 | 2025 | Under Review | 5 | 2026/9.-EIR-Status-Update-Oncor-Combined-Set-1-Set-2-North-Central-South-Central-TX-Reliability-Project_RPG-Apr_2026_Final.pdf 2026/10_EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026_Final.pdf 2026/EIR-Oncor-Combined-Set-1-and-2-North-Central-South-Central-Texas-Reliability-Project-Scope-RPG-Mar-2026.pdf 2026/Set-1-Set-2-and-Navarro-and-Ellis-Area-Reliability-Project-Overviews-01162026_Final.pptx 2026/9_EIR-Oncor-Combined-Set-1-and-Set-2-North-and-Central-Texas-Reliability-Project-Scope-RPG-Feb-2026.pdf
25RPG038 | Navarro and Ellis Area Reliability Project | Oncor and LST | Tier 1 | 759.95 | 2025 | Under Review | 4 | 2026/11_EIR_Oncor_Lone_Star_Navarro_and_Ellis_Area_Reliability_Project_Scope_RPG_February_2026.pdf 2026/Set-1-Set-2-and-Navarro-and-Ellis-Area-Reliability-Project-Overviews-01162026_Final.pptx 2024/EIR - REC - Rand Area Loop Project - Scope - RPG Jun 2024.pdf 2024/EIR_ONCOR_Venus_Switch_to_Sam_Switch_Project_Update.pdf
25RPG045 | Alice Area Improvements Transmission Project | AEPSC | Tier 3 | 67 | 2025 | Completed | 0
25RPG044 | Whitney Autotransformer Upgrade Project | BEC | Tier 3 | 33.5 | 2025 | Completed | 0
25RPG046 | Medina County Large Load Additions Project | STEC | Tier 1 | 492 | 2026 | Under Review | 5 | 2026/6_STEC_Medina-County-Large-Load-_RPG_final.pptx 2026/6_EIR-CPS-Energy-Large-Load-Additions-Project-and-STEC-Medina-County-Large-Load-Project_StatusUpdate_April2026_RPG.pdf 2026/8_EIR-CPS-Energy-Large-Load-Additions-Project_Updated_SCOPF_Feb2026_RPG.pdf 2026/7_EIR-STEC-Medina-County-Large-Load-Project_SCOPE_Feb2026_RPG.pdf 2025/EIR-CPS-Energy-Large-Load-Additions-Project_SCOPE_Aug2025_RPG.pdf
26RPG001 | Euclid 765-kV Substation and Transmission Line Addition Project | LCRA TSC and CEHE | Tier 1 | 1830 | 2026 | Under Review | 3 | 2026/13.-26RPG001-LCRA-TSC-and-CEHE-Euclid-765-kV-Substation-and-Transmission-Line-Addition-Project_final.pdf 2026/EIR-Euclid-765-kV-Substation-and-Transmission-Line-Addition-Status-Update-RPG-April_2026.pdf 2026/EIR-Euclid-765-kV-Substation-and-Transmission-Line-Addition-Scope-RPG-March_2026.pdf