## Projects
The following is a list of projects seen after P0, P1, P2.1, P7, P3, P6.2, P2.2(EHV), P2.3(EHV), P4.1(EHV), P4.2(EHV), P4.3(EHV), P4.4(EHV), P4.5(EHV), and P5(EHV) analysis. An "X" mark in column I to M indicates that the project is needed for that year. This project is then included in all subsequent study years. Projects identified in the Permian Basin Reliability Study with a 2030 year need are marked with "PB".
Project Index | Option | Project Description | Test | Transmission Owner or Facility Owner | ERCOT Contact | County | 2026 | 2027MIN | 2027 | 2029 | 2030
2021-W5 |  | Sacroc (1311) - Deep Creek Sub (1304) 138-kV Line Upgrade | P0 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Scurry | X | X | X | X | PB
2023-W6 |  | Cedar Hills (6423) to Silver Tap (6431) 69-kV Line Upgrade | P1.2 | AEP | Misael Rodriguez Misael.Rodriguez@ercot.com | Coke |  |  | X | X | PB
2023-W9 |  | New Load Bus 900110 138-kV Cap Bank Addition | P1.2, P1.3/P2.2_HV, P7.1_ERCOT1 | New | Jose Solchaga Jose.Solchaga@ercot.com | Reagan | X |  | X | X | X
2023-W10 |  | Dermott (11306) - Scurry Chevron (1312) - Kndrsacrc (11130) - Oncor900041 Tap (1366) - Knapp (1310) - Bluff Creek (1309) 138-kV Line Upgrade | P1.1,P1.2, P1.3, P7.1_ERCOT1, P6.2_ERCOT3 | ONCOR | Misael Rodriguez Misael.Rodriguez@ercot.com | Scurry | X | X | X | X | X
2023-W19 |  | Bluff Creek Switch (1309) - Exxon Sharon Ridge (1300) 138-kV Line Upgrade | P1.2, P7.1_ERCOT1 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Scurry | X | X | X | X | X
2024-W1 |  | Winters (6333) - Steamboat (60332) 69-kV Line Upgrade | P1.2, P7.1_ERCOT1 | AEP | Jose Solchaga Jose.Solchaga@ercot.com | Runnels | X |  | X | X | X
2024-W2 |  | Barber Lake Station (1189) 138-kV Cap Bank Addition | P1.3, P7.1_ERCOT1 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Mitchell | X | X | X | X | X
2024-W3 |  | Ranger (10050) to Frontier (11393) 138-kV Second Circuit Line Addition | P1.2 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Mitchell | X | X | X | X | PB
2024-W4 |  | San Angelo Concho (6450) - San Angelo Lake Nasworthy (6527) - San Angelo Mathis Field (6477) - Tankersley (6528) - Mertzon (6529) - Cassava (60359) 69-kV Line Upgrades | P0, P1.1, P1.2, P1.3, P7.1_ERCOT1 | AEP | Jose Solchaga Jose.Solchaga@ercot.com | Irion, Tom Green | X |  | X | X | X
2024-W5 |  | Ranger (10050) - Loraine South POI (11342) - Roscoe (10104) 138-kV Line Upgrade and Sweetwater Tap (1341) 138-kV Cap Bank Addition | P6.2_ERCOT3 | ONCOR | Misael Rodriguez Misael.Rodriguez@ercot.com | Mitchell, Nolan | X | X | X | X | X
2024-W6 |  | Roscoe (10105) 345-kV Substation and 345/138-kV Transformers Addition | P0 | ONCOR | Misael Rodriguez Misael.Rodriguez@ercot.com | Nolan | X | X | X | X | PB
2023-FW1 |  | Glasscock County North (1334) - Forsan Tap (1335) - Mcdonald (1333) - Polecat Creek Switch (11337) 138-kV Line Upgrades | P0, P1.2, P1.3, P7.1_ERCOT1 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Glasscock | X | X | X | X | X
2023-FW2 |  | Illinois (6565) - Pandale (6567) - Ozona Rea (6551) - Ozona (6560) - Friend Ranch (6550) - Atlantic Sonora (6511) 69-kV Line Upgrades | P1.2, P7.1_ERCOT1 | AEP | Jose Solchaga Jose.Solchaga@ercot.com | Crockett, Sutton |  | X | X | X | PB
2023-FW11 |  | New Load Bus 900062 138-kV Cap Bank Addition | P1.2, P7.1_ERCOT1 | New | Jose Solchaga Jose.Solchaga@ercot.com | Reagan |  |  | X | X | X
2023-FW16 |  | Fort Stockton Plant (6630) - Leon Creek TNP (38355) 138-kV Line Upgrade | P0 | AEP, TNMP | Jose Solchaga Jose.Solchaga@ercot.com | Pecos | X |  | X | X | X
2024-FW1 |  | Einstein (23852) - Carterville Ranch (10018) - Carterville (23851) 138-kV Line Upgrades | P1.2 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Midland, Glasscock | X |  |  |  | X
2024-FW2 |  | Big Spring Switch (1322) to Steer (10044) 138-kV Line Upgrade | P1.2 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Howard | X |  | X | X | PB
2024-FW3 |  | New Load bus 900100 138-kV Cap Bank Additions | P0, P1.2, P6.2_ERCOT3 | New | Misael Rodriguez Misael.Rodriguez@ercot.com | Howard | X | X | X | X | PB*
2024-FW4 |  | Luther (23831) - Coyote (23832) - Salem (10041) - Bulldog (23833) 138-kV Line Upgrades | P1.3, P7.1_ERCOT1 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Howard | X | X | X | X | PB
2024-FW5 |  | Natural Dam (23836) - Howard (11325) - Beals Creek Sub (11331) 138-kV Line Upgrades | P1.2 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Howard | X | X | X | X | PB
2024-FW6 |  | White Baker (38435) 345-kV Substation Expansion, and Bakersfield (76002) - White Baker (38435) 345-kV Double-Circuit Line Additions | P7.1_ERCOT1 | TNMP | Jose Solchaga Jose.Solchaga@ercot.com | Pecos | X | X | X | X | PB
2024-FW7 |  | White Baker (38340) - Keo (131453) - Fortblocks (9424) 138-kV Line Upgrades | P1.2, P1.3, P1.4 | TNMP, GOLDENSPREAD | Jose Solchaga Jose.Solchaga@ercot.com | Pecos | X |  | X | X | PB
2024-FW8 |  | Faulkner (38124) 138-kV Cap Bank Addition | P0, P1.4 | TNMP | Jose Solchaga Jose.Solchaga@ercot.com | Reeves | X | X | X | X | X
2024-FW9 |  | Oxy Century TNP (38432) 138-kV Cap Bank Addition | P0 | TNMP | Jose Solchaga Jose.Solchaga@ercot.com | Pecos | X | X | X | X | X
2024-FW10 |  | Prong Moss (10057) 345/138-kV Transformer Additions | P1.2 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Howard | X | X | X | X | PB
2024-FW11 |  | Faulkner (838124) and 90005Tap (811610) 345/138-kV Substation Expansion, and Solstice (60404) - Faulkner (838124) - 90005Tap (811610) 345-kV Double-Circuit Line Additions | P7.1_ERCOT1 | AEP, ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Reeves, Pecos |  |  | X | X | PB
2024-FW12 |  | New Load bus 900012 138-kV Cap Bank Addition | P0, P1.2, P1.3, P1.4, P7.1_ERCOT1 | New | Jose Solchaga Jose.Solchaga@ercot.com | Winkler |  |  | X | X | X
2024-FW13 |  | Courtney Creek Switch (11242) 138-kV Cap Bank Addition | P1.2 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Howard |  |  | X | X | X
2024-FW14 |  | TNMP 16th Street (38310) - Ocotillo (38383) 69-kV to 138-kV line Conversion | P0 | TNMP | Jose Solchaga Jose.Solchaga@ercot.com | Pecos | X | X | X | X | PB
2024-FW15 |  | Faulkner Toyah TNP (38124) - New Bus 900108 - Cryo (60721) 138-kV Line Additions | P3_ERCOT2 P6.2_ERCOT3 | AEP, TNMP | Misael Rodriguez Misael.Rodriguez@ercot.com | Reeves |  |  | X | X | PB
2024-FW16 |  | Elbow (23834) - New Bus 900100 - Eiland (23853) 138-kV Line Upgrades | P0 | ONCOR | Misael Rodriguez Misael.Rodriguez@ercot.com | Howard, Glasscock | X | X | X | X | PB
2024-FW17 |  | Chalk (1352) - Kinnebrew POI (11352) - Campeliz (6641) - Sterling City (6435) 69-kV Upgrades | P1.2 | AEP, ONCOR | Misael Rodriguez Misael.Rodriguez@ercot.com | Sterling | X |  | X | X | PB
2024-FW18 |  | Solstice (60384) – FT Stockton Plant (6630) 138-kV Line Upgrade and Solstice Phase Shifting Transformer Bypass | P6.2_ERCOT3 | AEP | Misael Rodriguez Misael.Rodriguez@ercot.com | Pecos |  |  |  | X | PB
2024-FW19 |  | New Load Bus 900052 138-kV Cap Bank Addition | P1.2 | New | Misael Rodriguez Misael.Rodriguez@ercot.com | Reagan |  |  |  | X | X
2024-FW20 |  | White Baker (38430) to Girvin (38430) 138-kV Line Upgrade | P7.1 | TNMP | Misael Rodriguez Misael.Rodriguez@ercot.com | Pecos | X | X | X | X | PB
2024-FW21 |  | Vealmoor (23835) - Koch Tap (23829) - Buzzard Draw Switch (1355) 138-kV Line Upgrades | P1.2, P7.1_ERCOT1 | ONCOR | Misael Rodriguez Misael.Rodriguez@ercot.com | Howard, Borden |  |  |  | X | X
2024-FW22 |  | Cottonwood (38099) 138-kV Cap Bank Addition | P0, P1.2, P7.1_ERCOT1 | TNMP | Misael Rodriguez Misael.Rodriguez@ercot.com | Reeves |  |  |  | X | X
2021-WFW1 |  | Big Lake (6534) - Cassava (60360) 69-kV to 138-kV Line Conversion | P0 | AEP | Jose Solchaga Jose.Solchaga@ercot.com | Irion | X | X | X | X | X
2022-WFW1 |  | Twin Buttes (76011) - Hargrove (6648) - Pumpjack (60374) - Jerry (6559) 138-kV Line Upgrade | P1.1, P1.2, P1.3, P7.1_ERCOT1 | AEP, LCRA TSC | Jose Solchaga Jose.Solchaga@ercot.com | Tom Green, Irion, Reagan |  |  |  | X | X
2023-WFW1 |  | Exxon Sharon Ridge (1300) - Willow Valley Switch (1301) 138-kV Line Upgrades | P1.2, P1.3, P7.1_ERCOT1 | ONCOR | Jose Solchaga Jose.Solchaga@ercot.com | Scurry, Borden | X | X | X | X | X
2022-S2 |  | Fanninsub (5736) to Goliad (8587) 69-kV Line Upgrade | P0 | AEP, STEC | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Goliad |  |  | X | X | X
2023-S7 |  | Static (8676) 345-kV Reactor Addition | P1.2, P7.1_ERCOT1 | AEP | Johanna Allen johanna.allen@ercot.com | Refugio |  | X
2024-S1 |  | Dupont Area 138-kV Line Upgrades | P0, P1.2 | AEP | Mahnoush Yousefian mahnoush.yousefian@ercot.com | San Patricio, Nueces | X |  | X | X | X
2024-S3 |  | San Diego Sub (5654) to Orange Groves Switch (5658) 69-kV Line Upgrade | P1.2 | STEC | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Duval, Jim Wells |  |  |  | X | X
2024-S4 |  | Grissom (8624) to Raptor (8673) 345-kV Line Upgrade | P1.2 | AEP | Mariela Zuniga mariela.zuniga@ercot.com | Bee, Goliad |  |  |  |  | X
2024-S6 |  | Seabird (84250) 138-kV Cap Bank Addition | P1.2 | AEP | Mahnoush Yousefian mahnoush.yousefian@ercot.com | San Patricio |  |  | X | X | X
2024-S7 |  | Brownsville Area Line Additions and Upgrades | P0, P1.2-2.2, P7.1_ERCOT1 | AEP | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Cameron |  |  | X | X | X
2024-S8 |  | Lon Hill Area 345-kV Upgrades | P0, P1.2, P7.1_ERCOT1, P1.3-2.2_EHV, P1.1 | AEP | Mariela Zuniga mariela.zuniga@ercot.com | Nueces, San Patricio, Bee |  |  |  | X | X
2024-S10 |  | Coleto (8164) to Haber (81003) to Raptor (8673) 345-kV Double-Circuit Line Addition | P1.2, P7.1_ERCOT1 | AEP | Mariela Zuniga mariela.zuniga@ercot.com | Victoria, Goliad |  |  |  |  | X
2024-S11 |  | Caravel (85010) 138-kV Cap Bank Additions | P1.2, P7.1_ERCOT1 | AEP | Mariela Zuniga mariela.zuniga@ercot.com | Kleberg |  |  |  | X | X
2024-S12 |  | Lon Hill (8452) to Bunsen (8459) 138-kV Line Upgrade | P3_ERCOT2 | AEP | Mariela Zuniga mariela.zuniga@ercot.com | Nueces |  |  |  | X
2024-S13 |  | Nelson Sharpe 345/138-kV Transformer Addition | P6.2_ERCOT3 | AEP | Mariela Zuniga mariela.zuniga@ercot.com | Nueces |  |  |  | X | X
2024-S14 |  | Naismith 345/138-kV Transformer Addition | P6.2_ERCOT3 | AEP | Mariela Zuniga mariela.zuniga@ercot.com | San Patricio |  |  |  | X | X
2022-SC7 |  | Decker (9188) 138-kV Bus Tie Breaker Upgrade | P0, P1.1, P1.3, P1.2, P7.1_ERCOT1 | AEN | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Travis |  |  | X | X | X
2023-SC3 |  | Dessau (9193) to McNeil AEN (9076) 138-kV Circuit 2 Upgrade | P7.1_ERCOT1 | AEN | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Travis |  |  | X | X | X
2023-SC7 |  | Cachena (5068) 345-kV Reactor Addition | P1.2, P7.1_ERCOT1 | CPS | Mariela Zuniga mariela.zuniga@ercot.com | Lavaca |  | X
2023-SC15 |  | Sim Gideon Area 138-kV Line Upgrades | P7.1_ERCOT1 | LCRA TSC, ONCOR, AEN | Mariela Zuniga mariela.zuniga@ercot.com | Bastrop, Fayette, Williamson | X |  | X | X | X
2023-SC17 |  | Georgetown Area 138-kV Line Upgrades | P1.2, P7.1_ERCOT1 | LCRA TSC | Mariela Zuniga mariela.zuniga@ercot.com | Williamson | X |  | X | X | X
2023-SC18 |  | El Campo (5538) to Nada Sub (5536) 69-kV Line Upgrade | P1.2 | STEC | Mariela Zuniga mariela.zuniga@ercot.com | Colorado, Wharton |  |  | X | X | X
2024-SC1 |  | San Marcos (7192) to Canyon (7200) 138-kV Line Upgrade | P1.2, P7.1_ERCOT1 | LCRA TSC | Mariela Zuniga mariela.zuniga@ercot.com | Hays | X |  | X | X | X
2024-SC2 |  | Trading Post (70505) 138-kV Cap Bank Addition | P0, P1.2, P7.1_ERCOT1 | AEN | Mariela Zuniga mariela.zuniga@ercot.com | Travis | X |  | X | X | X
2024-SC3 |  | Gay Hill (7572) to Sandy Hill (7570) to Brenham North (7294) 138-kV Line Upgrades | P1.2 | LCRA TSC, BBEC | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Washington |  |  | X | X | X
2024-SC4 |  | Wells Branch (7288) to Howard Lane (7335) 138-kV Line Upgrade | P1.2, P6.2_ERCOT3, P3_ERCOT2 | LCRA TSC | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Travis | X |  | X
2024-SC7 |  | Zorn (7180) to McCarty Lane (7182) and Beback (7187) 138-kV Line Upgrades | P1.2 | LCRA TSC | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Hays |  |  | X
2024-SC8 |  | Milano (64) to Minerva (3683) and Cannon (3707) 138-kV Line Upgrades | P1.2 | ONCOR | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Milam |  |  |  | X | X
2024-SC9 |  | Halletsville (7246) to Mont (7249) 138-kV Line Upgrade | P1.2 | LCRA TSC | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Lavaca |  |  |  | X | X
2024-SC10 |  | Peters (46220) to Bellville South (7270) 138-kV Line Upgrade | P1.1, P1.2, P1.3-2.2_HV, P7.1_ERCOT1 | CNP | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Austin |  |  |  | X | X
2024-SC11 |  | Vega (9285) to Barton (9158) 138-kV Line Upgrade | P0, P1.1, P1.2, P1.3, P7.1_ERCOT1 | AEN | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Travis |  |  |  | X | X
2024-SC12 |  | Calvert Switch (73) to Calvert (77) 69-kV Line Upgrade | P0 | BREC | Mariela Zuniga mariela.zuniga@ercot.com | Milam |  | X
2024-SC14 |  | Elroy (7209) 138-kV Cap Bank Addition | P1.2, P7.1_ERCOT1 | LCRA TSC | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Travis |  |  | X | X | X
2024-SC15 |  | Euclid (7510) 345-kV Cap Bank Addition | P1.2 | LCRA TSC | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Caldwell |  | X | X | X | X
2024-SC16 |  | Limmer (7341) 345-kV Cap Bank Addition | P1.2, P7.1_ERCOT1 | LCRA TSC | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Williamson | X | X | X | X | X
2024-SC17 |  | SLR AMLC (3740) 138-kV Cap Bank Addition | P7.1_ERCOT1 | ONCOR | Mahnoush Yousefian mahnoush.yousefian@ercot.com | Milam |  | X |  | X | X
2024-SC18 |  | Lytton (9074) to Fayette Plant (7055) to Winchester (9042) 345-kV Upgrades | P7.1_ERCOT1 | AEN, LCRA TSC | Mariela Zuniga mariela.zuniga@ercot.com | Caldwell, Bastrop, Fayette |  |  |  | X | X
2024-SC19 |  | Hillje (44200) to Zorn (7042) 345-kV Line Upgrades | P0, P1.1, P1.2, P7.1_ERCOT1, P1.3-2.2_EHV | CNP, AEN, LCRA TSC | Mariela Zuniga mariela.zuniga@ercot.com | Wharton, Fayette, Bastrop, Caldwell, Guadalupe |  |  |  | X | X
2024-SC20 |  | Lytton Area 138-kV Line Upgrades | P1.2, P7.1_ERCOT1, P6.2_ERCOT3, P3_ERCOT2 | AEN, LCRA TSC | Mariela Zuniga mariela.zuniga@ercot.com | Caldwell, Travis, Bastrop |  |  |  | X | X
2024-SC21 |  | Austrop (9328) to Dunlap (9045) 138-kV Double Circuit Line Addition | P7.1_ERCOT1 | AEN, LCRA TSC | Mariela Zuniga mariela.zuniga@ercot.com | Travis |  |  |  | X | X
2024-SC22 |  | Austrop 345/138-kV Transformer Addition | P7.1_ERCOT1, P6.2_ERCOT3, P3_ERCOT2 | AEN | Mariela Zuniga mariela.zuniga@ercot.com | Travis | X |  | X | X | X
2024-SC23 |  | Dunlap 345/138-kV Transformer Addition | P6.2_ERCOT3, P1.3 | AEN | Mariela Zuniga mariela.zuniga@ercot.com | Travis |  |  |  | X | X
2024-SC24 |  | Gillelend Creek (7340) 345-kV Cap Bank Addition | P1.2, P7.1_ERCOT1 | LCRA TSC | Mariela Zuniga mariela.zuniga@ercot.com | Travis |  |  |  | X | X
2024-SC25 |  | Karnes City (8913) to Kennedy (8186) to Falls City (5145) 138-kV Line Upgrades | P7.1_ERCOT1, P6.2_ERCOT3, P3_ERCOT2 | AEP, CPS | Mariela Zuniga mariela.zuniga@ercot.com | Karnes |  |  |  |  | X
2024-SC26 |  | Shaula (5380) to Elm Creek (5133) to Cachena (5068) 345-kV Line Upgrades | P0, P6.2_ERCOT3, P3_ERCOT2 | CPS | Mariela Zuniga mariela.zuniga@ercot.com | Wilson, Guadalupe, Dewitt |  |  |  | X | X
2024-SC27 |  | Lytton Springs (9074) to Garfield (7048) to Austrop (7040) 345-kV Line Upgrades | P7.1_ERCOT1, P6.2_ERCOT3 | LCRA TSC, AEN | Mariela Zuniga mariela.zuniga@ercot.com | Caldwell, Bastrop, Travis |  |  |  | X | X
2024-SC28 |  | Voss Lake 345/138-kV Substation Expansion and Bell County East (3687) to Voss Lake (3751) 345-kV Double Circuit Line Upgrade | P7.1_ERCOT1, P6.2_ERCOT3 | ONCOR | Mariela Zuniga mariela.zuniga@ercot.com | Milam |  | X | X | X | X
2024-SC29 |  | Muscovy 345/138-kV Substation Addition and Salado (3699) to Muscovy (3700) to Voss Lake (3751) 345-kV Double Circuit Addition | P6.2_ERCOT3 | ONCOR | Mariela Zuniga mariela.zuniga@ercot.com | Bell, Williamson, Milam |  |  | X | X | X
2024-SC30 |  | Holman (9073) to Fayette Plant (7055) 345-kV Line Upgrade | P6.2_ERCOT3 P3_ERCOT2 | AEN, LCRA TSC | Mariela Zuniga mariela.zuniga@ercot.com | Fayette |  |  |  | X | X
2024-SC31 |  | Lytton Springs 345/138-kV Transformer Addition | P6.2_ERCOT3 | AEN, LCRA TSC | Mariela Zuniga mariela.zuniga@ercot.com | Caldwell | X |  | X | X | X
2024-SC32 |  | McNeil AEN (9076) 138-kV Bus Tie Breaker Upgrade | P3_ERCOT2, P6.2_ERCOT3 | AEN | Mariela Zuniga mariela.zuniga@ercot.com | Travis |  |  |  | X | X
2024-CS1 |  | Old Hickory (5323) 345-kV Substation and 345-kV Line Additions | P0, P1.1, P1.2, P7.1_ERCOT1 | AEP, CPS | Mariela Zuniga mariela.zuniga@ercot.com | Goliad, Jackson |  |  |  | X | X
2024-CS2 |  | Victoria (8169) to Refugio (8410) 69-kV Line Upgrades | P1.2, P1.3, P7.1_ERCOT1 | AEP | Johanna Allen johanna.allen@ercot.com | Victoria, Refugio |  |  |  | X | X
2024-CS3 |  | Tungsten (8189) to Rincon (8437) 138-kV Line Upgrades | P0, P1.2, P7.1_ERCOT1 | AEP | Johanna Allen johanna.allen@ercot.com | Aransas, Calhoun, San Patricio |  |  |  | X | X
2023-C3 |  | Point Comfort (8132) to Cangrejo (8720) 69-kV Line Upgrade | P0, P1.2, P7.1_ERCOT1 | AEP | Johanna Allen johanna.allen@ercot.com | Calhoun |  |  |  | X | X
2024-C1 |  | South Texas Project Area 345-kV Cap Bank Additions | P0, P1.1, P1.2, P7.1_ERCOT1 | AEP | Johanna Allen johanna.allen@ercot.com | Matagorda, Jackson |  |  |  |  | X
2024-C2 |  | Clute Area 138-kV Line Upgrades | P0, P1.1, P1.2, P7.1_ERCOT1 | CNP | Johanna Allen johanna.allen@ercot.com | Brazoria |  |  |  | X | X
2024-C3 |  | South Texas Project (5915) to Haber (81003) 345-kV Line Upgrades | P0, P1.1, P1.2, P7.1_ERCOT1 | AEP, CNP | Johanna Allen johanna.allen@ercot.com | Matagorda, Jackson |  |  |  | X | X
2024-C4 |  | Radiant (8715) to Cobra (8728) to Haber (81003) 345-kV Double Circuit Line Addition | P7.1_ERCOT1 | AEP | Johanna Allen johanna.allen@ercot.com | Jackson |  |  |  |  | X
2024-C5 |  | Lake Jackson (42880) to Hofman (42810) to Basf (42150) 138-kV Line Upgrades | P6.2_ERCOT3 | CNP | Johanna Allen johanna.allen@ercot.com | Brazoria |  |  |  |  | X
2024-C6 |  | Franklins Camp Sub (5566) to Sargent Sub (5564) 69-kV Line Upgrade and Franklins Camp Sub (5566) 138/69-kV Transformer Upgrade | P0, P1.1, P1.2, P1.3, P7.1_ERCOT1 | STEC | Johanna Allen johanna.allen@ercot.com | Brazoria |  |  |  | X | X
2024-C7 |  | Jeanetta (47310) to Westwood (47461) 138-kV Line Upgrade | P3_ERCOT2, P6.2_ERCOT3, P7.1_ERCOT1 | CNP | Johanna Allen johanna.allen@ercot.com | Harris |  |  |  | X | X
2024-C8 |  | Hillje (44200) to South Texas Project (5915) 345-kV Line Upgrades | P1.2, P3_ERCOT2, P7.1_ERCOT1 | CNP, AEN | Johanna Allen johanna.allen@ercot.com | Wharton, Matagorda |  |  |  | X | X
2024-C9 |  | West Columbia (43384) to Needville (42380) 138-kV Line Upgrades | P0, P1.2, P7.1_ERCOT1 | CNP | Johanna Allen johanna.allen@ercot.com | Brazoria | X |  | X | X | X
2024-C10 |  | Fort Bend (44300) to Flewellen (44230) 138-kV Line Upgrades | P0, P1.2, P3_ERCOT2, P6.2_ERCOT3, P7.1_ERCOT1 | CNP | Johanna Allen johanna.allen@ercot.com | Fort Bend |  |  | X | X | X
2024-C11 |  | North Belt (46110) to Drilco (45740) 138-kV Line Upgrade | P7.1_ERCOT1 | CNP | Johanna Allen johanna.allen@ercot.com | Harris |  |  |  | X | X
2024-C12 |  | Sam Rayburn Switchyd (5500) to Warburton Road Switching Station (5605) 69-kV Line Upgrades | P1.2 | STEC | Johanna Allen johanna.allen@ercot.com | Victoria |  |  |  | X | X
2024-C13 |  | Sargent Sub (5564) to Bay City Sub (5560) 69-kV Line Upgrade | P0, P1.1, P1.2, P1.3, P6.2_ERCOT3, P7.1_ERCOT1 | STEC | Johanna Allen johanna.allen@ercot.com | Matagorda |  |  |  | X | X
2024-C14 |  | South Lane City (43190) 345/138-kV Substation Expansion and South Lane City Area 138-kV Line Upgrades | P1.1, P1.2, P7.1_ERCOT1 | AEP, CNP | Johanna Allen johanna.allen@ercot.com | Wharton |  |  |  | X | X
2024-C15 |  | Victoria Area 138-kV Line Upgrades and Furhman Switch (5506) to Magruder (8194) 138-kV Line Addition | P0, P1.1, P1.2, P1.3, P7.1_ERCOT1 | AEP, STEC | Johanna Allen johanna.allen@ercot.com | Victoria |  |  |  | X | X
2024-C16 |  | South Lane City (43190) to Lane CityB (8130) to Lane CityA (8127) 138-kV Line Upgrades | P6.2_ERCOT3 | AEP, CNP | Johanna Allen johanna.allen@ercot.com | Wharton |  |  |  |  | X
2024-C17 |  | Lane City (8127) to Blessing (8121) 138-kV Line Upgrades | P1.2 | AEP | Johanna Allen johanna.allen@ercot.com | Wharton, Matagorda |  |  |  | X | X
2024-C18 |  | Cedar Bayou (40000) Station Project | P3_ERCOT2, P6.2_ERCOT3 | CNP | Johanna Allen johanna.allen@ercot.com | Chambers |  |  |  | X | X
2024-C19 |  | Joslin (8140) to Gohlke (8141) to Dacosta (8722) 138-kV Line Upgrades | P1.2, P6.2_ERCOT3, P7.1_ERCOT1 | AEP | Johanna Allen johanna.allen@ercot.com | Calhoun, Victoria |  |  |  | X | X
2023-E2 |  | Canton Switch (3174) to Edgewood (3181) 138-kV Line Upgrade | P1.2, P7.1_ERCOT1 | ONCOR | Amy Chen jiayi.chen@ercot.com | Van Zandt |  |  |  |  | X
2024-E1 |  | Fairfield BEPC (196) to Fairfield WEST (3503) 138-kV Line Upgrade | P1.2 | ONCOR | Amy Chen jiayi.chen@ercot.com | Freestone | X |  | X | X | X
2024-E2 |  | Shamburger Switch (3103) to Elkton (3105) 345-kV Double Circuit Line Addition | P1.2, P7.1_ERCOT1 | ONCOR | Amy Chen jiayi.chen@ercot.com | Smith | X |  | X | X | X
2024-E3 |  | Big Brown SES West (3381) to Jewett (3391) 345-kV Line Upgrade and Substation Rebuilds | P1.1, P1.2, P7.1_ERCOT1 | ONCOR | Amy Chen jiayi.chen@ercot.com | Freestone, Leon |  |  |  | X | X
2024-E4 |  | Bryan Area Project | P1.2, P7.1_ERCOT1 | BTU, LCRA TSC, TNMP | Amy Chen jiayi.chen@ercot.com | Brazos, Burleson, Robertson |  |  | X | X | X
2024-E5 |  | Sulphur Springs East Tap (1797) to Martin Springs (ONCOR) (1800) 138-kV Line Upgrade | P3_ERCOT2, P6.2_ERCOT3 | ONCOR | Amy Chen jiayi.chen@ercot.com | Hopkins |  |  |  | X | X
2024-E6 |  | Cumby RC (6861) to Cumby (1812) to Cumby Tap (1813-1815) 138-kV Line and Breaker Upgrades | P1.2, P7.1_ERCOT1 | RAYBN, ONCOR | Amy Chen jiayi.chen@ercot.com | Hopkins |  |  |  | X | X
2024-E7 |  | Thorn Tree Switch (11688) to Saltillo Switch (11700) 345-kV Line Upgrade | P3_ERCOT2, P6.2_ERCOT3 | ONCOR | Amy Chen jiayi.chen@ercot.com | Titus, Hopkins |  |  |  | X | X
2024-E8 |  | Monticello Tap (1794) to Sulphur Springs East Tap (1797) 138-kV Line Upgrades | P1.2, P7.1_ERCOT1 | ONCOR | Amy Chen jiayi.chen@ercot.com | Titus, Hopkins |  |  |  | X | X
2024-E9 |  | Monticello SES (1695) to Cartwheel POI (888847) 345-kV Line Upgrades | P7.1_ERCOT1 | ONCOR | Amy Chen jiayi.chen@ercot.com | Titus, Hopkins |  |  |  | X | X
2024-E10 |  | Stryker Creek SES (3109) to Trinidad SES (3123) 345-kV Line Upgrade | P7.1_ERCOT1 | ONCOR | Amy Chen jiayi.chen@ercot.com | Cherokee, Henderson |  |  |  |  | X
2024-E11 |  | Herty Tap (3318) to Redland (3319) 138-kV Line Upgrade | P1.2 | ONCOR | Amy Chen jiayi.chen@ercot.com | Angelina |  |  |  |  | X
2024-E12 |  | Trinidad SES (3124) to Richland Chambers (3134) 345-kV Line Upgrade | P1.2, P3_ERCOT2, P6.2_ERCOT3, P7.1_ERCOT1 | ONCOR | Amy Chen jiayi.chen@ercot.com | Henderson, Freestone | X |  | X | X | X
2024-E13 |  | Stryker Creek SES (3110) to Dialville (3160) 138-kV Line Upgrade | P7.1_ERCOT1 | ONCOR | Amy Chen jiayi.chen@ercot.com | Cherokee |  |  |  | X | X
2024-E14 |  | Umbra (888843) to Monticello SES (1695) 345-kV Line Upgrade | P3_ERCOT2, P6.2_ERCOT3 | ONCOR | Amy Chen jiayi.chen@ercot.com | Franklin, Titus |  |  |  | X | X
2024-E15 |  | Umbra (888843) to Woodard Switch (11699) 345-kV Line Upgrade | P3_ERCOT2, P6.2_ERCOT3 | ONCOR | Amy Chen jiayi.chen@ercot.com | Franklin, Lamar |  |  |  |  | X
2016-N01 |  | Kiamichi Energy Facility (140077) 345-kV Reactors Addition | P0 | KIOWA POWER PARTNERS LLC (RE) | Eric Cen eric.cen@ercot.com | Pittsburg (Oklahoma) |  | X
2024-N01 |  | Childress West (6030/6028) 138/69-kV Transformer Upgrade and Cap Bank Addition | P1.2, P1.3, P7.1_ERCOT1 | AEP | Eric Cen eric.cen@ercot.com | Childress | X | X | X | X | X
2024-N02 |  | Lake Pauline (6050/6048) 138/69-kV Transformer Upgrade | P0, P1.1, P1.2, P1.3, P7.1_ERCOT1 | AEP | Eric Cen eric.cen@ercot.com | Hardeman | X |  | X | X | X
2024-N03 |  | Southwest Vernon (6064) Line and 138/69-kV Transformer Upgrade | P1.2, P1.3 | AEP | Eric Cen eric.cen@ercot.com | Wilbarger | X |  | X | X | X
2024-N04 |  | Vernon (6060/6055) 138/69-kV Transformer Upgrade | P1.2, P1.3 | AEP | Eric Cen eric.cen@ercot.com | Wilbarger | X |  | X | X | X
2024-N05 |  | Jayton (6153) to Spur (6148) 69-kV Line Upgrades and Spur (6150/6148) 138/69-kV Transformer Upgrade | P1.2, P6.2_ERCOT3 | AEP | Eric Cen eric.cen@ercot.com | Kent, Motley | X |  | X | X | X
2024-N06 |  | Seymour (779) to Seymour Tap (1534) 69-kV Line Upgrade | P1.2 | BEPC, ONCOR | Eric Cen eric.cen@ercot.com | Baylor | X |  | X | X | X
2024-N07 |  | Valley SES (1691) to Bells North POI (1699) to North Gate (12679) 138-kV Line Upgrade | P1.2, P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Fannin, Grayson |  |  | X | X | X
2024-N08 |  | Lubbock Area 115-kV Network Upgrades | P1.2, P6.2_ERCOT3 | LPL | Jack Thornton jack.thornton@ercot.com | Lubbock |  |  |  | X | X
2024-N09 |  | Nova Prime 138 (59909) to Nova Prime 345 (59998) 138-kV Line Upgrade | P0 | WETT | Jack Thornton jack.thornton@ercot.com | Kent |  |  |  | X | X
2024-N10 |  | Bonham (1808) to Copper Head Switch (11809) 138-kV Line Upgrade | P7.1_ERCOT1, P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Fannin |  |  |  |  | X
2024-N11 |  | Alla Hubbard (1757) to Epco POI (12468) 138-kV Line Upgrade | P1.2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Collin, Grayson |  |  |  | X | X
2024-N12 |  | Haggerty Switch (12677) to Northgate (12679) 138-kV Line Upgrade | P1.2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Grayson |  |  |  |  | X
2024-N13 |  | Epco POI (12468) to Gunter (2236) 138-kV Line Upgrade | P1.2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Grayson |  |  |  |  | X
2024-N14 |  | Hawk Hollow Switch (11768) to Monticello Tap (1794) 138-kV Line Upgrades | P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Franklin, Lamar, Red River, Titus | X |  | X | X | X
2024-N15 |  | Bobwhite (6037) 138-kV Cap Bank Addition | P6.2_ERCOT3 | AEP | Jack Thornton jack.thornton@ercot.com | Foard | X |  | X | X | X
2024-N16 |  | Delta Sub (1802) to Valley SES (1691) 138-kV Line Upgrades | P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Fannin, Hopkins, Hunt, Lamar |  |  |  | X | X
2024-N17 |  | Bonham Switch (1760) to Bonham (1808) 138-kV Line Upgrade | P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Fannin |  |  |  |  | X
2024-NC01 |  | Glen Heights (217) to Sterett Road (2237) 138-kV Line Upgrade | P1.2, P1.3, P7.1_ERCOT1 | BEPC | Eric Cen eric.cen@ercot.com | Ellis |  |  |  | X | X
2024-NC02 |  | Brownwood (1661/1662) 138/69-kV Transformer Upgrade | P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Brown | X |  | X | X | X
2024-NC03 |  | Dublin (1636/1637) 138/69-kV Transformer Upgrade | P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Erath | X |  | X | X | X
2024-NC04 |  | Railport (442) Area 138-kV Rebuild | P0, P1.2, P1.3, P7.1_ERCOT1, P6.2_ERCOT3 | BEPC, ONCOR | Eric Cen eric.cen@ercot.com | Ellis, Johnson | X | X | X | X | X
2024-NC05 |  | Hillboro (3522/3523) 138/69-kV Transformer Upgrade | P0, P1.2 | ONCOR | Eric Cen eric.cen@ercot.com | Hill |  |  | X | X | X
2024-NC06 |  | Miller (824) to Newman (849) 138-kV Line Upgrade | P1.2 | GRLND | Eric Cen eric.cen@ercot.com | Dallas | X |  | X | X | X
2024-NC07 |  | Walnut (823) to Naaman (825) 138-kV Line Upgrade | P1.2 | GRLND | Eric Cen eric.cen@ercot.com | Dallas | X | X | X | X | X
2024-NC08 |  | Centerville (810) to Miller (824) 138-kV Line Upgrade | P1.2 | GRLND | Eric Cen eric.cen@ercot.com | Dallas |  |  | X | X | X
2024-NC09 |  | Walnut (823) to Newman (849) 138-kV Line Upgrade | P1.2 | GRLND | Eric Cen eric.cen@ercot.com | Dallas |  |  | X | X | X
2024-NC10 |  | Glen Heights (217) to Desoto Switch 8 (2424) 138-kV Line Upgrade | P0, P1.2, P1.3, P7.1_ERCOT1, P6.2_ERCOT3 | BEPC, ONCOR | Eric Cen eric.cen@ercot.com | Ellis, Dallas | X |  | X | X | X
2024-NC11 |  | Watermill (2427) to Tricorner (2432) to Trinidad (3123/3124) 345-kV Line Upgrades and Substation Rebuilds | P0, P1.2, P6.2_ERCOT3, P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Dallas, Henderson |  |  | X | X | X
2024-NC12 |  | Knob Creek Switch (3413) to Salado Switch (3699) 345-kV Line Upgrade and Substation Rebuilds | P0, P1.2, P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Bell | X |  | X | X | X
2024-NC13 |  | Pebble Creek (2229) to Trumbull (221) to Gamma (12344) to Shankle Switch (12329) 138-kV Line Upgrades | P0, P1.2, P7.1_ERCOT1 | BEPC, ONCOR | Eric Cen eric.cen@ercot.com | Ellis |  |  | X | X | X
2024-NC14 |  | Green Road (3069) to Ten Mile (2126) to Watermill (2429) to Reindeer (3065) 138-kV Line Upgrades | P1.2, P1.3, P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Dallas |  |  | X | X | X
2024-NC15 |  | Waxahachie (2321) to Waxahachie North (2320) 138-kV Line Upgrade and Waxahachie (2335) to Waxahachie OCF (2343) 69-kV Line Upgrades | P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Ellis |  |  | X | X | X
2024-NC16 |  | Loop 9 (2847) to Watermill (2427) 345-kV Line Upgrade | P1.2 | ONCOR | Eric Cen eric.cen@ercot.com | Dallas |  |  | X
2024-NC17 |  | Dublin (1637) to Brownwood (1662) 69-kV Line Upgrade | P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Brown, Erath | X |  | X | X | X
2024-NC18 |  | Ennis West Switch (2241) to Templeton (12320) to Waxahachie (2321) 138-kV Line Upgrades | P0, P1.2, P1.3, P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Ellis, Waxahachie |  |  | X | X | X
2024-NC19 |  | Climax TNP (37280) to Bridge Point RC (37245) 69-kV Line Upgrade | P0, P1.2 | TNMP | Eric Cen eric.cen@ercot.com | Collin |  |  | X | X | X
2024-NC20 |  | Mexia Terminal Equipment Upgrade | P1.2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Limestone | X |  | X | X | X
2024-NC21 |  | Carrollton Northwest (2363) to South TNP (37100) to TI TNP (37080) 138-kV Line Upgrades | P6.2_ERCOT3 | ONCOR, TNMP | Eric Cen eric.cen@ercot.com | Dallas, Denton | X |  | X | X | X
2024-NC22 |  | Waxahachie Pump 2 (2315) to Waxahachie North (2320) 138-kV Line Upgrade | P1.1, P1.2, P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Ellis |  |  |  | X | X
2024-NC23 |  | Bale (3711) to St Johns Switch (3384) to Lake Creek SES (3409) 345-kV Line Upgrades | P0, P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Falls, McLennan |  |  |  | X | X
2024-NC24 |  | Lake Creek SES (3410) to Riesel Switch (3702) 138-kV Line Upgrade | P0, P1.2, P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Falls, McLennan |  |  | X | X | X
2024-NC25 |  | LTV Sub (2259) to Grand Prairie (2262) 138-kV Line Upgrade | P0, P1.2, P1.3, P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas |  |  |  | X | X
2024-NC26 |  | Eastland (1621) to Morton Valley (1623) 69-kV Line Upgrade | P1.2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Eastland |  |  |  | X | X
2024-NC27 |  | Navarro (3478) to Haney (213) to Payne Battlecreek POI (888876) to Hubbard (3515) 138-kV Line Upgrades | P1.2, P7.1_ERCOT1 | BEPC, ONCOR | Eric Cen eric.cen@ercot.com | Navarro, Hill | X |  | X | X | X
2024-NC28 |  | Olympus Switch (3723) to Montfort Switch (3454) to Chatfield (200) 138-kV Line Upgrade | P1.2, P6.2_ERCOT3 | ONCOR, BEPC | Jack Thornton jack.thornton@ercot.com | Henderson, Navarro |  |  |  | X | X
2024-NC29 |  | Allen Switch (2514) to Pineforest POI (888854) 345-kV Line Upgrade | P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Collin, Hopkins |  |  |  | X | X
2024-NC30 |  | Quinlan North (6883) to Quinland Sub POD (6884) 138-kV Line Upgrade | P1.2, P7.1_ERCOT1 | RAYBN | Eric Cen eric.cen@ercot.com | Hunt |  |  | X | X | X
2024-NC31 |  | Royse Area 345-kV Line Upgrades and Substation Rebuilds | P1.2, P7.1_ERCOT1, P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Collin, Hopkins, Rockwall, Fannin, Lamar |  |  | X | X | X
2024-NC32 |  | Lake Creek - Trading House Area 345-kV Line Upgrades | P1.2, P7.1_ERCOT1, P3_ERCOT2 | ONCOR, LST | Jack Thornton jack.thornton@ercot.com | Hill, McLennan |  |  | X | X | X
2024-NC33 |  | Air Products Tap (2305) to Midlothian TXI (2307) 138-kV Line Upgrade | P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Ellis |  |  |  |  | X
2024-NC34 |  | Trinidad SES (3127) to Nipak Tap (3260) to Mankin Switch (3265) 138-kV Line Upgrade | P7.1_ERCOT1, P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Henderson, Navarro |  |  | X | X | X
2024-NC35 |  | Firewheel (821) to Wylie Switch (833) 138-kV Line Upgrade | P1.2, P7.1_ERCOT1 | GRLND | Jack Thornton jack.thornton@ercot.com | Dallas, Collin |  |  |  | X | X
2024-NC36 |  | Commerce Switch (1816) to Crossroads Switch (1844) 138-kV Line Upgrade | P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Delta, Hunt | X |  | X | X | X
2024-NC37 |  | Bell East (3687) to Salado Switch (3699) 345-kV Line Addition and Substation Rebuilds | P1.2, P7.1_ERCOT1, P6.2_ERCOT3, P3_ERCOT2 | BEPC, ONCOR | Eric Cen eric.cen@ercot.com | Bell, Williamson | X |  | X | X | X
2024-NC38 |  | Seagoville Area Upgrades and Substation Rebuilds | P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas |  |  |  | X | X
2024-NC39 |  | Allen Switch (2510) to Plano Alma Road (2677) to Plano West (2673) 138-kV Line Upgrades | P1.2, P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Collin |  |  |  |  | X
2024-NC40 |  | Argyle (1984) to Argyle North (11986) to Krum Tap Switch (1986) 138-kV Line Upgrades | P1.2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Denton |  |  |  |  | X
2024-NC41 |  | Ben Davis (968) to Gob Lane (2497) 138-kV Line Upgrade | P7.1_ERCOT1 | TMPA, ONCOR | Eric Cen eric.cen@ercot.com | Dallas |  |  | X | X | X
2024-NC42 |  | Big Brown (3380/3381) to Navarro (68091) to Venus North (1907) 345-kV Line Upgrades | P7.1_ERCOT1 | ONCOR, LST | Jack Thornton jack.thornton@ercot.com | Freestone, Navarro, Ellis |  |  |  |  | X
2024-NC43 |  | Temple Switch (3415) to Belton (3610) 138-kV Line Upgrades | P7.1_ERCOT1, P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Bell |  |  |  | X | X
2024-NC44 |  | Cedar Creek Area 138-kV Line Upgrades | P1.2, P7.1_ERCOT1, P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Henderson |  |  | X | X | X
2024-NC45 |  | Cedar Hill Switch (2421) to Fish Creek Switch (12491) 138-kV Line Upgrade | P1.2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas |  |  |  |  | X
2024-NC46 |  | Cedar Hill Switch (2420) to Merrifield Rd (15204) 345-kV Line Upgrade | P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas |  |  |  |  | X
2024-NC47 |  | Cedar Hill TU (3058) to Desoto Hampton Road (3059) 138-kV Line Upgrade | P1.2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas |  |  |  |  | X
2024-NC48 |  | Centerville Road Area 138-kV Line Upgrades | P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas |  |  |  |  | X
2024-NC49 |  | Chatfield (200) to Corsicana (3455) 138-kV Line Upgrade | P1.2 | BEPC, ONCOR | Jack Thornton jack.thornton@ercot.com | Navarro |  |  |  |  | X
2024-NC50 |  | Crossroads Area 138-kV Line Upgrades | P7.1_ERCOT1, P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Delta, Hopkins, Hunt, Lamar |  |  |  | X | X
2024-NC51 |  | Waxahachie-Sterrett Area Upgrades | P1.2, P7.1_ERCOT1, P3_ERCOT2, P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Ellis |  |  |  | X | X
2024-NC52 |  | Lillian (419) to Highpoint (439) 138-kV Line Upgrade | P1.2 | BEPC | Jack Thornton jack.thornton@ercot.com | Johnson |  |  |  |  | X
2024-NC53 |  | Seven Points (3264) to Kaufman Northwest (2724) 138-kV Line Upgrades | P1.2, P7.1_ERCOT1, P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Kaufman |  |  |  | X | X
2024-NC54 |  | Sherry Switch (1920) to Park Row (2258) to LTV Sub (2259) 138-kV Line Upgrades | P1.2, P1.3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas, Tarrant |  |  |  |  | X
2024-NC55 |  | Outlaw Switch (3386) to Navarro (68091) 345-kV Line Upgrade | P1.2, P7.1_ERCOT1 | ONCOR, LST | Jack Thornton jack.thornton@ercot.com | Navarro |  |  |  |  | X
2024-NC56 |  | Miller Road (2632) to Oystercatcher POI (888857) 345-kV Line Upgrade | P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Ellis |  |  |  |  | X
2024-NC57 |  | Parkdale Switch (2442) to Prairie Creek 1 (2763) to Prairie Creek Switch (2441) to Prairie Creek 2 (2762) to Scyene Road (2743) 138-kV Line Upgrades | P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas |  |  |  |  | X
2024-NC58 |  | Miller (331) to Palo Pinto Tap (1576) 138-kV Line Upgrade | P1.2 | BEPC, ONCOR | Jack Thornton jack.thornton@ercot.com | Palo Pinto |  |  |  |  | X
2024-NC59 |  | Lavon Switch 345/138-kV Substation Expansion and Lavon Switch (2475) to Allen Switch (2511) 138-kV Line Addition | P3_ERCOT2, P6.2_ERCOT3 | ONCOR | Eric Cen eric.cen@ercot.com | Collin, Rockwall | X |  | X | X | X
2024-NC60 |  | Bell County East Switch (3687) to Littlepond (3377) and Bell County East Switch (3687) to Brangus Switch (3705) 345-kV Line Upgrades and Substation Rebuilds | P1.2, P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Milam, Bell |  |  |  | X | X
2024-NC61 |  | Blue Horse (612) to Spring (684) 138-kV Line Upgrade | P1.2 | BEPC | Jack Thornton jack.thornton@ercot.com | Denton, Cooke |  |  |  |  | X
2024-NC62 |  | Tyler Grande (3102) to Kings Creek 2 (15203) 345-kV Line Upgrade | P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Smith, Dallas |  |  |  |  | X
2024-NC63 |  | Watermill Area 345-kV Line Additions and Reactive Support | P1.1, P1.2, P1.3, P7.1_ERCOT1 | ONCOR, LST | Jack Thornton jack.thornton@ercot.com | Dallas, Navarro, Hill, Leon | X | X | X | X | X
2024-NC64 |  | Calmont Switch (1955) to Benbrook Switch (1874) 138-kV Line Upgrade | P6.2_ERCOT3 | ONCOR | Jose Solchaga jose.solchaga@ercot.com | Tarrant |  |  |  | X | X
2024-NC65 |  | Limestone Plant (46020) to Jewett (3390) 345-kV Line Upgrade | P7.1_ERCOT1 | CNP, ONCOR | Jack Thornton jack.thornton@ercot.com | Limestone, Leon |  |  |  |  | X
2024-NC66 |  | Tri Corner (2432) to Forney Switch (2437) 345-kV Line Upgrade | P7.1_ERCOT1 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas, Kaufman |  |  |  | X | X
2024-NC67 |  | Elkton (3105) to Tri Corner (2432) 345-kV Line Additions and Upgrades | P1.1, P1.2, P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Dallas, Kaufman, Smith, Van Zandt | X |  | X | X | X
2024-NC68 |  | Batchler Road (2217) to Watermill (2427) 345-kV Line Upgrades | P0, P1.2, P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Dallas | X |  | X | X | X
2024-NC69 |  | Sam Switch (68090) to Four Brothers Switch (3388) 345-kV Line Upgrade | P1.1, P1.2, P1.3, P7.1_ERCOT1, P3_ERCOT2 | ONCOR, LST | Eric Cen eric.cen@ercot.com | Hill |  |  | X | X | X
2024-NC70 |  | Miller Road (2632) 345/138-kV Substation Addition and 345-kV Lines Retermination | P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas, Ellis | X |  | X | X | X
2024-NC71 |  | Mitchell Bend Switch (1895) to Carmichael Bend Switch (2285) to Benbrook Switch (1873) 345-kV Line Upgrades and Substation Rebuilds | P7.1_ERCOT1 | ONCOR | Eric Cen eric.cen@ercot.com | Tarrant, Hood, Grayson |  |  | X | X | X
2024-NC72 |  | Argyle Area 138-kV Line Upgrades | P6.2_ERCOT3 | BEPC, ONCOR | Jack Thornton jack.thornton@ercot.com | Denton | X |  | X | X | X
2024-NC73 |  | Greene Road (3069) to Cedar Crest (2486) 138-kV Line Upgrades | P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas | X |  | X
2024-NC74 |  | Midlothian TXI (2307) to Waxahachie Northwest (2309) 138-kV Line Upgrades | P1.2, P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Ellis | X |  | X | X | X
2024-NC75 |  | Primrose Fort Worth (2196) to Rocky Creek (1881) to Primrose Fort Worth (2197) 138-kV Line Upgrades | P1.2, P6.2_ERCOT3 | ONCOR | Jose Solchaga jose.solchaga@ercot.com | Tarrant | X |  | X | X | X
2024-NC76 |  | Gunter (2235) 345/138-kV Substation Addition and Gunter (2236) to Collin (2370) 138-kV Line Addition | P1.2, P6.2_ERCOT3 | ONCOR | Eric Cen eric.cen@ercot.com | Cooke, Denton, Collin, Grayson | X |  | X | X | X
2024-NC77 |  | Skyview (2231) 345/138-kV Substation Addition and Area Upgrade | P6.2_ERCOT3 | ONCOR | Eric Cen eric.cen@ercot.com | Dallas, Tarrant | X |  | X | X | X
2024-NC78 |  | Seagoville (2433) to Greene Road (3063) 345-kV Double-Circuit Line Addition and Substation Rebuilds | P3_ERCOT2, P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas | X | X |  |  | X
2024-NC79 |  | Benbrook Switch 345/138-kV Transformer (1869/18741 and 1870/18751) Upgrades | P6.2_ERCOT3 | ONCOR | Jose Solchaga jose.solchaga@ercot.com | Tarrant |  |  | X | X | X
2024-NC80 |  | Desoto Switch 345/138-kV Transformer Addition (2431/2424) and Desoto Switch (2424) to Loop9 (2848) 138-kV Line Addition | P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas |  | X | X | X | X
2024-NC81 |  | Carter (2641) 345/138-kV Substation Addition | P6.2_ERCOT3 | ONCOR | Eric Cen eric.cen@ercot.com | Tarrant |  |  |  |  | X
2024-NC82 |  | Rocky Creek (1880/1881) 345/138-kV Transformer Addition | P6.2_ERCOT3 | ONCOR | Jose Solchaga jose.solchaga@ercot.com | Tarrant | X |  | X | X | X
2024-NC83 |  | Hempill (2164) to Mistletoe Heights (2173) 138-kV Line Upgrade | P6.2_ERCOT3 | ONCOR | Jose Solchaga jose.solchaga@ercot.com | Tarrant |  |  | X | X | X
2024-NC84 |  | Wedgewood Switch (2184) to Bryant Irvin (2182) 138-kV Line Upgrade | P6.2_ERCOT3 | ONCOR | Jose Solchaga jose.solchaga@ercot.com | Tarrant |  |  | X | X | X
2024-NC85 |  | Miller Road (2635) to Kemp Ranch Switch (2303) 138-kV Double-Circuit Line Upgrade | P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Ellis |  |  |  | X
2024-NC86 |  | Greene Road (3063/3069) New 138-kV and 345-kV Line Additions and Substation Rebuilds | P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas |  |  |  | X | X
2024-NC87 |  | Forney (2437) to Seagoville Switch (2433) 345-kV Line Upgrade | P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas, Kaufman |  |  |  |  | X
2024-NC88 |  | Ferris (2344/2342) 138/69-kV Transformer and Ferris (2342) to Waxahachie OCF (2343) 69-kV Line Upgrade | P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Ellis |  |  |  |  | X
2024-NC89 |  | Grand Prairie (2262) to Fish Creek Switch (12491) 138-kV Line Upgrade | P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Dallas |  |  |  |  | X
2024-NC90 |  | Shankle Switch (12329) to Ennis (2325) 138-kV Line Upgrade | P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Ellis |  |  |  |  | X
2024-NC91 |  | Gibson (3706) to Brangus Switch (3705) 345-kV Line Upgrade | P3_ERCOT2 | ONCOR | Jack Thornton jack.thornton@ercot.com | Milam |  |  |  |  | X
2024-NC92 |  | Killeen (3423) 138-kV Cap Bank Addition | P6.2_ERCOT3 | ONCOR | Jack Thornton jack.thornton@ercot.com | Bell | X